## PSR Overall Cycle
| Note: | 1. All MR Issuance with Attached File to be used IFR version, some long lead item to be used FEED document as MR Issuance basis which listed in Remark
2. In principle, Datasheet - IFA version shall be issued before TBE issuance as much as possible to avoid the big gap of changes.
3.TBE- AFC and MR-AFC should be issued before PO issuance.
4.For the Steel Structural, TJE will sign the frame agreement with alternative vendors firstly, once the MTO&IFA drawing issuance, TJE will purchase order promptly
5.The 3rd line of Each procuremnt package with "Proposal from TJE" in column N , has been aligned with GCME about date of MR issuance with atteched relative documents, then forward schedule in procurement and leadtime to ETA, this line is the basis for schedule developing.
[11 empty] | LA |  |  | 1 | 10 | 0 | 0 | 0 | 10 | 17 | 10 |  | 9
[11 empty] | LB |  |  | 1 | 10 | 0 | 0 | 0 | 10 | 17 | 10 |  | 9
[11 empty] | LC |  |  | 1 | 10 | 0 | 0 | 0 | 10 | 13 | 10 |  | 9
[11 empty] | LD |  |  | 1 | 10 | 0 | 0 | 0 | 5 | 7 | 10 |  | 5
| ZM167 PTTEPI ASK Procurement Plan | [9 empty] | LA |  |  | 1 | 5 | 1 | 5 |  | 10 | 20 | 3 |  | 10 | 2 | 5 | 20 | 10 |  |  |  | 5 | 5 | [7 empty] | Update
[11 empty] | LB |  |  | 1 | 5 | 1 | 5 |  | 10 | 20 | 3 |  | 10 | 2 | 5 | 20 | 10 |  |  |  | 5 | 5
[11 empty] | LC |  |  | 3 | 5 | 1 | 5 |  | 10 | 15 | 3 |  | 10 | 2 | 5 | 15 | 10 |  |  |  | 5 | 5
[11 empty] | LD |  |  | 3 | 5 | 1 | 3 |  | 5 | 7 | 2 |  | 5 | 2 | 5 | 10 | 10 |  |  |  | 5 | 5
No. | RFQ No. | Package Name | Actual Lead Time | Delivery Duration (Weeks) | Deviation | Float | CODE | Discripline | Long Lead Item (Y/N) | Criticality Rating | Priority Level |  | Bidder List Approval | MR Issued | MR Approved | RFQ Issued | RFQ Approved | CFT Issuance | Bid Closing Date | TBE Issued | TBE Approved | LOA SIGN | PO Issued | Vendor Acknowledgement | KOM | VD Submission | Approval of Key Vendor Documents | Delivery of Major Materials | PIM | Start Production | FAT | Ready for Shipment | Receipt at WORKSITE | Punch List Clearance | Approval of Final Documentation (To be confirmed later) | Delivery Duration (Weeks) | Lead Time | ETA date | ROS date | ROS date update | Construction Date | Remark | Float |  | Remark
[12 empty] | Matrix | [32 empty] | Installation
[12 empty] | Holiday | China | Thai | Thai | China | Thai |  | China | Thai | Thai | China | China | China | China | China | Thai
1 | RFQ-MEC-001 | Offshore Pedestal Crane | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-04-10 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-03 | 2026-05-15 | 2026-06-11 | 2026-06-25 |  | 2026-07-08 | 2026-07-10 | 2026-07-17 | 2026-08-14 | 2026-08-28 | 2026-10-12 | 2026-10-15 | 2026-10-18 | 2027-04-19 | 2027-05-19 | 2027-06-02 | 2027-06-16 | 2027-07-02 | 47 |  | 2027-06-02 | [5 empty] | WPA-01 | 2027-06-30
| RFQ-MEC-001 | Offshore Pedestal Crane |  |  |  | 4 | 4-2.1 | Mechanical | Y | 2 | LA | Forecast | [10 empty] | 2026-07-08 | 2026-07-10 | 2026-07-17 | 2026-08-14 | 2026-08-28 | 2026-10-12 | 2026-10-15 | 2026-10-18 | 2027-04-19 | 2027-05-19 | 2027-06-02 | 2027-06-16 | 2027-07-02 |  | 329 | 2027-06-02 | 2027-06-27 | 2027-06-23 | 2027-06-30 |  | 25 | WPA-02 | 2027-07-06
| RFQ-MEC-001 | Offshore Pedestal Crane | [5 empty] | Mechanical | Y | 2 | LA | Actual | 2026-04-08 | 2026-04-10 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-01 | 2026-06-12 | 2026-06-17 | 2026-07-20 | 2026-07-17: 2026-07-10 | [6 empty] | Upper Deck
2 | RFQ-MEC-002 | Material Handling Equipment | [5 empty] | Mechanical |  |  | LC | New Plan |  | 2026-06-30 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-14 | 2026-07-28 | 2026-08-18 | 2026-09-01 |  | 2026-09-14 | 2026-09-16 | 2026-09-23 | 2026-10-22 | 2026-11-06 | 2026-12-21 | 2026-12-24 | 2026-12-25 | 2027-01-23 | 2027-02-22 | 2027-03-08 | 2027-03-22 | 2027-04-07 | 25 |  | 2027-03-08 | [5 empty] | WPA-01 | 2027-06-30
| RFQ-MEC-002 | Material Handling Equipment |  |  |  | 111 | 4-2.2 | Mechanical | N | 4 | LC | Forecast | [7 empty] | 2026-08-18 | 2026-09-01 |  | 2026-09-14 | 2026-09-16 | 2026-09-23 | 2026-10-22 | 2026-11-06 | 2026-12-21 | 2026-12-24 | 2026-12-25 | 2027-01-23 | 2027-02-22 | 2027-03-08 | 2027-03-22 | 2027-04-07 |  | 175 | 2027-03-08 | 2027-06-27 |  |  | check Location | 111 | WPA-02 | 2027-07-06
| RFQ-MEC-002 | Material Handling Equipment | [5 empty] | Mechanical | N | 4 | LC | Actual |  | 2026-05-28 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-18 | 2031-06-01
3 | RFQ-MEC-003 | Instrument Gas Filter Coalescer | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-05-28 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-17 | 2026-07-01 | 2026-07-21 | 2026-08-06 |  | 2026-08-19 | 2026-08-21 | 2026-08-28 | 2026-09-28 | 2026-10-12 | 2026-12-11 | 2026-12-14 | 2026-12-15 | 2027-01-15 | 2027-02-14 | 2027-02-15 | 2027-03-01 | 2027-03-17 | 25.7143 |  | 2027-02-15 |  |  |  |  | 7 | WPA-01 | 2027-02-25
| RFQ-MEC-003 | Instrument Gas Filter Coalescer |  |  |  | 7 | 4-2.4 | Mechanical | Y | 3 | LA | Forecast | [13 empty] | 2026-08-20 | 2026-09-03 | 2026-11-02 | 2026-11-05 | 2026-11-06 | 2026-12-12 | 2027-01-11 | 2027-01-12 | 2027-01-26 | 2027-02-11 |  | 180 | 2027-01-12 | 2027-02-22 | 2027-02-22 | 2027-03-01 |  | 41 | WPA-02 | 2027-03-18
| RFQ-MEC-003 | Instrument Gas Filter Coalescer | [5 empty] | Mechanical | Y | 3 | LA | Actual | 2026-04-24 | 2026-05-23 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-19 | 2026-07-17 | 2026-07-21 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-23 | [16 empty] | Lower Deck
4 | RFQ-MEC-004 | TEST AND PRODUCTION SEPARATOR | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-05-12 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-28 | 2026-06-10 | 2026-07-08 | 2026-07-13 |  | 2026-07-27 | 2026-07-29 | 2026-08-05 | 2026-09-02 | 2026-09-16 | 2026-11-15 | 2026-11-18 | 2026-11-19 | 2027-02-12 | 2027-02-15 | 2027-02-22 | 2027-03-08 | 2027-03-24 | 30 |  | 2027-02-22 | 0 |  |  |  | 7 | WPA-01 | 2027-03-04
| RFQ-MEC-004 | TEST AND PRODUCTION SEPARATOR |  |  |  | 7 | 4-2.3 | Mechanical | Y | 2 | LA | Forecast | [13 empty] | 2026-08-20 | 2026-09-03 | 2026-11-02 | 2026-11-05 | 2026-11-06 | 2027-01-11 | 2027-02-10 | 2027-02-11 | 2027-02-25 | 2027-03-13 |  | 210 | 2027-02-11 | 2027-03-01 | 2027-02-22 | 2027-03-01 |  | 18 | WPA-02 | 2027-03-18
| RFQ-MEC-004 | TEST AND PRODUCTION SEPARATOR | [5 empty] | Mechanical | Y | 2 | LA | Actual | 2026-04-24 | 2026-05-15 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-17 | 2026-07-03 | 2026-07-07 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-23 | [16 empty] | Lower Deck
5 | RFQ-PIP-005 | QUICK OPENING CLOSURE | [5 empty] | Piping |  |  | LA | New Plan |  | 2026-05-15 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2026-06-03 | 2026-06-16 | 2026-07-14 | 2026-07-24 |  | 2026-07-31 | 2026-08-04 | 2026-08-11 | 2026-09-08 | 2026-09-22 | 2026-11-21 | 2026-11-24 | 2026-11-25 | 2027-02-09 | 2027-03-11 | 2027-03-12 | 2027-03-26 | 2027-04-11 | 32 |  | 2027-03-12 |  |  |  |  | 10 | WPA-01 | 2027-03-25
| RFQ-PIP-005 | QUICK OPENING CLOSURE |  |  |  | 10 | 4-2.6 | Piping | Y | 2 | LA | Forecast | [8 empty] | 2026-07-24 |  | 2026-08-06 | 2026-08-10 | 2026-08-17 | 2026-09-14 | 2026-09-28 | 2026-11-27 | 2026-11-30 | 2026-12-01 | 2027-02-15 | 2027-03-17 | 2027-03-18 | 2027-04-01 | 2027-04-17 |  | 224 | 2027-03-18 | 2027-03-22 | 2027-03-18 | 2027-03-25 | Lower Deck | 4 | WPA-02 | 2027-03-26
| RFQ-PIP-005 | QUICK OPENING CLOSURE | [5 empty] | Piping | Y | 2 | LA | Actual | 2026-04-24 | 2026-05-21 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-26 | 2026-07-22
6 | RFQ-MEC-006 | CHEMICAL INJECTION PUMPS PACKAGE | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-05-11 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-05-27 | 2026-06-09 | 2026-07-07 | 2026-07-10 |  | 2026-07-24 | 2026-07-28 | 2026-08-04 | 2026-09-01 | 2026-09-15 | 2027-01-05 | 2027-01-08 | 2027-01-09 | 2027-02-03 | 2027-02-19 | 2027-03-05 | 2027-03-19 | 2027-04-04 | 32 |  | 2027-03-05 | 0 |  |  |  | 18 | WPA-01 | 2027-03-26
| RFQ-MEC-006 | CHEMICAL INJECTION PUMPS PACKAGE |  |  |  | 4 | 4-2.8 | Mechanical | Y | 3 | LA | Forecast | [10 empty] | 2026-07-24 | 2026-07-28 | 2026-08-04 | 2026-09-01 | 2026-09-15 | 2027-01-05 | 2027-01-08 | 2027-01-09 | 2027-01-20 | 2027-02-19 | 2027-03-05 | 2027-03-19 | 2027-04-04 |  | 224 | 2027-03-05 | 2027-03-23 | 2027-03-19 | 2027-03-26 |  | 18 | WPA-02 | 2027-03-31
| RFQ-MEC-006 | CHEMICAL INJECTION PUMPS PACKAGE | [5 empty] | Mechanical | Y | 3 | LA | Actual | 2026-04-21 | 5/15/202 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-07-03 | 2026-07-07 | [20 empty] | Lower Deck
8 | RFQ-MEC-008 | DEOILER HYDRO CYCLONE PACKAGE | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-04-29 | 2026-05-11 | 2026-05-11 | 2026-05-18 | 2026-05-19 | 2026-06-01 | 2026-06-30 | 2026-07-03 |  | 2026-07-17 | 2026-07-21 | 2026-07-28 | 2026-08-25 | 2026-09-08 | 2026-11-07 | 2026-11-10 | 2026-11-11 | 2026-12-15 | 2027-03-05 | 2027-03-12 | 2027-03-26 | 2027-04-11 | 34 |  | 2027-03-12 | 0 |  |  |  | 9 | WPA-01 | NA
| RFQ-MEC-008 | DEOILER HYDRO CYCLONE PACKAGE |  |  |  | 65 | 4-2.10 | Mechanical | Y | 2 | LA | Forecast | [12 empty] | 2026-07-28 | 2026-08-25 | 2026-09-08 | 2026-11-07 | 2026-11-10 | 2026-11-11 | 2027-02-08 | 2027-03-10 | 2027-03-11 | 2027-03-25 | 2027-04-10 |  | 238 | 2027-03-11 | 2027-03-21 | 2027-03-17 | 2027-03-24 | only WPA02 | 10 | WPA-02 | 2027-03-24
| RFQ-MEC-008 | DEOILER HYDRO CYCLONE PACKAGE | [5 empty] | Mechanical | Y | 2 | LA | Actual | 2026-04-24 | 2026-04-27 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-06-09 | 2026-06-27 | 2026-06-29 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-28: 2026-07-23 | [6 empty] | Lower Deck
9 | RFQ-MEC-009 | DEGASSER DRUM | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-04-22 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-12 | 2026-05-25 | 2026-06-24 | 2026-06-29 |  | 2026-07-13 | 2026-07-15 | 2026-07-22 | 2026-08-19 | 2026-09-02 | 2026-11-01 | 2026-11-04 | 2026-11-05 | 2026-12-24 | 2027-02-01 | 2027-02-08 | 2027-02-22 | 2027-03-10 | 30 |  | 2027-02-08 | 0 |  |  |  | 36 | WPA-01 | NA
| RFQ-MEC-009 | DEGASSER DRUM |  |  |  | 54 | 4-2.11 | Mechanical | Y | 2 | LA | Forecast | [12 empty] | 2026-07-22 | 2026-08-19 | 2026-09-02 | 2026-11-01 | 2026-11-04 | 2026-11-05 | 2027-01-11 | 2027-02-10 | 2027-02-11 | 2027-02-25 | 2027-03-13 |  | 210 | 2027-02-11 | 2027-03-16 | 2027-03-11 | 2027-03-18 | only WPA02 | 33 | WPA-02 | 2027-03-19
| RFQ-MEC-009 | DEGASSER DRUM | [5 empty] | Mechanical | Y | 2 | LA | Actual | 2026-04-23 | 2026-04-23 | 2026-05-09 | 2026-05-09 | 2026-05-09 | 2026-05-09 | 2026-06-08 | 2026-06-29 | 2026-07-01 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-22: 2026-07-23 | [6 empty] | Lower Deck
10 | RFQ-MEC-010 | Skim Tank Vessel | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-05-05 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-21 | 2026-06-17 | 2026-07-01 | 2026-07-06 |  | 2026-07-20 | 2026-07-22 | 2026-07-29 | 2026-08-26 | 2026-09-09 | 2026-11-08 | 2026-11-11 | 2026-11-12 | 2026-12-18 | 2027-02-28 | 2027-03-01 | 2027-03-15 | 2027-03-31 | 32 |  | 2027-03-01 | 0 |  |  |  | 18 | WPA-01 | NA
| RFQ-MEC-010 | Skim Tank Vessel |  |  |  | 60 | 4-2.13 | Mechanical | Y | 2 | LA | Forecast | [13 empty] | 2026-08-20 | 2026-09-03 | 2026-11-02 | 2026-11-05 | 2026-11-06 | 2027-01-25 | 2027-02-24 | 2027-02-25 | 2027-03-11 | 2027-03-27 |  | 224 | 2027-02-25 | 2027-03-19 | 2027-03-08 | 2027-03-15 | only WPA02 | 22 | WPA-02 | 2027-03-22
| RFQ-MEC-010 | Skim Tank Vessel | [5 empty] | Mechanical | Y | 2 | LA | Actual | 2026-04-24 | 2026-05-08 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-17 | 2026-07-03 | 2026-07-07 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-23 | [16 empty] | Lower Deck
11 | RFQ-MEC-011 | Closed Drain Sump Vessel | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-05-13 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-05-29 | 2026-06-12 | 2026-07-09 | 2026-07-14 |  | 2026-07-28 | 2026-07-30 | 2026-08-06 | 2026-09-03 | 2026-09-17 | 2026-11-16 | 2026-11-19 | 2026-11-20 | 2026-12-26 | 2027-01-25 | 2027-01-26 | 2027-02-09 | 2027-02-25 | 26 |  | 2027-01-26 |  |  |  |  | 4 | WPA-01 | 2027-02-02
| RFQ-MEC-011 | Closed Drain Sump Vessel |  |  |  | 22 | 4-2.12 | Mechanical | Y | 3 | LA | Forecast | [13 empty] | 2026-08-20 | 2026-09-03 | 2026-11-02 | 2026-11-05 | 2026-11-06 | 2026-12-14 | 2027-01-13 | 2027-01-14 | 2027-01-28 | 2027-02-13 |  | 182 | 2027-01-14 | 2027-01-30 | 2027-01-25 | 2027-02-01 |  | 16 | WPA-02 | 2027-03-05
| RFQ-MEC-011 | Closed Drain Sump Vessel | [5 empty] | Mechanical | Y | 3 | LA | Actual | 2026-04-24 | 2026-05-15 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-12 | 2026-07-03 | 2026-07-07 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-23 | [16 empty] | Sump Deck
13 | RFQ-MEC-013 | Storage Tank | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-05-22 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-24 | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-29 | 2026-10-14 | 2026-12-13 | 2026-12-16 | 2026-12-17 | 2027-01-04 | 2027-02-03 | 2027-02-04 | 2027-02-18 | 2027-03-06 | 24 |  | 2027-02-04 |  |  |  |  | 40 | WPA-01 | 2027-03-19
| RFQ-MEC-013 | Storage Tank |  |  |  | 53 | 4-2.17 | Mechanical | Y | 3 | LA | Forecast | [13 empty] | 2026-08-20 | 2026-09-03 | 2026-11-02 | 2026-11-05 | 2026-11-06 | 2026-11-30 | 2026-12-30 | 2026-12-31 | 2027-01-14 | 2027-01-30 |  | 168 | 2026-12-31 | 2027-03-16 | 2027-03-10 | 2027-03-17 |  | 75 | WPA-02 | 2027-04-12
| RFQ-MEC-013 | Storage Tank | [5 empty] | Mechanical | Y | 3 | LA | Actual | 2026-04-24 | 2026-05-22 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-07-09 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-23 | [16 empty] | Mezz & Lower
14 | RFQ-MEC-014 | CLOSED DRAIN SUMP PUMP AND RECOVERY WATER PUMP PACKAGE | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-05-13 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-05-29 | 2026-06-12 | 2026-07-09 | 2026-07-14 |  | 2026-07-28 | 2026-07-30 | 2026-08-06 | 2026-09-03 | 2026-09-17 | 2027-01-07 | 2027-01-10 | 2027-01-11 | 2027-01-24 | 2027-02-23 | 2027-03-09 | 2027-03-23 | 2027-04-08 | 32 |  | 2027-03-09 |  |  |  |  | 10 | WPA-01 | 2027-03-22
| RFQ-MEC-014 | CLOSED DRAIN SUMP PUMP AND RECOVERY WATER PUMP PACKAGE |  |  |  | 10 | 4-2.21 | Mechanical | Y | 3 | LA | Forecast | [10 empty] | 2026-07-28 | 2026-07-30 | 2026-08-06 | 2026-09-03 | 2026-09-17 | 2027-01-07 | 2027-01-10 | 2027-01-11 | 2027-01-24 | 2027-02-23 | 2027-03-09 | 2027-03-23 | 2027-04-08 |  | 224 | 2027-03-09 | 2027-03-19 | 2027-03-15 | 2027-03-22 |  | 10 | WPA-02 | 2027-03-22
| RFQ-MEC-014 | CLOSED DRAIN SUMP PUMP AND RECOVERY WATER PUMP PACKAGE | [5 empty] | Mechanical | Y | 3 | LA | Actual | 2026-04-21 | 2026-05-15 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-05 | 2026-07-03 | 2026-07-08 | [20 empty] | Sump Deck
15 | RFQ-MEC-015 | DIESEL TRANSFER PUMP PACKAGE | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-20 | 2026-06-22 | 2026-08-04 | 2026-08-07 |  | 2026-08-21 | 2026-08-25 | 2026-09-01 | 2026-09-30 | 2026-10-15 | 2027-02-03 | 2027-02-06 | 2027-02-07 | 2027-02-17 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-05-02 | 32 |  | 2027-04-02 |  |  |  |  | 1 | WPA-01 | 2027-04-06
| RFQ-MEC-015 | DIESEL TRANSFER PUMP PACKAGE |  |  |  | 1 | 4-2.23 | Mechanical | Y | 3 | LA | Forecast | [10 empty] | 2026-08-06 | 2026-08-10 | 2026-08-17 | 2026-09-14 | 2026-09-28 | 2027-01-18 | 2027-01-21 | 2027-01-22 | 2027-02-02 | 2027-03-04 | 2027-03-18 | 2027-04-01 | 2027-04-17 |  | 224 | 2027-03-18 | 2027-04-03 | 2027-03-30 | 2027-04-06 |  | 16 | WPA-02 | 2027-04-09
| RFQ-MEC-015 | DIESEL TRANSFER PUMP PACKAGE | [5 empty] | Mechanical | Y | 3 | LA | Actual |  | 2026-05-28 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-18 | 2026-07-10 | 2026-07-14 | [20 empty] | Lower Deck
16 | RFQ-MEC-016 | OPEN DRAIN CAISSON PUMP PACKAGE | [5 empty] | Mechanical |  |  | LA | New Plan |  | 2026-05-08 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-06-11 | 2026-07-20 | 2026-08-05 |  | 2026-08-18 | 2026-08-20 | 2026-08-27 | 2026-09-24 | 2026-10-08 | 2027-01-28 | 2027-01-07 | 2027-01-08 | 2027-02-27 | 2027-03-29 | 2027-03-30 | 2027-04-13 | 2027-04-29 | 32 |  | 2027-03-30 |  |  |  |  | 95 | WPA-01 | NA
| RFQ-MEC-016 | OPEN DRAIN CAISSON PUMP PACKAGE |  |  |  | 121 | 4-2.24 | Mechanical | Y | 2 | LA | Forecast | [10 empty] | 2026-08-06 | 2026-08-10 | 2026-08-17 | 2026-09-14 | 2026-09-28 | 2027-01-18 | 2027-01-21 | 2027-01-22 | 2027-01-17 | 2027-02-16 | 2027-03-18 | 2027-04-01 | 2027-04-17 |  | 224 | 2027-03-18 | 2027-07-03 | 2027-04-02 | 2027-04-09 |  | 107 | WPA-02 | 2027-07-06
| RFQ-MEC-016 | OPEN DRAIN CAISSON PUMP PACKAGE | [5 empty] | Mechanical | Y | 2 | LA | Actual | 2026-04-21 | 2026-05-10 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-11 | 2026-07-10 | 2026-07-16 | [20 empty] | check Location
17 | RFQ-ELE-017 | AC/DC Distribution Board | [5 empty] | Electrical |  |  | LB | New Plan |  | 2026-04-27 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-13 | 2026-05-22 | 2026-06-26 | 2026-07-10 |  | 2026-07-23 | 2026-07-27 | 2026-08-03 | 2026-08-31 | 2026-09-14 | 2026-10-04 | 2026-10-07 | 2026-10-08 | 2027-03-12 | 2027-03-25 | 2027-04-01 | 2027-04-15 | 2027-05-01 | 36 |  | 2027-04-01 | 0 |  |  |  | 20 | WPA-01 | 2027-04-28
| RFQ-ELE-017 | AC/DC Distribution Board |  |  |  | 0 | 4-3.1 | Electrical | Y | 3 | LB | Forecast | [10 empty] | 2026-07-23 | 2026-07-27 | 2026-08-03 | 2026-08-31 | 2026-09-14 | 2026-10-04 | 2026-10-07 | 2026-10-08 | 2027-03-05 | 2027-03-25 | 2027-04-01 | 2027-04-15 | 2027-05-01 |  | 252 | 2027-04-01 | 2027-04-21 | 2027-04-21 | 2027-04-28 |  | 20 | WPA-02 | 2027-05-11
| RFQ-ELE-017 | AC/DC Distribution Board | [5 empty] | Electrical | Y | 3 | LB | Actual | 2026-04-21 | 2026-04-27 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-22 | 2026-07-03 | 2026-07-10 | [23 empty] | It is included in RFQ for Solar Power System
18 | RFQ-ELE-018 | Solar Power System | [5 empty] | Electrical |  |  | LA | New Plan |  | 2026-04-27 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-13 | 2026-05-22 | 2026-06-26 | 2026-07-10 |  | 2026-07-23 | 2026-07-27 | 2026-08-03 | 2026-08-31 | 2026-09-14 | 2026-10-04 | 2026-10-07 | 2026-10-08 | 2027-03-12 | 2027-04-01 | 2027-04-08 | 2027-04-22 | 2027-05-08 | 37 |  | 2027-04-08 |  |  |  |  | 13 | WPA-01 | 2027-04-28
| RFQ-ELE-018 | Solar Power System |  |  |  | 0 | 4-3.3 | Electrical | Y | 2 | LA | Forecast | [10 empty] | 2026-07-23 | 2026-07-27 | 2026-08-03 | 2026-08-31 | 2026-09-14 | 2026-10-04 | 2026-10-07 | 2026-10-08 | 2027-03-12 | 2027-04-01 | 2027-04-08 | 2027-04-22 | 2027-05-08 |  | 259 | 2027-04-08 | 2027-04-21 | 2027-04-21 | 2027-04-28 |  | 13 | WPA-02 | 2027-05-11
| RFQ-ELE-018 | Solar Power System | [5 empty] | Electrical | Y | 2 | LA | Actual | 2026-04-21 | 2026-04-27 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-22 | 2026-07-03 | 2026-07-10
19 | RFQ-ELE-019 | Navigation Aid System | [5 empty] | Electrical |  |  | LB | New Plan |  | 2026-05-08 | 2026-05-28 | 2026-05-28 | 2026-05-28 | 2026-05-22 | 2026-05-29 | 2026-07-15 | 2026-07-31 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-10-25 | 2026-10-25 | 2026-10-28 | 2027-03-26 | 2027-04-15 | 2027-04-22 | 2027-05-06 | 2027-05-22 | 36 |  | 2027-04-22 |  |  |  |  | 31 | WPA-01 | 2027-05-30
| RFQ-ELE-019 | Navigation Aid System |  |  |  | 12 | 4-3.2 | Electrical | Y | 4 | LB | Forecast | [8 empty] | 2026-07-31 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-10-25 | 2026-10-25 | 2026-10-28 | 2027-03-26 | 2027-04-15 | 2027-04-22 | 2027-05-06 | 2027-05-22 |  | 252 | 2027-04-22 | 2027-05-23 | 2027-05-23 | 2027-05-30 |  | 31 | WPA-02 | 2027-05-30
| RFQ-ELE-019 | Navigation Aid System | [5 empty] | Electrical | Y | 4 | LB | Actual | 2026-04-21 | 2026-05-08 | 2026-05-28 | 2026-05-28 | 2026-05-28 | 2026-05-28 | 2026-05-29 | 2026-07-12 | 2026-07-21
20 | RFQ-ELE-020 | External Battery Charger | [5 empty] | Electrical |  |  | LC | New Plan |  | 2026-04-24 | 2026-05-06 | 2026-05-07 | 2026-05-14 | 2026-05-14 | 2026-05-27 | 2026-06-26 | 2026-07-10 |  | 2026-07-23 | 2026-07-27 | 2026-08-03 | 2026-08-31 | 2026-09-14 | 2026-10-04 | 2027-03-12 | 2027-04-01 | 2027-03-12 | 2027-04-01 | 2027-04-08 | 2027-04-22 | 2027-05-08 | 37 |  | 2027-04-08 | 0 |  |  |  | 13 | WPA-01 | 2027-04-28
| RFQ-ELE-020 | External Battery Charger |  |  |  | 6 | 4-3.3 | Electrical | N | 3 | LC | Forecast | [10 empty] | 2026-07-23 | 2026-07-27 | 2026-08-03 | 2026-08-31 | 2026-09-14 | 2026-10-04 | 2027-03-12 | 2027-04-01 | 2027-03-12 | 2027-04-01 | 2027-04-08 | 2027-04-22 | 2027-05-08 |  | 259 | 2027-04-08 | 2027-04-21 | 2027-04-21 | 2027-04-28 |  | 13 | WPA-02 | 2027-05-11
| RFQ-ELE-020 | External Battery Charger | [5 empty] | Electrical | N | 3 | LC | Actual | 2026-04-21 | 2026-04-27 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-22 | 2026-07-07 | 2026-07-16 | [23 empty] | It is included in RFQ for Solar Power System
21 | RFQ-INS-021 | Control Valve | [5 empty] | Instrument |  |  | LB | New Plan |  | 2026-05-22 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-18 | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-29 | 2026-10-14 | 2026-12-13 | 2026-12-16 | 2026-12-17 | 2027-02-25 | 2027-03-11 | 2027-03-18 | 2027-04-01 | 2027-04-17 | 30 |  | 2027-03-18 | 0 |  |  |  | 14 | WPA-01 | 2027-04-08
| RFQ-INS-021 | Control Valve |  |  |  | 6 | 4-4.5 | Instrument | N | 2 | LB | Forecast | [7 empty] | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-29 | 2026-10-14 | 2026-12-13 | 2026-12-16 | 2026-12-17 | 2027-02-25 | 2027-03-11 | 2027-03-18 | 2027-04-01 | 2027-04-17 |  | 210 | 2027-03-18 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 14 | WPA-02 | 2027-04-08
| RFQ-INS-021 | Control Valve | [5 empty] | Instrument | N | 2 | LB | Actual | 2026-04-21 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-15
22 | RFQ-INS-022 | Self Regulator Valve | [5 empty] | Instrument |  |  | LB | New Plan |  | 2026-05-22 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-15 | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-29 | 2026-10-14 | 2026-12-13 | 2026-12-16 | 2026-12-17 | 2027-03-11 | 2027-03-25 | 2027-04-01 | 2027-04-15 | 2027-05-01 | 32 |  | 2027-04-01 |  |  |  |  | 0 | WPA-01 | 2027-04-08
| RFQ-INS-022 | Self Regulator Valve |  |  |  | 13 | 4-4.6 | Instrument | N | 4 | LB | Forecast | [7 empty] | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-29 | 2026-10-14 | 2026-12-13 | 2026-12-16 | 2026-12-17 | 2027-03-11 | 2027-03-25 | 2027-04-01 | 2027-04-15 | 2027-05-01 |  | 224 | 2027-04-01 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 0 | WPA-02 | 2027-04-08
| RFQ-INS-022 | Self Regulator Valve | [5 empty] | Instrument | N | 4 | LB | Actual | 2026-04-21 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-15 | 2026-07-24
23 | RFQ-INS-023 | Actuated Choke Valve | [5 empty] | Instrument |  |  | LA | New Plan |  | 2026-05-22 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-10 | 2026-06-18 | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-29 | 2026-10-14 | 2026-12-13 | 2026-12-16 | 2026-12-17 | 2027-04-13 | 2027-04-27 | 2027-05-27 | 2027-06-10 | 2027-06-26 | 40 |  | 2027-05-27 | 0 |  |  |  | 16 | WPA-01 | 2027-06-15
| RFQ-INS-023 | Actuated Choke Valve |  |  |  | 1 | 4-4.3 | Instrument | Y | 2 | LA | Forecast | [7 empty] | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-29 | 2026-10-14 | 2026-12-13 | 2026-12-16 | 2026-12-17 | 2027-04-13 | 2027-04-27 | 2027-05-27 | 2027-06-10 | 2027-06-26 |  | 280 | 2027-05-27 | 2027-06-12 | 2027-06-13 | 2027-06-20 | installation during Reinstatement | 16 | WPA-02 | 2027-06-15
| RFQ-INS-023 | Actuated Choke Valve | [5 empty] | Instrument | Y | 2 | LA | Actual | 2026-04-21 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-18 | 2026-07-24
24 | RFQ-INS-024 | Actuated Ball Valve | [5 empty] | Instrument |  |  | LB | New Plan |  | 2026-06-05 | 2026-06-12 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-17 | 2026-08-05 | 2026-08-20 |  | 2026-09-02 | 2026-09-04 | 2026-09-11 | 2026-10-19 | 2026-11-03 | 2027-01-02 | 2027-01-05 | 2027-01-06 | 2027-03-29 | 2027-04-12 | 2027-05-12 | 2027-05-26 | 2027-06-11 | 36 |  | 2027-05-12 |  |  |  |  | 11 | WPA-01 | 2027-05-30
| RFQ-INS-024 | Actuated Ball Valve |  |  |  | 20 | 4-4.4 | Instrument | N | 2 | LB | Forecast | [7 empty] | 2026-08-05 | 2026-08-20 |  | 2026-09-02 | 2026-09-04 | 2026-09-11 | 2026-10-19 | 2026-11-03 | 2027-01-02 | 2027-01-05 | 2027-01-06 | 2027-03-29 | 2027-04-12 | 2027-05-12 | 2027-05-26 | 2027-06-11 |  | 252 | 2027-05-12 | 2027-05-23 | 2027-05-23 | 2027-05-30 | installation during Reinstatement | 11 | WPA-02 | 2027-05-30
| RFQ-INS-024 | Actuated Ball Valve | [5 empty] | Instrument | N | 2 | LB | Actual |  | 2026-06-05 | 2026-06-13 | 2026-06-13 | 2026-06-13 | 2026-06-13 | 2026-06-23
25 | RFQ-INS-025 | Actuated Compact Ball Valve | [5 empty] | Instrument |  |  | LB | New Plan |  | 2026-05-20 | 2026-06-09 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-07-21 | 2026-07-27 |  | 2026-08-07 | 2026-08-11 | 2026-08-18 | 2026-09-15 | 2026-09-29 | 2026-11-28 | 2026-12-01 | 2026-12-02 | 2027-03-31 | 2027-04-14 | 2027-05-14 | 2027-05-28 | 2027-06-13 | 40 |  | 2027-05-14 |  |  |  |  | 9 | WPA-01 | 2027-05-30
| RFQ-INS-025 | Actuated Compact Ball Valve |  |  |  | 9 | 4-4.4 | Instrument | Y | 2 | LB | Forecast | [7 empty] | 2026-07-13 | 2026-07-27 |  | 2026-08-07 | 2026-08-11 | 2026-08-18 | 2026-09-15 | 2026-09-29 | 2026-11-28 | 2026-12-01 | 2026-12-02 | 2027-03-31 | 2027-04-14 | 2027-05-14 | 2027-05-28 | 2027-06-13 |  | 280 | 2027-05-14 | 2027-05-23 | 2027-05-23 | 2027-05-30 | installation during Reinstatement | 9 | WPA-02 | 2027-05-30
| RFQ-INS-025 | Actuated Compact Ball Valve | [5 empty] | Instrument | Y | 2 | LB | Actual | 2026-04-21 | 2026-05-27 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-18
26 | RFQ-INS-026 | Safety Relief Valves | [5 empty] | Instrument |  |  | LB | New Plan |  | 2026-06-12 | 2026-06-19 | 2026-06-22 | 2026-06-29 | 2026-06-30 | 2026-07-13 | 2026-08-13 | 2026-08-27 |  | 2026-09-09 | 2026-09-11 | 2026-09-18 | 2026-10-26 | 2026-11-09 | 2027-01-08 | 2027-01-11 | 2027-01-12 | 2027-03-31 | 2027-04-14 | 2027-04-21 | 2027-05-05 | 2027-05-21 | 32 |  | 2027-04-21 |  |  |  |  | 32 | WPA-01 | 2027-05-30
| RFQ-INS-026 | Safety Relief Valves |  |  |  | 40 | 4-4.7 | Instrument | N | 2 | LB | Forecast | [6 empty] | 2026-07-13 | 2026-08-13 | 2026-08-27 |  | 2026-09-09 | 2026-09-11 | 2026-09-18 | 2026-10-26 | 2026-11-09 | 2027-01-08 | 2027-01-11 | 2027-01-12 | 2027-03-31 | 2027-04-14 | 2027-04-21 | 2027-05-05 | 2027-05-21 |  | 224 | 2027-04-21 | 2027-05-23 | 2027-05-23 | 2027-05-30 | installation during Reinstatement | 32 | WPA-02 | 2027-05-30
| RFQ-INS-026 | Safety Relief Valves | [5 empty] | Instrument | N | 2 | LB | Actual |  | 2026-06-16 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-06-30
27 | RFQ-INS-027 | Coriolis Flow Meters | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-07-24 | 2026-07-06 | 2026-07-06 | 2026-08-11 | 2026-08-11 | 2026-08-25 | 2026-09-11 | 2026-09-25 |  | 2026-10-15 | 2026-10-19 | 2026-10-26 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-12-15 | 2026-12-17 | 2027-02-16 | 2027-03-02 | 2027-03-09 | 2027-03-23 | 2027-04-08 | 20.7143 |  | 2027-03-09 |  |  |  |  | 23 | WPA-01 | 2027-04-08
| RFQ-INS-027 | Coriolis Flow Meters |  |  |  | 60 | 4-4.9 | Instrument | N | 3 | LC | Forecast | [5 empty] | 2026-08-11 | 2026-08-25 | 2026-09-11 | 2026-09-25 |  | 2026-10-15 | 2026-10-19 | 2026-10-26 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-12-15 | 2026-12-17 | 2027-02-16 | 2027-03-02 | 2027-03-09 | 2027-03-23 | 2027-04-08 |  | 145 | 2027-03-09 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 23 | WPA-02 | 2027-04-08
| RFQ-INS-027 | Coriolis Flow Meters | [5 empty] | Instrument | N | 3 | LC | Actual |  | 2026-06-25 | 2026-07-16 | 2026-07-16 | 2026-07-16
28 | RFQ-INS-028 | WELLHEAD CONTROL PANEL (WHCP) | [5 empty] | Instrument |  |  | LA | New Plan |  | 2026-04-24 | 2026-05-06 | 2026-05-06 | 2026-05-13 | 2026-05-14 | 2026-05-20 | 2026-06-26 | 2026-07-01 |  | 2026-07-15 | 2026-07-17 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-10-14 | 2026-10-14 | 2026-10-16 | 2027-02-15 | 2027-03-17 | 2027-03-24 | 2027-04-07 | 2027-04-23 | 36 |  | 2027-03-24 |  |  |  |  | 8 | WPA-01 | 2027-04-08
| RFQ-INS-028 | WELLHEAD CONTROL PANEL (WHCP) |  |  |  | 10 | 4-4.2 | Instrument | Y | 2 | LA | Forecast | [10 empty] | 2026-07-23 | 2026-07-27 | 2026-08-03 | 2026-08-31 | 2026-09-14 | 2026-10-24 | 2026-10-24 | 2026-10-26 | 2027-02-23 | 2027-03-25 | 2027-04-01 | 2027-04-15 | 2027-05-01 |  | 252 | 2027-04-01 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 0 | WPA-02 | 2027-04-08
| RFQ-INS-028 | WELLHEAD CONTROL PANEL (WHCP) | [5 empty] | Instrument | Y | 2 | LA | Actual | 2026-04-21 | 2026-04-28 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-20 | 2026-07-03 | 2026-07-07 | 2026-07-24
29 | RFQ-INS-029 | Pressure Gauge | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-08-05 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-09-03 | 2026-09-22 | 2026-10-06 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-03 | 2027-02-17 | 2027-02-24 | 2027-03-10 | 2027-03-26 | 18 |  | 2027-02-24 |  |  |  |  | 36 | WPA-01 | 2027-04-08
| RFQ-INS-029 | Pressure Gauge |  |  |  | 37 | 4-4.12 | Instrument | N | 4 | LC | Forecast |  | 2026-08-05 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-09-03 | 2026-09-22 | 2026-10-06 |  | 2026-10-20 | 2026-10-22 | 2026-10-29 | 2026-11-19 | 2026-12-03 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-02-02 | 2027-02-16 | 2027-02-23 | 2027-03-09 | 2027-03-25 |  | 126 | 2027-02-23 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 37 | WPA-02 | 2027-04-08
| RFQ-INS-029 | Pressure Gauge | [5 empty] | Instrument | N | 4 | LC | Actual
30 | RFQ-INS-030 | Pressure Transmitter | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-08-05 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-09-03 | 2026-09-22 | 2026-10-06 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-03 | 2027-02-17 | 2027-02-24 | 2027-03-10 | 2027-03-26 | 18 |  | 2027-02-24 |  |  |  |  | 36 | WPA-01 | 2027-04-08
| RFQ-INS-030 | Pressure Transmitter |  |  |  | 37 | 4-4.12 | Instrument | N | 4 | LC | Forecast |  | 2026-08-05 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-09-03 | 2026-09-22 | 2026-10-06 |  | 2026-10-20 | 2026-10-22 | 2026-10-29 | 2026-11-19 | 2026-12-03 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-02-02 | 2027-02-16 | 2027-02-23 | 2027-03-09 | 2027-03-25 |  | 126 | 2027-02-23 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 37 | WPA-02 | 2027-04-08
| RFQ-INS-030 | Pressure Transmitter | [5 empty] | Instrument | N | 4 | LC | Actual
31 | RFQ-INS-031 | Temperature Gauge | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-08-05 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-09-03 | 2026-09-22 | 2026-10-06 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-03 | 2027-02-17 | 2027-02-24 | 2027-03-10 | 2027-03-26 | 18 |  | 2027-02-24 |  |  |  |  | 36 | WPA-01 | 2027-04-08
| RFQ-INS-031 | Temperature Gauge |  |  |  | 37 | 4-4.12 | Instrument | N | 4 | LC | Forecast |  | 2026-08-05 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-09-03 | 2026-09-22 | 2026-10-06 |  | 2026-10-20 | 2026-10-22 | 2026-10-29 | 2026-11-19 | 2026-12-03 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-02-02 | 2027-02-16 | 2027-02-23 | 2027-03-09 | 2027-03-25 |  | 126 | 2027-02-23 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 37 | WPA-02 | 2027-04-08
| RFQ-INS-031 | Temperature Gauge | [5 empty] | Instrument | N | 4 | LC | Actual
32 | RFQ-INS-032 | Temperature Transmitter | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-08-05 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-09-03 | 2026-09-22 | 2026-10-06 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-03 | 2027-02-17 | 2027-02-24 | 2027-03-10 | 2027-03-26 | 18 |  | 2027-02-24 |  |  |  |  | 36 | WPA-01 | 2027-04-08
| RFQ-INS-032 | Temperature Transmitter |  |  |  | 37 | 4-4.12 | Instrument | N | 4 | LC | Forecast |  | 2026-08-05 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-09-03 | 2026-09-22 | 2026-10-06 |  | 2026-10-20 | 2026-10-22 | 2026-10-29 | 2026-11-19 | 2026-12-03 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-02-02 | 2027-02-16 | 2027-02-23 | 2027-03-09 | 2027-03-25 |  | 126 | 2027-02-23 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 37 | WPA-02 | 2027-04-08
| RFQ-INS-032 | Temperature Transmitter | [5 empty] | Instrument | N | 4 | LC | Actual
33 | RFQ-INS-033 | Vortex Flow Meter | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-07-24 | 2026-07-06 | 2026-07-06 | 2026-08-11 | 2026-08-11 | 2026-08-25 | 2026-09-11 | 2026-09-25 |  | 2026-10-15 | 2026-10-19 | 2026-10-26 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-12-15 | 2026-12-17 | 2027-01-28 | 2027-02-11 | 2027-02-18 | 2027-03-04 | 2027-03-20 | 18 |  | 2027-02-18 |  |  |  |  | 42 | WPA-01 | 2027-04-08
| RFQ-INS-033 | Vortex Flow Meter |  |  |  | 79 | 4-4.10 | Instrument | N | 3 | LC | Forecast | [5 empty] | 2026-08-11 | 2026-08-25 | 2026-09-11 | 2026-09-25 |  | 2026-10-15 | 2026-10-19 | 2026-10-26 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-12-15 | 2026-12-17 | 2027-01-28 | 2027-02-11 | 2027-02-18 | 2027-03-04 | 2027-03-20 |  | 126 | 2027-02-18 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 42 | WPA-02 | 2027-04-08
| RFQ-INS-033 | Vortex Flow Meter | [5 empty] | Instrument | N | 3 | LC | Actual |  | 2026-06-24 | 2026-07-08 | 2026-07-08 | 2026-07-08
34 | RFQ-INS-034 | LEVEL GAUGE AND TRANSMITTERS | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-07-24 | 2026-07-06 | 2026-07-06 | 2026-08-11 | 2026-08-11 | 2026-08-25 | 2026-09-11 | 2026-09-25 |  | 2026-10-15 | 2026-09-10 | 2026-09-17 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-11-14 | 2026-11-16 | 2027-01-28 | 2027-02-11 | 2027-02-18 | 2027-03-04 | 2027-03-20 | 18 |  | 2027-02-18 |  |  |  |  | 42 | WPA-01 | 2027-04-08
| RFQ-INS-034 | LEVEL GAUGE AND TRANSMITTERS |  |  |  | 79 | 4-4.12 | Instrument | N | 4 | LC | Forecast |  |  | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-25 | 2026-09-11 | 2026-09-25 |  | 2026-10-15 | 2026-10-19 | 2026-10-26 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-12-15 | 2026-12-17 | 2027-01-28 | 2027-02-11 | 2027-02-18 | 2027-03-04 | 2027-03-20 |  | 126 | 2027-02-18 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 42 | WPA-02 | 2027-04-08
| RFQ-INS-034 | LEVEL GAUGE AND TRANSMITTERS | [5 empty] | Instrument | N | 4 | LC | Actual |  | 2026-06-30 | 2026-07-22 | 2026-07-22 | 2026-07-22
35 | RFQ-INS-035 | Pig Signaller | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-08-05 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-09-03 | 2026-09-22 | 2026-10-06 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-03 | 2027-02-17 | 2027-02-24 | 2027-03-10 | 2027-03-26 | 18 |  | 2027-02-24 |  |  |  |  | 36 | WPA-01 | 2027-04-08
| RFQ-INS-035 | Pig Signaller |  |  |  | 37 | 4-4.11 | Instrument | N | 4 | LC | Forecast |  | 2026-08-05 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-09-03 | 2026-09-22 | 2026-10-06 |  | 2026-10-20 | 2026-10-22 | 2026-10-29 | 2026-11-19 | 2026-12-03 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-02-02 | 2027-02-16 | 2027-02-23 | 2027-03-09 | 2027-03-25 |  | 126 | 2027-02-23 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 37 | WPA-02 | 2027-04-08
| RFQ-INS-035 | Pig Signaller | [5 empty] | Instrument | N | 4 | LC | Actual
36 | RFQ-INS-036 | Rrestriction Orifice | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-07-24 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-17 | 2026-09-11 | 2026-09-25 |  | 2026-10-15 | 2026-09-29 | 2026-10-13 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-12-01 | 2026-12-03 | 2027-02-25 | 2027-03-11 | 2027-03-18 | 2027-04-01 | 2027-04-17 | 22 |  | 2027-03-18 |  |  |  |  | 14 | WPA-01 | 2027-04-08
| RFQ-INS-036 | Rrestriction Orifice |  |  |  | 35 | 4-4.12 | Instrument | N | 4 | LC | Forecast |  |  | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-25 | 2026-09-11 | 2026-09-25 |  | 2026-10-15 | 2026-10-19 | 2026-10-26 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-12-15 | 2026-12-17 | 2027-02-25 | 2027-03-11 | 2027-03-18 | 2027-04-01 | 2027-04-17 |  | 154 | 2027-03-18 | 2027-04-01 | 2027-04-21 | 2027-04-28 | installation during Reinstatement | 14 | WPA-02 | 2027-04-08
| RFQ-INS-036 | Rrestriction Orifice | [5 empty] | Instrument | N | 4 | LC | Actual |  | 2026-07-03 | 2026-07-22 | 2026-07-22 | 2026-07-22
37 | RFQ-INS-037 | PLC System | [5 empty] | Instrument |  |  | LB | New Plan |  | 2026-05-19 | 2026-05-27 | 2026-05-27 | 2026-06-05 | 2026-06-06 | 2026-06-22 | 2026-07-20 | 2026-07-23 |  | 2026-08-06 | 2026-08-10 | 2026-08-17 | 2026-09-14 | 2026-09-28 | 2026-10-13 | 2026-10-13 | 2026-10-15 | 2027-03-02 | 2027-04-01 | 2027-04-15 | 2027-04-29 | 2027-05-15 | 36 |  | 2027-04-15 |  |  |  |  | 8 | WPA-01 | 2027-04-30
| RFQ-INS-037 | PLC System |  |  |  | 8 | 4-4.1 | Instrument | N | 2 | LB | Forecast | [10 empty] | 2026-08-06 | 2026-08-10 | 2026-08-17 | 2026-09-14 | 2026-09-28 | 2026-10-13 | 2026-10-13 | 2026-10-15 | 2027-03-02 | 2027-04-01 | 2027-04-15 | 2027-04-29 | 2027-05-15 |  | 252 | 2027-04-15 | 2027-04-23 | 2027-04-21 | 2027-04-28 |  | 8 | WPA-02 | 2027-04-30
| RFQ-INS-037 | PLC System | [5 empty] | Instrument | N | 2 | LB | Actual | 2026-04-21 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-15 | 2026-07-10 | 2026-07-16
38 | RFQ-INS-038 | Fire and Gas Detector | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-08-10 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-09-09 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-08 | 2027-02-22 | 2027-03-01 | 2027-03-15 | 2027-03-31 | 18.7143 |  | 2027-03-01 |  |  |  |  | 31 | WPA-01 | 2027-04-08
| RFQ-INS-038 | Fire and Gas Detector |  |  |  | 31 | 4-4.20 | Instrument | N | 4 | LC | Forecast |  | 2026-08-09 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-09-07 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-08 | 2027-02-22 | 2027-03-01 | 2027-03-15 | 2027-03-31 |  | 131 | 2027-03-01 | 2027-04-01 | 2027-04-08 | 2027-04-15 |  | 31 | WPA-02 | 2027-04-08
| RFQ-INS-038 | Fire and Gas Detector | [5 empty] | Instrument | N | 4 | LC | Actual
39 | RFQ-INS-039 | Dip Tape Level Indicator | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-07-24 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-24 | 2026-09-11 | 2026-09-25 |  | 2026-10-15 | 2026-10-08 | 2026-10-15 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-12-12 | 2026-12-14 | 2027-01-28 | 2027-02-11 | 2027-02-18 | 2027-03-04 | 2027-03-20 | 18 |  | 2027-02-18 |  |  |  |  | 42 | WPA-01 | 2027-04-08
| RFQ-INS-039 | Dip Tape Level Indicator |  |  |  | 79 | 4-4.12 | Instrument | N | 4 | LC | Forecast |  | 2026-07-24 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-25 | 2026-09-11 | 2026-09-25 |  | 2026-10-15 | 2026-10-19 | 2026-10-26 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-12-15 | 2026-12-17 | 2027-01-28 | 2027-02-11 | 2027-02-18 | 2027-03-04 | 2027-03-20 |  | 126 | 2027-02-18 | 2027-04-01 | 2027-04-08 | 2027-04-15 |  | 42 | WPA-02 | 2027-04-08
| RFQ-INS-039 | Dip Tape Level Indicator | [5 empty] | Instrument | N | 4 | LC | Actual | [32 empty] | Combined into RFQ-006 CHEMICAL INJECTION PUMPS PACKAGE | bar: 2026-10-15 to 2026-12-15; 2027-01-28 to 2027-03-20
40 | RFQ-INS-040 | Position Limit Switches | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-08-10 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-09-09 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-03 | 2027-02-17 | 2027-02-24 | 2027-03-10 | 2027-03-26 | 18 |  | 2027-02-24 |  |  |  |  | 36 | WPA-01 | 2027-04-08
| RFQ-INS-040 | Position Limit Switches |  |  |  | 36 | 4-4.14 | Instrument | N | 4 | LC | Forecast |  | 2026-08-09 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-09-07 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-03 | 2027-02-17 | 2027-02-24 | 2027-03-10 | 2027-03-26 |  | 126 | 2027-02-24 | 2027-04-01 | 2027-04-08 | 2027-04-15 |  | 36 | WPA-02 | 2027-04-08
| RFQ-INS-040 | Position Limit Switches | [5 empty] | Instrument | N | 4 | LC | Actual
41 | RFQ-INS-041 | Guided Wave Radar Level Transmitter | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-07-17 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-04 | 2026-08-10 | 2026-08-31 | 2026-09-05 |  | 2026-09-18 | 2026-09-21 | 2026-09-28 | 2026-10-27 | 2026-11-13 | 2026-11-25 | 2026-11-25 | 2026-11-27 | 2027-03-27 | 2027-04-10 | 2027-04-17 | 2027-05-01 | 2027-05-17 | 30 |  | 2027-04-16 |  |  |  |  | 7 | WPA-01 | 2027-04-30
| RFQ-INS-041 | Guided Wave Radar Level Transmitter |  |  |  | 17 | 4-4.12 | Instrument | N | 4 | LC | Forecast |  |  | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-10 | 2026-08-28 | 2026-09-11 |  | 2026-09-24 | 2026-09-29 | 2026-10-13 | 2026-11-03 | 2026-11-17 | 2026-12-02 | 2026-12-02 | 2026-12-04 | 2027-04-01 | 2027-04-15 | 2027-04-22 | 2027-05-06 | 2027-05-22 |  | 210 | 2027-04-22 | 2027-04-23 | 2027-04-21 | 2027-04-28 |  | 1 | WPA-02 | 2027-04-30
| RFQ-INS-041 | Guided Wave Radar Level Transmitter | [5 empty] | Instrument | N | 4 | LC | Actual |  | 2026-07-01 | 2026-07-22 | 2026-07-22 | 2026-07-22
42 | RFQ-INS-042 | OIL IN WATER ANALYZER | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-07-17 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-04 | 2026-08-17 | 2026-09-10 | 2026-09-15 |  | 2026-09-29 | 2026-10-01 | 2026-10-08 | 2026-11-06 | 2026-11-23 | 2026-12-05 | 2026-12-05 | 2026-12-07 | 2027-02-23 | 2027-03-09 | 2027-03-16 | 2027-03-30 | 2027-04-15 | 24 |  | 2027-03-16 |  |  |  |  | 16 | WPA-01 | 2027-04-08
| RFQ-INS-042 | OIL IN WATER ANALYZER |  |  |  | 37 | 4-4.8 | Instrument | N | 3 | LC | Forecast |  |  | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-10 | 2026-08-28 | 2026-09-11 |  | 2026-09-24 | 2026-09-29 | 2026-10-13 | 2026-11-03 | 2026-11-17 | 2026-12-02 | 2026-12-02 | 2026-12-04 | 2027-02-18 | 2027-03-04 | 2027-03-11 | 2027-03-25 | 2027-04-10 |  | 168 | 2027-03-11 | 2027-04-01 | 2027-04-08 | 2027-04-15 |  | 21 | WPA-02 | 2027-04-08
| RFQ-INS-042 | OIL IN WATER ANALYZER | [5 empty] | Instrument | N | 3 | LC | Actual |  | 2026-07-01 | 2026-07-22 | 2026-07-22 | 2026-07-22
43 | RFQ-INS-043 | Level Switch | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-08-10 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-09-09 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-28 | 2026-11-09 | 2026-11-17 | 2026-11-24 | 2026-12-19 | 2026-12-21 | 2026-11-29 | 2026-12-13 | 2026-12-20 | 2027-01-03 | 2027-01-19 | 8.5714 |  | 2026-12-20 |  |  |  |  | 102 | WPA-01 | 2027-04-08
| RFQ-INS-043 | Level Switch |  |  |  | 102 | 4-4.13 | Instrument | N | 4 | LC | Forecast |  | 2026-08-09 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-09-07 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-28 | 2026-11-07 | 2026-11-17 | 2026-11-24 | 2026-11-24 | 2026-11-26 | 2026-11-29 | 2026-12-13 | 2026-12-20 | 2027-01-03 | 2027-01-19 |  | 60 | 2026-12-20 | 2027-04-01 | 2027-04-08 | 2027-04-15 |  | 102 | WPA-02 | 2027-04-08
| RFQ-INS-043 | Level Switch | [5 empty] | Instrument | N | 4 | LC | Actual
44 | RFQ-INS-044 | Flow Switch | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-08-10 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 2026-08-27 | 2026-09-09 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-28 | 2026-11-09 | 2026-11-19 | 2026-11-26 | 2026-12-19 | 2026-12-21 | 2026-11-29 | 2026-12-13 | 2026-12-20 | 2027-01-03 | 2027-01-19 | 8.5714 |  | 2026-12-20 |  |  |  |  | 102 | WPA-01 | 2027-04-08
| RFQ-INS-044 | Flow Switch |  |  |  | 102 | 4-4.13 | Instrument | N | 4 | LC | Forecast |  | 2026-08-09 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-09-07 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2026-11-29 | 2026-12-13 | 2026-12-20 | 2027-01-03 | 2027-01-19 |  | 60 | 2026-12-20 | 2027-04-01 | 2027-04-08 | 2027-04-15 |  | 102 | WPA-02 | 2027-04-08
| RFQ-INS-044 | Flow Switch | [5 empty] | Instrument | N | 4 | LC | Actual
45 | RFQ-INS-045 | SCADA System | [5 empty] | Instrument |  |  | LB | New Plan |  | 2026-05-19 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-06 | 2026-06-26 | 2026-09-01 | 2026-09-15 |  | 2026-09-29 | 2026-10-08 | 2026-10-15 | 2026-11-12 | 2026-11-26 | 2026-12-11 | 2026-10-13 | 2026-10-15 | 2027-04-25 | 2027-05-25 | 2027-06-08 | 2027-06-22 | 2027-07-08 | 36 |  | 2027-06-08 |  |  |  |  | 45 | WPA-01 | 2027-07-30
| RFQ-INS-045 | SCADA System |  |  |  | 8 | 4-4.18 | Instrument | N | 2 | LB | Forecast | [7 empty] | 2026-09-01 | 2026-09-15 |  | 2026-09-29 | 2026-10-08 | 2026-10-15 | 2026-11-12 | 2026-11-26 | 2026-12-11 | 2026-12-11 | 2026-12-13 | 2027-04-25 | 2027-05-25 | 2027-06-08 | 2027-06-22 | 2027-07-08 |  | 252 | 2027-06-08 | 2027-07-23 | 2027-04-21 | 2027-04-28 |  | 45 | WPA-02 | 2027-07-30
| RFQ-INS-045 | SCADA System | [5 empty] | Instrument | N | 2 | LB | Actual | 2026-04-21 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-17
46 | RFQ-TEL-046 | TELECOMMUNICATION SYSTEM | [5 empty] | Telecommunication |  |  | LC | New Plan |  | 2026-06-16 | 2026-06-25 | 2026-06-26 | 2026-07-03 | 2026-07-04 | 2026-07-20 | 2026-08-14 | 2026-08-28 |  | 2026-09-10 | 2026-09-14 | 2026-09-21 | 2026-10-20 | 2026-11-04 | 2026-11-19 | 2026-11-19 | 2026-11-21 | 2027-02-16 | 2027-03-02 | 2027-03-09 | 2027-03-23 | 2027-04-08 | 25.7143 |  | 2027-03-09 |  |  |  |  | 7 | WPA-01 | 2027-03-23
| RFQ-TEL-046 | TELECOMMUNICATION SYSTEM |  |  |  | 42 | 4-4.15 | Telecommunication | N | 3 | LC | Forecast | [6 empty] | 2026-07-20 | 2026-08-15 | 2026-08-28 |  | 2026-09-10 | 2026-09-14 | 2026-09-21 | 2026-10-20 | 2026-11-04 | 2026-11-19 | 2026-11-19 | 2026-11-21 | 2027-02-16 | 2027-03-02 | 2027-03-09 | 2027-03-23 | 2027-04-08 |  | 180 | 2027-03-09 | 2027-03-16 | 2027-03-08 | 2027-03-15 |  | 7 | WPA-02 | 2027-04-03
| RFQ-TEL-046 | TELECOMMUNICATION SYSTEM | [5 empty] | Telecommunication | N | 3 | LC | Actual |  | 2026-05-27 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-07-09
47 | RFQ-TEL-047 | MARINE RACON (RACON) | [5 empty] | Telecommunication |  |  | LC | New Plan |  | 2026-06-16 | 2026-06-25 | 2026-06-26 | 2026-07-03 | 2026-07-04 | 2026-07-20 | 2026-08-14 | 2026-08-28 |  | 2026-09-10 | 2026-09-14 | 2026-09-21 | 2026-10-20 | 2026-11-04 | 2026-11-19 | 2026-11-19 | 2026-11-21 | 2026-12-10 | 2026-12-24 | 2026-12-31 | 2027-01-14 | 2027-01-30 | 16 |  | 2026-12-31 | 0 |  |  |  | 75 | WPA-01 | 2027-03-23
| RFQ-TEL-047 | MARINE RACON (RACON) |  |  |  | 110 | 4-4.16 | Telecommunication | N | 3 | LC | Forecast | [6 empty] | 2026-07-20 | 2026-08-15 | 2026-08-28 |  | 2026-09-10 | 2026-09-14 | 2026-09-21 | 2026-10-20 | 2026-11-04 | 2026-11-19 | 2026-11-19 | 2026-11-21 | 2026-12-10 | 2026-12-24 | 2026-12-31 | 2027-01-14 | 2027-01-30 |  | 112 | 2026-12-31 | 2027-03-16 | 2027-05-23 | 2027-05-30 |  | 75 | WPA-02 | 2027-04-03
| RFQ-TEL-047 | MARINE RACON (RACON) | [5 empty] | Telecommunication | N | 3 | LC | Actual |  | 2026-05-27 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-07-09
48 | RFQ-PIP-048 | BALL VALVE (FLANGE END) | [5 empty] | Piping |  |  | LC | New Plan |  | 2026-05-21 | 2026-05-28 | 2026-05-29 | 2026-06-09 | 2026-06-10 | 2026-06-24 | 2026-07-15 | 2026-07-31 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-14 | 2026-09-28 | 2026-11-27 | 2026-11-30 | 2026-12-01 | 2027-01-19 | 2027-02-02 | 2027-02-09 | 2027-02-23 | 2027-03-11 | 25.7143 |  | 2027-02-09 |  |  |  |  | 25 | WPA-01 | 2027-03-13
| RFQ-PIP-048 | BALL VALVE (FLANGE END) |  |  |  | 35 | 4-1 | Piping | Y | 2/3 | LC | Forecast | [7 empty] | 2026-07-23 | 2026-08-10 |  | 2026-08-21 | 2026-08-25 | 2026-09-01 | 2026-09-22 | 2026-10-06 | 2026-12-05 | 2026-12-08 | 2026-12-09 | 2027-01-27 | 2027-02-10 | 2027-02-17 | 2027-03-03 | 2027-03-19 |  | 180 | 2027-02-17 | 2027-03-06 | 2027-03-23 | 2027-03-30 |  | 17 | WPA-02 | 2027-03-30
| RFQ-PIP-048 | BALL VALVE (FLANGE END) | [5 empty] | Piping | Y | 2/3 | LC | Actual | 2026-06-01 | 2026-05-25 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-25 | 2026-07-24 | [21 empty] | install before Testing
49 | RFQ-PIP-049 | BALL VALVE (Welded END) | [5 empty] | Piping |  |  | LC | New Plan |  | 2026-05-21 | 2026-05-28 | 2026-05-29 | 2026-06-09 | 2026-06-10 | 2026-06-24 | 2026-07-15 | 2026-07-31 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-14 | 2026-09-28 | 2026-11-27 | 2026-11-30 | 2026-12-01 | 2027-01-19 | 2027-02-02 | 2027-02-09 | 2027-02-23 | 2027-03-11 | 25.7143 |  | 2027-02-09 |  |  |  |  | 25 | WPA-01 | 2027-03-13
| RFQ-PIP-049 | BALL VALVE (Welded END) |  |  |  | 35 | 4-1 | Piping | Y | 2/3 | LC | Forecast | [7 empty] | 2026-07-23 | 2026-08-10 |  | 2026-08-21 | 2026-08-25 | 2026-09-01 | 2026-09-22 | 2026-10-06 | 2026-12-05 | 2026-12-08 | 2026-12-09 | 2027-01-27 | 2027-02-10 | 2027-02-17 | 2027-03-03 | 2027-03-19 |  | 180 | 2027-02-17 | 2027-03-06 | 2027-03-08 | 2027-03-15 |  | 17 | WPA-02 | 2027-03-30
| RFQ-PIP-049 | BALL VALVE (Welded END) | [5 empty] | Piping | Y | 2/3 | LC | Actual | 2026-06-01 | 2026-05-25 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-25 | 2026-07-24
50 | RFQ-PIP-050 | GLOBE VALVE (FLANGE END) | [5 empty] | Piping |  |  | LC | New Plan |  | 2026-05-21 | 2026-05-28 | 2026-05-29 | 2026-06-09 | 2026-06-10 | 2026-06-24 | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-21 | 2026-10-05 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2027-01-26 | 2027-02-09 | 2027-02-16 | 2027-03-02 | 2027-03-18 | 25.7143 |  | 2027-02-16 | 0 |  |  |  | 18 | WPA-01 | 2027-03-13
| RFQ-PIP-050 | GLOBE VALVE (FLANGE END) |  |  |  | 28 | 4-1 | Piping | Y | 2/3 | LC | Forecast | [8 empty] | 2026-08-11 |  | 2026-08-24 | 2026-08-26 | 2026-09-02 | 2026-09-23 | 2026-10-07 | 2026-12-06 | 2026-12-09 | 2026-12-10 | 2027-01-30 | 2027-02-13 | 2027-02-20 | 2027-03-06 | 2027-03-22 |  | 180 | 2027-02-20 | 2027-03-06 | 2027-03-23 | 2027-03-30 |  | 14 | WPA-02 | 2027-03-30
| RFQ-PIP-050 | GLOBE VALVE (FLANGE END) | [5 empty] | Piping | Y | 2/3 | LC | Actual | 2026-06-01 | 2026-05-25 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-25 | 2026-07-24 | [21 empty] | install before Testing
51 | RFQ-PIP-051 | GLOBE VALVE (WELDED END) | [5 empty] | Piping |  |  | LC | New Plan |  | 2026-05-21 | 2026-05-28 | 2026-05-29 | 2026-06-09 | 2026-06-10 | 2026-06-24 | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-21 | 2026-10-05 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2027-01-26 | 2027-02-09 | 2027-02-16 | 2027-03-02 | 2027-03-18 | 25.7143 |  | 2027-02-16 | 0 |  |  |  | 18 | WPA-01 | 2027-03-13
| RFQ-PIP-051 | GLOBE VALVE (WELDED END) |  |  |  | 28 | 4-1 | Piping | Y | 2/3 | LC | Forecast | [8 empty] | 2026-08-11 |  | 2026-08-24 | 2026-08-26 | 2026-09-02 | 2026-09-23 | 2026-10-07 | 2026-12-06 | 2026-12-09 | 2026-12-10 | 2027-01-30 | 2027-02-13 | 2027-02-20 | 2027-03-06 | 2027-03-22 |  | 180 | 2027-02-20 | 2027-03-06 | 2027-03-08 | 2027-03-15 |  | 14 | WPA-02 | 2027-03-30
| RFQ-PIP-051 | GLOBE VALVE (WELDED END) | [5 empty] | Piping | Y | 2/3 | LC | Actual | 2026-06-01 | 2026-05-25 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-25 | 2026-07-24
52 | RFQ-PIP-052 | CHECK VALVE (FLANGE END) | [5 empty] | Piping |  |  | LC | New Plan |  | 2026-05-21 | 2026-05-28 | 2026-05-29 | 2026-06-09 | 2026-06-10 | 2026-06-24 | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-21 | 2026-10-05 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2027-02-11 | 2027-02-25 | 2027-03-04 | 2027-03-18 | 2027-04-03 | 28 |  | 2027-03-04 | 0 |  |  |  | 2 | WPA-01 | 2027-03-13
| RFQ-PIP-052 | CHECK VALVE (FLANGE END) |  |  |  | 12 | 4-1 | Piping | Y | 2/3 | LC | Forecast | [7 empty] | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-21 | 2026-10-05 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2027-02-11 | 2027-02-25 | 2027-03-04 | 2027-03-18 | 2027-04-03 |  | 196 | 2027-03-04 | 2027-03-06 | 2027-03-23 | 2027-03-30 |  | 2 | WPA-02 | 2027-03-30
| RFQ-PIP-052 | CHECK VALVE (FLANGE END) | [5 empty] | Piping | Y | 2/3 | LC | Actual | 2026-06-01 | 2026-05-25 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-25 | 2026-07-24 | [21 empty] | install before Testing
53 | RFQ-PIP-053 | CHECK VALVE (WELDED END) | [5 empty] | Piping |  |  | LC | New Plan |  | 2026-05-21 | 2026-05-28 | 2026-05-29 | 2026-06-09 | 2026-06-10 | 2026-06-24 | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-21 | 2026-10-05 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2027-02-11 | 2027-02-25 | 2027-03-04 | 2027-03-18 | 2027-04-03 | 28 |  | 2027-03-04 | 0 |  |  |  | 2 | WPA-01 | 2027-03-13
| RFQ-PIP-053 | CHECK VALVE (WELDED END) |  |  |  | 12 | 4-1 | Piping | Y | 2/3 | LC | Forecast | [7 empty] | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-21 | 2026-10-05 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2027-02-11 | 2027-02-25 | 2027-03-04 | 2027-03-18 | 2027-04-03 |  | 196 | 2027-03-04 | 2027-03-06 | 2027-03-08 | 2027-03-15 |  | 2 | WPA-02 | 2027-03-30
| RFQ-PIP-053 | CHECK VALVE (WELDED END) | [5 empty] | Piping | Y | 2/3 | LC | Actual | 2026-06-01 | 2026-05-25 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-25 | 2026-07-24
54 | RFQ-PIP-054 | COMPACT CHECK VALVE (WELDED END) | [5 empty] | Piping |  |  | LB | New Plan |  | 2026-05-21 | 2026-05-28 | 2026-05-29 | 2026-06-09 | 2026-06-10 | 2026-06-24 | 2026-07-22 | 2026-08-07 |  | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-21 | 2026-10-05 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2027-02-11 | 2027-02-25 | 2027-03-04 | 2027-03-18 | 2027-04-03 | 28 |  | 2027-03-04 |  |  |  |  | 2 | WPA-01 | 2027-03-13
| RFQ-PIP-054 | COMPACT CHECK VALVE (WELDED END) |  |  |  | 12 | 4-1 | Piping | Y | 2/3 | LB | Forecast | [8 empty] | 2026-08-10 |  | 2026-08-21 | 2026-08-25 | 2026-09-01 | 2026-09-30 | 2026-10-15 | 2026-12-14 | 2026-12-17 | 2026-12-18 | 2027-02-12 | 2027-02-26 | 2027-03-05 | 2027-03-19 | 2027-04-04 |  | 196 | 2027-03-05 | 2027-03-06 | 2027-03-08 | 2027-03-15 |  | 1 | WPA-02 | 2027-03-30
| RFQ-PIP-054 | COMPACT CHECK VALVE (WELDED END) | [5 empty] | Piping | Y | 2/3 | LB | Actual | 2026-06-01 | 2026-05-25 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-25 | 2026-07-23
55 | RFQ-STR-055 | Primary Steel - Plates for topside | [5 empty] | Structural |  |  | LA | New Plan |  | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-29 | 2026-05-30 | 2026-06-02 | 2026-06-05 | 2026-06-09 |  | 2026-06-10 | 2026-06-12 | 2026-06-17 | 2026-06-29 | 2026-07-09 | 2026-07-16 | 2026-06-22 | 2026-06-24 | 2026-07-30 | 2026-08-06 | 2026-08-09 | 2026-08-23 | 2026-09-08 | 8.5714 |  | 2026-08-09 |  |  |  |  | 8 | WPA-01 | 2026-08-24
| RFQ-STR-055 | Primary Steel - Plates for topside |  |  |  | 8 | 5-2 | Structural | Y | 2 | LA | Forecast | 2026-04-08 | [13 empty] | 2026-07-24 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-01 | 2026-08-08 | 2026-08-11 | 2026-08-25 | 2026-09-10 |  | 60 | 2026-08-11 | 2026-08-17 | 2026-08-13 | 2026-08-16 | 1st Cutting Change to 16-Aug | 6 | WPA-02 | 2026-09-10
| RFQ-STR-055 | Primary Steel - Plates for topside | [5 empty] | Structural | Y | 2 | LA | Actual | 2026-04-08 | 2026-05-20 | 2026-06-02 | 2026-06-02 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-08-21: 2026-06-12; 2026-08-25: 2026-06-12; 2026-09-01: 2026-06-17; 2026-09-30: 2026-06-17
56 | RFQ-STR-056 | Primary Steel – Beam for topside | [5 empty] | Structural |  |  | LA | New Plan |  | 2026-06-13 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-18 | 2026-06-26 | 2026-06-29 | 2026-07-02 |  | 2026-07-06 | 2026-07-06 | 2026-07-11 | 2026-07-21 | 2026-07-31 | 2026-08-07 | 2026-08-05 | 2026-08-07 | 2026-09-22 | 2026-09-29 | 2026-10-02 | 2026-10-16 | 2026-11-01 | 12.8571 |  | 2026-10-04 |  |  |  |  | -1 | WPA-01 | 2026-09-25
| RFQ-STR-056 | Primary Steel – Beam for topside |  |  |  | 1 | 5-2 | Structural | Y | 2 | LA | Forecast | 2026-04-25 | [12 empty] | 2026-07-21 | 2026-07-31 | 2026-08-07 | 2026-08-05 | 2026-08-07 | 2026-10-04 | 2026-10-11 | 2026-10-14 | 2026-10-28 | 2026-11-13 |  | 90 | 2026-10-14 | 2026-10-03 | 2026-09-23 | 2026-09-26 | for Deck Pre-assembly | -11 | WPA-02 | 2026-10-10
| RFQ-STR-056 | Primary Steel – Beam for topside | [5 empty] | Structural | Y | 2 | LA | Actual | 2026-04-25 | 2026-05-20 | 2026-06-02 | 2026-06-02 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-07-10 | 2026-07-14 | 2026-07-16 | 2026-08-21: 2026-07-16; 2026-08-25: 2026-07-16; 2026-09-01: 2026-06-29
57 | RFQ-STR-057 | Secondary Steel – Beam for topside (W-Type) |  |  |  |  | 3 | Structural |  |  | LA | New Plan |  | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-20 | 2026-06-29 | 2026-07-01 | 2026-07-04 |  | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 2026-08-03 | 2026-08-09 | 2026-08-07 | 2026-08-09 | 2026-09-24 | 2026-10-01 | 2026-10-04 | 2026-10-18 | 2026-11-03 | 12.8571 |  | 2026-10-04 | 0 |  |  |  | 1 | WPA-01 | 2026-10-12
| RFQ-STR-057 | Secondary Steel – Beam for topside (W-Type) |  |  |  | 1 | 5-4 | Structural | Y | 2 | LA | Forecast | 2026-04-25 | [6 empty] | 2026-07-01 | 2026-07-04 |  | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 2026-08-02 | 2026-08-09 | 2026-08-07 | 2026-08-09 | 2026-09-24 | 2026-10-01 | 2026-10-04 | 2026-10-18 | 2026-11-03 |  | 90 | 2026-10-04 | 2026-10-05 | 2026-09-27 | 2026-09-30 | for Deck Pre-assembly | 1 | WPA-02 | 2026-10-23
| RFQ-STR-057 | Secondary Steel – Beam for topside (W-Type) | [5 empty] | Structural | Y | 2 | LA | Actual | 2026-04-25 | 2026-07-01 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-15 |  |  |  | 2026-09-01: 2026-06-29
102 | RFQ-STR-102 | Secondary Steel – Beam for topside (L&C Type) |  |  |  |  | 4 | Structural |  |  | LA | New Plan |  | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-20 | 2026-06-29 | 2026-07-01 | 2026-07-04 |  | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 2026-08-03 | 2026-08-09 | 2026-08-07 | 2026-08-09 | 2026-09-24 | 2026-10-01 | 2026-10-04 | 2026-10-18 | 2026-11-03 | 12.8571 |  | 2026-10-04 | 0 |  |  |  | 1 | WPA-01 | 2026-10-12
| RFQ-STR-102 | Secondary Steel – Beam for topside (L&C Type) |  |  |  | 1 | 5-4 | Structural | Y | 2 | LA | Forecast | 2026-04-25 | 2026-06-15 | 2026-06-20 | 2026-06-20 | 2026-06-20 | 2026-06-20 | 2026-06-29 | 2026-07-01 | 2026-07-04 |  | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-23 | 2026-08-02 | 2026-08-09 | 2026-08-07 | 2026-08-09 | 2026-09-24 | 2026-10-01 | 2026-10-04 | 2026-10-18 | 2026-11-03 |  | 90 | 2026-10-04 | 2026-10-05 | 2026-09-27 | 2026-09-30 | for Deck Pre-assembly | 1 | WPA-02 | 2026-10-23
| RFQ-STR-102 | Secondary Steel – Beam for topside (L&C Type) | [5 empty] | Structural | Y | 2 | LA | Actual | 2026-04-25 | 2026-07-01 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-15
58 | RFQ-STR-058 | Topside Tertiary Steel | [5 empty] | Structural |  |  | LA | New Plan |  | 2026-07-05 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-24 |  | 2026-07-27 | 2026-07-28 | 2026-08-02 | 2026-08-12 | 2026-08-24 | 2026-08-29 | 2026-08-27 | 2026-08-29 | 2026-10-14 | 2026-10-21 | 2026-10-24 | 2026-11-07 | 2026-11-23 | 12.8571 |  | 2026-10-25 |  |  |  |  | 2 | WPA-01 | 2026-11-03
| RFQ-STR-058 | Topside Tertiary Steel |  |  |  | 3 | 5-4 | Structural | Y | 3 | LA | Forecast | #REF! | 2026-07-05 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-19 | 2026-07-21 | 2026-07-24 |  | 2026-07-26 | 2026-07-28 | 2026-08-02 | 2026-08-12 | 2026-08-22 | 2026-08-29 | 2026-08-27 | 2026-08-29 | 2026-10-14 | 2026-10-21 | 2026-10-24 | 2026-11-07 | 2026-11-23 |  | 90 | 2026-10-24 | 2026-10-27 | 2026-11-06 | 2026-11-09 |  | 3 | WPA-02 | 2026-12-09
| RFQ-STR-058 | Topside Tertiary Steel | [5 empty] | Structural | Y | 3 | LA | Actual
59 | RFQ-STR-059 | Primary Steel - Tubular for topside | [5 empty] | Structural |  |  | LA | New Plan |  | 2026-07-09 | 2026-07-23 | 2026-07-23 | 2026-07-23 | 2026-07-23 | 2026-07-23 | 2026-07-27 | 2026-07-28 |  | 2026-07-30 | 2026-07-31 | 2026-08-05 | 2026-08-13 | 2026-08-24 | 2026-08-30 | 2026-08-30 | 2026-09-04 | 2026-09-14 | 2026-09-21 | 2026-09-24 | 2026-10-08 | 2026-10-24 | 8 |  | 2026-09-24 | 0 |  |  |  | 22 | WPA-01 | 2026-10-23
| RFQ-STR-059 | Primary Steel - Tubular for topside |  |  |  | 11 | 5-2 | Structural | Y | 2 | LA | Forecast | [7 empty] | 2026-07-25 | 2026-07-28 |  | 2026-07-30 | 2026-07-31 | 2026-08-05 | 2026-08-13 | 2026-08-23 | 2026-08-30 | 2026-08-30 | 2026-09-04 | 2026-09-09 | 2026-09-21 | 2026-09-24 | 2026-10-08 | 2026-10-24 |  | 56 | 2026-09-24 | 2026-10-16 | 2026-10-22 | 2026-10-25 | Column and Brace | 22 | WPA-02 | 2026-11-23
| RFQ-STR-059 | Primary Steel - Tubular for topside | [5 empty] | Structural | Y | 2 | LA | Actual | 2026-04-25 | 2026-05-21 | 2026-06-02 | 2026-06-02 | 2026-06-06 | 2026-06-06 | 2026-06-06
60 | RFQ-STR-060 | Primary Steel - Plates for jacket | [5 empty] | Structural |  |  | LA | New Plan |  | 2026-07-01 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-16 | 2026-07-20 | 2026-07-28 |  | 2026-07-30 | 2026-08-01 | 2026-08-06 | 2026-08-17 | 2026-08-26 | 2026-09-02 | 2026-08-31 | 2026-09-02 | 2026-09-18 | 2026-09-25 | 2026-09-28 | 2026-10-19 | 2026-11-04 | 8.5714 |  | 2026-09-28 |  |  |  |  | 21 | WPA-01 | 2026-11-20
| RFQ-STR-060 | Primary Steel - Plates for jacket |  |  |  | 25 | 5-2 | Structural | Y | 2 | LA | Forecast | 2026-04-08 | [9 empty] | 2026-07-30 | 2026-08-01 | 2026-08-06 | 2026-08-16 | 2026-08-26 | 2026-09-02 | 2026-08-31 | 2026-09-02 | 2026-09-18 | 2026-09-25 | 2026-09-28 | 2026-10-12 | 2026-10-28 |  | 60 | 2026-09-28 | 2026-10-19 | 2026-10-19 | 2026-09-26 |  | 21 | WPA-02 | 2026-12-12
| RFQ-STR-060 | Primary Steel - Plates for jacket | [5 empty] | Structural | Y | 2 | LA | Actual | 2026-04-25 | 2026-05-20 | 2026-06-02 | 2026-06-02 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-12 | 2026-06-17 |  | 2026-08-05: 2026-07-20; 2026-08-13: 2026-07-20
61 | RFQ-STR-061 | Secondary Steel -Beam for jacket |  |  |  |  | 5 | Structural |  |  | LA | New Plan |  | 2026-07-10 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-24 | 2026-07-27 | 2026-07-29 |  | 2026-07-31 | 2026-08-02 | 2026-08-07 | 2026-08-17 | 2026-08-27 | 2026-09-03 | 2026-09-01 | 2026-09-03 | 2026-10-29 | 2026-11-05 | 2026-11-08 | 2026-11-22 | 2026-12-08 | 14.2857 |  | 2026-11-08 | 0 |  |  |  | 5 | WPA-01 | 2026-11-20
| RFQ-STR-061 | Secondary Steel -Beam for jacket |  |  |  | 5 | 5-4 | Structural | Y | 3 | LA | Forecast | 2026-04-25 | [6 empty] | 2026-07-26 | 2026-07-29 |  | 2026-07-31 | 2026-08-02 | 2026-08-07 | 2026-08-17 | 2026-08-27 | 2026-09-03 | 2026-09-01 | 2026-09-03 | 2026-10-29 | 2026-11-05 | 2026-11-08 | 2026-11-22 | 2026-12-08 |  | 100 | 2026-11-08 | 2026-11-13 | 2026-11-05 | 2026-10-30 |  | 5 | WPA-02 | 2026-12-12
| RFQ-STR-061 | Secondary Steel -Beam for jacket | [5 empty] | Structural | Y | 3 | LA | Actual | 2026-04-25 | 2026-07-01 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | [25 empty] | Same information with RFQ--057
62 | RFQ-STR-062 | Primary Steel -Tubular for jacket | [5 empty] | Structural |  |  | LA | New Plan |  | 2026-07-01 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-07-16 | 2026-07-20 | 2026-07-28 |  | 2026-07-30 | 2026-08-01 | 2026-08-06 | 2026-08-17 | 2026-08-26 | 2026-09-02 | 2026-08-31 | 2026-09-02 | 2026-09-14 | 2026-09-21 | 2026-09-24 | 2026-10-08 | 2026-10-24 | 8 |  | 2026-09-24 | 0 |  |  |  | 16 | WPA-01 | 2026-10-19
| RFQ-STR-062 | Primary Steel -Tubular for jacket |  |  |  | 2 | 5-2 | Structural | Y | 2 | LA | Forecast | [5 empty] | 2026-06-08 | 2026-07-16 | 2026-07-18 | 2026-07-28 |  | 2026-07-30 | 2026-08-01 | 2026-08-06 | 2026-08-16 | 2026-08-26 | 2026-09-02 | 2026-08-31 | 2026-09-02 | 2026-09-05 | 2026-09-21 | 2026-09-24 | 2026-10-08 | 2026-10-24 |  | 56 | 2026-09-24 | 2026-10-10 | 2026-10-10 | 2026-09-30 |  | 16 | WPA-02 | 2026-11-14
| RFQ-STR-062 | Primary Steel -Tubular for jacket | [5 empty] | Structural | Y | 2 | LA | Actual | 2026-04-25 | 2026-05-21 | 2026-06-02 | 2026-06-02 | 2026-06-02
64 | RFQ-STR-064 | Primary Steel - Plates for Pile | [5 empty] | Structural |  |  | LA | New Plan |  | 2026-10-05 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 2026-10-14 | 2026-10-14 | 2026-10-21 | 2026-11-05 |  | 2026-11-09 | 2026-11-09 | 2026-11-14 | 2026-11-24 | 2026-12-04 | 2026-12-11 | 2026-12-09 | 2026-12-11 | 2026-12-27 | 2027-01-03 | 2027-01-06 | 2027-01-20 | 2027-02-05 | 8.5714 |  | 2027-01-08 |  |  |  |  | 62 | WPA-01 | 2027-03-18
| RFQ-STR-064 | Primary Steel - Plates for Pile |  |  |  | 81 | 5-3 | Structural | Y | 2 | LA | Forecast | 2026-04-08 | [9 empty] | 2026-11-07 | 2026-11-09 | 2026-11-14 | 2026-11-24 | 2026-12-04 | 2026-12-11 | 2026-12-09 | 2026-12-11 | 2026-12-27 | 2027-01-03 | 2027-01-06 | 2027-01-20 | 2027-02-05 |  | 60 | 2027-01-06 | 2027-03-11 | 2027-02-14 | 2027-02-17 |  | 64 | WPA-02 | 2027-05-14
| RFQ-STR-064 | Primary Steel - Plates for Pile | [5 empty] | Structural | Y | 2 | LA | Actual | 2026-04-08 | 2026-05-20 | 2026-06-02 | 2026-06-02 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-12 | 2026-06-17 |  | 2026-08-05: 2026-07-20; 2026-08-13: 2026-07-20
65 | RFQ-STR-065 | Primary Steel -Tubular for Pile | [5 empty] | Structural |  |  | LA | New Plan |  | 2026-10-07 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 2026-10-14 | 2026-10-14 | 2026-10-23 | 2026-11-04 |  | 2026-11-06 | 2026-11-08 | 2026-11-13 | 2026-11-23 | 2026-12-03 | 2026-12-10 | 2026-12-08 | 2026-12-25 | 2027-01-25 | 2027-02-01 | 2027-02-04 | 2027-02-18 | 2027-03-06 | 12.8571 |  | 2027-02-04 |  |  |  |  | 35 | WPA-01 | 2027-03-18
| RFQ-STR-065 | Primary Steel -Tubular for Pile |  |  |  | 35 | 5-3 | Structural | Y | 2 | LA | Forecast | [8 empty] | 2026-11-04 |  | 2026-11-06 | 2026-11-08 | 2026-11-13 | 2026-11-23 | 2026-12-03 | 2026-12-10 | 2026-12-08 | 2027-01-06 | 2027-01-25 | 2027-02-01 | 2027-02-04 | 2027-02-18 | 2027-03-06 |  | 90 | 2027-02-04 | 2027-03-11 | 2027-02-22 | 2027-02-25 |  | 35 | WPA-02 | 2027-05-14
| RFQ-STR-065 | Primary Steel -Tubular for Pile | [5 empty] | Structural | Y | 2 | LA | Actual |  | 2026-05-21 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-12
67 | RFQ-PIP-067 | CS Fitting | [5 empty] | Piping |  |  | LD | New Plan |  | 2026-07-20 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-10 | 2026-08-24 |  | 2026-08-31 | 2026-09-02 | 2026-09-09 | 2026-09-23 | 2026-10-07 | 2026-11-06 | 2026-11-06 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-11-29 | 2026-12-13 | 2026-12-29 | 12.8571 |  | 2026-11-29 |  |  |  |  | 5 | WPA-01 | 2026-12-11
| RFQ-PIP-067 | CS Fitting |  |  |  | 5 | 5-5 | Piping | Y | 3 | LD | Forecast | 2026-07-05 | 2026-07-20 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-08 | 2026-08-10 | 2026-08-25 |  | 2026-09-01 | 2026-09-03 | 2026-09-10 | 2026-09-24 | 2026-10-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-14 | 2026-12-30 |  | 90 | 2026-11-30 | 2026-12-04 | 2026-12-04 | 2026-12-11 |  | 4 | WPA-02 | 2026-12-11
| RFQ-PIP-067 | CS Fitting | [5 empty] | Piping | Y | 3 | LD | Actual
68 | RFQ-PIP-068 | SS Fitting | [5 empty] | Piping |  |  | LD | New Plan |  | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-24 |  | 2026-08-31 | 2026-09-02 | 2026-09-09 | 2026-09-23 | 2026-10-07 | 2026-11-06 | 2026-11-06 | 2026-11-08 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-03-01 | 2027-03-17 | 24 |  | 2027-02-15 |  |  |  |  | 6 | WPA-01 | 2027-02-28
| RFQ-PIP-068 | SS Fitting |  |  |  | 6 | 5-5 | Piping | Y | 3 | LD | Forecast | 2026-07-05 | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-30 | 2026-08-10 | 2026-08-25 |  | 2026-09-01 | 2026-09-03 | 2026-09-10 | 2026-09-24 | 2026-10-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2027-02-02 | 2027-02-09 | 2027-02-16 | 2027-03-02 | 2027-03-18 |  | 168 | 2027-02-16 | 2027-02-21 | 2027-02-18 | 2027-02-25 |  | 5 | WPA-02 | 2027-02-28
| RFQ-PIP-068 | SS Fitting | [5 empty] | Piping | Y | 3 | LD | Actual |  | 2026-07-17
103 | RFQ-PIP-103 | DSS Fitting | [5 empty] | Piping |  |  | LD | New Plan |  | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-24 |  | 2026-08-31 | 2026-09-02 | 2026-09-09 | 2026-09-23 | 2026-10-07 | 2026-11-06 | 2026-11-06 | 2026-11-08 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-03-01 | 2027-03-17 | 24 |  | 2027-02-15 |  |  |  |  | 6 | WPA-01 | 2027-02-28
| RFQ-PIP-103 | DSS Fitting |  |  |  | 6 | 5-5 | Piping | Y | 3 | LD | Forecast | 2026-07-05 | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-30 | 2026-08-10 | 2026-08-25 |  | 2026-09-01 | 2026-09-03 | 2026-09-10 | 2026-09-24 | 2026-10-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2027-02-02 | 2027-02-09 | 2027-02-16 | 2027-03-02 | 2027-03-18 |  | 168 | 2027-02-16 | 2027-02-21 | 2027-02-18 | 2027-02-25 |  | 5 | WPA-02 | 2027-02-28
| RFQ-PIP-103 | DSS Fitting | [5 empty] | Piping | Y | 3 | LD | Actual |  | 2026-07-17
69 | RFQ-PIP-069 | CS Flange | [5 empty] | Piping |  |  | LD | New Plan |  | 2026-07-20 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-10 | 2026-08-24 |  | 2026-08-31 | 2026-09-02 | 2026-09-09 | 2026-09-23 | 2026-10-07 | 2026-11-06 | 2026-11-06 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-11-29 | 2026-12-13 | 2026-12-29 | 12.8571 |  | 2026-11-29 |  |  |  |  | 5 | WPA-01 | 2026-12-11
| RFQ-PIP-069 | CS Flange |  |  |  | 5 | 5-5 | Piping | Y | 3 | LD | Forecast | 2026-07-05 | 2026-07-20 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-08 | 2026-08-10 | 2026-08-25 |  | 2026-09-01 | 2026-09-03 | 2026-09-10 | 2026-09-24 | 2026-10-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-14 | 2026-12-30 |  | 90 | 2026-11-30 | 2026-12-04 | 2026-12-23 | 2026-12-30 |  | 4 | WPA-02 | 2026-12-11
| RFQ-PIP-069 | CS Flange | [5 empty] | Piping | Y | 3 | LD | Actual
70 | RFQ-PIP-070 | SS Flange | [5 empty] | Piping |  |  | LD | New Plan |  | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-24 |  | 2026-08-31 | 2026-09-02 | 2026-09-09 | 2026-09-23 | 2026-10-07 | 2026-11-06 | 2026-11-06 | 2026-11-08 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-03-01 | 2027-03-17 | 24 |  | 2027-02-15 |  |  |  |  | 6 | WPA-01 | 2027-02-28
| RFQ-PIP-070 | SS Flange |  |  |  | 6 | 5-5 | Piping | Y | 3 | LD | Forecast | 2026-07-05 | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-30 | 2026-08-10 | 2026-08-25 |  | 2026-09-01 | 2026-09-03 | 2026-09-10 | 2026-09-24 | 2026-10-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2027-02-02 | 2027-02-09 | 2027-02-16 | 2027-03-02 | 2027-03-18 |  | 168 | 2027-02-16 | 2027-02-21 | 2027-03-08 | 2027-03-15 |  | 5 | WPA-02 | 2027-02-28
| RFQ-PIP-070 | SS Flange | [5 empty] | Piping | Y | 3 | LD | Actual |  | 2026-07-17
104 | RFQ-PIP-104 | DSS Flange | [5 empty] | Piping |  |  | LD | New Plan |  | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-24 |  | 2026-08-31 | 2026-09-02 | 2026-09-09 | 2026-09-23 | 2026-10-07 | 2026-11-06 | 2026-11-06 | 2026-11-08 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-03-01 | 2027-03-17 | 24 |  | 2027-02-15 |  |  |  |  | 6 | WPA-01 | 2027-02-28
| RFQ-PIP-104 | DSS Flange |  |  |  | 6 | 5-5 | Piping | Y | 3 | LD | Forecast | 2026-07-05 | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-30 | 2026-08-10 | 2026-08-25 |  | 2026-09-01 | 2026-09-03 | 2026-09-10 | 2026-09-24 | 2026-10-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2027-02-02 | 2027-02-09 | 2027-02-16 | 2027-03-02 | 2027-03-18 |  | 168 | 2027-02-16 | 2027-02-21 | 2027-03-08 | 2027-03-15 |  | 5 | WPA-02 | 2027-02-28
| RFQ-PIP-104 | DSS Flange | [5 empty] | Piping | Y | 3 | LD | Actual |  | 2026-07-17
72 | RFQ-PIP-072 | CS Pipe | [5 empty] | Piping |  |  | LD | New Plan |  | 2026-07-20 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-06 | 2026-08-10 | 2026-08-24 |  | 2026-08-31 | 2026-09-02 | 2026-09-09 | 2026-09-23 | 2026-10-07 | 2026-11-06 | 2026-11-06 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-11-29 | 2026-12-13 | 2026-12-29 | 12.8571 |  | 2026-11-29 |  |  |  |  | 5 | WPA-01 | 2026-12-11
| RFQ-PIP-072 | CS Pipe |  |  |  | 5 | 5-5 | Piping | Y | 3 | LD | Forecast | 2026-07-05 | 2026-07-20 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-08 | 2026-08-10 | 2026-08-25 |  | 2026-09-01 | 2026-09-03 | 2026-09-10 | 2026-09-24 | 2026-10-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-14 | 2026-12-30 |  | 90 | 2026-11-30 | 2026-12-04 | 2026-12-04 | 2026-12-11 |  | 4 | WPA-02 | 2026-12-11
| RFQ-PIP-072 | CS Pipe | [5 empty] | Piping | Y | 3 | LD | Actual |  | 2026-07-24
73 | RFQ-PIP-073 | SS AND DSS PIPE | [5 empty] | Piping |  |  | LD | New Plan |  | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 |  | 2026-08-24 | 2026-08-26 | 2026-09-02 | 2026-09-16 | 2026-09-30 | 2026-10-30 | 2026-10-30 | 2026-11-01 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-22 | 2027-03-10 | 24 |  | 2027-02-08 |  |  |  |  | 3 | WPA-01 | 2027-03-05
| RFQ-PIP-073 | SS AND DSS PIPE |  |  |  | 11 | 5-5 | Piping | Y | 3 | LD | Forecast | 2026-07-15 | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-30 | 2026-08-10 | 2026-08-25 |  | 2026-09-01 | 2026-09-03 | 2026-09-10 | 2026-09-24 | 2026-10-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2027-02-02 | 2027-02-09 | 2027-02-16 | 2027-03-02 | 2027-03-18 |  | 168 | 2027-02-16 | 2027-02-11 | 2027-02-18 | 2027-02-25 |  | -5 | WPA-02 | 2027-03-05
| RFQ-PIP-073 | SS AND DSS PIPE | [5 empty] | Piping | Y | 3 | LD | Actual |  | 2026-07-17
75 | RFQ-PIP-075 | STUD BOLTS AND NUTS | [5 empty] | Piping |  |  | 0 | New Plan |  | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-03 | 2026-08-04 | 2026-08-10 | 2026-08-20 | 2026-08-24 |  | 2026-08-31 | 2026-09-02 | 2026-09-09 | 2026-09-23 | 2026-10-07 | 2026-10-14 | 2026-10-14 | 2026-10-16 | 2026-12-15 | 2026-12-22 | 2026-12-29 | 2027-01-12 | 2027-01-28 | 17.1429 |  | 2026-12-29 |  |  |  |  | 1900-02-22 | WPA-01 | 2027-02-28
| RFQ-PIP-075 | STUD BOLTS AND NUTS |  |  |  | 43 | 5-5 | Piping |  |  |  | Forecast | 2026-07-05 | 2026-07-20 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-12 | 2026-08-21 | 2026-09-04 |  | 2026-09-11 | 2026-09-15 | 2026-09-22 | 2026-10-14 | 2026-10-29 | 2026-11-05 | 2026-11-05 | 2026-11-07 | 2026-12-26 | 2027-01-02 | 2027-01-09 | 2027-01-23 | 2027-02-08 |  | 120 | 2027-01-09 | 2027-02-21 | 2027-02-18 | 2027-02-25 |  | 1900-02-11 | WPA-02 | 2027-02-28
| RFQ-PIP-075 | STUD BOLTS AND NUTS | [5 empty] | Piping |  |  |  | Actual |  | 2026-07-24
76 | RFQ-PIP-076 | Gasket | [5 empty] | Piping |  |  | 0 | New Plan |  | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-03 | 2026-08-04 | 2026-08-10 | 2026-08-20 | 2026-08-24 |  | 2026-08-31 | 2026-09-02 | 2026-09-09 | 2026-09-23 | 2026-10-07 | 2026-10-14 | 2026-10-14 | 2026-10-16 | 2026-12-15 | 2026-12-22 | 2026-12-29 | 2027-01-12 | 2027-01-28 | 17.1429 |  | 2026-12-29 |  |  |  |  | 1900-02-22 | WPA-01 | 2027-02-28
| RFQ-PIP-076 | Gasket |  |  |  | 43 | 5-5 | Piping |  |  |  | Forecast | 2026-07-05 | 2026-07-20 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-12 | 2026-08-21 | 2026-09-04 |  | 2026-09-11 | 2026-09-15 | 2026-09-22 | 2026-10-14 | 2026-10-29 | 2026-11-05 | 2026-11-05 | 2026-11-07 | 2026-12-26 | 2027-01-02 | 2027-01-09 | 2027-01-23 | 2027-02-08 |  | 120 | 2027-01-09 | 2027-02-21 | 2027-02-18 | 2027-02-25 |  | 1900-02-11 | WPA-02 | 2027-02-28
| RFQ-PIP-076 | Gasket | [5 empty] | Piping |  |  |  | Actual |  | 2026-07-24
77 | RFQ-ELE-077 | ELECTRICAL CABLES | [5 empty] | Electrical |  |  | LD | New Plan |  | 2026-08-03 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-25 | 2026-09-03 | 2026-09-17 |  | 2026-09-24 | 2026-09-29 | 2026-10-13 | 2026-10-27 | 2026-11-10 | 2026-11-20 | 2026-11-20 | 2026-11-22 | 2026-12-17 | 2026-12-24 | 2026-12-31 | 2027-01-14 | 2027-01-30 | 14 |  | 2026-12-31 | 0 |  |  |  | 131 | WPA-01 | 2027-05-18
| RFQ-ELE-077 | ELECTRICAL CABLES |  |  |  | 148 | 5-7 | Electrical | N | 3 | LD | Forecast | 2026-07-18 | 2026-08-03 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-25 | 2026-09-03 | 2026-09-17 |  | 2026-09-24 | 2026-09-29 | 2026-10-13 | 2026-10-27 | 2026-11-10 | 2026-11-20 | 2026-11-20 | 2026-11-22 | 2026-12-17 | 2026-12-24 | 2026-12-31 | 2027-01-14 | 2027-01-30 |  | 98 | 2026-12-31 | 2027-05-11 | 2027-05-01 | 2027-05-08 |  | 131 | WPA-02 | 2027-05-31
| RFQ-ELE-077 | ELECTRICAL CABLES | [5 empty] | Electrical | N | 3 | LD | Actual
78 | RFQ-ELE-078 | ELECTRICAL BULK MATERIALS | [5 empty] | Electrical |  |  | LD | New Plan |  | 2026-09-04 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-28 | 2026-10-07 | 2026-10-22 |  | 2026-10-29 | 2026-11-02 | 2026-11-09 | 2026-11-23 | 2026-12-08 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-01-28 | 2027-02-04 | 2027-02-11 | 2027-02-25 | 2027-03-13 | 15 |  | 2027-02-11 |  |  |  |  | 19 | WPA-01 | 2027-03-09
| RFQ-ELE-078 | ELECTRICAL BULK MATERIALS |  |  |  | 34 | 5-7 | Electrical | Y | 3 | LD | Forecast | 2026-08-20 | 2026-09-04 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-28 | 2026-10-07 | 2026-10-22 |  | 2026-10-29 | 2026-11-02 | 2026-11-09 | 2026-11-23 | 2026-12-08 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-01-28 | 2027-02-04 | 2027-02-11 | 2027-02-25 | 2027-03-13 |  | 105 | 2027-02-11 | 2027-03-02 | 2027-02-20 | 2027-02-27 | cable Tray | 19 | WPA-02 | 2027-03-20
| RFQ-ELE-078 | ELECTRICAL BULK MATERIALS | [5 empty] | Electrical | Y | 3 | LD | Actual
79 | RFQ-ELE-079 | FOG HORN | [5 empty] | Electrical |  |  | LD | New Plan |  | 2026-09-04 | 2026-09-18 | 2026-09-18 | 2026-10-07 | 2026-10-22 | 2026-10-29 | 2026-10-07 | 2026-10-22 |  | 2026-10-29 | 2027-01-13 | 2027-01-20 | 2026-11-23 | 2026-12-08 | 2026-12-18 | 2026-10-17 | 2026-10-19 | 2027-01-13 | 2027-01-20 | 2027-01-27 | 2027-02-10 | 2027-02-26 | 12.8571 |  | 2027-01-27 |  |  |  |  | 84 | WPA-01 | 2027-04-28
| RFQ-ELE-079 | FOG HORN |  |  |  | 143 | 4-3.2 | Electrical | N | 3 | LD | Forecast | 2026-07-05 | 2026-09-04 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-28 | 2026-10-07 | 2026-10-22 |  | 2026-10-29 | 2026-11-02 | 2026-11-09 | 2026-11-23 | 2026-12-08 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-01-13 | 2027-01-20 | 2027-01-27 | 2027-02-10 | 2027-02-26 |  | 90 | 2027-01-27 | 2027-04-21 | 2027-05-23 | 2027-05-30 |  | 84 | WPA-02 | 2027-05-11
| RFQ-ELE-079 | FOG HORN | [5 empty] | Electrical | N | 3 | LD | Actual |  | 2026-07-24
80 | RFQ-INS-080 | INSTRUMENT BULK MATERIALS | [5 empty] | Instrument |  |  | LD | New Plan |  | 2026-09-30 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-21 | 2026-11-03 | 2026-11-17 |  | 2026-11-24 | 2026-11-13 | 2026-11-20 | 2026-12-17 | 2027-01-04 | 2027-01-14 | 2026-12-31 | 2027-01-02 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-08 | 2027-03-24 | 12.8571 |  | 2027-02-22 |  |  |  |  | 8 | WPA-01 | 2027-03-09
| RFQ-INS-080 | INSTRUMENT BULK MATERIALS |  |  |  | 21 | 5-8 | Instrument | N | 4 | LD | Forecast | 2026-09-08 | 2026-09-30 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-22 | 2026-11-03 | 2026-11-17 |  | 2026-11-24 | 2026-11-26 | 2026-12-03 | 2026-12-17 | 2027-01-04 | 2027-01-14 | 2027-01-14 | 2027-01-16 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-08 | 2027-03-24 |  | 90 | 2027-02-22 | 2027-03-02 | 2027-03-02 | 2027-03-09 |  | 8 | WPA-02 | 2027-03-20
| RFQ-INS-080 | INSTRUMENT BULK MATERIALS | [5 empty] | Instrument | N | 4 | LD | Actual
81 | RFQ-INS-081 | Instrument Cables | [5 empty] | Instrument |  |  | LD | New Plan |  | 2026-08-21 | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-09-10 | 2026-09-22 | 2026-10-06 |  | 2026-10-14 | 2026-10-12 | 2026-10-19 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-23 | 2026-11-25 | 2026-12-29 | 2027-01-05 | 2027-01-12 | 2027-01-26 | 2027-02-11 | 12.8571 |  | 2027-01-12 | 0 |  |  |  | 132 | WPA-01 | 2027-05-31
| RFQ-INS-081 | Instrument Cables |  |  |  | 138 | 5-8 | Instrument | N | 4 | LD | Forecast | 2026-08-06 | 2026-08-21 | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-09-11 | 2026-09-22 | 2026-10-06 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2026-12-29 | 2027-01-05 | 2027-01-12 | 2027-01-26 | 2027-02-11 |  | 90 | 2027-01-12 | 2027-05-24 | 2027-03-24 | 2027-03-31 |  | 132 | WPA-02 | 2027-06-15
| RFQ-INS-081 | Instrument Cables | [5 empty] | Instrument | N | 4 | LD | Actual
82 | RFQ-SAF-082 | FIREFIGHTING EQUIPMENT | [5 empty] | Safety |  |  | LD | New Plan |  | 2026-07-30 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-21 | 2026-09-01 | 2026-09-15 |  | 2026-09-22 | 2026-09-24 | 2026-10-09 | 2026-10-23 | 2026-11-06 | 2027-01-05 | 2027-01-05 | 2027-01-08 | 2027-04-06 | 2027-04-13 | 2027-04-20 | 2027-05-04 | 2027-05-20 | 30 |  | 2027-04-20 |  |  |  |  | 64 | WPA-01 | 2027-06-30
| RFQ-SAF-082 | FIREFIGHTING EQUIPMENT |  |  |  | 34 | 4-5 | Safety | N | 3 | LD | Forecast | 2026-06-22 | 2026-07-30 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-21 | 2026-09-01 | 2026-09-15 |  | 2026-09-22 | 2026-09-24 | 2026-10-09 | 2026-10-23 | 2026-11-06 | 2027-01-05 | 2027-01-05 | 2027-01-08 | 2027-04-06 | 2027-04-13 | 2027-04-20 | 2027-05-04 | 2027-05-20 |  | 210 | 2027-04-20 | 2027-06-23 | 2027-05-23 | 2027-05-30 |  | 64 | WPA-02 | 2027-07-15
| RFQ-SAF-082 | FIREFIGHTING EQUIPMENT | [5 empty] | Safety | N | 3 | LD | Actual |  | 2026-07-15
83 | RFQ-SAF-083 | LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT | [5 empty] | Safety |  |  | LD | New Plan |  | 2026-07-30 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-21 | 2026-09-01 | 2026-09-15 |  | 2026-09-22 | 2026-09-24 | 2026-10-09 | 2026-10-23 | 2026-11-06 | 2027-01-05 | 2027-01-05 | 2027-01-08 | 2027-04-06 | 2027-04-13 | 2027-04-20 | 2027-05-04 | 2027-05-20 | 30 |  | 2027-04-20 |  |  |  |  | 64 | WPA-01 | 2027-06-30
| RFQ-SAF-083 | LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT |  |  |  | 34 | 4-5 | Safety | N | 4 | LD | Forecast | 2026-06-22 | 2026-07-30 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-21 | 2026-09-01 | 2026-09-15 |  | 2026-09-22 | 2026-09-24 | 2026-10-09 | 2026-10-23 | 2026-11-06 | 2027-01-05 | 2027-01-05 | 2027-01-08 | 2027-04-06 | 2027-04-13 | 2027-04-20 | 2027-05-04 | 2027-05-20 |  | 210 | 2027-04-20 | 2027-06-23 | 2027-05-23 | 2027-05-30 |  | 64 | WPA-02 | 2027-07-15
| RFQ-SAF-083 | LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT | [5 empty] | Safety | N | 4 | LD | Actual |  | 2026-07-15
84 | RFQ-SAF-084 | SAFETY SIGNS | [5 empty] | Safety |  |  | LD | New Plan |  | 2026-07-30 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-21 | 2026-09-01 | 2026-09-15 |  | 2026-09-22 | 2026-09-24 | 2026-10-09 | 2026-10-23 | 2026-11-06 | 2026-11-06 | 2026-11-16 | 2026-11-19 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-12-05 | 2026-12-21 | 8.5714 |  | 2026-11-21 | 0 |  |  |  | 214 | WPA-01 | 2027-06-30
| RFQ-SAF-084 | SAFETY SIGNS |  |  |  | 169 | 4-5 | Safety | N | 4 | LD | Forecast | 2026-06-22 | 2026-07-30 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-21 | 2026-09-01 | 2026-09-15 |  | 2026-09-22 | 2026-09-24 | 2026-10-09 | 2026-10-23 | 2026-11-06 | 2026-11-06 | 2026-11-06 | 2026-11-09 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-12-05 | 2026-12-21 |  | 60 | 2026-11-21 | 2027-06-23 | 2027-05-23 | 2027-05-30 |  | 214 | WPA-02 | 2027-07-15
| RFQ-SAF-084 | SAFETY SIGNS | [5 empty] | Safety | N | 4 | LD | Actual |  | 2026-07-15
85 | RFQ-PLR-085 | PIPELINE FLANGES | [5 empty] | Piping & Riser |  |  | LD | New Plan |  | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-13 | 2026-08-27 |  | 2026-09-03 | 2026-09-07 | 2026-09-14 | 2026-09-29 | 2026-10-14 | 2026-11-13 | 2026-11-13 | 2026-11-15 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-16 | 2027-01-01 | 12.8571 |  | 2026-12-02 |  |  |  |  | 2 | WPA-01 | 2026-12-11
| RFQ-PLR-085 | PIPELINE FLANGES |  |  |  | 26 | 5-6 | Piping & Riser | N | 3 | LD | Forecast | 2026-06-15 |  |  |  |  | 2026-07-17 | 2026-07-24 | 2026-08-06 | 2026-08-21 |  | 2026-08-28 | 2026-09-01 | 2026-09-08 | 2026-09-22 | 2026-10-06 | 2026-11-05 | 2026-11-05 | 2026-11-07 | 2026-11-12 | 2026-11-19 | 2026-11-26 | 2026-12-10 | 2026-12-26 |  | 90 | 2026-11-26 | 2026-12-04 | 2026-12-23 | 2026-12-30 |  | 8 | WPA-02 | 2026-12-11
| RFQ-PLR-085 | PIPELINE FLANGES | [5 empty] | Piping & Riser | N | 3 | LD | Actual |  | 2026-07-07 | 2026-07-17 | 2026-07-17 | 2026-07-17
86 | RFQ-PLR-086 | BARRED TEE | [5 empty] | Piping & Riser |  |  | LD | New Plan |  | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-13 | 2026-08-27 |  | 2026-09-03 | 2026-09-07 | 2026-09-14 | 2026-09-29 | 2026-10-14 | 2026-11-13 | 2026-11-13 | 2026-11-15 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-16 | 2027-01-01 | 12.8571 |  | 2026-12-02 |  |  |  |  | 2 | WPA-01 | 2026-12-11
| RFQ-PLR-086 | BARRED TEE |  |  |  | 15 | 5-6 | Piping & Riser | Y | 2 | LD | Forecast | 2026-06-25 |  |  |  |  | 2026-07-19 | 2026-07-24 | 2026-08-06 | 2026-08-21 |  | 2026-08-28 | 2026-09-01 | 2026-09-08 | 2026-09-22 | 2026-10-06 | 2026-11-05 | 2026-11-05 | 2026-11-07 | 2026-11-12 | 2026-11-19 | 2026-11-26 | 2026-12-10 | 2026-12-26 |  | 90 | 2026-11-26 | 2026-12-04 | 2026-12-23 | 2026-12-30 |  | 8 | WPA-02 | 2026-12-11
| RFQ-PLR-086 | BARRED TEE | [5 empty] | Piping & Riser | Y | 2 | LD | Actual |  | 2026-07-07 | 2026-07-19 | 2026-07-19 | 2026-07-19
87 | RFQ-PLR-087 | PIGGABLE WYE | [5 empty] | Piping & Riser |  |  | LD | New Plan |  | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-13 | 2026-08-27 |  | 2026-09-03 | 2026-09-07 | 2026-09-14 | 2026-09-29 | 2026-10-14 | 2026-11-13 | 2026-11-13 | 2026-11-15 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-16 | 2027-01-01 | 12.8571 |  | 2026-12-02 |  |  |  |  | 2 | WPA-01 | 2026-12-11
| RFQ-PLR-087 | PIGGABLE WYE |  |  |  | 15 | 5-6 | Piping & Riser | N | 2 | LD | Forecast | 2026-06-25 |  |  |  |  | 2026-07-19 | 2026-07-24 | 2026-08-06 | 2026-08-21 |  | 2026-08-28 | 2026-09-01 | 2026-09-08 | 2026-09-22 | 2026-10-06 | 2026-11-05 | 2026-11-05 | 2026-11-07 | 2026-11-12 | 2026-11-19 | 2026-11-26 | 2026-12-10 | 2026-12-26 |  | 90 | 2026-11-26 | 2026-12-04 | 2026-12-23 | 2026-12-30 |  | 8 | WPA-02 | 2026-12-11
| RFQ-PLR-087 | PIGGABLE WYE | [5 empty] | Piping & Riser | N | 2 | LD | Actual |  | 2026-07-07 | 2026-07-19 | 2026-07-19 | 2026-07-19
88 | RFQ-PLR-088 | BARREL REDUCER | [5 empty] | Piping & Riser |  |  | LD | New Plan |  | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-13 | 2026-08-27 |  | 2026-09-03 | 2026-09-07 | 2026-09-14 | 2026-09-29 | 2026-10-14 | 2026-11-13 | 2026-11-13 | 2026-11-15 | 2026-11-18 | 2026-11-25 | 2027-01-01 | 2027-01-15 | 2027-01-31 | 17.1429 |  | 2027-01-01 |  |  |  |  | -9 | WPA-01 | 2026-12-30
| RFQ-PLR-088 | BARREL REDUCER |  |  |  | 4 | 5-6 | Piping & Riser | N | 2 | LD | Forecast | 2026-06-25 |  |  |  |  | 2026-07-19 | 2026-07-24 | 2026-08-06 | 2026-08-21 |  | 2026-08-28 | 2026-09-01 | 2026-09-08 | 2026-09-22 | 2026-10-06 | 2026-11-05 | 2026-11-05 | 2026-11-07 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-09 | 2027-01-25 |  | 120 | 2026-12-26 | 2026-12-23 | 2026-12-23 | 2026-12-30 |  | -3 | WPA-02 | 2026-12-30
| RFQ-PLR-088 | BARREL REDUCER | [5 empty] | Piping & Riser | N | 2 | LD | Actual |  | 2026-07-07 | 2026-07-19 | 2026-07-19 | 2026-07-19 | [27 empty] | Request CPY for support to shorten the approval cycle.
89 | RFQ-TEL- 089 | Telecommunication System Bulk Material | [5 empty] | Telecommunication |  |  | LD | New Plan |  | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-08 | 2026-10-20 | 2026-11-04 |  | 2026-11-11 | 2026-11-13 | 2026-11-20 | 2026-12-04 | 2026-12-21 | 2026-12-31 | 2026-12-31 | 2027-01-02 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-03-05 | 2027-03-21 | 14.2857 |  | 2027-02-19 |  |  |  |  | 20 | WPA-01 | 2027-03-18
| RFQ-TEL- 089 | Telecommunication System Bulk Material |  |  |  | 130 | 5-9 | Telecommunication | N | 3 | LD | Forecast | 2026-08-27 |  |  |  |  | 2026-06-15 | 2026-06-23 | 2026-07-02 | 2026-07-16 |  | 2026-07-23 | 2026-07-27 | 2026-08-03 | 2026-08-17 | 2026-08-31 | 2026-09-10 | 2026-09-10 | 2026-09-12 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-14 | 2026-11-30 |  | 100 | 2026-10-31 | 2027-03-11 | 2027-03-02 | 2027-03-09 |  | 131 | WPA-02 | 2027-03-30
| RFQ-TEL- 089 | Telecommunication System Bulk Material | [5 empty] | Telecommunication | N | 3 | LD | Actual |  | 2026-05-29 | 2026-06-15 | 2026-06-15 | 2026-06-15
90 | RFQ-STR-090 | JKT Anode | [5 empty] | Structural |  |  | LD | New Plan |  | 2026-08-24 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-23 | 2026-10-07 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-01 | 2026-12-06 | 2026-12-09 | 2026-12-13 | 2026-12-23 | 2027-01-02 | 8.5714 |  | 2026-12-13 |  |  |  |  | 10 | WPA-01 | 2026-12-30
| RFQ-STR-090 | JKT Anode |  |  |  | 15 | 5-11 | Structural | Y | 4 | LD | Forecast | 2026-08-10 |  |  |  |  | 2026-07-19 | 2026-07-24 | 2026-08-06 | 2026-08-21 |  | 2026-08-28 | 2026-09-01 | 2026-09-08 | 2026-09-22 | 2026-10-06 | 2026-10-16 | 2026-10-16 | 2026-10-17 | 2026-10-20 | 2026-10-23 | 2026-10-27 | 2026-11-06 | 2026-11-16 |  | 60 | 2026-10-27 | 2026-12-23 | 2027-11-27 | 2027-11-30 |  | 57 | WPA-02 | 2027-01-15
| RFQ-STR-090 | JKT Anode | [5 empty] | Structural | Y | 4 | LD | Actual |  | 2026-07-07 | 2026-07-19 | 2026-07-19 | 2026-07-19 | [27 empty] | Request CPY for support to shorten the approval cycle.
93 | RFQ-PIP-093 | Coat | [5 empty] | Coating |  |  | LD | New Plan |  | 2026-07-20 | 2026-08-05 | 2026-08-05 | 2026-08-03 | 2026-08-04 | 2026-08-10 | 2026-08-20 | 2026-08-24 |  | 2026-08-31 | 2026-09-02 | 2026-09-09 | 2026-09-23 | 2026-10-07 | 2026-09-23 | 2026-10-17 | 2026-10-19 | 2026-10-20 | 2026-10-23 | 2026-10-26 | 2026-11-05 | 2026-11-15 | 8 |  | 2026-10-26 |  |  |  |  | 28 | WPA-01 | 2026-11-30
| RFQ-PIP-093 | Coat |  |  |  | 3 |  | Coating | N | 0 | LD | Forecast | 2026-08-22 | 2026-07-20 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-12 | 2026-08-21 | 2026-09-04 |  | 2026-08-28: 2026-09-11; 2026-09-01: 2026-10-16; 2026-09-08: 2026-10-23; 2026-09-22: 2026-11-06; 2026-10-06: 2026-11-20 |  | 56 | 2026-11-06 | 2026-11-23 | 2026-10-31 | 2026-11-07 | Topside Deck B&P | 17 | WPA-02 | 2026-12-30
| RFQ-PIP-093 | Coat | [5 empty] | Coating | N |  | LD | Actual
92 | RFQ-PIP-092 | CORROSION FITTINGS (PROBE, COUPON AND CHEMICAL INJECTION QUILL) | [5 empty] | Piping |  |  | LA | New Plan |  | 2026-05-25 | 2026-06-04 | 2026-06-04 | 2026-06-11 | 2026-06-11 | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 | 24 |  | 2027-03-03 |  |  |  |  | 51 | WPA-01 | 2027-04-30
| RFQ-PIP-092 | CORROSION FITTINGS (PROBE, COUPON AND CHEMICAL INJECTION QUILL) |  |  |  | 85 | 5-5 | Piping | Y | 3 | LA | Forecast | 2026-05-19 | [5 empty] | 2026-08-10 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 |  | 168 | 2027-03-03 | 2027-04-23 | 2027-04-24 | 2027-05-01 |  | 51 | WPA-02 | 2027-04-30
| RFQ-PIP-092 | CORROSION FITTINGS (PROBE, COUPON AND CHEMICAL INJECTION QUILL) | [5 empty] | Piping | Y | 3 | LA | Actual |  | 2026-05-27 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-15 | [26 empty] | Request CPY for support to shorten the approval cycle.
94 | RFQ-PIP-094 | HOSE AND HOSE CONNECTOR | [5 empty] | Piping |  |  | LA | New Plan |  | 2026-05-25 | 2026-06-04 | 2026-06-04 | 2026-06-11 | 2026-06-11 | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 | 24 |  | 2027-03-03 |  |  |  |  | 51 | WPA-01 | 2027-04-30
| RFQ-PIP-094 | HOSE AND HOSE CONNECTOR |  |  |  | 85 | 5-5 | Piping | Y | 3 | LA | Forecast | 2026-05-19 | [5 empty] | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 |  | 168 | 2027-03-03 | 2027-04-23 | 2027-04-24 | 2027-05-01 |  | 51 | WPA-02 | 2027-04-30
| RFQ-PIP-094 | HOSE AND HOSE CONNECTOR | [5 empty] | Piping | Y | 3 | LA | Actual |  | 2026-05-27 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-15 | [26 empty] | Request CPY for support to shorten the approval cycle.
95 | RFQ-PIP-095 | STRAINER | [5 empty] | Piping |  |  | LA | New Plan |  | 2026-05-25 | 2026-06-04 | 2026-06-04 | 2026-06-11 | 2026-06-11 | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 | 24 |  | 2027-03-03 |  |  |  |  | -10 | WPA-01 | 2027-02-28
| RFQ-PIP-095 | STRAINER |  |  |  | 24 | 5-5 | Piping | Y | 3 | LA | Forecast | 2026-05-19 | [5 empty] | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 |  | 168 | 2027-03-03 | 2027-02-21 | 2026-04-23 | 2026-04-30 |  | -10 | WPA-02 | 2027-02-28
| RFQ-PIP-095 | STRAINER | [5 empty] | Piping | Y | 3 | LA | Actual |  | 2026-05-27 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-15 | [23 empty] | install before Testing |  |  | Request CPY for support to shorten the approval cycle.
96 | RFQ-PIP-096 | LIQUID TRAP | [5 empty] | Piping |  |  | LA | New Plan |  | 2026-05-25 | 2026-06-04 | 2026-06-04 | 2026-06-11 | 2026-06-11 | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 | 24 |  | 2027-03-03 |  |  |  |  | 51 | WPA-01 | 2027-04-30
| RFQ-PIP-096 | LIQUID TRAP |  |  |  | 85 | 5-5 | Piping | Y | 3 | LA | Forecast | 2026-05-19 | [5 empty] | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 |  | 168 | 2027-03-03 | 2027-04-23 | 2026-04-23 | 2026-04-30 |  | 51 | WPA-02 | 2027-04-30
| RFQ-PIP-096 | LIQUID TRAP | [5 empty] | Piping | Y | 3 | LA | Actual |  | 2026-05-27 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-15 | [23 empty] | install before Testing |  |  | Request CPY for support to shorten the approval cycle.
97 | RFQ-PIP-097 | G-CLAMP | [5 empty] | Piping |  |  | LA | New Plan |  | 2026-05-25 | 2026-06-04 | 2026-06-04 | 2026-06-11 | 2026-06-11 | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 | 24 |  | 2027-03-03 |  |  |  |  | 51 | WPA-01 | 2027-04-30
| RFQ-PIP-097 | G-CLAMP |  |  |  | 85 | 5-5 | Piping | Y | 3 | LA | Forecast | 2026-05-19 | [5 empty] | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 |  | 168 | 2027-03-03 | 2027-04-23 | 2026-04-23 | 2026-04-30 |  | 51 | WPA-02 | 2027-04-30
| RFQ-PIP-097 | G-CLAMP | [5 empty] | Piping | Y | 3 | LA | Actual |  | 2026-05-27 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-15 | [26 empty] | Request CPY for support to shorten the approval cycle.
98 | RFQ-PIP-098 | FLAME ARRESTOR | [5 empty] | Piping |  |  | LA | New Plan |  | 2026-05-25 | 2026-06-04 | 2026-06-04 | 2026-06-11 | 2026-06-11 | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 | 24 |  | 2027-03-03 |  |  |  |  | 51 | WPA-01 | 2027-04-30
| RFQ-PIP-098 | FLAME ARRESTOR |  |  |  | 85 | 5-5 | Piping | Y | 3 | LA | Forecast | 2026-05-19 | [5 empty] | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 |  | 168 | 2027-03-03 | 2027-04-23 | 2026-04-23 | 2026-04-30 |  | 51 | WPA-02 | 2027-04-30
| RFQ-PIP-098 | FLAME ARRESTOR | [5 empty] | Piping | Y | 3 | LA | Actual |  | 2026-05-27 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-15 | [23 empty] | install before Testing |  |  | Request CPY for support to shorten the approval cycle.
99 | RFQ-PIP-099 | Sightt Glass | [5 empty] | Piping |  |  | LA | New Plan |  | 2026-05-25 | 2026-06-04 | 2026-06-04 | 2026-06-11 | 2026-06-11 | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 | 24 |  | 2027-03-03 |  |  |  |  | 51 | WPA-01 | 2027-04-30
| RFQ-PIP-099 | Sightt Glass |  |  |  | 85 | 5-5 | Piping | Y | 3 | LA | Forecast | 2026-05-19 | [5 empty] | 2026-07-23 | 2026-08-20 | 2026-09-03 |  | 2026-09-16 | 2026-09-18 | 2026-09-28 | 2026-11-02 | 2026-11-16 | 2026-12-16 | 2026-12-16 | 2026-12-18 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-17 | 2027-04-02 |  | 168 | 2027-03-03 | 2027-04-23 | 2026-04-23 | 2026-04-30 |  | 51 | WPA-02 | 2027-04-30
| RFQ-PIP-099 | Sightt Glass | [5 empty] | Piping | Y | 3 | LA | Actual |  | 2026-05-27 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-15 | [23 empty] | install before Testing |  |  | Request CPY for support to shorten the approval cycle.
100 | RFQ-PIP-100 | PIPE SUPPORT | [5 empty] | Piping |  |  | LD | New Plan |  | 2026-05-27 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-07-30 | 2026-08-27 | 2026-09-10 |  | 2026-09-17 | 2026-09-19 | 2026-09-24 | 2026-10-08 | 2026-10-22 | 2026-10-08 | 2026-10-08 | 2026-10-10 | 2026-10-29 | 2026-11-01 | 2026-11-16 | 2026-11-30 | 2026-12-16 | 8.5714 |  | 2026-11-16 |  |  |  |  | 16 | WPA-01 | 2026-12-09
| RFQ-PIP-100 | PIPE SUPPORT |  |  |  | 13 | 5-5 | Piping | N | 0 | LD | Forecast | 2026-05-20 | [5 empty] | 2026-08-18 | 2026-08-27 | 2026-09-10 |  | 2026-09-17 | 2026-09-19 | 2026-09-24 | 2026-10-08 | 2026-10-22 | 2026-10-08 | 2026-10-08 | 2026-10-10 | 2026-10-29 | 2026-11-01 | 2026-11-16 | 2026-11-30 | 2026-12-16 |  | 60 | 2026-11-16 | 2026-12-02 | 2026-12-02 | 2026-12-09 | 基于Standard Piping Support | 16 | WPA-02 | 2026-12-09
| RFQ-PIP-100 | PIPE SUPPORT | [5 empty] | Piping | N |  | LD | Actual |  | 2026-05-27 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-11
101 | RFQ-INS-101 | DP LEVEL TRANSMITERS | [5 empty] | Instrument |  |  | LC | New Plan |  | 2026-08-11 | 2026-08-26 | 2026-08-26 | 2026-08-27 | 2026-08-27 | 2026-09-10 | 2026-09-28 | 2026-10-12 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-03 | 2027-02-17 | 2027-02-24 | 2027-03-10 | 2027-03-26 | 18 |  | 2027-02-24 |  |  |  |  | 36 | WPA-01 | 2027-04-08
| RFQ-INS-101 | DP LEVEL TRANSMITTERS |  |  |  | 34 | 4-4.12 | Instrument | N | 4 | LC | Forecast |  | 2026-08-11 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-09-09 | 2026-09-28 | 2026-10-12 |  | 2026-10-23 | 2026-10-27 | 2026-11-03 | 2026-11-24 | 2026-12-09 | 2026-12-24 | 2026-12-24 | 2026-12-26 | 2027-02-05 | 2027-02-19 | 2027-02-26 | 2027-03-12 | 2027-03-28 |  | 126 | 2027-02-26 | 2027-04-01 | 2027-04-08 | 2027-04-15 |  | 34 | WPA-02 | 2027-04-08
| RFQ-INS-101 | DP LEVEL TRANSMITERS | [5 empty] | Instrument | N | 4 | LC | Actual
105 | RFQ-STR-105 | Primary Seamless Pipe | [5 empty] | Structural |  |  | LA | New Plan |  | 2026-07-05 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-17 | 2026-07-20 | 2026-07-24 |  | 2026-07-27 | 2026-07-28 | 2026-08-02 | 2026-08-12 | 2026-08-24 | 2026-08-29 | 2026-08-27 | 2026-08-29 | 2026-10-14 | 2026-10-21 | 2026-10-24 | 2026-11-07 | 2026-11-23 | 12.8571 |  | 2026-10-25 | 1 |  |  |  | 7 | WPA-01 | 2026-10-12
| RFQ-STR-105 | Primary Seamless Pipe |  |  |  | 1 | 5-4 | Structural | Y | 2 | LA | Forecast | 2026-04-25 | [10 empty] | 1900-01-01 | 1900-01-06 | 2026-08-12 | 2026-08-22 | 2026-08-29 | 2026-08-27 | 2026-08-29 | 2026-10-04 | 2026-10-11 | 2026-10-14 | 2026-10-28 | 2026-11-13 |  | 90 | 2026-10-14 | 2026-11-01 | 2026-09-27 | 2026-09-30 | for Deck Pre-assembly | 18 | WPA-02 | 2026-10-23
| RFQ-STR-105 | Primary Seamless Pipe | [5 empty] | Structural | Y | 2 | LA | Actual | 2026-04-25 | 2026-05-20 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2026-06-04 | 2026-07-08 | 2026-07-13 | 2026-07-16 | 2026-10-23: 2026-07-16; 2026-10-27: 2026-07-16; 2026-11-03: 2026-07-17
106 | RFQ-STR-106 | Secondary Steel – Seamless pipe |  |  |  |  | 2 | Structural |  |  | LA | New Plan |  | 2026-07-04 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-15 | 2026-07-20 | 2026-07-23 |  | 2026-07-27 | 2026-07-27 | 2026-08-01 | 2026-08-11 | 2026-08-21 | 2026-08-28 | 2026-08-26 | 2026-08-28 | 2026-10-13 | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-22 | 12.8571 |  | 2026-10-25 | 2 |  |  |  | 7 | WPA-01 | 2026-10-12
| RFQ-STR-106 | Secondary Steel – Seamless pipe |  |  |  | 1 | 5-4 | Structural | Y | 2 | LA | Forecast | 2026-04-25 | [6 empty] | 2026-07-27 | 2026-07-30 |  | 2026-08-01 | 2026-08-03 | 2026-08-08 | 2026-08-18 | 2026-08-28 | 2026-09-04 | 2026-09-02 | 2026-09-04 | 2026-10-20 | 2026-10-27 | 2026-10-30 | 2026-11-13 | 2026-11-29 |  | 90 | 2026-10-30 | 2026-11-01 | 2026-09-27 | 2026-09-30 | for Deck Pre-assembly | 2 | WPA-02 | 2026-10-23
| RFQ-STR-106 | Secondary Steel – Seamless pipe | [5 empty] | Structural | Y | 2 | LA | Actual | 2026-04-25 | 2026-07-07 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-15
107 | RFQ-STR-107 | Secondary Steel – Plate |  |  |  |  | 1 | Structural |  |  | LA | New Plan |  | 2026-07-04 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-07-15 | 2026-07-20 | 2026-07-23 |  | 2026-07-27 | 2026-07-27 | 2026-08-01 | 2026-08-11 | 2026-08-21 | 2026-08-28 | 2026-08-26 | 2026-08-28 | 2026-09-13 | 2026-09-18 | 2026-09-23 | 2026-11-06 | 2026-11-22 | 8.5714 |  | 2026-09-25 |  |  |  |  | 10 | WPA-01 | 2026-10-12
| RFQ-STR-107 | Secondary Steel – Plate |  |  |  | 1 | 5-4 | Structural | Y | 2 | LA | Forecast | 2026-04-25 | [6 empty] | 2026-07-27 | 2026-07-30 |  | 2026-08-01 | 2026-08-03 | 2026-08-08 | 2026-08-18 | 2026-08-28 | 2026-09-04 | 2026-09-02 | 2026-09-04 | 2026-09-20 | 2026-09-27 | 2026-09-30 | 2026-10-14 | 2026-10-30 |  | 60 | 2026-09-30 | 2026-10-05 | 2026-09-27 | 2026-09-30 | for Deck Pre-assembly | 5 | WPA-02 | 2026-10-23
| RFQ-STR-107 | Secondary Steel – Plate | [5 empty] | Structural | Y | 2 | LA | Actual | 2026-04-25 | 2026-07-07 | 2026-07-19 | 2026-07-19 | 2026-07-19 | 2026-07-19 | 2026-07-21
8.5714
Formulas:
ETA date = [PO Issued]+[Lead Time, row below]
ETA date = [PO Issued]+[Lead Time]
ROS date = [Remark, row above]-3
ROS date = [Remark]-3
ROS date update = [Construction Date]-7
RFQ Issued = [MR Approved]
RFQ Issued = WORKDAY.INTL([MR Approved],INDEX(Q8:Q11,MATCH([Priority Level],L8:L11,0)),1,IF(Q18="China",'China Holidays'!$A2:A82,'Thai Holidays'!$A2:A63))
RFQ Approved = [RFQ Issued]
RFQ Approved = [MR Approved]
CFT Issuance = [RFQ Approved]
CFT Issuance = [MR Approved]
TBE Approved = WORKDAY.INTL([TBE Issued],INDEX(V8:V11,MATCH([Priority Level],L8:L11,0)),1,IF(V18="China",'China Holidays'!$A2:A82,'Thai Holidays'!$A2:A63))
TBE Approved = [TBE Issued]+10
FAT = [Ready for Shipment]-30
Ready for Shipment = [Receipt at WORKSITE]-1
Receipt at WORKSITE = [ETA date]
Punch List Clearance = [ETA date]+14
Vendor Acknowledgement = WORKDAY.INTL([PO Issued],INDEX(Y12:Y15,MATCH([Priority Level],L12:L15,0)),1,IF(Y18="China",'China Holidays'!$A2:A82,'Thai Holidays'!$A2:A63))
KOM = WORKDAY.INTL([Vendor Acknowledgement],INDEX(Z12:Z15,MATCH([Priority Level],L12:L15,0)),1,IF(Z18="China",'China Holidays'!$A2:A82,'Thai Holidays'!$A2:A63))
VD Submission = WORKDAY.INTL([KOM],INDEX(AA12:AA15,MATCH([Priority Level],L12:L15,0)),1,IF(AA18="China",'China Holidays'!$A2:A82,'Thai Holidays'!$A2:A63))
Approval of Key Vendor Documents = WORKDAY.INTL([VD Submission],INDEX(AB12:AB15,MATCH([Priority Level],L12:L15,0)),1,IF(AB18="China",'China Holidays'!$A2:A82,'Thai Holidays'!$A2:A63))
Delivery of Major Materials = [Approval of Key Vendor Documents]+16*7
PIM = [Delivery of Major Materials]+3
Start Production = [PIM]+1
Bid Closing Date = WORKDAY.INTL([CFT Issuance],INDEX(T8:T11,MATCH([Priority Level],L8:L11,0)),1,IF(T18="China",'China Holidays'!$A2:A82,'Thai Holidays'!$A2:A63))
Bid Closing Date = [CFT Issuance]+2
TBE Issued = WORKDAY.INTL([Bid Closing Date],INDEX(U8:U11,MATCH([Priority Level],L8:L11,0)),1,IF(U18="China",'China Holidays'!$A2:A82,'Thai Holidays'!$A2:A63))
TBE Issued = [Bid Closing Date]+2
MR Approved = WORKDAY.INTL([MR Issued],INDEX(P8:P11,MATCH([Priority Level],L8:L11,0)),1,IF(P18="China",'China Holidays'!$A2:A82,'Thai Holidays'!$A2:A63))
MR Approved = [MR Issued]+5
Float = [ROS date, row below]-[ETA date]
Float = [ROS date]-[ETA date]

## Sheet1
2026-02-01
2026-03-01 | 1
2026-04-01 | 2
2026-05-01 | 3
2026-06-01 | 4
2026-07-01 | 5
2026-08-01 | 6
2026-09-01 | 7
2026-10-01 | 8
2026-11-01 | 9
2026-12-01 | 10
2027-01-01 | 11
2027-02-01 | 12
2027-03-01 | 13
2027-04-01 | 14
2027-05-01 | 15
2027-06-01 | 16
2027-07-01 | 17
2027-08-01 | 18
2027-09-01 | 19

## P6 (hidden)
ActivityID | Activity Name | Planned Duration | Start | Finish | Total Float | Calendar
DETAILENGINEERINGFORWELLHEADPLATFORMS(WPA01ANDWPA02)(ASKPROJECT) |  | 211 | 2026-03-04 | 2027-01-18 | 0 | PTTME Office 5dx8h
PROJECTMILESTONE |  | 211 | 2026-03-04 | 2027-01-18 | 0 | PTTME Office 5dx8h
MI-1000 | Project Start, KOM | 0 | 2026-03-04 |  | -47 | PTTME Office 5dx8h
MI-1010 | P&ID Issue for Review | 0 |  | 27-Apr-26* | -7 | PTTME Office 5dx8h
MI-1020 | 30% Model Review | 2 | 2026-05-13 | 2026-05-14 | 10 | PTTME Office 5dx8h
MI-1030 | P&ID issue for HAZOP | 0 |  | 2026-05-28 | 22 | PTTME Office 5dx8h
MI-1040 | HAZID Review Meeting | 2 | 2026-05-20 | 2026-05-21 | 105 | PTTME Office 5dx8h
MI-1050 | HAZOP Review Meeting | 5 | 2026-06-05 | 2026-06-11 | 22 | PTTME Office 5dx8h
MI-1060 | SIL Review Meeting | 2 | 2026-06-19 | 2026-06-22 | 75 | PTTME Office 5dx8h
MI-1070 | Structural - Primary MTO Issue for review | 0 |  | 26-May-26* | 0 | PTTME Office 5dx8h
MI-1080 | 60% Model Review | 5 | 2026-08-24 | 2026-08-28 | 0 | PTTME Office 5dx8h
MI-1090 | 90% Model Review | 1 | 2026-10-26 | 2026-10-26 | 11 | PTTME Office 5dx8h
MI-1100 | Issue all AFC Documents /Drawing | 0 |  | 2027-01-05 | 0 | PTTME Office 5dx8h
MI-1110 | Design Engineering Compilation | 0 |  | 2027-01-18 | 0 | PTTME Office 5dx8h
GENERALSTUDIES |  | 35 | 2026-03-05 | 2026-04-28 | 166 | PTTME Office 5dx8h
PJ-1000 | Master Deliverable Register - IFR | 10 | 2026-03-05 | 2026-03-18 | 166 | PTTME Office 5dx8h
PJ-1010 | Master Deliverable Register - AFC | 5 | 2026-04-02 | 2026-04-09 | 171 | PTTME Office 5dx8h
PJ-1020 | Engineering Master Schedule - IFR | 10 | 2026-03-19 | 2026-04-01 | 166 | PTTME Office 5dx8h
PJ-1030 | Engineering Master Schedule - AFC | 5 | 2026-04-22 | 2026-04-28 | 166 | PTTME Office 5dx8h
PROCESSANDUTILITIESENGINEERING |  | 80 | 2026-03-25 | 2026-07-23 | 107 | PTTME Office 5dx8h
PR-1000 | Process Basis of Design - IFR | 10 | 2026-04-01 | 2026-04-20 | 33 | PTTME Office 5dx8h
PR-1010 | Process Basis of Design - IFA | 5 | 2026-05-06 | 2026-05-12 | 33 | PTTME Office 5dx8h
PR-1020 | Process Basis of Design - AFC | 5 | 2026-05-27 | 2026-06-04 | 33 | PTTME Office 5dx8h
PR-1090 | Process Simulation Report - IFR | 5 | 2026-06-12 | 2026-06-18 | 117 | PTTME Office 5dx8h
PR-1100 | Process Simulation Report - AFC | 5 | 2026-07-03 | 2026-07-09 | 117 | PTTME Office 5dx8h
PR-1110 | Utility Balance and Consumption Report - IFR | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
PR-1120 | Utility Balance and Consumption Report - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
PR-1130 | AIV And FIV Study Report - IFR | 15 | 2026-05-20 | 2026-06-11 | 109 | PTTME Office 5dx8h
PR-1140 | AIV And FIV Study Report - AFC | 5 | 2026-06-26 | 2026-07-02 | 122 | PTTME Office 5dx8h
PR-1150 | Depressurization and Low Temperature Study Report - IFR | 20 | 2026-06-02 | 2026-06-30 | 109 | PTTME Office 5dx8h
PR-1160 | Depressurization and Low Temperature Study Report - AFC | 5 | 2026-07-15 | 2026-07-21 | 109 | PTTME Office 5dx8h
PR-1170 | Vent Sizing and Relief Load Report - IFR | 13 | 2026-06-02 | 2026-06-19 | 116 | PTTME Office 5dx8h
PR-1180 | Vent Sizing and Relief Load Report - AFC | 5 | 2026-07-06 | 2026-07-10 | 116 | PTTME Office 5dx8h
PR-1190 | Instrument Gas System Study Report - IFR | 15 | 2026-06-12 | 2026-07-02 | 107 | PTTME Office 5dx8h
PR-1200 | Instrument Gas System Study Report - AFC | 5 | 2026-07-17 | 2026-07-23 | 107 | PTTME Office 5dx8h
PR-1201 | Produced Water Study Report - IFR | 15 | 2026-06-12 | 2026-07-02 | 107 | PTTME Office 5dx8h
PR-1202 | Produced Water Study Report - AFC | 5 | 2026-07-17 | 2026-07-23 | 107 | PTTME Office 5dx8h
PR-1210 | Topside Dynamic Overpressure Protection Study Report - IFR | 13 | 2026-06-02 | 2026-06-19 | 116 | PTTME Office 5dx8h
PR-1220 | Topside Dynamic Overpressure Protection Study Report - AFC | 5 | 2026-07-06 | 2026-07-10 | 116 | PTTME Office 5dx8h
PR-1230 | Process Line List - IFR | 15 | 2026-04-28 | 2026-05-19 | 105 | PTTME Office 5dx8h
PR-1240 | Process Line List - AFC | 5 | 2026-06-26 | 2026-07-02 | 122 | PTTME Office 5dx8h
PR-1250 | ESD Logic Diagram - IFR | 15 | 2026-04-28 | 2026-05-19 | 137 | PTTME Office 5dx8h
PR-1260 | ESD Logic Diagram - AFC | 5 | 2026-06-26 | 2026-07-02 | 122 | PTTME Office 5dx8h
PR-1270 | Operating, Control, Shutdown and Black Start Philosophy - IFR | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
PR-1280 | Operating, Control, Shutdown and Black Start Philosophy - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
PR-1290 | Isolation Philosophy - IFR | 10 | 2026-04-01 | 2026-04-20 | 157 | PTTME Office 5dx8h
PR-1300 | Isolation Philosophy - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
PR-1310 | Vent and Drain Philosophy - AFC | 10 | 2026-04-01 | 2026-04-20 | 172 | PTTME Office 5dx8h
PR-1320 | Process Control Narrative - AFC | 10 | 2026-07-03 | 2026-07-16 | 112 | PTTME Office 5dx8h
PR-1330 | Process Flow Diagram (WP01) (1 Sheet) - IFR | 5 | 2026-04-01 | 2026-04-08 | -47 | PTTME Office 5dx8h
PR-1340 | Process Flow Diagram (WP01) (1 Sheet) - IFA | 10 | 2026-04-28 | 2026-05-12 | -17 | PTTME Office 5dx8h
PR-1350 | Process Flow Diagram (WP01) (1 Sheet) - AFC | 10 | 2026-05-27 | 2026-06-11 | -17 | PTTME Office 5dx8h
PR-1360 | Utility Flow Diagram (WP01) (4 Sheets) - IFR | 5 | 2026-04-01 | 2026-04-08 | -47 | PTTME Office 5dx8h
PR-1370 | Utility Flow Diagram (WP01) (4 Sheets) - IFA | 10 | 2026-04-28 | 2026-05-12 | -17 | PTTME Office 5dx8h
PR-1380 | Utility Flow Diagram (WP01) (4 Sheets) - AFC | 10 | 2026-05-27 | 2026-06-11 | -17 | PTTME Office 5dx8h
PR-1390 | Process Flow Diagram (WP02) (3 Sheets) - IFR | 5 | 2026-04-01 | 2026-04-08 | -47 | PTTME Office 5dx8h
PR-1400 | Process Flow Diagram (WP02) (3 Sheets) - IFA | 10 | 2026-04-28 | 2026-05-12 | -17 | PTTME Office 5dx8h
PR-1410 | Process Flow Diagram (WP02) (3 Sheets)- AFC | 10 | 2026-05-27 | 2026-06-11 | -17 | PTTME Office 5dx8h
PR-1420 | Utility Flow Diagram (WP02) (4 Sheets) - IFR | 5 | 2026-04-01 | 2026-04-08 | -47 | PTTME Office 5dx8h
PR-1430 | Utility Flow Diagram (WP02) (4 Sheets) - IFA | 10 | 2026-04-28 | 2026-05-12 | -17 | PTTME Office 5dx8h
PR-1440 | Utility Flow Diagram (WP02) (4 Sheets) - AFC | 10 | 2026-05-27 | 2026-06-11 | -17 | PTTME Office 5dx8h
PR-1450 | Piping & Instrumentation Diagram (10 Sheets) - IFR | 15 | 2026-04-01 | 2026-04-27 | -47 | PTTME Office 5dx8h
PR-1460 | Piping & Instrumentation Diagram (10 Sheets) - IFA | 10 | 2026-05-13 | 2026-05-26 | -17 | PTTME Office 5dx8h
PR-1470 | Piping & Instrumentation Diagram (10 Sheets) - AFC | 10 | 2026-06-12 | 2026-06-25 | -17 | PTTME Office 5dx8h
PR-1480 | Piping & Instrumentation Diagram (WP01) (19 Sheets) - IFR | 15 | 2026-04-01 | 2026-04-27 | -47 | PTTME Office 5dx8h
PR-1490 | Piping & Instrumentation Diagram (WP01) (19 Sheets) - IFA | 10 | 2026-05-13 | 2026-05-26 | -17 | PTTME Office 5dx8h
PR-1500 | Piping & Instrumentation Diagram (WP01) (19 Sheets) - AFC | 10 | 2026-06-12 | 2026-06-25 | -17 | PTTME Office 5dx8h
PR-1510 | Piping & Instrumentation Diagram (WP02) (10 Sheets) - IFR | 15 | 2026-04-01 | 2026-04-27 | -47 | PTTME Office 5dx8h
PR-1520 | Piping & Instrumentation Diagram (WP02) (26 Sheets) - IFA | 10 | 2026-05-13 | 2026-05-26 | -17 | PTTME Office 5dx8h
PR-1530 | Piping & Instrumentation Diagram (WP02) (26 Sheets) - AFC | 10 | 2026-06-12 | 2026-06-25 | -17 | PTTME Office 5dx8h
PR-1540 | Heat and Material Balance for WP01 - IFR | 10 | 2026-03-25 | 2026-04-08 | 162 | PTTME Office 5dx8h
PR-1550 | Heat and Material Balance for WP01 - AFC | 5 | 2026-06-12 | 2026-06-18 | 132 | PTTME Office 5dx8h
PR-1560 | Heat and Material Balance for WP02 - IFR | 10 | 2026-03-25 | 2026-04-08 | 162 | PTTME Office 5dx8h
PR-1570 | Heat and Material Balance for WP02 - AFC | 5 | 2026-06-12 | 2026-06-18 | 132 | PTTME Office 5dx8h
PR-1580 | Flow Assurance Basis of Design - IFR | 25 | 2026-04-28 | 2026-06-04 | 107 | PTTME Office 5dx8h
PR-1590 | Flow Assurance Basis of Design - IFA | 10 | 2026-06-19 | 2026-07-02 | 107 | PTTME Office 5dx8h
PR-1600 | Flow Assurance Basis of Design - AFC | 5 | 2026-07-17 | 2026-07-23 | 107 | PTTME Office 5dx8h
PR-1610 | Steady State Flow Assurance Study Report - IFR | 25 | 2026-04-28 | 2026-06-04 | 127 | PTTME Office 5dx8h
PR-1620 | Steady State Flow Assurance Study Report - AFC | 5 | 2026-07-17 | 2026-07-23 | 107 | PTTME Office 5dx8h
PR-1630 | Transient Flow Assurance Study Report - IFR | 25 | 2026-04-28 | 2026-06-04 | 107 | PTTME Office 5dx8h
PR-1640 | Transient Flow Assurance Study Report - IFA | 10 | 2026-06-19 | 2026-07-02 | 107 | PTTME Office 5dx8h
PR-1650 | Transient Flow Assurance Study Report - AFC | 5 | 2026-07-17 | 2026-07-23 | 107 | PTTME Office 5dx8h
ProcessCalculationNote |  | 45 | 2026-04-28 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1660 | Process Calculation Note for Line Sizing - IFR | 23 | 2026-04-28 | 2026-05-29 | -10 | PTTME Office 5dx8h
PR-1670 | Process Calculation Note for Line Sizing - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1680 | Process Calculation Note for Test Separator Sizing - IFR | 15 | 2026-04-28 | 2026-05-19 | -2 | PTTME Office 5dx8h
PR-1690 | Process Calculation Note for Test Separator Sizing - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1700 | Process Calculation Note for Production Separator (V-01001) - IFR | 15 | 2026-04-28 | 2026-05-19 | -2 | PTTME Office 5dx8h
PR-1710 | Process Calculation Note for Production Separator (V-01001) - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1720 | Process Calculation Note for Skim Tank Vessel (V-10002) - IFR | 15 | 2026-04-28 | 2026-05-19 | -2 | PTTME Office 5dx8h
PR-1730 | Process Calculation Note for Skim Tank Vessel (V-10002) - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1740 | Process Calculation Note for Degasser - IFR | 15 | 2026-04-28 | 2026-05-19 | -2 | PTTME Office 5dx8h
PR-1750 | Process Calculation Note for Degasser - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1760 | Process Calculation Note for Closed Drain Sump Vessel Sizing (V-05001) - IFR | 23 | 2026-04-28 | 2026-05-29 | -10 | PTTME Office 5dx8h
PR-1770 | Process Calculation Note for Closed Drain Sump Vessel Sizing (V-05001) - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1780 | Process Calculation Note for Closed Drain Sump Pump Sizing (P-05001) - IFR | 23 | 2026-04-28 | 2026-05-29 | -10 | PTTME Office 5dx8h
PR-1790 | Process Calculation Note for Closed Drain Sump Pump Sizing (P-05001) - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1800 | Process Calculation Note for Open Drain Caisson Tank (T-05003) - IFR | 23 | 2026-04-28 | 2026-05-29 | -10 | PTTME Office 5dx8h
PR-1810 | Process Calculation Note for Open Drain Caisson Tank (T-05003) - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1820 | Process Calculation Note for Open Drain Caisson Pump - IFR | 23 | 2026-04-28 | 2026-05-29 | -10 | PTTME Office 5dx8h
PR-1830 | Process Calculation Note for Open Drain Caisson Pump - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1840 | Process Calculation Note for Recovered Water Pump (P-05002) - IFR | 15 | 2026-04-28 | 2026-05-19 | -2 | PTTME Office 5dx8h
PR-1850 | Process Calculation Note for Recovered Water Pump (P-05002) - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1860 | Process Calculation Note for Instrument Gas Filter Coalescer and Stand Pipe Sizing - IFR | 23 | 2026-04-28 | 2026-05-29 | -30 | PTTME Office 5dx8h
PR-1870 | Process Calculation Note for Instrument Gas Filter Coalescer and Stand Pipe Sizing - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1880 | Process Calculation Note for Corrosion Inhibitor/Volatile Corrosion Inhibitor Tank and Pump Sizing - IFR | 15 | 2026-04-28 | 2026-05-19 | -44 | PTTME Office 5dx8h
PR-1890 | Process Calculation Note for Corrosion Inhibitor/Volatile Corrosion Inhibitor Tank and Pump Sizing - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1900 | Process Calculation Note for Demulsifier / Water Clarifier Tank and Pump Sizing - IFR | 15 | 2026-04-28 | 2026-05-19 | -47 | PTTME Office 5dx8h
PR-1910 | Process Calculation Note for Demulsifier / Water Clarifier Tank and Pump Sizing - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1920 | Process Calculation Note for Biocide Tank and Pump Sizing (Provision) - IFR | 15 | 2026-04-28 | 2026-05-19 | -2 | PTTME Office 5dx8h
PR-1930 | Process Calculation Note for Biocide Tank and Pump Sizing (Provision) - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1940 | Process Calculation Note for Diesel Tote Tank, Day Tank and Diesel Transfer Pump - IFR | 15 | 2026-04-28 | 2026-05-19 | -21 | PTTME Office 5dx8h
PR-1950 | Process Calculation Note for Diesel Tote Tank, Day Tank and Diesel Transfer Pump - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1960 | Process Calculation Note for Fresh Water Tote Tank - IFR | 15 | 2026-04-28 | 2026-05-19 | -16 | PTTME Office 5dx8h
PR-1970 | Process Calculation Note for Fresh Water Tote Tank - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-1980 | Process Calculation Note for Choke Valve Sizing - IFR | 8 | 2026-04-28 | 2026-05-08 | 5 | PTTME Office 5dx8h
PR-1990 | Process Calculation Note for Choke Valve Sizing - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-2000 | Process Calculation Note for Control Valve Sizing - IFR | 13 | 2026-04-28 | 2026-05-15 | 0 | PTTME Office 5dx8h
PR-2010 | Process Calculation Note for Control Valve Sizing - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-2020 | Process Calculation Note for RO Sizing - IFR | 23 | 2026-04-28 | 2026-05-29 | -10 | PTTME Office 5dx8h
PR-2030 | Process Calculation Note for RO Sizing - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-2040 | Process Calculation Note for PSV Sizing - IFR | 23 | 2026-04-28 | 2026-05-29 | -10 | PTTME Office 5dx8h
PR-2050 | Process Calculation Note for PSV Sizing - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
PR-2060 | Process Calculation Note - Depressurization and Blowdown - IFR | 23 | 2026-04-28 | 2026-05-29 | -10 | PTTME Office 5dx8h
PR-2070 | Process Calculation Note - Depressurization and Blowdown - AFC | 5 | 2026-06-26 | 2026-07-02 | -17 | PTTME Office 5dx8h
MECHANICALENGINEERING |  | 194 | 2026-03-10 | 2026-12-28 | 4 | PTTME Office 5dx8h
ME-1000 | Mechanical Basis of Design - IFR | 19 | 2026-03-10 | 2026-04-03 | 4 | PTTME Office 5dx8h
ME-1010 | Mechanical Basis of Design - AFC | 10 | 2026-04-24 | 2026-05-08 | 159 | PTTME Office 5dx8h
ME-1020 | Material Handling Study Reports - IFR | 15 | 2026-04-17 | 2026-05-08 | 4 | PTTME Office 5dx8h
ME-1030 | Material Handling Study Reports - AFC | 10 | 2026-09-09 | 2026-09-22 | 68 | PTTME Office 5dx8h
ME-1040 | WPA01 Mechanical Equipment List - IFR | 20 | 2026-04-29 | 2026-05-27 | 32 | PTTME Office 5dx8h
ME-1050 | WPA01 Mechanical Equipment List - AFC | 10 | 2026-06-26 | 2026-07-09 | 82 | PTTME Office 5dx8h
ME-1060 | WPA02 Mechanical Equipment List - IFR | 20 | 2026-04-29 | 2026-05-27 | 32 | PTTME Office 5dx8h
ME-1070 | WPA02 Mechanical Equipment List - AFC | 10 | 2026-06-26 | 2026-07-09 | 82 | PTTME Office 5dx8h
ME-1080 | Project Particular Specification for Test and Production Separators - IFR | 25 | 2026-03-10 | 2026-04-17 | 153 | PTTME Office 5dx8h
ME-1090 | Project Particular Specification for Test and Production Separators - AFC | 10 | 2026-05-05 | 2026-05-18 | 153 | PTTME Office 5dx8h
ME-1100 | Project Particular Specification for Instrument Gas Filter coalescers - IFR | 23 | 2026-03-10 | 2026-04-10 | 155 | PTTME Office 5dx8h
ME-1110 | Project Particular Specification for Instrument Gas Filter coalescers - AFC | 10 | 2026-04-30 | 2026-05-14 | 155 | PTTME Office 5dx8h
ME-1120 | Project Particular Specification for Storage Tote Tanks - IFR | 29 | 2026-03-10 | 2026-04-23 | 149 | PTTME Office 5dx8h
ME-1130 | Project Particular Specification for Storage Tote Tanks - AFC | 10 | 2026-05-11 | 2026-05-22 | 149 | PTTME Office 5dx8h
ME-1140 | Project Particular Specification for Storage Tanks - IFR | 29 | 2026-03-10 | 2026-04-23 | 149 | PTTME Office 5dx8h
ME-1150 | Project Particular Specification for Storage Tanks - AFC | 10 | 2026-05-11 | 2026-05-22 | 149 | PTTME Office 5dx8h
ME-1160 | Project Particular Specification for Chemical Injection Pumps Package - IFR | 27 | 2026-03-10 | 2026-04-21 | 57 | PTTME Office 5dx8h
ME-1170 | Project Particular Specification for Chemical Injection Pumps Package - AFC | 10 | 2026-05-07 | 2026-05-20 | 141 | PTTME Office 5dx8h
ME-1180 | Project Particular Specification for Diesel Oil Transfer Pump Package - IFR | 19 | 2026-05-15 | 2026-06-12 | 41 | PTTME Office 5dx8h
ME-1190 | Project Particular Specification for Diesel Oil Transfer Pump Package - AFC | 10 | 2026-06-29 | 2026-07-10 | 106 | PTTME Office 5dx8h
ME-1200 | Project Particular Specification for Offshore Pedestal Crane - IFR | 15 | 2026-03-16 | 2026-04-03 | -34 | PTTME Office 5dx8h
ME-1210 | Project Particular Specification for Offshore Pedestal Crane - AFC | 10 | 2026-04-24 | 2026-05-08 | 20 | PTTME Office 5dx8h
ME-1220 | Project Particular Specification for Closed Drain Sump Vessels - IFR | 15 | 2026-04-01 | 2026-04-27 | 147 | PTTME Office 5dx8h
ME-1230 | Project Particular Specification for Closed Drain Sump Vessels - AFC | 10 | 2026-05-13 | 2026-05-26 | 147 | PTTME Office 5dx8h
ME-1240 | Project Particular Specification for Closed Drain Sump and Recovered Water Pump Package - IFR | 15 | 2026-04-01 | 2026-04-27 | 147 | PTTME Office 5dx8h
ME-1250 | Project Particular Specification for Closed Drain Sump and Recovered Water Pump Package - AFC | 10 | 2026-05-13 | 2026-05-26 | 147 | PTTME Office 5dx8h
ME-1260 | Project Particular Specification for Material Handling Equipment - IFR | 10 | 2026-05-11 | 2026-05-22 | 99 | PTTME Office 5dx8h
ME-1270 | Project Particular Specification for Material Handling Equipment - AFC | 10 | 2026-06-10 | 2026-06-23 | 119 | PTTME Office 5dx8h
ME-1280 | Project Particular Specification for Deoiler Hydro cyclone Package - IFR | 18 | 2026-03-16 | 2026-04-09 | -33 | PTTME Office 5dx8h
ME-1290 | Project Particular Specification for Deoiler Hydro cyclone Package - AFC | 10 | 2026-04-29 | 2026-05-13 | 28 | PTTME Office 5dx8h
ME-1300 | Project Particular Specification for Degasser Drum - IFR | 23 | 2026-03-10 | 2026-04-10 | 155 | PTTME Office 5dx8h
ME-1310 | Project Particular Specification for Degasser Drum - AFC | 10 | 2026-04-30 | 2026-05-14 | 155 | PTTME Office 5dx8h
ME-1320 | Project Particular Specification for Skim Tank Vessel - IFR | 15 | 2026-03-31 | 2026-04-24 | 148 | PTTME Office 5dx8h
ME-1330 | Project Particular Specification for Skim Tank Vessel - AFC | 10 | 2026-05-12 | 2026-05-25 | 148 | PTTME Office 5dx8h
ME-1340 | Project Particular Specification for Open Drain Caisson Pump Package - IFR | 15 | 2026-04-22 | 2026-05-13 | 136 | PTTME Office 5dx8h
ME-1350 | Project Particular Specification for Open Drain Caisson Pump Package - AFC | 10 | 2026-05-28 | 2026-06-12 | 136 | PTTME Office 5dx8h
ME-2510 | Criticality Rating Report for Equipment - IFR | 15 | 2026-03-25 | 2026-04-20 | 152 | PTTME Office 5dx8h
ME-2520 | Criticality Rating Report for Equipment - AFC | 10 | 2026-05-06 | 2026-05-19 | 152 | PTTME Office 5dx8h
Datasheets-Mechanical |  | 104 | 2026-03-16 | 2026-08-21 | 90 | PTTME Office 5dx8h
ME-1360 | Mechanical Datasheet for Corrosion Inhibitor Storage Tank (T-09001) - IFR | 10 | 2026-04-28 | 2026-05-12 | -44 | PTTME Office 5dx8h
ME-1370 | Mechanical Datasheet for Corrosion Inhibitor Storage Tank (T-09001) - IFA | 10 | 2026-06-02 | 2026-06-16 | 34 | PTTME Office 5dx8h
ME-1380 | Mechanical Datasheet for Corrosion Inhibitor Storage Tank (T-09001) - AFC | 5 | 2026-07-03 | 2026-07-09 | 32 | PTTME Office 5dx8h
ME-1390 | Mechanical Datasheet for Corrosion Inhibitor Storage Tote Tank (T-09011) - IFR | 12 | 2026-04-28 | 2026-05-14 | -16 | PTTME Office 5dx8h
ME-1400 | Mechanical Datasheet for Corrosion Inhibitor Storage Tote Tank (T-09011) - IFA | 10 | 2026-06-05 | 2026-06-18 | 32 | PTTME Office 5dx8h
ME-1410 | Mechanical Datasheet for Corrosion Inhibitor Storage Tote Tank (T-09011) - AFC | 5 | 2026-07-03 | 2026-07-09 | 32 | PTTME Office 5dx8h
ME-1420 | Mechanical Datasheet for Utility Water Storage Tote Tank (T-07003, T-07013) - IFR | 10 | 2026-04-30 | 2026-05-14 | -16 | PTTME Office 5dx8h
ME-1430 | Mechanical Datasheet for Utility Water Storage Tote Tank (T-07003, T-07013) - IFA | 10 | 2026-06-05 | 2026-06-18 | 32 | PTTME Office 5dx8h
ME-1440 | Mechanical Datasheet for Utility Water Storage Tote Tank (T-07003, T-07013) - AFC | 5 | 2026-07-03 | 2026-07-09 | 32 | PTTME Office 5dx8h
ME-1450 | Mechanical Datasheet for Diesel Storage Tote Tank (T-07001,T-07011) - IFR | 10 | 2026-05-04 | 2026-05-15 | -21 | PTTME Office 5dx8h
ME-1460 | Mechanical Datasheet for Diesel Storage Tote Tank (T-07001,T-07011) - IFA | 10 | 2026-06-08 | 2026-06-19 | 32 | PTTME Office 5dx8h
ME-1470 | Mechanical Datasheet for Diesel Storage Tote Tank (T-07001,T-07011) - AFC | 5 | 2026-07-03 | 2026-07-09 | 32 | PTTME Office 5dx8h
ME-1480 | Mechanical Datasheet for Offshore Pedestal Crane CR-07001 - IFR | 15 | 2026-03-16 | 2026-04-03 | -34 | PTTME Office 5dx8h
ME-1490 | Mechanical Datasheet for Offshore Pedestal Crane CR-07001 - IFA | 5 | 2026-05-04 | 2026-05-08 | 10 | PTTME Office 5dx8h
ME-1500 | Mechanical Datasheet for Offshore Pedestal Crane CR-07001 - AFC | 5 | 2026-07-03 | 2026-07-09 | -17 | PTTME Office 5dx8h
ME-1540 | Mechanical Datasheet for Instrument Gas Filter coalescer (V-03001) - IFR | 12 | 2026-04-28 | 2026-05-14 | -30 | PTTME Office 5dx8h
ME-1550 | Mechanical Datasheet for Instrument Gas Filter coalescer (V-03001) - IFA | 10 | 2026-06-05 | 2026-06-18 | 117 | PTTME Office 5dx8h
ME-1560 | Mechanical Datasheet for Instrument Gas Filter coalescer (V-03001) - AFC | 5 | 2026-07-03 | 2026-07-09 | 117 | PTTME Office 5dx8h
ME-1570 | Mechanical Datasheet for Diesel Transfer Pump Package (Sk-07001) - IFR | 15 | 2026-06-15 | 2026-07-03 | 41 | PTTME Office 5dx8h
ME-1580 | Mechanical Datasheet for Diesel Transfer Pump Package (Sk-07001) - IFA | 10 | 2026-07-22 | 2026-08-07 | 85 | PTTME Office 5dx8h
ME-1590 | Mechanical Datasheet for Diesel Transfer Pump Package (Sk-07001) - AFC | 5 | 2026-08-17 | 2026-08-21 | 85 | PTTME Office 5dx8h
ME-1600 | WPA01 Mechanical Datasheet for Test Separator (V-01001) - IFR | 10 | 2026-03-31 | 2026-04-17 | -21 | PTTME Office 5dx8h
ME-1610 | WPA01 Mechanical Datasheet for Test Separator (V-01001) - IFA | 10 | 2026-05-11 | 2026-05-22 | 49 | PTTME Office 5dx8h
ME-1620 | WPA01 Mechanical Datasheet for Test Separator (V-01001) - AFC | 5 | 2026-07-03 | 2026-07-09 | 32 | PTTME Office 5dx8h
ME-1660 | WPA01 Mechanical Datasheet for Corrosion Inhibitor Injection Pump Package SK-09001 - IFR | 12 | 2026-04-28 | 2026-05-14 | 92 | PTTME Office 5dx8h
ME-1670 | WPA01 Mechanical Datasheet for Corrosion Inhibitor Injection Pump Package SK-09001 - IFA | 10 | 2026-06-05 | 2026-06-18 | 112 | PTTME Office 5dx8h
ME-1680 | WPA01 Mechanical Datasheet for Corrosion Inhibitor Injection Pump Package SK-09001 - AFC | 5 | 2026-07-03 | 2026-07-09 | 112 | PTTME Office 5dx8h
ME-1720 | WPA01 Mechanical Datasheet for Closed Drain Sump Vessel (V-05001) - IFR | 8 | 2026-04-28 | 2026-05-08 | 1 | PTTME Office 5dx8h
ME-1730 | WPA01 Mechanical Datasheet for Closed Drain Sump Vessel (V-05001) - IFA | 10 | 2026-05-28 | 2026-06-12 | 43 | PTTME Office 5dx8h
ME-1740 | WPA01 Mechanical Datasheet for Closed Drain Sump Vessel (V-05001) - AFC | 5 | 2026-07-03 | 2026-07-09 | 39 | PTTME Office 5dx8h
ME-1750 | WPA01 Mechanical Datasheet for Closed Drain Sump Pump (P-05001) - IFR | 8 | 2026-04-28 | 2026-05-08 | 0 | PTTME Office 5dx8h
ME-1760 | WPA01 Mechanical Datasheet for Closed Drain Sump Pump (P-05001) - IFA | 10 | 2026-05-28 | 2026-06-12 | 16 | PTTME Office 5dx8h
ME-1770 | WPA01 Mechanical Datasheet for Closed Drain Sump Pump (P-05001) - AFC | 5 | 2026-07-03 | 2026-07-09 | 12 | PTTME Office 5dx8h
ME-1780 | WPA01 Mechanical Datasheet for Material Handling Equipment - IFR | 10 | 2026-05-18 | 2026-05-29 | 4 | PTTME Office 5dx8h
ME-1790 | WPA01 Mechanical Datasheet for Material Handling Equipment - IFA | 10 | 2026-06-22 | 2026-07-03 | 106 | PTTME Office 5dx8h
ME-1800 | WPA01 Mechanical Datasheet for Material Handling Equipment - AFC | 5 | 2026-07-13 | 2026-07-17 | 106 | PTTME Office 5dx8h
ME-1810 | WPA02 Mechanical Datasheet for Test Separator (V-01001) - IFR | 15 | 2026-03-31 | 2026-04-24 | -26 | PTTME Office 5dx8h
ME-1820 | WPA02 Mechanical Datasheet for Test Separator (V-01001) - IFA | 5 | 2026-05-25 | 2026-05-29 | 44 | PTTME Office 5dx8h
ME-1830 | WPA02 Mechanical Datasheet for Test Separator (V-01001) - AFC | 5 | 2026-07-03 | 2026-07-09 | 32 | PTTME Office 5dx8h
ME-1840 | WPA02 Mechanical Datasheet for Production Separator (V-10001) - IFR | 15 | 2026-03-31 | 2026-04-24 | 138 | PTTME Office 5dx8h
ME-1850 | WPA02 Mechanical Datasheet for Production Separator (V-10001) - IFA | 5 | 2026-05-25 | 2026-05-29 | 129 | PTTME Office 5dx8h
ME-1860 | WPA02 Mechanical Datasheet for Production Separator (V-10001) - AFC | 5 | 2026-07-03 | 2026-07-09 | 117 | PTTME Office 5dx8h
ME-1900 | WPA02 Mechanical Datasheet for De-mulsifier / Water Clarifier Storage Tank (T-09003) - IFR | 13 | 2026-04-28 | 2026-05-15 | -47 | PTTME Office 5dx8h
ME-1910 | WPA02 Mechanical Datasheet for De-mulsifier / Water Clarifier Storage Tank (T-09003) - IFA | 10 | 2026-06-08 | 2026-06-19 | 32 | PTTME Office 5dx8h
ME-1920 | WPA02 Mechanical Datasheet for De-mulsifier / Water Clarifier Storage Tank (T-09003) - AFC | 5 | 2026-07-03 | 2026-07-09 | 32 | PTTME Office 5dx8h
ME-1930 | WPA02 Mechanical Datasheet for De-mulsifier / Water Clarifier Storage Tote Tank (T-09013) - IFR | 12 | 2026-04-28 | 2026-05-14 | -46 | PTTME Office 5dx8h
ME-1940 | WPA02 Mechanical Datasheet for De-mulsifier / Water Clarifier Storage Tote Tank (T-09013) - IFA | 10 | 2026-06-05 | 2026-06-18 | 32 | PTTME Office 5dx8h
ME-1950 | WPA02 Mechanical Datasheet for De-mulsifier / Water Clarifier Storage Tote Tank (T-09013) - AFC | 5 | 2026-07-03 | 2026-07-09 | 32 | PTTME Office 5dx8h
ME-1960 | WPA02 Mechanical Datasheet for Chemical Injection Pumps Package SK-09001 - IFR | 12 | 2026-04-28 | 2026-05-14 | 92 | PTTME Office 5dx8h
ME-1970 | WPA02 Mechanical Datasheet for Chemical Injection Pumps Package SK-09001 - IFA | 10 | 2026-06-05 | 2026-06-18 | 112 | PTTME Office 5dx8h
ME-1980 | WPA02 Mechanical Datasheet for Chemical Injection Pumps Package SK-09001 - AFC | 5 | 2026-07-03 | 2026-07-09 | 112 | PTTME Office 5dx8h
ME-2020 | WPA02 Mechanical Datasheet for Closed Drain Sump Vessel (V-05001) - IFR | 9 | 2026-04-28 | 2026-05-11 | 0 | PTTME Office 5dx8h
ME-2030 | WPA02 Mechanical Datasheet for Closed Drain Sump Vessel (V-05001) - IFA | 10 | 2026-05-29 | 2026-06-15 | 42 | PTTME Office 5dx8h
ME-2040 | WPA02 Mechanical Datasheet for Closed Drain Sump Vessel (V-05001) - AFC | 5 | 2026-07-03 | 2026-07-09 | 39 | PTTME Office 5dx8h
ME-2050 | WPA02 Mechanical Datasheet for Closed Drain Sump Pump and Recovery Water Pump (SK-05001) - IFR | 8 | 2026-04-28 | 2026-05-08 | 0 | PTTME Office 5dx8h
ME-2060 | WPA02 Mechanical Datasheet for Closed Drain Sump Pump and Recovery Water Pump (SK-05001) - IFA | 10 | 2026-05-28 | 2026-06-12 | 16 | PTTME Office 5dx8h
ME-2070 | WPA02 Mechanical Datasheet for Closed Drain Sump Pump and Recovery Water Pump (SK-05001) - AFC | 5 | 2026-07-03 | 2026-07-09 | 12 | PTTME Office 5dx8h
ME-2080 | WPA02 Mechanical Datasheet for Material Handling Equipment - IFR | 10 | 2026-05-18 | 2026-05-29 | 4 | PTTME Office 5dx8h
ME-2090 | WPA02 Mechanical Datasheet for Material Handling Equipment - IFA | 10 | 2026-06-22 | 2026-07-03 | 106 | PTTME Office 5dx8h
ME-2100 | WPA02 Mechanical Datasheet for Material Handling Equipment - AFC | 5 | 2026-07-13 | 2026-07-17 | 106 | PTTME Office 5dx8h
ME-2110 | WPA02 Mechanical Datasheet for Skim Tank Vessel (V-10002) - IFR | 8 | 2026-04-28 | 2026-05-08 | 0 | PTTME Office 5dx8h
ME-2120 | WPA02 Mechanical Datasheet for Skim Tank Vessel (V-10002) - IFA | 10 | 2026-05-28 | 2026-06-12 | 31 | PTTME Office 5dx8h
ME-2130 | WPA02 Mechanical Datasheet for Skim Tank Vessel (V-10002) - AFC | 5 | 2026-07-03 | 2026-07-09 | 27 | PTTME Office 5dx8h
ME-2140 | WPA02 Mechanical Datasheet for Deoiler Hydro cyclone Package (SK-11001) - IFR | 6 | 2026-04-10 | 2026-04-22 | -33 | PTTME Office 5dx8h
ME-2150 | WPA02 Mechanical Datasheet for Deoiler Hydro cyclone Package (SK-11001) - IFA | 10 | 2026-05-14 | 2026-05-27 | 8 | PTTME Office 5dx8h
ME-2160 | WPA02 Mechanical Datasheet for Deoiler Hydro cyclone Package (SK-11001) - AFC | 5 | 2026-07-03 | 2026-07-09 | -6 | PTTME Office 5dx8h
ME-2170 | WPA02 Mechanical Datasheet for Degasser Drum (V-11003) - IFR | 6 | 2026-04-10 | 2026-04-22 | 0 | PTTME Office 5dx8h
ME-2180 | WPA02 Mechanical Datasheet for Degasser Drum (V-11003) - IFA | 10 | 2026-05-14 | 2026-05-27 | 41 | PTTME Office 5dx8h
ME-2190 | WPA02 Mechanical Datasheet for Degasser Drum (V-11003) - AFC | 5 | 2026-07-03 | 2026-07-09 | 27 | PTTME Office 5dx8h
ME-2200 | WPA02 Mechanical Datasheet for Open Drain Caisson Pump Package SK-05003) - IFR | 15 | 2026-05-14 | 2026-06-05 | 72 | PTTME Office 5dx8h
ME-2210 | WPA02 Mechanical Datasheet for Open Drain Caisson Pump Package SK-05003) - IFA | 10 | 2026-06-29 | 2026-07-10 | 101 | PTTME Office 5dx8h
ME-2220 | WPA02 Mechanical Datasheet for Open Drain Caisson Pump Package SK-05003) - AFC | 5 | 2026-07-20 | 2026-07-24 | 101 | PTTME Office 5dx8h
MR-Mechanical |  | 165 | 2026-04-24 | 2026-12-28 | 4 | PTTME Office 5dx8h
ME-2230 | Material Requisition for Test and Production Separator - IFR | 10 | 2026-06-26 | 2026-07-09 | -26 | PTTME Office 5dx8h
ME-2240 | Material Requisition for Test and Production Separator - AFC | 5 | 2026-10-06 | 2026-10-12 | -26 | PTTME Office 5dx8h
ME-2250 | Material Requisition for Instrument Gas Filter coalescer - IFR | 10 | 2026-07-08 | 2026-07-21 | -30 | PTTME Office 5dx8h
ME-2260 | Material Requisition for Instrument Gas Filter coalescer - AFC | 5 | 2026-10-12 | 2026-10-19 | -30 | PTTME Office 5dx8h
ME-2270 | Material Requisition for Storage Tote Tanks - IFR | 10 | 2026-06-19 | 2026-07-02 | -21 | PTTME Office 5dx8h
ME-2280 | Material Requisition for Storage Tote Tanks - AFC | 5 | 2026-09-29 | 2026-10-05 | -21 | PTTME Office 5dx8h
ME-2290 | Material Requisition for Storage Tanks - IFR | 10 | 2026-07-22 | 2026-08-07 | -47 | PTTME Office 5dx8h
ME-2300 | Material Requisition for Storage Tanks - AFC | 5 | 2026-11-06 | 2026-11-12 | -47 | PTTME Office 5dx8h
ME-2310 | Material Requisition for Chemical Injection Pumps Package - IFR | 10 | 2026-05-05 | 2026-05-18 | 92 | PTTME Office 5dx8h
ME-2320 | Material Requisition for Chemical Injection Pumps Package - AFC | 5 | 2026-08-13 | 2026-08-19 | 92 | PTTME Office 5dx8h
ME-2330 | Material Requisition for Diesel Oil Transfer Pump Package - IFR | 10 | 2026-07-16 | 2026-08-03 | 41 | PTTME Office 5dx8h
ME-2340 | Material Requisition for Diesel Oil Transfer Pump Package - AFC | 5 | 2026-10-27 | 2026-11-02 | 41 | PTTME Office 5dx8h
ME-2350 | Material Requisition for Offshore Pedestal Crane - IFR | 5 | 2026-05-07 | 2026-05-13 | -34 | PTTME Office 5dx8h
ME-2360 | Material Requisition for Offshore Pedestal Crane - AFC | 5 | 2026-08-07 | 2026-08-14 | -34 | PTTME Office 5dx8h
ME-2370 | Material Requisition for Closed Drain Sump Vessel - IFR | 10 | 2026-05-27 | 2026-06-11 | 0 | PTTME Office 5dx8h
ME-2380 | Material Requisition for Closed Drain Sump Vessel - AFC | 5 | 2026-09-09 | 2026-09-15 | 0 | PTTME Office 5dx8h
ME-2390 | Material Requisition for Closed Drain Sump Pump and Recovery Water Pump Package - IFR | 10 | 2026-04-24 | 2026-05-08 | 0 | PTTME Office 5dx8h
ME-2400 | Material Requisition for Closed Drain Sump Pump and Recovery Water Pump Package - AFC | 5 | 2026-07-31 | 2026-08-06 | 0 | PTTME Office 5dx8h
ME-2410 | Material Requisition for Material Handling Equipment - IFR | 10 | 2026-09-07 | 2026-09-18 | 4 | PTTME Office 5dx8h
ME-2420 | Material Requisition for Material Handling Equipment - AFC | 5 | 2026-12-21 | 2026-12-28 | 4 | PTTME Office 5dx8h
ME-2430 | Material Requisition for Deoiler Hydro cyclone Package - IFR | 10 | 2026-05-08 | 2026-05-21 | -33 | PTTME Office 5dx8h
ME-2440 | Material Requisition for Deoiler Hydro cyclone Package - AFC | 5 | 2026-08-24 | 2026-08-28 | -33 | PTTME Office 5dx8h
ME-2450 | Material Requisition for Degasser Drum - IFR | 10 | 2026-05-08 | 2026-05-21 | 0 | PTTME Office 5dx8h
ME-2460 | Material Requisition for Degasser Drum - AFC | 5 | 2026-08-24 | 2026-08-28 | 0 | PTTME Office 5dx8h
ME-2470 | Material Requisition for Skim Tank Vessel - IFR | 10 | 2026-05-08 | 2026-05-21 | 0 | PTTME Office 5dx8h
ME-2480 | Material Requisition for Skim Tank Vessel - AFC | 5 | 2026-08-24 | 2026-08-28 | 0 | PTTME Office 5dx8h
ME-2490 | Material Requisition for Open Drain Caisson Pump - IFR | 10 | 2026-06-05 | 2026-06-18 | 72 | PTTME Office 5dx8h
ME-2500 | Material Requisition for Open Drain Caisson Pump - AFC | 5 | 2026-09-10 | 2026-09-16 | 72 | PTTME Office 5dx8h
TBE-Mechanical |  | 129 | 2026-05-26 | 2026-12-02 | 4 | PTTME Office 5dx8h
ME-2530 | Technical Bid Evaluation for Test and Production Separator - IFR | 20 | 2026-08-03 | 2026-08-31 | -26 | PTTME Office 5dx8h
ME-2540 | Technical Bid Evaluation for Test and Production Separator - AFC | 5 | 2026-09-15 | 2026-09-21 | -26 | PTTME Office 5dx8h
ME-2550 | Technical Bid Evaluation for Instrument Gas Filter coalescer - IFR | 20 | 2026-08-07 | 2026-09-04 | -30 | PTTME Office 5dx8h
ME-2560 | Technical Bid Evaluation for Instrument Gas Filter coalescer - AFC | 5 | 2026-09-21 | 2026-09-25 | -30 | PTTME Office 5dx8h
ME-2570 | Technical Bid Evaluation for Storage Tote Tanks - IFR | 17 | 2026-07-27 | 2026-08-24 | -21 | PTTME Office 5dx8h
ME-2580 | Technical Bid Evaluation for Storage Tote Tanks - AFC | 5 | 2026-09-08 | 2026-09-14 | -21 | PTTME Office 5dx8h
ME-2590 | Technical Bid Evaluation for Storage Tanks - IFR | 20 | 2026-09-02 | 2026-09-29 | -47 | PTTME Office 5dx8h
ME-2600 | Technical Bid Evaluation for Storage Tanks - AFC | 5 | 2026-10-15 | 2026-10-21 | -47 | PTTME Office 5dx8h
ME-2610 | Technical Bid Evaluation for Chemical Injection Pumps Package - IFR | 20 | 2026-06-05 | 2026-07-02 | 92 | PTTME Office 5dx8h
ME-2620 | Technical Bid Evaluation for Chemical Injection Pumps Package - AFC | 5 | 2026-07-17 | 2026-07-23 | 92 | PTTME Office 5dx8h
ME-2630 | Technical Bid Evaluation for Diesel Oil Transfer Pump Package - IFR | 20 | 2026-08-21 | 2026-09-17 | 41 | PTTME Office 5dx8h
ME-2640 | Technical Bid Evaluation for Diesel Oil Transfer Pump Package - AFC | 5 | 2026-10-02 | 2026-10-08 | 41 | PTTME Office 5dx8h
ME-2650 | Technical Bid Evaluation for Offshore Pedestal Crane - IFR | 20 | 2026-05-29 | 2026-06-29 | -34 | PTTME Office 5dx8h
ME-2660 | Technical Bid Evaluation for Offshore Pedestal Crane - AFC | 5 | 2026-07-14 | 2026-07-20 | -34 | PTTME Office 5dx8h
ME-2670 | Technical Bid Evaluation for Closed Drain Sump Vessel - IFR | 17 | 2026-07-07 | 2026-08-03 | 0 | PTTME Office 5dx8h
ME-2680 | Technical Bid Evaluation for Closed Drain Sump Vessel - AFC | 5 | 2026-08-19 | 2026-08-25 | 0 | PTTME Office 5dx8h
ME-2690 | Technical Bid Evaluation for Closed Drain Sump Pump and Recovery Water Pump Package - IFR | 18 | 2026-05-26 | 2026-06-22 | 0 | PTTME Office 5dx8h
ME-2700 | Technical Bid Evaluation for Closed Drain Sump Pump and Recovery Water Pump Package - AFC | 5 | 2026-07-07 | 2026-07-13 | 0 | PTTME Office 5dx8h
ME-2710 | Technical Bid Evaluation for Material Handling Equipment - IFR | 14 | 2026-10-22 | 2026-11-11 | 4 | PTTME Office 5dx8h
ME-2720 | Technical Bid Evaluation for Material Handling Equipment - AFC | 5 | 2026-11-26 | 2026-12-02 | 4 | PTTME Office 5dx8h
ME-2730 | Technical Bid Evaluation for Deoiler Hydro cyclone Package - IFR | 20 | 2026-06-16 | 2026-07-13 | -33 | PTTME Office 5dx8h
ME-2740 | Technical Bid Evaluation for Deoiler Hydro cyclone Package - AFC | 5 | 2026-07-31 | 2026-08-06 | -33 | PTTME Office 5dx8h
ME-2750 | Technical Bid Evaluation for Degasser Drum - IFR | 20 | 2026-06-16 | 2026-07-13 | 0 | PTTME Office 5dx8h
ME-2760 | Technical Bid Evaluation for Degasser Drum - AFC | 5 | 2026-07-31 | 2026-08-06 | 0 | PTTME Office 5dx8h
ME-2770 | Technical Bid Evaluation for Skim Tank Vessel - IFR | 20 | 2026-06-16 | 2026-07-13 | 0 | PTTME Office 5dx8h
ME-2780 | Technical Bid Evaluation for Skim Tank Vessel - AFC | 5 | 2026-07-31 | 2026-08-06 | 0 | PTTME Office 5dx8h
ME-2790 | Technical Bid Evaluation for Open Drain Caisson Pump - IFR | 17 | 2026-07-08 | 2026-08-04 | 72 | PTTME Office 5dx8h
ME-2800 | Technical Bid Evaluation for Open Drain Caisson Pump - AFC | 5 | 2026-08-20 | 2026-08-26 | 72 | PTTME Office 5dx8h
PIPINGENGINEERING |  | 166 | 2026-04-09 | 2026-12-16 | 20 | PTTME Office 5dx8h
PI-1000 | Piping Basis of Design (offshore) - IFR | 20 | 2026-04-21 | 2026-05-19 | 52 | PTTME Office 5dx8h
PI-1010 | Piping Basis of Design (offshore) - AFC | 5 | 2026-06-05 | 2026-06-11 | 127 | PTTME Office 5dx8h
PI-1020 | Piping Stress Basis of Design - IFR | 20 | 2026-04-28 | 2026-05-26 | 112 | PTTME Office 5dx8h
PI-1030 | Piping Stress Basis of Design - AFC | 5 | 2026-06-12 | 2026-06-18 | 127 | PTTME Office 5dx8h
PI-1040 | 3D Model Review Report 30% - IFR | 10 | 2026-05-15 | 2026-05-28 | 130 | PTTME Office 5dx8h
PI-1050 | 3D Model Review Report 30% - AFC | 5 | 2026-06-16 | 2026-06-22 | 130 | PTTME Office 5dx8h
PI-1060 | 3D Model Review Report 60% - IFR | 10 | 2026-08-31 | 2026-09-11 | 60 | PTTME Office 5dx8h
PI-1070 | 3D Model Review Report 60% - AFC | 5 | 2026-09-28 | 2026-10-02 | 60 | PTTME Office 5dx8h
PI-1080 | 3D Model Review & Clash Check Reports (90% and Final 3D Model) - IFR | 10 | 2026-10-27 | 2026-11-09 | 21 | PTTME Office 5dx8h
PI-1090 | 3D Model Review & Clash Check Reports (90% and Final 3D Model) - AFC | 5 | 2026-11-24 | 2026-11-30 | 21 | PTTME Office 5dx8h
PI-1100 | 30% 3D Modeling | 20 | 2026-04-09 | 2026-05-12 | 0 | PTTME Office 5dx8h
PI-1110 | 60%3D Modeling | 60 | 2026-05-13 | 2026-08-11 | 0 | PTTME Office 5dx8h
PI-1120 | 90%3D Modeling | 45 | 2026-08-13 | 2026-10-15 | 11 | PTTME Office 5dx8h
PI-1130 | Drilling Rig Clash Check Report : WPA01 and WPA02 - IFR | 5 | 2026-05-13 | 2026-05-19 | 137 | PTTME Office 5dx8h
PI-1140 | Drilling Rig Clash Check Report : WPA01 and WPA02 - AFC | 5 | 2026-08-13 | 2026-08-19 | 92 | PTTME Office 5dx8h
PI-1150 | Criticality Rating Report for Piping - IFR | 5 | 2026-05-13 | 2026-05-19 | 137 | PTTME Office 5dx8h
PI-1160 | Criticality Rating Report for Piping - AFC | 5 | 2026-08-13 | 2026-08-19 | 92 | PTTME Office 5dx8h
PI-1170 | Piping Material Specification - IFR | 5 | 2026-05-20 | 2026-05-26 | 52 | PTTME Office 5dx8h
PI-1180 | Piping Material Specification - AFC | 5 | 2026-06-12 | 2026-06-18 | 127 | PTTME Office 5dx8h
PI-1190 | Piping Design Standard - IFR | 20 | 2026-05-20 | 2026-06-18 | 52 | PTTME Office 5dx8h
PI-1200 | Piping Design Standard - AFC | 5 | 2026-07-03 | 2026-07-09 | 117 | PTTME Office 5dx8h
PI-1210 | Pipe Support Standard - IFR | 20 | 2026-05-20 | 2026-06-18 | 117 | PTTME Office 5dx8h
PI-1220 | Pipe Support Standard - AFC | 5 | 2026-07-03 | 2026-07-09 | 117 | PTTME Office 5dx8h
PI-1230 | Piping Stress Critical Line List - IFR | 15 | 2026-04-28 | 2026-05-19 | 112 | PTTME Office 5dx8h
PI-1235 | Piping Stress Critical Line List - IFA | 10 | 2026-06-05 | 2026-06-18 | 112 | PTTME Office 5dx8h
PI-1240 | Piping Stress Critical Line List - AFC | 10 | 2026-07-03 | 2026-07-16 | 112 | PTTME Office 5dx8h
PI-1250 | Piping Specialty Item List - IFR | 15 | 2026-05-27 | 2026-06-18 | 52 | PTTME Office 5dx8h
PI-1255 | Piping Specialty Item List - IFA | 10 | 2026-07-03 | 2026-07-16 | 92 | PTTME Office 5dx8h
PI-1260 | Piping Specialty Item List - AFC | 10 | 2026-08-05 | 2026-08-19 | 92 | PTTME Office 5dx8h
PI-1270 | WPA01 Equipment Layout Drawing (6 Sheets) - IFR | 15 | 2026-04-09 | 2026-05-05 | 47 | PTTME Office 5dx8h
PI-1280 | WPA01 Equipment Layout Drawing (6 Sheets) - IFA | 15 | 2026-06-19 | 2026-07-09 | 47 | PTTME Office 5dx8h
PI-1290 | WPA01 Equipment Layout Drawing (6 Sheets) - AFC | 10 | 2026-08-27 | 2026-09-09 | 47 | PTTME Office 5dx8h
PI-1300 | WPA01 Equipment Layout Elevation Looking (4 Sheets) - IFR | 15 | 2026-04-09 | 2026-05-05 | 47 | PTTME Office 5dx8h
PI-1310 | WPA01 Equipment Layout Elevation Looking (4 Sheets) - IFA | 15 | 2026-06-19 | 2026-07-09 | 47 | PTTME Office 5dx8h
PI-1320 | WPA01 Equipment Layout Elevation Looking (4 Sheets) - AFC | 10 | 2026-08-27 | 2026-09-09 | 47 | PTTME Office 5dx8h
PI-1330 | WPA01 Drilling And Well Service Equipment Layout (5 Sheets) - IFR | 15 | 2026-04-09 | 2026-05-05 | 65 | PTTME Office 5dx8h
PI-1340 | WPA01 Drilling And Well Service Equipment Layout (5 Sheets) - IFA | 15 | 2026-06-19 | 2026-07-09 | 67 | PTTME Office 5dx8h
PI-1350 | WPA01 Drilling And Well Service Equipment Layout (5 Sheets) - AFC | 10 | 2026-08-27 | 2026-09-09 | 47 | PTTME Office 5dx8h
PI-1360 | WPA02 Equipment Layout Drawing (6 Sheets) - IFR | 15 | 2026-04-09 | 2026-05-05 | 32 | PTTME Office 5dx8h
PI-1370 | WPA02 Equipment Layout Drawing (6 Sheets) - IFA | 15 | 2026-06-19 | 2026-07-09 | 42 | PTTME Office 5dx8h
PI-1380 | WPA02 Equipment Layout Drawing (6 Sheets) - AFC | 10 | 2026-08-27 | 2026-09-09 | 47 | PTTME Office 5dx8h
PI-1390 | WPA02 Equipment Layout Elevation Looking (4 Sheets) - IFR | 15 | 2026-04-09 | 2026-05-05 | 32 | PTTME Office 5dx8h
PI-1400 | WPA02 Equipment Layout Elevation Looking (4 Sheets) - IFA | 15 | 2026-06-19 | 2026-07-09 | 42 | PTTME Office 5dx8h
PI-1410 | WPA02 Equipment Layout Elevation Looking (4 Sheets) - AFC | 10 | 2026-08-27 | 2026-09-09 | 47 | PTTME Office 5dx8h
PI-1420 | WPA02 Drilling And Well Service Equipment Layout (5 Sheets) - IFR | 15 | 2026-04-09 | 2026-05-05 | 65 | PTTME Office 5dx8h
PI-1430 | WPA02 Drilling And Well Service Equipment Layout (5 Sheets) - IFA | 15 | 2026-06-19 | 2026-07-09 | 87 | PTTME Office 5dx8h
PI-1440 | WPA02 Drilling And Well Service Equipment Layout (5 Sheets) - AFC | 10 | 2026-08-27 | 2026-09-09 | 67 | PTTME Office 5dx8h
PI-1450 | WPA01 Piping General Arrangement and Support Location Plan (27 Sheets) - IFR | 35 | 2026-08-31 | 2026-10-19 | 25 | PTTME Office 5dx8h
PI-1460 | WPA01 Piping General Arrangement and Support Location Plan (27 Sheets) - AFC | 15 | 2026-11-04 | 2026-11-24 | 25 | PTTME Office 5dx8h
PI-1470 | WPA02 Piping General Arrangement and Support Location Plan (27 Sheets) - IFR | 35 | 2026-08-31 | 2026-10-19 | 25 | PTTME Office 5dx8h
PI-1480 | WPA02 Piping General Arrangement and Support Location Plan (27 Sheets) - AFC | 15 | 2026-11-04 | 2026-11-24 | 25 | PTTME Office 5dx8h
PI-1490 | Piping Wall Thickness Calculation - IFR | 15 | 2026-05-06 | 2026-05-26 | 117 | PTTME Office 5dx8h
PI-1500 | Piping Wall Thickness Calculation - AFC | 10 | 2026-06-26 | 2026-07-09 | 117 | PTTME Office 5dx8h
PI-1510 | Small Bore Connection Assessment - IFR | 15 | 2026-10-27 | 2026-11-16 | 11 | PTTME Office 5dx8h
PI-1520 | Small Bore Connection Assessment - AFC | 10 | 2026-12-01 | 2026-12-16 | 11 | PTTME Office 5dx8h
PI-1530 | WPA01 Piping Stress Analysis Report (Flowline) - IFR | 20 | 2026-08-24 | 2026-09-18 | 50 | PTTME Office 5dx8h
PI-1540 | WPA01 Piping Stress Analysis Report (Flowline) - AFC | 10 | 2026-10-05 | 2026-10-19 | 50 | PTTME Office 5dx8h
PI-1550 | WPA01 Piping Stress Analysis Report (PIG Launcher/Receiver) - IFR | 20 | 2026-08-24 | 2026-09-18 | 50 | PTTME Office 5dx8h
PI-1560 | WPA01 Piping Stress Analysis Report (PIG Launcher/Receiver) - AFC | 10 | 2026-10-05 | 2026-10-19 | 50 | PTTME Office 5dx8h
PI-1570 | WPA01 Piping Stress Analysis Report (Other GC lines, IG lines, and HP vent) - IFR | 20 | 2026-08-24 | 2026-09-18 | 50 | PTTME Office 5dx8h
PI-1580 | WPA01 Piping Stress Analysis Report (Other GC lines, IG lines, and HP vent) - AFC | 10 | 2026-10-05 | 2026-10-19 | 50 | PTTME Office 5dx8h
PI-1590 | WPA01 Piping Stress Analysis Report (LP vent and DP lines level 2) - IFR | 20 | 2026-08-24 | 2026-09-18 | 50 | PTTME Office 5dx8h
PI-1600 | WPA01 Piping Stress Analysis Report (LP vent and DP lines level 2) - AFC | 10 | 2026-10-05 | 2026-10-19 | 50 | PTTME Office 5dx8h
PI-1610 | WPA01 Piping Stress Analysis Report (Future Booster Compressor Package) - IFR | 20 | 2026-08-24 | 2026-09-18 | 50 | PTTME Office 5dx8h
PI-1620 | WPA01 Piping Stress Analysis Report (Future Booster Compressor Package) - AFC | 10 | 2026-10-05 | 2026-10-19 | 50 | PTTME Office 5dx8h
PI-1630 | WPA02 Piping Stress Analysis Report (Flowline) - IFR | 20 | 2026-08-31 | 2026-09-25 | 45 | PTTME Office 5dx8h
PI-1640 | WPA02 Piping Stress Analysis Report (Flowline) - AFC | 10 | 2026-10-12 | 2026-10-27 | 45 | PTTME Office 5dx8h
PI-1650 | WPA02 Piping Stress Analysis Report (PIG Launcher/Receiver) - IFR | 20 | 2026-08-31 | 2026-09-25 | 45 | PTTME Office 5dx8h
PI-1660 | WPA02 Piping Stress Analysis Report (PIG Launcher/Receiver) - AFC | 10 | 2026-10-12 | 2026-10-27 | 45 | PTTME Office 5dx8h
PI-1670 | WPA02 Piping Stress Analysis Report (Other GC lines, IG lines, and HP vent) - IFR | 20 | 2026-08-31 | 2026-09-25 | 45 | PTTME Office 5dx8h
PI-1680 | WPA02 Piping Stress Analysis Report (Other GC lines, IG lines, and HP vent) - AFC | 10 | 2026-10-12 | 2026-10-27 | 45 | PTTME Office 5dx8h
PI-1690 | WPA02 Piping Stress Analysis Report (LP vent and DP lines level 2) - IFR | 20 | 2026-08-31 | 2026-09-25 | 45 | PTTME Office 5dx8h
PI-1700 | WPA02 Piping Stress Analysis Report (LP vent and DP lines level 2) - AFC | 10 | 2026-10-12 | 2026-10-27 | 45 | PTTME Office 5dx8h
PI-1710 | WPA02 Piping Stress Analysis Report required for any other lines as specific in the Piping StressCritical LL - IFR | 20 | 2026-08-31 | 2026-09-25 | 45 | PTTME Office 5dx8h
PI-1720 | WPA02 Piping Stress Analysis Report required for any other lines as specific in the Piping Stress Critical LL - AFC | 10 | 2026-10-12 | 2026-10-27 | 45 | PTTME Office 5dx8h
PI-1730 | Material Take-Off for Manual Valves WP01 - IFR | 10 | 2026-05-06 | 2026-05-19 | 65 | PTTME Office 5dx8h
PI-1740 | Material Take-Off for Manual Valves WP01 - IFA | 10 | 2026-06-05 | 2026-06-18 | 107 | PTTME Office 5dx8h
PI-1750 | Material Take-Off for Manual Valves WP01 - AFC | 5 | 2026-07-03 | 2026-07-09 | 107 | PTTME Office 5dx8h
PI-1760 | Material Take-Off for Piping Bulk WP01 - IFR | 20 | 2026-07-21 | 2026-08-21 | 55 | PTTME Office 5dx8h
PI-1770 | Material Take-Off for Piping Bulk WP01 - IFA | 10 | 2026-09-21 | 2026-10-02 | 45 | PTTME Office 5dx8h
PI-1780 | Material Take-Off for Piping Bulk WP01 - AFC | 5 | 2026-11-17 | 2026-11-23 | 26 | PTTME Office 5dx8h
PI-1790 | Material Take-Off for Manual Valves WP02 - IFR | 15 | 2026-05-06 | 2026-05-26 | 69 | PTTME Office 5dx8h
PI-1800 | Material Take-Off for Manual Valves WP02 - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
PI-1810 | Material Take-Off for Manual Valves WP02 - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
PI-1820 | Material Take-Off for Piping Bulk WP02 - IFR | 20 | 2026-07-21 | 2026-08-21 | 55 | PTTME Office 5dx8h
PI-1830 | Material Take-Off for Piping Bulk WP02 - IFA | 10 | 2026-09-21 | 2026-10-02 | 45 | PTTME Office 5dx8h
PI-1840 | Material Take-Off for Piping Bulk WP02 - AFC | 5 | 2026-11-17 | 2026-11-23 | 26 | PTTME Office 5dx8h
PI-3010 | WPA01 Piping Isometric Drawings - IFR | 20 | 2026-08-24 | 2026-09-18 | 40 | PTTME Office 5dx8h
PI-3020 | WPA01 Piping Isometric Drawings - AFC | 10 | 2026-10-27 | 2026-11-09 | 26 | PTTME Office 5dx8h
PI-3030 | WPA01 Piping Support List - IFR | 10 | 2026-09-21 | 2026-10-02 | 40 | PTTME Office 5dx8h
PI-3040 | WPA01 Piping Support List - AFC | 10 | 2026-11-10 | 2026-11-23 | 26 | PTTME Office 5dx8h
PI-3050 | WPA01 Piping Shiploose List - IFR | 10 | 2026-09-21 | 2026-10-02 | 40 | PTTME Office 5dx8h
PI-3060 | WPA01 Piping Shiploose List - AFC | 10 | 2026-11-10 | 2026-11-23 | 26 | PTTME Office 5dx8h
PI-3070 | WPA01 Piping Support Arrangement Drawings - IFR | 10 | 2026-09-21 | 2026-10-02 | 40 | PTTME Office 5dx8h
PI-3080 | WPA01 Piping Support Arrangement Drawings - AFC | 10 | 2026-11-10 | 2026-11-23 | 26 | PTTME Office 5dx8h
PI-3090 | WPA01 Special Pipe Support Drawings - IFR | 10 | 2026-09-21 | 2026-10-02 | 40 | PTTME Office 5dx8h
PI-3100 | WPA01 Special Pipe Support Drawings - AFC | 10 | 2026-11-10 | 2026-11-23 | 26 | PTTME Office 5dx8h
PI-4000 | WPA02 Piping Isometric Drawings - IFR | 15 | 2026-08-31 | 2026-09-18 | 50 | PTTME Office 5dx8h
PI-4001 | WPA02 Piping Isometric Drawings - AFC | 10 | 2026-10-27 | 2026-11-09 | 36 | PTTME Office 5dx8h
PI-4002 | WPA02 Piping Support List - IFR | 10 | 2026-09-21 | 2026-10-02 | 40 | PTTME Office 5dx8h
PI-4003 | WPA02 Piping Support List - AFC | 10 | 2026-11-10 | 2026-11-23 | 26 | PTTME Office 5dx8h
PI-4004 | WPA02 Piping Shiploose List - IFR | 10 | 2026-09-21 | 2026-10-02 | 40 | PTTME Office 5dx8h
PI-4005 | WPA02 Piping Shiploose List - AFC | 10 | 2026-11-10 | 2026-11-23 | 26 | PTTME Office 5dx8h
PI-4006 | WPA02 Piping Support Arrangement Drawings - IFR | 10 | 2026-09-21 | 2026-10-02 | 40 | PTTME Office 5dx8h
PI-4007 | WPA02 Piping Support Arrangement Drawings - AFC | 10 | 2026-11-10 | 2026-11-23 | 26 | PTTME Office 5dx8h
PI-4008 | WPA02 Special Pipe Support Drawings - IFR | 10 | 2026-09-21 | 2026-10-02 | 40 | PTTME Office 5dx8h
PI-4009 | WPA02 Special Pipe Support Drawings - AFC | 10 | 2026-11-10 | 2026-11-23 | 26 | PTTME Office 5dx8h
Datasheets-Piping |  | 70 | 2026-05-13 | 2026-08-26 | 91 | PTTME Office 5dx8h
PI-1850 | Datasheet for Manual Valves - IFR | 10 | 2026-05-13 | 2026-05-26 | 65 | PTTME Office 5dx8h
PI-1860 | Datasheet for Manual Valves - IFA | 5 | 2026-06-19 | 2026-06-25 | 107 | PTTME Office 5dx8h
PI-1870 | Datasheet for Manual Valves - AFC | 5 | 2026-07-10 | 2026-07-16 | 107 | PTTME Office 5dx8h
PI-1880 | Datasheet for Corrosion Fittings (Probe, Coupon and Chemical Injection Quill) - IFR | 20 | 2026-05-27 | 2026-06-25 | 52 | PTTME Office 5dx8h
PI-1890 | Datasheet for Corrosion Fittings (Probe, Coupon and Chemical Injection Quill) - IFA | 10 | 2026-07-10 | 2026-07-23 | 82 | PTTME Office 5dx8h
PI-1900 | Datasheet for Corrosion Fittings (Probe, Coupon and Chemical Injection Quill) - AFC | 10 | 2026-08-13 | 2026-08-26 | 82 | PTTME Office 5dx8h
PI-1910 | Datasheet for Hose and Hose Connector - IFR | 20 | 2026-05-27 | 2026-06-25 | 52 | PTTME Office 5dx8h
PI-1920 | Datasheet for Hose and Hose Connector - IFA | 10 | 2026-07-10 | 2026-07-23 | 82 | PTTME Office 5dx8h
PI-1930 | Datasheet for Hose and Hose Connector - AFC | 10 | 2026-08-13 | 2026-08-26 | 82 | PTTME Office 5dx8h
PI-1940 | Datasheet for Strainer - IFR | 20 | 2026-05-27 | 2026-06-25 | 52 | PTTME Office 5dx8h
PI-1950 | Datasheet for Strainer - IFA | 10 | 2026-07-10 | 2026-07-23 | 82 | PTTME Office 5dx8h
PI-1960 | Datasheet for Strainer - AFC | 10 | 2026-08-13 | 2026-08-26 | 82 | PTTME Office 5dx8h
PI-1970 | Datasheet for Liquid Trap - IFR | 20 | 2026-05-27 | 2026-06-25 | 52 | PTTME Office 5dx8h
PI-1980 | Datasheet for Liquid Trap - IFA | 10 | 2026-07-10 | 2026-07-23 | 82 | PTTME Office 5dx8h
PI-1990 | Datasheet for Liquid Trap - AFC | 10 | 2026-08-13 | 2026-08-26 | 82 | PTTME Office 5dx8h
PI-2000 | Datasheet for G-Clamp - IFR | 20 | 2026-05-27 | 2026-06-25 | 52 | PTTME Office 5dx8h
PI-2010 | Datasheet for G-Clamp - IFA | 10 | 2026-07-10 | 2026-07-23 | 82 | PTTME Office 5dx8h
PI-2020 | Datasheet for G-Clamp - AFC | 10 | 2026-08-13 | 2026-08-26 | 82 | PTTME Office 5dx8h
PI-2030 | Datasheet for Flame Arrestor - IFR | 20 | 2026-05-27 | 2026-06-25 | 52 | PTTME Office 5dx8h
PI-2040 | Datasheet for Flame Arrestor - IFA | 10 | 2026-07-10 | 2026-07-23 | 82 | PTTME Office 5dx8h
PI-2050 | Datasheet for Flame Arrestor - AFC | 10 | 2026-08-13 | 2026-08-26 | 82 | PTTME Office 5dx8h
PI-2060 | Datasheet for Sight Glass - IFR | 20 | 2026-05-27 | 2026-06-25 | 52 | PTTME Office 5dx8h
PI-2070 | Datasheet for Sight Glass - IFA | 10 | 2026-07-10 | 2026-07-23 | 82 | PTTME Office 5dx8h
PI-2080 | Datasheet for Sight Glass - AFC | 10 | 2026-08-13 | 2026-08-26 | 82 | PTTME Office 5dx8h
PI-4019 | Datasheet for Quick Opening Closure - IFR | 20 | 2026-05-27 | 2026-06-25 | 61 | PTTME Office 5dx8h
PI-4029 | Datasheet for Quick Opening Closure - IFA | 10 | 2026-07-10 | 2026-07-23 | 91 | PTTME Office 5dx8h
PI-4039 | Datasheet for Quick Opening Closure - AFC | 10 | 2026-08-13 | 2026-08-26 | 91 | PTTME Office 5dx8h
MR-Piping |  | 109 | 2026-05-07 | 2026-10-15 | 61 | PTTME Office 5dx8h
PI-2090 | Material Requisition for Ball valve (Flange end) - IFR | 15 | 2026-05-20 | 2026-06-11 | 71 | PTTME Office 5dx8h
PI-2100 | Material Requisition for Ball valve (Flange end) - AFC | 5 | 2026-09-11 | 2026-09-17 | 71 | PTTME Office 5dx8h
PI-2110 | Material Requisition for Ball valve (Welded end) - IFR | 15 | 2026-05-20 | 2026-06-11 | 71 | PTTME Office 5dx8h
PI-2120 | Material Requisition for Ball valve (Welded end) - AFC | 5 | 2026-09-11 | 2026-09-17 | 71 | PTTME Office 5dx8h
PI-2130 | Material Requisition for Globe valve (Flange end) - IFR | 15 | 2026-06-04 | 2026-06-24 | 65 | PTTME Office 5dx8h
PI-2140 | Material Requisition for Globe valve (Flange end) - AFC | 5 | 2026-09-21 | 2026-09-25 | 65 | PTTME Office 5dx8h
PI-2150 | Material Requisition for Globe valve (Welded end) - IFR | 15 | 2026-06-04 | 2026-06-24 | 65 | PTTME Office 5dx8h
PI-2160 | Material Requisition for Globe valve (Welded end) - AFC | 5 | 2026-09-21 | 2026-09-25 | 65 | PTTME Office 5dx8h
PI-2170 | Material Requisition for Check valve (Flange end) - IFR | 15 | 2026-06-04 | 2026-06-24 | 65 | PTTME Office 5dx8h
PI-2180 | Material Requisition for Check valve (Flange end) - AFC | 5 | 2026-09-21 | 2026-09-25 | 65 | PTTME Office 5dx8h
PI-2190 | Material Requisition for Check valve (Welded end) - IFR | 15 | 2026-06-04 | 2026-06-24 | 65 | PTTME Office 5dx8h
PI-2200 | Material Requisition for Check valve (Welded end) - AFC | 5 | 2026-09-21 | 2026-09-25 | 65 | PTTME Office 5dx8h
PI-2210 | Material Requisition for Compact Check valve (Welded end) - IFR | 15 | 2026-05-07 | 2026-05-27 | 81 | PTTME Office 5dx8h
PI-2220 | Material Requisition for Compact Check valve (Welded end) - AFC | 5 | 2026-08-28 | 2026-09-03 | 81 | PTTME Office 5dx8h
PI-2230 | Material Requisition for Carbon steel pipe - IFR | 15 | 2026-06-05 | 2026-06-25 | 78 | PTTME Office 5dx8h
PI-2240 | Material Requisition for Carbon steel pipe - AFC | 5 | 2026-09-02 | 2026-09-08 | 78 | PTTME Office 5dx8h
PI-2250 | Material Requisition for Carbon steel fitting - IFR | 15 | 2026-06-05 | 2026-06-25 | 78 | PTTME Office 5dx8h
PI-2260 | Material Requisition for Carbon steel fitting - AFC | 5 | 2026-09-02 | 2026-09-08 | 78 | PTTME Office 5dx8h
PI-2270 | Material Requisition for Carbon steel flange - IFR | 15 | 2026-06-05 | 2026-06-25 | 78 | PTTME Office 5dx8h
PI-2280 | Material Requisition for Carbon steel flange - AFC | 5 | 2026-09-02 | 2026-09-08 | 78 | PTTME Office 5dx8h
PI-2290 | Material Requisition for SS and DSS Pipe - IFR | 15 | 2026-06-05 | 2026-06-25 | 78 | PTTME Office 5dx8h
PI-2300 | Material Requisition for SS and DSS Pipe - AFC | 5 | 2026-09-02 | 2026-09-08 | 78 | PTTME Office 5dx8h
PI-2310 | Material Requisition for SS and DSS fitting - IFR | 15 | 2026-06-05 | 2026-06-25 | 78 | PTTME Office 5dx8h
PI-2320 | Material Requisition for SS and DSS fitting - AFC | 5 | 2026-09-02 | 2026-09-08 | 78 | PTTME Office 5dx8h
PI-2330 | Material Requisition for SS and DSS flange - IFR | 15 | 2026-06-05 | 2026-06-25 | 78 | PTTME Office 5dx8h
PI-2340 | Material Requisition for SS and DSS flange - AFC | 5 | 2026-09-02 | 2026-09-08 | 78 | PTTME Office 5dx8h
PI-2350 | Material Requisition for stud bolts and nuts - IFR | 15 | 2026-06-05 | 2026-06-25 | 78 | PTTME Office 5dx8h
PI-2360 | Material Requisition for stud bolts and nuts - AFC | 5 | 2026-09-02 | 2026-09-08 | 78 | PTTME Office 5dx8h
PI-2370 | Material Requisition for gaskets - IFR | 15 | 2026-06-05 | 2026-06-25 | 80 | PTTME Office 5dx8h
PI-2380 | Material Requisition for gaskets - AFC | 5 | 2026-09-02 | 2026-09-08 | 78 | PTTME Office 5dx8h
PI-2390 | Material Requisition for pipe support - IFR | 15 | 2026-06-26 | 2026-07-16 | 52 | PTTME Office 5dx8h
PI-2400 | Material Requisition for pipe support - AFC | 5 | 2026-10-08 | 2026-10-15 | 52 | PTTME Office 5dx8h
PI-2410 | Material Requisition for Corrosion Fittings (Probe, Coupon and Chemical Injection Quill) - IFR | 15 | 2026-06-26 | 2026-07-16 | 52 | PTTME Office 5dx8h
PI-2420 | Material Requisition for Corrosion Fittings (Probe, Coupon and Chemical Injection Quill) - AFC | 5 | 2026-10-08 | 2026-10-15 | 52 | PTTME Office 5dx8h
PI-2430 | Material Requisition for Hose and Hose Connector - IFR | 15 | 2026-06-26 | 2026-07-16 | 52 | PTTME Office 5dx8h
PI-2440 | Material Requisition for Hose and Hose Connector - AFC | 5 | 2026-10-08 | 2026-10-15 | 52 | PTTME Office 5dx8h
PI-2450 | Material Requisition for Strainer - IFR | 15 | 2026-06-26 | 2026-07-16 | 52 | PTTME Office 5dx8h
PI-2460 | Material Requisition for Strainer - AFC | 5 | 2026-10-08 | 2026-10-15 | 52 | PTTME Office 5dx8h
PI-2470 | Material Requisition for Liquid Trap - IFR | 15 | 2026-06-26 | 2026-07-16 | 52 | PTTME Office 5dx8h
PI-2480 | Material Requisition for Liquid Trap - AFC | 5 | 2026-10-08 | 2026-10-15 | 52 | PTTME Office 5dx8h
PI-2490 | Material Requisition for G-Clamp - IFR | 15 | 2026-06-26 | 2026-07-16 | 52 | PTTME Office 5dx8h
PI-2500 | Material Requisition for G-Clamp - AFC | 5 | 2026-10-08 | 2026-10-15 | 52 | PTTME Office 5dx8h
PI-2510 | Material Requisition for Flame Arrestor - IFR | 15 | 2026-06-26 | 2026-07-16 | 52 | PTTME Office 5dx8h
PI-2520 | Material Requisition for Flame Arrestor - AFC | 5 | 2026-10-08 | 2026-10-15 | 52 | PTTME Office 5dx8h
PI-2530 | Material Requisition for Sight Glass - IFR | 15 | 2026-06-26 | 2026-07-16 | 52 | PTTME Office 5dx8h
PI-2540 | Material Requisition for Sight Glass - AFC | 5 | 2026-10-08 | 2026-10-15 | 52 | PTTME Office 5dx8h
PI-4049 | Material Requisition for Quick Opening Closure - IFR | 15 | 2026-06-26 | 2026-07-16 | 61 | PTTME Office 5dx8h
PI-4059 | Material Requisition for Quick Opening Closure - AFC | 5 | 2026-10-08 | 2026-10-15 | 61 | PTTME Office 5dx8h
TBE-Piping |  | 64 | 2026-06-22 | 2026-09-23 | 61 | PTTME Office 5dx8h
PI-2550 | Technical Bid Evaluation for Ball valve (Flange end) - IFR | 11 | 2026-07-17 | 2026-08-05 | 71 | PTTME Office 5dx8h
PI-2560 | Technical Bid Evaluation for Ball valve (Flange end) - AFC | 5 | 2026-08-21 | 2026-08-27 | 71 | PTTME Office 5dx8h
PI-2570 | Technical Bid Evaluation for Ball valve (Welded end) - IFR | 11 | 2026-07-17 | 2026-08-05 | 71 | PTTME Office 5dx8h
PI-2580 | Technical Bid Evaluation for Ball valve (Welded end) - AFC | 5 | 2026-08-21 | 2026-08-27 | 71 | PTTME Office 5dx8h
PI-2590 | Technical Bid Evaluation for Globe valve (Flange end) - IFR | 16 | 2026-07-20 | 2026-08-14 | 65 | PTTME Office 5dx8h
PI-2600 | Technical Bid Evaluation for Globe valve (Flange end) - AFC | 5 | 2026-08-31 | 2026-09-04 | 65 | PTTME Office 5dx8h
PI-2610 | Technical Bid Evaluation for Globe valve (Welded end) - IFR | 16 | 2026-07-20 | 2026-08-14 | 65 | PTTME Office 5dx8h
PI-2620 | Technical Bid Evaluation for Globe valve (Welded end) - AFC | 5 | 2026-08-31 | 2026-09-04 | 65 | PTTME Office 5dx8h
PI-2630 | Technical Bid Evaluation for Check valve (Flange end) - IFR | 16 | 2026-07-20 | 2026-08-14 | 65 | PTTME Office 5dx8h
PI-2640 | Technical Bid Evaluation for Check valve (Flange end) - AFC | 5 | 2026-08-31 | 2026-09-04 | 65 | PTTME Office 5dx8h
PI-2650 | Technical Bid Evaluation for Check valve (Welded end) - IFR | 16 | 2026-07-20 | 2026-08-14 | 65 | PTTME Office 5dx8h
PI-2660 | Technical Bid Evaluation for Check valve (Welded end) - AFC | 5 | 2026-08-31 | 2026-09-04 | 65 | PTTME Office 5dx8h
PI-2670 | Technical Bid Evaluation for Compact Check valve (Welded end) - IFR | 20 | 2026-06-22 | 2026-07-17 | 81 | PTTME Office 5dx8h
PI-2680 | Technical Bid Evaluation for Compact Check valve (Welded end) - AFC | 5 | 2026-08-06 | 2026-08-13 | 81 | PTTME Office 5dx8h
PI-2690 | Technical Bid Evaluation for Carbon steel pipe - IFR | 8 | 2026-07-13 | 2026-07-22 | 78 | PTTME Office 5dx8h
PI-2700 | Technical Bid Evaluation for Carbon steel pipe - AFC | 5 | 2026-08-11 | 2026-08-18 | 78 | PTTME Office 5dx8h
PI-2710 | Technical Bid Evaluation for Carbon steel fitting - IFR | 8 | 2026-07-13 | 2026-07-22 | 78 | PTTME Office 5dx8h
PI-2720 | Technical Bid Evaluation for Carbon steel fitting - AFC | 5 | 2026-08-11 | 2026-08-18 | 78 | PTTME Office 5dx8h
PI-2730 | Technical Bid Evaluation for Carbon steel flange - IFR | 8 | 2026-07-13 | 2026-07-22 | 78 | PTTME Office 5dx8h
PI-2740 | Technical Bid Evaluation for Carbon steel flange - AFC | 5 | 2026-08-11 | 2026-08-18 | 78 | PTTME Office 5dx8h
PI-2750 | Technical Bid Evaluation for SS and DSS Pipe - IFR | 8 | 2026-07-13 | 2026-07-22 | 78 | PTTME Office 5dx8h
PI-2760 | Technical Bid Evaluation for SS and DSS Pipe - AFC | 5 | 2026-08-11 | 2026-08-18 | 78 | PTTME Office 5dx8h
PI-2770 | Technical Bid Evaluation for SS and DSS fitting - IFR | 8 | 2026-07-13 | 2026-07-22 | 78 | PTTME Office 5dx8h
PI-2780 | Technical Bid Evaluation for SS and DSS fitting - AFC | 5 | 2026-08-11 | 2026-08-18 | 78 | PTTME Office 5dx8h
PI-2790 | Technical Bid Evaluation for SS and DSS flange - IFR | 8 | 2026-07-13 | 2026-07-22 | 78 | PTTME Office 5dx8h
PI-2800 | Technical Bid Evaluation for SS and DSS flange - AFC | 5 | 2026-08-11 | 2026-08-18 | 78 | PTTME Office 5dx8h
PI-2810 | Technical Bid Evaluation for stud bolts and nuts - IFR | 8 | 2026-07-13 | 2026-07-22 | 78 | PTTME Office 5dx8h
PI-2820 | Technical Bid Evaluation for stud bolts and nuts - AFC | 5 | 2026-08-11 | 2026-08-18 | 78 | PTTME Office 5dx8h
PI-2830 | Technical Bid Evaluation for gaskets - IFR | 8 | 2026-07-13 | 2026-07-22 | 80 | PTTME Office 5dx8h
PI-2840 | Technical Bid Evaluation for gaskets - AFC | 3 | 2026-08-11 | 2026-08-14 | 80 | PTTME Office 5dx8h
PI-2850 | Technical Bid Evaluation for pipe support - IFR | 15 | 2026-08-13 | 2026-09-02 | 52 | PTTME Office 5dx8h
PI-2860 | Technical Bid Evaluation for pipe support - AFC | 5 | 2026-09-17 | 2026-09-23 | 52 | PTTME Office 5dx8h
PI-2870 | Technical Bid Evaluation for Corrosion Fittings (Probe, Coupon and Chemical Injection Quill) - IFR | 15 | 2026-08-13 | 2026-09-02 | 52 | PTTME Office 5dx8h
PI-2880 | Technical Bid Evaluation for Corrosion Fittings (Probe, Coupon and Chemical Injection Quill) - AFC | 5 | 2026-09-17 | 2026-09-23 | 52 | PTTME Office 5dx8h
PI-2890 | Technical Bid Evaluation for Hose and Hose Connector - IFR | 15 | 2026-08-13 | 2026-09-02 | 52 | PTTME Office 5dx8h
PI-2900 | Technical Bid Evaluation for Hose and Hose Connector - AFC | 5 | 2026-09-17 | 2026-09-23 | 52 | PTTME Office 5dx8h
PI-2910 | Technical Bid Evaluation for Strainer - IFR | 15 | 2026-08-13 | 2026-09-02 | 52 | PTTME Office 5dx8h
PI-2920 | Technical Bid Evaluation for Strainer - AFC | 5 | 2026-09-17 | 2026-09-23 | 52 | PTTME Office 5dx8h
PI-2930 | Technical Bid Evaluation for Liquid Trap - IFR | 15 | 2026-08-13 | 2026-09-02 | 52 | PTTME Office 5dx8h
PI-2940 | Technical Bid Evaluation for Liquid Trap - AFC | 5 | 2026-09-17 | 2026-09-23 | 52 | PTTME Office 5dx8h
PI-2950 | Technical Bid Evaluation for G-Clamp - IFR | 15 | 2026-08-13 | 2026-09-02 | 52 | PTTME Office 5dx8h
PI-2960 | Technical Bid Evaluation for G-Clamp - AFC | 5 | 2026-09-17 | 2026-09-23 | 52 | PTTME Office 5dx8h
PI-2970 | Technical Bid Evaluation for Flame Arrestor - IFR | 15 | 2026-08-13 | 2026-09-02 | 52 | PTTME Office 5dx8h
PI-2980 | Technical Bid Evaluation for Flame Arrestor - AFC | 5 | 2026-09-17 | 2026-09-23 | 52 | PTTME Office 5dx8h
PI-2990 | Technical Bid Evaluation for Sight Glass - IFR | 15 | 2026-08-13 | 2026-09-02 | 52 | PTTME Office 5dx8h
PI-3000 | Technical Bid Evaluation for Sight Glass - AFC | 5 | 2026-09-17 | 2026-09-23 | 52 | PTTME Office 5dx8h
PI-4069 | Technical Bid Evaluation for Quick Opening Closure - IFR | 15 | 2026-08-13 | 2026-09-02 | 61 | PTTME Office 5dx8h
PI-4079 | Technical Bid Evaluation for Quick Opening Closure - AFC | 5 | 2026-09-17 | 2026-09-23 | 61 | PTTME Office 5dx8h
STRUCTUREENGINEERING-TOPSIDE |  | 175 | 2026-03-04 | 2026-11-20 | 36 | PTTME Office 5dx8h
ST-1000 | WPA01 Topside Drawing Index (2 Sheets) - IFR | 10 | 2026-07-17 | 2026-08-04 | 76 | PTTME Office 5dx8h
ST-1010 | WPA01 Topside Drawing Index (2 Sheets) - IFA | 10 | 2026-08-20 | 2026-09-02 | 76 | PTTME Office 5dx8h
ST-1020 | WPA01 Topside Drawing Index (2 Sheets) - AFC | 5 | 2026-09-17 | 2026-09-23 | 76 | PTTME Office 5dx8h
ST-1030 | WPA01 Topside Deck Loading Diagrams - IFR | 10 | 2026-05-14 | 2026-05-27 | 46 | PTTME Office 5dx8h
ST-1040 | WPA01 Topside Deck Loading Diagrams - IFA | 10 | 2026-06-15 | 2026-06-26 | 71 | PTTME Office 5dx8h
ST-1050 | WPA01 Topside Deck Loading Diagrams - AFC | 5 | 2026-07-13 | 2026-07-17 | 81 | PTTME Office 5dx8h
ST-1060 | WPA01 Topside - Upper Deck Primary Steel Framing Plan - IFR | 10 | 2026-05-13 | 2026-05-26 | 0 | PTTME Office 5dx8h
ST-1070 | WPA01 Topside - Upper Deck Primary Steel Framing Plan - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-1080 | WPA01 Topside - Upper Deck Primary Steel Framing Plan - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-1090 | WPA02 Topside - Lower Deck Primary Steel Framing Plan - IFR | 10 | 2026-05-13 | 2026-05-26 | 0 | PTTME Office 5dx8h
ST-1100 | WPA02 Topside - Lower Deck Primary Steel Framing Plan - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-1110 | WPA02 Topside - Lower Deck Primary Steel Framing Plan - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-1120 | WPA01 Topside - Elevation Truss Row A, B, 1, 2 - IFR | 10 | 2026-05-13 | 2026-05-26 | 0 | PTTME Office 5dx8h
ST-1130 | WPA01 Topside - Elevation Truss Row A, B, 1, 2 - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-1140 | WPA01 Topside - Elevation Truss Row A, B, 1, 2 - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-1150 | WPA01 Topside - Sections (2 Sheets) - IFR | 10 | 2026-05-13 | 2026-05-26 | 0 | PTTME Office 5dx8h
ST-1160 | WPA01 Topside - Sections (2 Sheets) - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-1170 | WPA01 Topside - Sections (2 Sheets) - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-1180 | WPA01 Topside Joint Connection Details (14 Sheets) - IFR | 10 | 2026-05-13 | 2026-05-26 | 0 | PTTME Office 5dx8h
ST-1190 | WPA01 Topside Joint Connection Details (14 Sheets) - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-1200 | WPA01 Topside Joint Connection Details (14 Sheets) - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-1210 | WPA01 Topside Upper Deck Secondary Steel Framing Plan - IFR | 25 | 2026-05-27 | 2026-07-02 | 27 | PTTME Office 5dx8h
ST-1220 | WPA01 Topside Upper Deck Secondary Steel Framing Plan - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-1230 | WPA01 Topside Upper Deck Secondary Steel Framing Plan - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-1240 | WPA01 Topside Lower Deck Secondary Steel Framing Plan - IFR | 25 | 2026-05-27 | 2026-07-02 | 47 | PTTME Office 5dx8h
ST-1250 | WPA01 Topside Lower Deck Secondary Steel Framing Plan - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-1260 | WPA01 Topside Lower Deck Secondary Steel Framing Plan - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-1270 | WPA01 Topside Mezzanine Deck Framing Plan - IFR | 25 | 2026-05-27 | 2026-07-02 | 42 | PTTME Office 5dx8h
ST-1280 | WPA01 Topside Mezzanine Deck Framing Plan - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-1290 | WPA01 Topside Mezzanine Deck Framing Plan - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-1300 | WPA01 Topside Mezzanine Deck Section & Details (3 Sheets) - IFR | 25 | 2026-06-05 | 2026-07-09 | 42 | PTTME Office 5dx8h
ST-1310 | WPA01 Topside Mezzanine Deck Section & Details (3 Sheets) - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-1320 | WPA01 Topside Mezzanine Deck Section & Details (3 Sheets) - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-1330 | WPA01 Topside Sump Deck Framing Plan - IFR | 25 | 2026-05-27 | 2026-07-02 | 42 | PTTME Office 5dx8h
ST-1340 | WPA01 Topside Sump Deck Framing Plan - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-1350 | WPA01 Topside Sump Deck Framing Plan - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-1360 | WPA01 Topside Sump Deck Section & Details (3 Sheets) - IFR | 25 | 2026-06-05 | 2026-07-09 | 42 | PTTME Office 5dx8h
ST-1370 | WPA01 Topside Sump Deck Section & Details (3 Sheets) - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-1380 | WPA01 Topside Sump Deck Section & Details (3 Sheets) - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-1390 | WPA01 Topside Standard Joint Details for Secondary Beam - IFR | 25 | 2026-06-05 | 2026-07-09 | 42 | PTTME Office 5dx8h
ST-1400 | WPA01 Topside Standard Joint Details for Secondary Beam - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-1410 | WPA01 Topside Standard Joint Details for Secondary Beam - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-1420 | WPA01 Topside Vent Boom Plan and Elevation - IFR | 25 | 2026-05-27 | 2026-07-02 | 27 | PTTME Office 5dx8h
ST-1430 | WPA01 Topside Vent Boom Plan and Elevation - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-1440 | WPA01 Topside Vent Boom Plan and Elevation - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-1450 | WPA01 Topside Vent Boom Sections - IFR | 25 | 2026-06-05 | 2026-07-09 | 27 | PTTME Office 5dx8h
ST-1460 | WPA01 Topside Vent Boom Sections - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-1470 | WPA01 Topside Vent Boom Sections - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-1480 | WPA01 Topside Vent Boom Walkway Plan and Sections - IFR | 25 | 2026-06-05 | 2026-07-09 | 27 | PTTME Office 5dx8h
ST-1490 | WPA01 Topside Vent Boom Walkway Plan and Sections - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-1500 | WPA01 Topside Vent Boom Walkway Plan and Sections - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-1510 | WPA01 Topside Vent Boom Walkway Sections and Details (3 Sheets) - IFR | 25 | 2026-06-12 | 2026-07-16 | 37 | PTTME Office 5dx8h
ST-1520 | WPA01 Topside Vent Boom Walkway Sections and Details (3 Sheets) - IFA | 15 | 2026-08-05 | 2026-08-26 | 62 | PTTME Office 5dx8h
ST-1530 | WPA01 Topside Vent Boom Walkway Sections and Details (3 Sheets) - AFC | 15 | 2026-09-10 | 2026-09-30 | 62 | PTTME Office 5dx8h
ST-1540 | WPA01 Topside Solar Panel Arrangement & Support Details (7 Sheets) - IFR | 25 | 2026-06-12 | 2026-07-16 | 37 | PTTME Office 5dx8h
ST-1550 | WPA01 Topside Solar Panel Arrangement & Support Details (7 Sheets) - IFA | 15 | 2026-08-05 | 2026-08-26 | 62 | PTTME Office 5dx8h
ST-1560 | WPA01 Topside Solar Panel Arrangement & Support Details (7 Sheets) - AFC | 15 | 2026-09-10 | 2026-09-30 | 62 | PTTME Office 5dx8h
ST-1570 | WPA01 Topside Upper Deck Flooring & Handrail Layout - IFR | 25 | 2026-06-05 | 2026-07-09 | 27 | PTTME Office 5dx8h
ST-1580 | WPA01 Topside Upper Deck Flooring & Handrail Layout - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-1590 | WPA01 Topside Upper Deck Flooring & Handrail Layout - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-1600 | WPA01 Topside Lower Deck Flooring & Handrail Layout - IFR | 25 | 2026-06-05 | 2026-07-09 | 42 | PTTME Office 5dx8h
ST-1610 | WPA01 Topside Lower Deck Flooring & Handrail Layout - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-1620 | WPA01 Topside Lower Deck Flooring & Handrail Layout - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-1630 | WPA01 Topside Mezzanine Deck Flooring & Handrail Layout - IFR | 25 | 2026-06-05 | 2026-07-09 | 42 | PTTME Office 5dx8h
ST-1640 | WPA01 Topside Mezzanine Deck Flooring & Handrail Layout - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-1650 | WPA01 Topside Mezzanine Deck Flooring & Handrail Layout - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-1660 | WPA01 Topside Sump Deck Flooring & Handrail Layout - IFR | 25 | 2026-06-05 | 2026-07-09 | 42 | PTTME Office 5dx8h
ST-1670 | WPA01 Topside Sump Deck Flooring & Handrail Layout - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-1680 | WPA01 Topside Sump Deck Flooring & Handrail Layout - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-1690 | WPA01 Topside Flooring Sections & Details (2 Sheets) - IFR | 25 | 2026-06-05 | 2026-07-09 | 42 | PTTME Office 5dx8h
ST-1700 | WPA01 Topside Flooring Sections & Details (2 Sheets) - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-1710 | WPA01 Topside Flooring Sections & Details (2 Sheets) - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-1720 | WPA01 Topside Stairway Layout & Details (11 Sheets) - IFR | 25 | 2026-06-05 | 2026-07-09 | 42 | PTTME Office 5dx8h
ST-1730 | WPA01 Topside Stairway Layout & Details (11 Sheets) - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-1740 | WPA01 Topside Stairway Layout & Details (11 Sheets) - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-1750 | WPA01 Topside Deck Hatch Arrangement & Details (11 Sheets) - IFR | 25 | 2026-06-19 | 2026-07-23 | 27 | PTTME Office 5dx8h
ST-1760 | WPA01 Topside Deck Hatch Arrangement & Details (11 Sheets) - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-1770 | WPA01 Topside Deck Hatch Arrangement & Details (11 Sheets) - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-1780 | WPA01 Topside Monorail Layout and Details - IFR | 25 | 2026-06-19 | 2026-07-23 | 32 | PTTME Office 5dx8h
ST-1790 | WPA01 Topside Monorail Layout and Details - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-1800 | WPA01 Topside Monorail Layout and Details - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-1810 | WPA01 Topside Condensate Burner Boom Support Details (2 Sheets) - IFR | 25 | 2026-06-19 | 2026-07-23 | 32 | PTTME Office 5dx8h
ST-1820 | WPA01 Topside Condensate Burner Boom Support Details (2 Sheets) - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-1830 | WPA01 Topside Condensate Burner Boom Support Details (2 Sheets) - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-1840 | WPA01 Topside Helideck Marking and Safety Netting Layout - IFR | 25 | 2026-06-19 | 2026-07-23 | 27 | PTTME Office 5dx8h
ST-1850 | WPA01 Topside Helideck Marking and Safety Netting Layout - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-1860 | WPA01 Topside Helideck Marking and Safety Netting Layout - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-1870 | WPA01 Topside Helideck Marking and Safety Netting Details (2 Sheets) - IFR | 25 | 2026-06-19 | 2026-07-23 | 32 | PTTME Office 5dx8h
ST-1880 | WPA01 Topside Helideck Marking and Safety Netting Details (2 Sheets) - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-1890 | WPA01 Topside Helideck Marking and Safety Netting Details (2 Sheets) - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-1900 | WPA01 Topside Upper Deck Equipment Support Location Plan - IFR | 25 | 2026-06-19 | 2026-07-23 | 27 | PTTME Office 5dx8h
ST-1910 | WPA01 Topside Upper Deck Equipment Support Location Plan - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-1920 | WPA01 Topside Upper Deck Equipment Support Location Plan - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-1930 | WPA01 Topside Lower Deck Equipment Support Location Plan - IFR | 25 | 2026-06-19 | 2026-07-23 | 32 | PTTME Office 5dx8h
ST-1940 | WPA01 Topside Lower Deck Equipment Support Location Plan - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-1950 | WPA01 Topside Lower Deck Equipment Support Location Plan - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-1960 | WPA01 Topside Mezzanine Deck Equipment Support Location Plan - IFR | 25 | 2026-06-19 | 2026-07-23 | 32 | PTTME Office 5dx8h
ST-1970 | WPA01 Topside Mezzanine Deck Equipment Support Location Plan - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-1980 | WPA01 Topside Mezzanine Deck Equipment Support Location Plan - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-1990 | WPA01 Topside Sump Deck Equipment Support Location Plan - IFR | 25 | 2026-06-19 | 2026-07-23 | 32 | PTTME Office 5dx8h
ST-2000 | WPA01 Topside Sump Deck Equipment Support Location Plan - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-2010 | WPA01 Topside Sump Deck Equipment Support Location Plan - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-2020 | WPA01 Topside Equipment Support Details (12 Sheets) - IFR | 25 | 2026-06-26 | 2026-08-04 | 27 | PTTME Office 5dx8h
ST-2030 | WPA01 Topside Equipment Support Details (12 Sheets) - IFA | 15 | 2026-08-20 | 2026-09-09 | 52 | PTTME Office 5dx8h
ST-2040 | WPA01 Topside Equipment Support Details (12 Sheets) - AFC | 15 | 2026-09-24 | 2026-10-15 | 52 | PTTME Office 5dx8h
ST-2050 | WPA01 Topside Platform Name Plate Details - IFR | 25 | 2026-06-26 | 2026-08-04 | 27 | PTTME Office 5dx8h
ST-2060 | WPA01 Topside Platform Name Plate Details - IFA | 15 | 2026-08-20 | 2026-09-09 | 52 | PTTME Office 5dx8h
ST-2070 | WPA01 Topside Platform Name Plate Details - AFC | 15 | 2026-09-24 | 2026-10-15 | 52 | PTTME Office 5dx8h
ST-2080 | WPA01 Topside Lifting Configuration - IFR | 25 | 2026-06-26 | 2026-08-04 | 27 | PTTME Office 5dx8h
ST-2090 | WPA01 Topside Lifting Configuration - IFA | 15 | 2026-08-20 | 2026-09-09 | 52 | PTTME Office 5dx8h
ST-2100 | WPA01 Topside Lifting Configuration - AFC | 15 | 2026-09-24 | 2026-10-15 | 52 | PTTME Office 5dx8h
ST-2110 | WPA01 Topside Lifting Padeye Details (4 Sheets) - IFR | 25 | 2026-06-26 | 2026-08-04 | 27 | PTTME Office 5dx8h
ST-2120 | WPA01 Topside Lifting Padeye Details (4 Sheets) - IFA | 15 | 2026-08-20 | 2026-09-09 | 52 | PTTME Office 5dx8h
ST-2130 | WPA01 Topside Lifting Padeye Details (4 Sheets) - AFC | 15 | 2026-09-24 | 2026-10-15 | 52 | PTTME Office 5dx8h
ST-2140 | WPA01 Topside Primary Steel MTO Report - IFR | 20 | 2026-04-28 | 2026-05-26 | 0 | PTTME Office 5dx8h
ST-2150 | WPA01 Topside Primary Steel MTO Report - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-2160 | WPA01 Topside Primary Steel MTO Report - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-2170 | WPA01 Topside Secondary and Tertiary Steel MTO Report - IFR | 25 | 2026-08-05 | 2026-09-09 | 27 | PTTME Office 5dx8h
ST-2180 | WPA01 Topside Secondary and Tertiary Steel MTO Report - IFA | 15 | 2026-09-24 | 2026-10-15 | 27 | PTTME Office 5dx8h
ST-2190 | WPA01 Topside Secondary and Tertiary Steel MTO Report - AFC | 15 | 2026-11-02 | 2026-11-20 | 27 | PTTME Office 5dx8h
ST-2200 | WPA01 Topside Computer Modeling and Load Formulation Report - IFR | 25 | 2026-05-28 | 2026-07-03 | 46 | PTTME Office 5dx8h
ST-2210 | WPA01 Topside Computer Modeling and Load Formulation Report - IFA | 15 | 2026-07-20 | 2026-08-13 | 56 | PTTME Office 5dx8h
ST-2220 | WPA01 Topside Computer Modeling and Load Formulation Report - AFC | 15 | 2026-08-28 | 2026-09-17 | 56 | PTTME Office 5dx8h
ST-2230 | WPA01 Topside In-Place Analysis Report - IFR | 25 | 2026-05-28 | 2026-07-03 | 46 | PTTME Office 5dx8h
ST-2240 | WPA01 Topside In-Place Analysis Report - IFA | 15 | 2026-07-20 | 2026-08-13 | 56 | PTTME Office 5dx8h
ST-2250 | WPA01 Topside In-Place Analysis Report - AFC | 15 | 2026-08-28 | 2026-09-17 | 56 | PTTME Office 5dx8h
ST-2253 | WPA01 Topside Vibration Anaysis Report - IFR | 25 | 2026-05-28 | 2026-07-03 | 71 | PTTME Office 5dx8h
ST-2255 | WPA01 Topside Vibration Anaysis Report - IFA | 15 | 2026-07-20 | 2026-08-13 | 71 | PTTME Office 5dx8h
ST-2256 | WPA01 Topside Vibration Anaysis Report - AFC | 15 | 2026-08-28 | 2026-09-17 | 71 | PTTME Office 5dx8h
ST-2260 | WPA01 Topside Loadout Analysis Report - IFR | 25 | 2026-05-28 | 2026-07-03 | 46 | PTTME Office 5dx8h
ST-2270 | WPA01 Topside Loadout Analysis Report - IFA | 15 | 2026-07-20 | 2026-08-13 | 56 | PTTME Office 5dx8h
ST-2280 | WPA01 Topside Loadout Analysis Report - AFC | 15 | 2026-08-28 | 2026-09-17 | 56 | PTTME Office 5dx8h
ST-2290 | WPA01 Topside Transportation Analysis Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-2300 | WPA01 Topside Transportation Analysis Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-2310 | WPA01 Topside Transportation Analysis Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-2320 | WPA01 Topside Transportation Fatigue Analysis Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-2330 | WPA01 Topside Transportation Fatigue Analysis Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-2340 | WPA01 Topside Transportation Fatigue Analysis Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-2350 | WPA01 Topside Lifting Analysis Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-2360 | WPA01 Topside Lifting Analysis Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-2370 | WPA01 Topside Lifting Analysis Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-2380 | WPA01 Topside Miscellaneous Design Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-2390 | WPA01 Topside Miscellaneous Design Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-2400 | WPA01 Topside Miscellaneous Design Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-2401 | WPA01 Topside Finite Element Analysis for Casing Slot and Unihead Spacer Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-2402 | WPA01 Topside Finite Element Analysis for Casing Slot and Unihead Spacer Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-2403 | WPA01 Topside Finite Element Analysis for Casing Slot and Unihead Spacer Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-2407 | WPA01 Structural Design for Dropped Object Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-2408 | WPA01 Structural Design for Dropped Object Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-2409 | WPA01 Structural Design for Dropped Object Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-24091 | WPA01 Topside Weight Control Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-24092 | WPA01 Topside Weight Control Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-24093 | WPA01 Topside Weight Control Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-2410 | WPA02 Topside Drawing Index (2 Sheets) - IFR | 10 | 2026-08-20 | 2026-09-02 | 47 | PTTME Office 5dx8h
ST-2420 | WPA02 Topside Drawing Index (2 Sheets) - IFA | 10 | 2026-09-17 | 2026-09-30 | 47 | PTTME Office 5dx8h
ST-2430 | WPA02 Topside Drawing Index (2 Sheets) - AFC | 5 | 2026-10-16 | 2026-10-22 | 47 | PTTME Office 5dx8h
ST-2440 | WPA02 Topside Deck Loading Diagrams - IFR | 10 | 2026-05-14 | 2026-05-27 | 111 | PTTME Office 5dx8h
ST-2450 | WPA02 Topside Deck Loading Diagrams - IFA | 10 | 2026-06-15 | 2026-06-26 | 111 | PTTME Office 5dx8h
ST-2460 | WPA02 Topside Deck Loading Diagrams - AFC | 5 | 2026-07-13 | 2026-07-17 | 111 | PTTME Office 5dx8h
ST-2470 | WPA02 Topside - Upper Deck Primary Steel Framing Plan - IFR | 10 | 2026-05-13 | 2026-05-26 | 112 | PTTME Office 5dx8h
ST-2480 | WPA02 Topside - Upper Deck Primary Steel Framing Plan - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-2490 | WPA02 Topside - Upper Deck Primary Steel Framing Plan - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-2500 | WPA02 Topside - Lower Deck Primary Steel Framing Plan - IFR | 10 | 2026-05-13 | 2026-05-26 | 112 | PTTME Office 5dx8h
ST-2510 | WPA02 Topside - Lower Deck Primary Steel Framing Plan - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-2520 | WPA02 Topside - Lower Deck Primary Steel Framing Plan - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-2530 | WPA02 Topside - Elevation Truss Row A, B, 1, 2 - IFR | 10 | 2026-05-13 | 2026-05-26 | 112 | PTTME Office 5dx8h
ST-2540 | WPA02 Topside - Elevation Truss Row A, B, 1, 2 - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-2550 | WPA02 Topside - Elevation Truss Row A, B, 1, 2 - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-2560 | WPA02 Topside - Sections (2 Sheets) - IFR | 10 | 2026-05-13 | 2026-05-26 | 112 | PTTME Office 5dx8h
ST-2570 | WPA02 Topside - Sections (2 Sheets) - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-2580 | WPA02 Topside - Sections (2 Sheets) - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-2590 | WPA02 Topside Joint Connection Details (14 Sheets) - IFR | 10 | 2026-05-13 | 2026-05-26 | 112 | PTTME Office 5dx8h
ST-2600 | WPA02 Topside Joint Connection Details (14 Sheets) - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-2610 | WPA02 Topside Joint Connection Details (14 Sheets) - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-2620 | WPA02 Topside Upper Deck Secondary Steel Framing Plan - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-2630 | WPA02 Topside Upper Deck Secondary Steel Framing Plan - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-2640 | WPA02 Topside Upper Deck Secondary Steel Framing Plan - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-2650 | WPA02 Topside Lower Deck Secondary Steel Framing Plan - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-2660 | WPA02 Topside Lower Deck Secondary Steel Framing Plan - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-2670 | WPA02 Topside Lower Deck Secondary Steel Framing Plan - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-2680 | WPA02 Topside Mezzanine Deck Framing Plan - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-2690 | WPA02 Topside Mezzanine Deck Framing Plan - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-2700 | WPA02 Topside Mezzanine Deck Framing Plan - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-2710 | WPA02 Topside Mezzanine Deck Section & Details (3 Sheets) - IFR | 25 | 2026-06-05 | 2026-07-09 | 67 | PTTME Office 5dx8h
ST-2720 | WPA02 Topside Mezzanine Deck Section & Details (3 Sheets) - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-2730 | WPA02 Topside Mezzanine Deck Section & Details (3 Sheets) - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-2740 | WPA02 Topside Sump Deck Framing Plan - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-2750 | WPA02 Topside Sump Deck Framing Plan - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-2760 | WPA02 Topside Sump Deck Framing Plan - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-2770 | WPA02 Topside Sump Deck Section & Details (3 Sheets) - IFR | 25 | 2026-06-05 | 2026-07-09 | 67 | PTTME Office 5dx8h
ST-2780 | WPA02 Topside Sump Deck Section & Details (3 Sheets) - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-2790 | WPA02 Topside Sump Deck Section & Details (3 Sheets) - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-2800 | WPA02 Topside Standard Joint Details for Secondary Beam - IFR | 25 | 2026-06-05 | 2026-07-09 | 67 | PTTME Office 5dx8h
ST-2810 | WPA02 Topside Standard Joint Details for Secondary Beam - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-2820 | WPA02 Topside Standard Joint Details for Secondary Beam - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-2830 | WPA02 Topside Vent Boom Plan and Elevation - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-2840 | WPA02 Topside Vent Boom Plan and Elevation - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-2850 | WPA02 Topside Vent Boom Plan and Elevation - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-2860 | WPA02 Topside Vent Boom Sections - IFR | 25 | 2026-06-05 | 2026-07-09 | 67 | PTTME Office 5dx8h
ST-2870 | WPA02 Topside Vent Boom Sections - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-2880 | WPA02 Topside Vent Boom Sections - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-2890 | WPA02 Topside Vent Boom Walkway Plan and Sections - IFR | 25 | 2026-06-05 | 2026-07-09 | 67 | PTTME Office 5dx8h
ST-2900 | WPA02 Topside Vent Boom Walkway Plan and Sections - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-2910 | WPA02 Topside Vent Boom Walkway Plan and Sections - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-2920 | WPA02 Topside Vent Boom Walkway Section and Details (3 Sheets) - IFR | 25 | 2026-06-12 | 2026-07-16 | 62 | PTTME Office 5dx8h
ST-2930 | WPA02 Topside Vent Boom Walkway Section and Details (3 Sheets) - IFA | 15 | 2026-08-05 | 2026-08-26 | 62 | PTTME Office 5dx8h
ST-2940 | WPA02 Topside Vent Boom Walkway Section and Details (3 Sheets) - AFC | 15 | 2026-09-10 | 2026-09-30 | 62 | PTTME Office 5dx8h
ST-2950 | WPA02 Topside Solar Panel Arrangement & Support Details (7 Sheets) - IFR | 25 | 2026-06-12 | 2026-07-16 | 62 | PTTME Office 5dx8h
ST-2960 | WPA02 Topside Solar Panel Arrangement & Support Details (7 Sheets) - IFA | 15 | 2026-08-05 | 2026-08-26 | 62 | PTTME Office 5dx8h
ST-2970 | WPA02 Topside Solar Panel Arrangement & Support Details (7 Sheets) - AFC | 15 | 2026-09-10 | 2026-09-30 | 62 | PTTME Office 5dx8h
ST-2980 | WPA02 Topside Upper Deck Flooring & Handrail Layout Plan - IFR | 25 | 2026-06-05 | 2026-07-09 | 67 | PTTME Office 5dx8h
ST-2990 | WPA02 Topside Upper Deck Flooring & Handrail Layout Plan - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-3000 | WPA02 Topside Upper Deck Flooring & Handrail Layout Plan - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-3010 | WPA02 Topside Lower Deck Flooring & Handrail Layout - IFR | 25 | 2026-06-05 | 2026-07-09 | 67 | PTTME Office 5dx8h
ST-3020 | WPA02 Topside Lower Deck Flooring & Handrail Layout - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-3030 | WPA02 Topside Lower Deck Flooring & Handrail Layout - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-3040 | WPA02 Topside Mezzanine Deck Flooring & Handrail Layout - IFR | 25 | 2026-06-05 | 2026-07-09 | 67 | PTTME Office 5dx8h
ST-3050 | WPA02 Topside Mezzanine Deck Flooring & Handrail Layout - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-3060 | WPA02 Topside Mezzanine Deck Flooring & Handrail Layout - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-3070 | WPA02 Topside Sump Deck Flooring & Handrail Layout - IFR | 25 | 2026-06-05 | 2026-07-09 | 67 | PTTME Office 5dx8h
ST-3080 | WPA02 Topside Sump Deck Flooring & Handrail Layout - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-3090 | WPA02 Topside Sump Deck Flooring & Handrail Layout - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-3100 | WPA02 Topside Flooring Sections & Details (2 Sheets) - IFR | 25 | 2026-06-05 | 2026-07-09 | 67 | PTTME Office 5dx8h
ST-3110 | WPA02 Topside Flooring Sections & Details (2 Sheets) - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-3120 | WPA02 Topside Flooring Sections & Details (2 Sheets) - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-3130 | WPA02 Topside Stairway Layout & Details (11 Sheets) - IFR | 25 | 2026-06-05 | 2026-07-09 | 67 | PTTME Office 5dx8h
ST-3140 | WPA02 Topside Stairway Layout & Details (11 Sheets) - IFA | 15 | 2026-07-24 | 2026-08-19 | 67 | PTTME Office 5dx8h
ST-3150 | WPA02 Topside Stairway Layout & Details (11 Sheets) - AFC | 15 | 2026-09-03 | 2026-09-23 | 67 | PTTME Office 5dx8h
ST-3160 | WPA02 Topside Deck Hatch Arrangement & Details (11 Sheets) - IFR | 25 | 2026-07-24 | 2026-09-02 | 32 | PTTME Office 5dx8h
ST-3170 | WPA02 Topside Deck Hatch Arrangement & Details (11 Sheets) - IFA | 15 | 2026-09-17 | 2026-10-07 | 32 | PTTME Office 5dx8h
ST-3180 | WPA02 Topside Deck Hatch Arrangement & Details (11 Sheets) - AFC | 15 | 2026-10-26 | 2026-11-13 | 32 | PTTME Office 5dx8h
ST-3190 | WPA02 Topside Monorail Layout and Details - IFR | 25 | 2026-06-19 | 2026-07-23 | 57 | PTTME Office 5dx8h
ST-3200 | WPA02 Topside Monorail Layout and Details - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-3210 | WPA02 Topside Monorail Layout and Details - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-3220 | WPA02 Topside Condensate Burner Boom Support Details (2 Sheets) - IFR | 25 | 2026-06-19 | 2026-07-23 | 57 | PTTME Office 5dx8h
ST-3230 | WPA02 Topside Condensate Burner Boom Support Details (2 Sheets) - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-3240 | WPA02 Topside Condensate Burner Boom Support Details (2 Sheets) - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-3250 | WPA02 Topside Helideck Marking and Safety Netting Layout - IFR | 25 | 2026-06-19 | 2026-07-23 | 57 | PTTME Office 5dx8h
ST-3260 | WPA02 Topside Helideck Marking and Safety Netting Layout - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-3270 | WPA02 Topside Helideck Marking and Safety Netting Layout - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-3280 | WPA02 Topside Helideck Marking and Safety Netting Details (2 Sheets) - IFR | 25 | 2026-06-19 | 2026-07-23 | 57 | PTTME Office 5dx8h
ST-3290 | WPA02 Topside Helideck Marking and Safety Netting Details (2 Sheets) - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-3300 | WPA02 Topside Helideck Marking and Safety Netting Details (2 Sheets) - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-3310 | WPA02 Topside Upper Deck Equipment Support Location Plan - IFR | 25 | 2026-06-19 | 2026-07-23 | 57 | PTTME Office 5dx8h
ST-3320 | WPA02 Topside Upper Deck Equipment Support Location Plan - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-3330 | WPA02 Topside Upper Deck Equipment Support Location Plan - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-3340 | WPA02 Topside Lower Deck Equipment Support Location Plan - IFR | 25 | 2026-06-19 | 2026-07-23 | 57 | PTTME Office 5dx8h
ST-3350 | WPA02 Topside Lower Deck Equipment Support Location Plan - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-3360 | WPA02 Topside Lower Deck Equipment Support Location Plan - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-3370 | WPA02 Topside Mezzanine Deck Equipment Support Location Plan - IFR | 25 | 2026-06-19 | 2026-07-23 | 57 | PTTME Office 5dx8h
ST-3380 | WPA02 Topside Mezzanine Deck Equipment Support Location Plan - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-3390 | WPA02 Topside Mezzanine Deck Equipment Support Location Plan - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-3400 | WPA02 Topside Sump Deck Equipment Support Location Plan - IFR | 25 | 2026-06-19 | 2026-07-23 | 57 | PTTME Office 5dx8h
ST-3410 | WPA02 Topside Sump Deck Equipment Support Location Plan - IFA | 15 | 2026-08-13 | 2026-09-02 | 57 | PTTME Office 5dx8h
ST-3420 | WPA02 Topside Sump Deck Equipment Support Location Plan - AFC | 15 | 2026-09-17 | 2026-10-07 | 57 | PTTME Office 5dx8h
ST-3430 | WPA02 Topside Equipment Support Details (17 Sheets) - IFR | 25 | 2026-06-26 | 2026-08-04 | 52 | PTTME Office 5dx8h
ST-3440 | WPA02 Topside Equipment Support Details (17 Sheets) - IFA | 15 | 2026-08-20 | 2026-09-09 | 52 | PTTME Office 5dx8h
ST-3450 | WPA02 Topside Equipment Support Details (17 Sheets) - AFC | 15 | 2026-09-24 | 2026-10-15 | 52 | PTTME Office 5dx8h
ST-3460 | WPA02 Topside Platform Name Plate Details - IFR | 25 | 2026-06-26 | 2026-08-04 | 52 | PTTME Office 5dx8h
ST-3470 | WPA02 Topside Platform Name Plate Details - IFA | 15 | 2026-08-20 | 2026-09-09 | 52 | PTTME Office 5dx8h
ST-3480 | WPA02 Topside Platform Name Plate Details - AFC | 15 | 2026-09-24 | 2026-10-15 | 52 | PTTME Office 5dx8h
ST-3490 | WPA02 Topside Lifting Configuration - IFR | 25 | 2026-06-26 | 2026-08-04 | 52 | PTTME Office 5dx8h
ST-3500 | WPA02 Topside Lifting Configuration - IFA | 15 | 2026-08-20 | 2026-09-09 | 52 | PTTME Office 5dx8h
ST-3510 | WPA02 Topside Lifting Configuration - AFC | 15 | 2026-09-24 | 2026-10-15 | 52 | PTTME Office 5dx8h
ST-3520 | WPA02 Topside Lifting Padeye Details (4 Sheets) - IFR | 25 | 2026-06-26 | 2026-08-04 | 52 | PTTME Office 5dx8h
ST-3530 | WPA02 Topside Lifting Padeye Details (4 Sheets) - IFA | 15 | 2026-08-20 | 2026-09-09 | 52 | PTTME Office 5dx8h
ST-3540 | WPA02 Topside Lifting Padeye Details (4 Sheets) - AFC | 15 | 2026-09-24 | 2026-10-15 | 52 | PTTME Office 5dx8h
ST-3550 | WPA02 Topside Primary Steel MTO Report - IFR | 20 | 2026-04-28 | 2026-05-26 | 0 | PTTME Office 5dx8h
ST-3560 | WPA02 Topside Primary Steel MTO Report - IFA | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
ST-3570 | WPA02 Topside Primary Steel MTO Report - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
ST-3580 | WPA02 Topside Secondary and Tertiary Steel MTO Report - IFR | 25 | 2026-08-05 | 2026-09-09 | 27 | PTTME Office 5dx8h
ST-3590 | WPA02 Topside Secondary and Tertiary Steel MTO Report - IFA | 15 | 2026-09-24 | 2026-10-15 | 27 | PTTME Office 5dx8h
ST-3600 | WPA02 Topside Secondary and Tertiary Steel MTO Report - AFC | 15 | 2026-11-02 | 2026-11-20 | 27 | PTTME Office 5dx8h
ST-3610 | WPA02 Topside Computer Modeling and Load Formulation Report - IFR | 25 | 2026-05-28 | 2026-07-03 | 71 | PTTME Office 5dx8h
ST-3620 | WPA02 Topside Computer Modeling and Load Formulation Report - IFA | 15 | 2026-07-20 | 2026-08-13 | 71 | PTTME Office 5dx8h
ST-3630 | WPA02 Topside Computer Modeling and Load Formulation Report - AFC | 15 | 2026-08-28 | 2026-09-17 | 71 | PTTME Office 5dx8h
ST-3640 | WPA02 Topside In-Place Analysis Report - IFR | 25 | 2026-05-28 | 2026-07-03 | 71 | PTTME Office 5dx8h
ST-3650 | WPA02 Topside In-Place Analysis Report - IFA | 15 | 2026-07-20 | 2026-08-13 | 71 | PTTME Office 5dx8h
ST-3660 | WPA02 Topside In-Place Analysis Report - AFC | 15 | 2026-08-28 | 2026-09-17 | 71 | PTTME Office 5dx8h
ST-3670 | WPA02 Topside Loadout Analysis Report - IFR | 25 | 2026-05-28 | 2026-07-03 | 71 | PTTME Office 5dx8h
ST-3680 | WPA02 Topside Loadout Analysis Report - IFA | 15 | 2026-07-20 | 2026-08-13 | 71 | PTTME Office 5dx8h
ST-3690 | WPA02 Topside Loadout Analysis Report - AFC | 15 | 2026-08-28 | 2026-09-17 | 71 | PTTME Office 5dx8h
ST-3700 | WPA02 Topside Transportation Analysis Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-3710 | WPA02 Topside Transportation Analysis Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-3720 | WPA02 Topside Transportation Analysis Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-3730 | WPA02 Topside Transportation Fatigue Analysis Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-3740 | WPA02 Topside Transportation Fatigue Analysis Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-3750 | WPA02 Topside Transportation Fatigue Analysis Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-3760 | WPA02 Topside Lifting Analysis Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-3770 | WPA02 Topside Lifting Analysis Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-3780 | WPA02 Topside Lifting Analysis Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-3790 | WPA02 Topside Miscellaneous Design Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-3800 | WPA02 Topside Miscellaneous Design Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-3810 | WPA02 Topside Miscellaneous Design Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-3811 | WPA02 Topside Finite Element Analysis for Casing Slot and Unihead Spacer Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-3812 | WPA02 Topside Finite Element Analysis for Casing Slot and Unihead Spacer Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-3813 | WPA02 Topside Finite Element Analysis for Casing Slot and Unihead Spacer Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-3817 | WPA02 Structural Design for Dropped Object Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-3818 | WPA02 Structural Design for Dropped Object Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-3819 | WPA02 Structural Design for Dropped Object Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-3820 | WPA02 Topside Weight Control Report - IFR | 25 | 2026-07-06 | 2026-08-13 | 46 | PTTME Office 5dx8h
ST-3830 | WPA02 Topside Weight Control Report - IFA | 15 | 2026-08-28 | 2026-09-17 | 46 | PTTME Office 5dx8h
ST-3840 | WPA02 Topside Weight Control Report - AFC | 15 | 2026-10-02 | 2026-10-26 | 46 | PTTME Office 5dx8h
ST-3880 | Structural Design Basis - IFR | 25 | 2026-03-04 | 2026-04-08 | 127 | PTTME Office 5dx8h
ST-3890 | Structural Design Basis - IFA | 15 | 2026-04-28 | 2026-05-19 | 127 | PTTME Office 5dx8h
ST-3900 | Structural Design Basis - AFC | 15 | 2026-06-05 | 2026-06-25 | 127 | PTTME Office 5dx8h
ST-3902 | Topside General Notes - IFR | 25 | 2026-03-04 | 2026-04-08 | 127 | PTTME Office 5dx8h
ST-3904 | Topside General Notes - IFA | 15 | 2026-04-28 | 2026-05-19 | 127 | PTTME Office 5dx8h
ST-3907 | Topside General Notes - AFC | 15 | 2026-06-05 | 2026-06-25 | 127 | PTTME Office 5dx8h
ST-3910 | Topside Standard Details Welding Detail (2 Sheets) - IFR | 25 | 2026-03-04 | 2026-04-08 | 127 | PTTME Office 5dx8h
ST-3920 | Topside Standard Details Welding Detail (2 Sheets) - IFA | 15 | 2026-04-28 | 2026-05-19 | 127 | PTTME Office 5dx8h
ST-3930 | Topside Standard Details Welding Detail (2 Sheets) - AFC | 15 | 2026-06-05 | 2026-06-25 | 127 | PTTME Office 5dx8h
ST-3940 | Topside Standard Details Beam Connections (4 Sheets) - IFR | 25 | 2026-03-04 | 2026-04-08 | 127 | PTTME Office 5dx8h
ST-3950 | Topside Standard Details Beam Connections (4 Sheets) - IFA | 15 | 2026-04-28 | 2026-05-19 | 127 | PTTME Office 5dx8h
ST-3960 | Topside Standard Details Beam Connections (4 Sheets) - AFC | 15 | 2026-06-05 | 2026-06-25 | 127 | PTTME Office 5dx8h
ST-3970 | Topside Standard Details Tubular Connections - IFR | 25 | 2026-03-04 | 2026-04-08 | 127 | PTTME Office 5dx8h
ST-3980 | Topside Standard Details Tubular Connections - IFA | 15 | 2026-04-28 | 2026-05-19 | 127 | PTTME Office 5dx8h
ST-3990 | Topside Standard Details Tubular Connections - AFC | 15 | 2026-06-05 | 2026-06-25 | 127 | PTTME Office 5dx8h
ST-4000 | Topside Standard Details Handrail Details (2 Sheets) - IFR | 25 | 2026-03-04 | 2026-04-08 | 127 | PTTME Office 5dx8h
ST-4010 | Topside Standard Details Handrail Details (2 Sheets) - IFA | 15 | 2026-04-28 | 2026-05-19 | 127 | PTTME Office 5dx8h
ST-4020 | Topside Standard Details Handrail Details (2 Sheets) - AFC | 15 | 2026-06-05 | 2026-06-25 | 127 | PTTME Office 5dx8h
ST-4030 | Topside Standard Details Ladder Details (3 Sheets) - IFR | 25 | 2026-03-04 | 2026-04-08 | 127 | PTTME Office 5dx8h
ST-4040 | Topside Standard Details Ladder Details (3 Sheets) - IFA | 15 | 2026-04-28 | 2026-05-19 | 127 | PTTME Office 5dx8h
ST-4050 | Topside Standard Details Ladder Details (3 Sheets) - AFC | 15 | 2026-06-05 | 2026-06-25 | 127 | PTTME Office 5dx8h
ST-4060 | Topside Standard Details Plating and Grating Details (2 Sheets) - IFR | 25 | 2026-03-04 | 2026-04-08 | 127 | PTTME Office 5dx8h
ST-4070 | Topside Standard Details Plating and Grating Details (2 Sheets) - IFA | 15 | 2026-04-28 | 2026-05-19 | 127 | PTTME Office 5dx8h
ST-4080 | Topside Standard Details Plating and Grating Details (2 Sheets) - AFC | 15 | 2026-06-05 | 2026-06-25 | 127 | PTTME Office 5dx8h
ST-4090 | Topside Standard Details Deck Drain Details ( 2 Sheets) - IFR | 25 | 2026-03-04 | 2026-04-08 | 127 | PTTME Office 5dx8h
ST-4100 | Topside Standard Details Deck Drain Details ( 2 Sheets) - IFA | 15 | 2026-04-28 | 2026-05-19 | 127 | PTTME Office 5dx8h
ST-4110 | Topside Standard Details Deck Drain Details ( 2 Sheets) - AFC | 15 | 2026-06-05 | 2026-06-25 | 127 | PTTME Office 5dx8h
ST-4120 | Topside Standard Details Logo Painting - IFR | 25 | 2026-03-04 | 2026-04-08 | 127 | PTTME Office 5dx8h
ST-4130 | Topside Standard Details Logo Painting - IFA | 15 | 2026-04-28 | 2026-05-19 | 127 | PTTME Office 5dx8h
ST-4140 | Topside Standard Details Logo Painting - AFC | 15 | 2026-06-05 | 2026-06-25 | 127 | PTTME Office 5dx8h
ST-4150 | Topside Casing Slot Arrangement (2 Sheets) - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-4160 | Topside Casing Slot Arrangement (2 Sheets) - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-4170 | Topside Casing Slot Arrangement (2 Sheets) - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-4180 | Topside Unihead Spacer Arrangement and Details (2 Sheets) - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-4190 | Topside Unihead Spacer Arrangement and Details (2 Sheets) - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-4200 | Topside Unihead Spacer Arrangement and Details (2 Sheets) - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-4210 | Topside Deck to Pile Connection Details - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-4220 | Topside Deck to Pile Connection Details - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-4230 | Topside Deck to Pile Connection Details - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-4240 | Topside E&I Room Plans and Elevations (2 Sheets) - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-4250 | Topside E&I Room Plans and Elevations (2 Sheets) - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-4260 | Topside E&I Room Plans and Elevations (2 Sheets) - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-4270 | Topside E&I Room Sections and Details (2 Sheets) - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-4280 | Topside E&I Room Sections and Details (2 Sheets) - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-4290 | Topside E&I Room Sections and Details (2 Sheets) - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-4300 | Topside Crane Boom Rest Details - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-4310 | Topside Crane Boom Rest Details - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-4320 | Topside Crane Boom Rest Details - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-4330 | Topside Amenities Cubicle Plan, Sections and Details (2 Sheets) - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-4340 | Topside Amenities Cubicle Plan, Sections and Details (2 Sheets) - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-4350 | Topside Amenities Cubicle Plan, Sections and Details (2 Sheets) - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-4360 | Topside Swing Ropes and Details (2 Sheets) - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-4370 | Topside Swing Ropes and Details (2 Sheets) - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-4380 | Topside Swing Ropes and Details (2 Sheets) - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-4390 | Topside Life Raft and Descending Device Support Details - IFR | 25 | 2026-05-27 | 2026-07-02 | 72 | PTTME Office 5dx8h
ST-4400 | Topside Life Raft and Descending Device Support Details - IFA | 15 | 2026-07-17 | 2026-08-11 | 72 | PTTME Office 5dx8h
ST-4410 | Topside Life Raft and Descending Device Support Details - AFC | 15 | 2026-08-27 | 2026-09-16 | 72 | PTTME Office 5dx8h
ST-4420 | Weight Control Procedure - IFR | 25 | 2026-03-04 | 2026-04-08 | 127 | PTTME Office 5dx8h
ST-4430 | Weight Control Procedure - IFA | 15 | 2026-04-28 | 2026-05-19 | 127 | PTTME Office 5dx8h
ST-4440 | Weight Control Procedure - AFC | 15 | 2026-06-05 | 2026-06-25 | 127 | PTTME Office 5dx8h
STRUCTUREENGINEERING-JACKET |  | 177 | 2026-04-01 | 2026-12-24 | 14 | PTTME Office 5dx8h
STJ-1000 | WPA01 Jacket Loadout Analysis Report - IFR | 11 | 2026-07-16 | 2026-08-04 | 60 | PTTME Office 5dx8h
STJ-1010 | WPA01 Jacket Loadout Analysis Report - IFA | 10 | 2026-08-20 | 2026-09-02 | 71 | PTTME Office 5dx8h
STJ-1020 | WPA01 Jacket Loadout Analysis Report - AFC | 10 | 2026-09-17 | 2026-09-30 | 71 | PTTME Office 5dx8h
STJ-1030 | WPA02 Jacket Loadout Analysis Report - IFR | 15 | 2026-07-16 | 2026-08-10 | 67 | PTTME Office 5dx8h
STJ-1040 | WPA02 Jacket Loadout Analysis Report - IFA | 10 | 2026-08-26 | 2026-09-08 | 67 | PTTME Office 5dx8h
STJ-1050 | WPA02 Jacket Loadout Analysis Report - AFC | 10 | 2026-09-23 | 2026-10-06 | 67 | PTTME Office 5dx8h
STJ-1060 | WPA01 Jacket Transportation Analysis Report - IFR | 17 | 2026-07-23 | 2026-08-20 | 60 | PTTME Office 5dx8h
STJ-1070 | WPA01 Jacket Transportation Analysis Report - IFA | 10 | 2026-09-04 | 2026-09-17 | 60 | PTTME Office 5dx8h
STJ-1080 | WPA01 Jacket Transportation Analysis Report - AFC | 10 | 2026-10-02 | 2026-10-16 | 60 | PTTME Office 5dx8h
STJ-1090 | WPA02 Jacket Transportation Analysis Report - IFR | 17 | 2026-07-23 | 2026-08-20 | 60 | PTTME Office 5dx8h
STJ-1100 | WPA02 Jacket Transportation Analysis Report - IFA | 10 | 2026-09-04 | 2026-09-17 | 60 | PTTME Office 5dx8h
STJ-1110 | WPA02 Jacket Transportation Analysis Report - AFC | 10 | 2026-10-02 | 2026-10-16 | 60 | PTTME Office 5dx8h
STJ-1120 | WPA01 Jacket Lifting Analysis Report - IFR | 19 | 2026-05-05 | 2026-05-29 | 91 | PTTME Office 5dx8h
STJ-1130 | WPA01 Jacket Lifting Analysis Report - IFA | 10 | 2026-06-17 | 2026-06-30 | 113 | PTTME Office 5dx8h
STJ-1140 | WPA01 Jacket Lifting Analysis Report - AFC | 10 | 2026-07-15 | 2026-07-31 | 113 | PTTME Office 5dx8h
STJ-1150 | WPA02 Jacket Lifting Analysis Report - IFR | 19 | 2026-05-05 | 2026-05-29 | 113 | PTTME Office 5dx8h
STJ-1160 | WPA02 Jacket Lifting Analysis Report - IFA | 10 | 2026-06-17 | 2026-06-30 | 113 | PTTME Office 5dx8h
STJ-1170 | WPA02 Jacket Lifting Analysis Report - AFC | 10 | 2026-07-15 | 2026-07-31 | 113 | PTTME Office 5dx8h
STJ-1180 | WPA01 Jacket Miscellaneous Design Report - IFR | 22 | 2026-05-12 | 2026-06-12 | 91 | PTTME Office 5dx8h
STJ-1190 | WPA01 Jacket Miscellaneous Design Report - IFA | 10 | 2026-06-29 | 2026-07-10 | 91 | PTTME Office 5dx8h
STJ-1200 | WPA01 Jacket Miscellaneous Design Report - AFC | 10 | 2026-07-27 | 2026-08-13 | 91 | PTTME Office 5dx8h
STJ-1210 | WPA02 Jacket Miscellaneous Design Report - IFR | 22 | 2026-05-12 | 2026-06-12 | 105 | PTTME Office 5dx8h
STJ-1220 | WPA02 Jacket Miscellaneous Design Report - IFA | 10 | 2026-06-29 | 2026-07-10 | 105 | PTTME Office 5dx8h
STJ-1230 | WPA02 Jacket Miscellaneous Design Report - AFC | 10 | 2026-07-27 | 2026-08-13 | 105 | PTTME Office 5dx8h
STJ-1240 | Jacket General Notes (2 Sheets) - IFR | 11 | 2026-05-26 | 2026-06-11 | 5 | PTTME Office 5dx8h
STJ-1250 | Jacket General Notes (2 Sheets) - IFA | 5 | 2026-06-26 | 2026-07-02 | 107 | PTTME Office 5dx8h
STJ-1260 | Jacket General Notes (2 Sheets) - AFC | 5 | 2026-07-17 | 2026-07-23 | 107 | PTTME Office 5dx8h
STJ-1270 | Jacket Casing Guides Layout - IFR | 11 | 2026-05-27 | 2026-06-12 | 5 | PTTME Office 5dx8h
STJ-1280 | Jacket Casing Guides Layout - IFA | 5 | 2026-06-29 | 2026-07-03 | 106 | PTTME Office 5dx8h
STJ-1290 | Jacket Casing Guides Layout - AFC | 5 | 2026-07-20 | 2026-07-24 | 106 | PTTME Office 5dx8h
STJ-1300 | Jacket Casing Guides Section & Details (3 Sheets) - IFR | 11 | 2026-05-27 | 2026-06-12 | 106 | PTTME Office 5dx8h
STJ-1310 | Jacket Casing Guides Section & Details (3 Sheets) - IFA | 5 | 2026-06-29 | 2026-07-03 | 106 | PTTME Office 5dx8h
STJ-1320 | Jacket Casing Guides Section & Details (3 Sheets) - AFC | 5 | 2026-07-20 | 2026-07-24 | 106 | PTTME Office 5dx8h
STJ-1330 | Jacket Pile to Jacket Connection Details - IFR | 10 | 2026-06-05 | 2026-06-18 | 5 | PTTME Office 5dx8h
STJ-1340 | Jacket Pile to Jacket Connection Details - IFA | 5 | 2026-07-03 | 2026-07-09 | 102 | PTTME Office 5dx8h
STJ-1350 | Jacket Pile to Jacket Connection Details - AFC | 5 | 2026-07-24 | 2026-08-04 | 102 | PTTME Office 5dx8h
STJ-1360 | Jacket Boatlanding Arrangement - IFR | 10 | 2026-06-10 | 2026-06-23 | 5 | PTTME Office 5dx8h
STJ-1370 | Jacket Boatlanding Arrangement - IFA | 5 | 2026-07-13 | 2026-07-17 | 96 | PTTME Office 5dx8h
STJ-1380 | Jacket Boatlanding Arrangement - AFC | 5 | 2026-08-14 | 2026-08-20 | 91 | PTTME Office 5dx8h
STJ-1390 | Jacket Boatlanding Section & Details (7 Sheets) - IFR | 10 | 2026-06-10 | 2026-06-23 | 5 | PTTME Office 5dx8h
STJ-1400 | Jacket Boatlanding Section & Details (7 Sheets) - IFA | 5 | 2026-07-13 | 2026-07-17 | 96 | PTTME Office 5dx8h
STJ-1410 | Jacket Boatlanding Section & Details (7 Sheets) - AFC | 5 | 2026-08-14 | 2026-08-20 | 91 | PTTME Office 5dx8h
STJ-1420 | Jacket Paint Marking Details - IFR | 12 | 2026-06-22 | 2026-07-07 | 5 | PTTME Office 5dx8h
STJ-1430 | Jacket Paint Marking Details - IFA | 5 | 2026-07-22 | 2026-07-31 | 89 | PTTME Office 5dx8h
STJ-1440 | Jacket Paint Marking Details - AFC | 5 | 2026-08-18 | 2026-08-24 | 89 | PTTME Office 5dx8h
STJ-1450 | Jacket Vortex Shedding Prevention Plan & Details - IFR | 12 | 2026-06-23 | 2026-07-08 | 5 | PTTME Office 5dx8h
STJ-1460 | Jacket Vortex Shedding Prevention Plan & Details - IFA | 5 | 2026-07-23 | 2026-08-03 | 88 | PTTME Office 5dx8h
STJ-1470 | Jacket Vortex Shedding Prevention Plan & Details - AFC | 5 | 2026-08-19 | 2026-08-25 | 88 | PTTME Office 5dx8h
STJ-1480 | WPA01 Jacket Computer Modelling & Load Formulation Report - IFR | 10 | 2026-04-01 | 2026-04-20 | 43 | PTTME Office 5dx8h
STJ-1490 | WPA01 Jacket Computer Modelling & Load Formulation Report - IFA | 5 | 2026-05-06 | 2026-05-12 | 87 | PTTME Office 5dx8h
STJ-1500 | WPA01 Jacket Computer Modelling & Load Formulation Report - AFC | 5 | 2026-05-27 | 2026-06-04 | 97 | PTTME Office 5dx8h
STJ-1510 | WPA01 Jacket In-place Analysis Report - IFR | 12 | 2026-04-16 | 2026-05-04 | 43 | PTTME Office 5dx8h
STJ-1520 | WPA01 Jacket In-place Analysis Report - IFA | 5 | 2026-05-19 | 2026-05-25 | 83 | PTTME Office 5dx8h
STJ-1530 | WPA01 Jacket In-place Analysis Report - AFC | 5 | 2026-06-11 | 2026-06-17 | 93 | PTTME Office 5dx8h
STJ-1540 | WPA01 Jacket Dynamic Analysis Report - IFR | 15 | 2026-04-20 | 2026-05-11 | 95 | PTTME Office 5dx8h
STJ-1550 | WPA01 Jacket Dynamic Analysis Report - IFA | 5 | 2026-05-26 | 2026-06-02 | 113 | PTTME Office 5dx8h
STJ-1560 | WPA01 Jacket Dynamic Analysis Report - AFC | 5 | 2026-06-18 | 2026-06-24 | 118 | PTTME Office 5dx8h
STJ-1570 | WPA01 Platform Spectral Fatigue Analysis Report - IFR | 19 | 2026-05-18 | 2026-06-15 | 95 | PTTME Office 5dx8h
STJ-1580 | WPA01 Platform Spectral Fatigue Analysis Report - IFA | 10 | 2026-06-30 | 2026-07-13 | 95 | PTTME Office 5dx8h
STJ-1590 | WPA01 Platform Spectral Fatigue Analysis Report - AFC | 10 | 2026-07-31 | 2026-08-14 | 95 | PTTME Office 5dx8h
STJ-1600 | WPA01 Jacket On-bottom Stability Analysis & Mudmat Design Report - IFR | 20 | 2026-05-05 | 2026-06-02 | 43 | PTTME Office 5dx8h
STJ-1610 | WPA01 Jacket On-bottom Stability Analysis & Mudmat Design Report - IFA | 10 | 2026-06-18 | 2026-07-01 | 73 | PTTME Office 5dx8h
STJ-1620 | WPA01 Jacket On-bottom Stability Analysis & Mudmat Design Report - AFC | 10 | 2026-07-16 | 2026-08-03 | 73 | PTTME Office 5dx8h
STJ-1630 | WPA01 Jacket Cathodic Protection Design Report - IFR | 16 | 2026-08-11 | 2026-09-02 | 42 | PTTME Office 5dx8h
STJ-1640 | WPA01 Jacket Cathodic Protection Design Report - IFA | 10 | 2026-09-17 | 2026-09-30 | 42 | PTTME Office 5dx8h
STJ-1650 | WPA01 Jacket Cathodic Protection Design Report - AFC | 10 | 2026-10-16 | 2026-10-30 | 42 | PTTME Office 5dx8h
STJ-1660 | WPA01 Topside and Jacket Seismic Analysis Report (Extreme Level Earthquake - ELE) - IFR | 19 | 2026-05-25 | 2026-06-22 | 49 | PTTME Office 5dx8h
STJ-1670 | WPA01 Topside and Jacket Seismic Analysis Report (Extreme Level Earthquake - ELE) - IFA | 10 | 2026-07-07 | 2026-07-20 | 90 | PTTME Office 5dx8h
STJ-1680 | WPA01 Topside and Jacket Seismic Analysis Report (Extreme Level Earthquake - ELE) - AFC | 10 | 2026-08-07 | 2026-08-21 | 90 | PTTME Office 5dx8h
STJ-1690 | WPA01 Topside and Jacket Seismic Analysis Report (Abnormal Level Earthquake - ALE) - IFR | 19 | 2026-06-02 | 2026-06-29 | 85 | PTTME Office 5dx8h
STJ-1700 | WPA01 Topside and Jacket Seismic Analysis Report (Abnormal Level Earthquake - ALE) - IFA | 10 | 2026-07-14 | 2026-07-27 | 85 | PTTME Office 5dx8h
STJ-1710 | WPA01 Topside and Jacket Seismic Analysis Report (Abnormal Level Earthquake - ALE) - AFC | 10 | 2026-08-17 | 2026-08-28 | 85 | PTTME Office 5dx8h
STJ-1720 | WPA01 Boat Impact Analysis - IFR | 21 | 2026-06-15 | 2026-07-13 | 49 | PTTME Office 5dx8h
STJ-1730 | WPA01 Boat Impact Analysis - IFA | 10 | 2026-07-31 | 2026-08-14 | 75 | PTTME Office 5dx8h
STJ-1740 | WPA01 Boat Impact Analysis - AFC | 10 | 2026-08-31 | 2026-09-11 | 75 | PTTME Office 5dx8h
STJ-1750 | WPA01 Non-Linear Static Pushover Analysis - IFR | 21 | 2026-06-22 | 2026-07-20 | 54 | PTTME Office 5dx8h
STJ-1760 | WPA01 Non-Linear Static Pushover Analysis - IFA | 10 | 2026-08-07 | 2026-08-21 | 70 | PTTME Office 5dx8h
STJ-1770 | WPA01 Non-Linear Static Pushover Analysis - AFC | 10 | 2026-09-07 | 2026-09-18 | 70 | PTTME Office 5dx8h
STJ-1780 | WPA01 Jacket Transportation Fatigue Analysis Report - IFR | 17 | 2026-07-20 | 2026-08-17 | 54 | PTTME Office 5dx8h
STJ-1790 | WPA01 Jacket Transportation Fatigue Analysis Report - IFA | 10 | 2026-09-01 | 2026-09-14 | 54 | PTTME Office 5dx8h
STJ-1800 | WPA01 Jacket Transportation Fatigue Analysis Report - AFC | 10 | 2026-09-29 | 2026-10-12 | 54 | PTTME Office 5dx8h
STJ-1810 | WPA01 Levelling Analysis Report - IFR | 12 | 2026-07-27 | 2026-08-17 | 54 | PTTME Office 5dx8h
STJ-1820 | WPA01 Levelling Analysis Report - IFA | 10 | 2026-09-01 | 2026-09-14 | 54 | PTTME Office 5dx8h
STJ-1830 | WPA01 Levelling Analysis Report - AFC | 10 | 2026-09-29 | 2026-10-12 | 54 | PTTME Office 5dx8h
STJ-1840 | WPA01 Pile Fatigue, Pile Handling, Stuck-Up and Pile Driving Analysis Report - IFR | 17 | 2026-04-16 | 2026-05-11 | 118 | PTTME Office 5dx8h
STJ-1850 | WPA01 Pile Fatigue, Pile Handling, Stuck-Up and Pile Driving Analysis Report - IFA | 10 | 2026-05-26 | 2026-06-10 | 118 | PTTME Office 5dx8h
STJ-1860 | WPA01 Pile Fatigue, Pile Handling, Stuck-Up and Pile Driving Analysis Report - AFC | 10 | 2026-06-25 | 2026-07-08 | 118 | PTTME Office 5dx8h
STJ-1870 | WPA01 Jacket - Drawing Index - IFR | 17 | 2026-06-26 | 2026-07-20 | 5 | PTTME Office 5dx8h
STJ-1880 | WPA01 Jacket - Drawing Index - IFA | 10 | 2026-08-07 | 2026-08-21 | 35 | PTTME Office 5dx8h
STJ-1890 | WPA01 Jacket - Drawing Index - AFC | 10 | 2026-09-07 | 2026-09-18 | 40 | PTTME Office 5dx8h
STJ-1900 | WPA01 Jacket - Elevation Row A, B, 1, 2 - IFR | 17 | 2026-06-26 | 2026-07-20 | 39 | PTTME Office 5dx8h
STJ-1910 | WPA01 Jacket - Elevation Row A, B, 1, 2 - IFA | 10 | 2026-08-07 | 2026-08-21 | 50 | PTTME Office 5dx8h
STJ-1920 | WPA01 Jacket - Elevation Row A, B, 1, 2 - AFC | 10 | 2026-09-07 | 2026-09-18 | 50 | PTTME Office 5dx8h
STJ-1930 | WPA01 Jacket - Horizontal Framing Plan (4 Sheets) - IFR | 16 | 2026-07-06 | 2026-07-27 | 39 | PTTME Office 5dx8h
STJ-1940 | WPA01 Jacket - Horizontal Framing Plan (4 Sheets) - IFA | 10 | 2026-08-17 | 2026-08-28 | 45 | PTTME Office 5dx8h
STJ-1950 | WPA01 Jacket - Horizontal Framing Plan (4 Sheets) - AFC | 10 | 2026-09-14 | 2026-09-25 | 45 | PTTME Office 5dx8h
STJ-1960 | WPA01 Jacket - Sections - IFR | 15 | 2026-07-15 | 2026-08-07 | 39 | PTTME Office 5dx8h
STJ-1970 | WPA01 Jacket - Sections - IFA | 10 | 2026-08-25 | 2026-09-07 | 39 | PTTME Office 5dx8h
STJ-1980 | WPA01 Jacket - Sections - AFC | 10 | 2026-09-22 | 2026-10-05 | 39 | PTTME Office 5dx8h
STJ-1990 | WPA01 Jacket - Pile Make Up & Details (2 Sheets) - IFR | 15 | 2026-07-15 | 2026-08-07 | 39 | PTTME Office 5dx8h
STJ-2000 | WPA01 Jacket - Pile Make Up & Details (2 Sheets) - IFA | 10 | 2026-08-25 | 2026-09-07 | 39 | PTTME Office 5dx8h
STJ-2010 | WPA01 Jacket - Pile Make Up & Details (2 Sheets) - AFC | 10 | 2026-09-22 | 2026-10-05 | 39 | PTTME Office 5dx8h
STJ-2020 | WPA01 Jacket - Pile Marking Details - IFR | 15 | 2026-07-15 | 2026-08-07 | 39 | PTTME Office 5dx8h
STJ-2030 | WPA01 Jacket - Pile Marking Details - IFA | 10 | 2026-08-25 | 2026-09-07 | 39 | PTTME Office 5dx8h
STJ-2040 | WPA01 Jacket - Pile Marking Details - AFC | 10 | 2026-09-22 | 2026-10-05 | 39 | PTTME Office 5dx8h
STJ-2050 | WPA01 Jacket - Access Walkway Layout & Details (3 Sheets) - IFR | 12 | 2026-07-22 | 2026-08-11 | 33 | PTTME Office 5dx8h
STJ-2060 | WPA01 Jacket - Access Walkway Layout & Details (3 Sheets) - IFA | 10 | 2026-08-27 | 2026-09-09 | 37 | PTTME Office 5dx8h
STJ-2070 | WPA01 Jacket - Access Walkway Layout & Details (3 Sheets) - AFC | 10 | 2026-09-24 | 2026-10-07 | 37 | PTTME Office 5dx8h
STJ-2080 | WPA01 Jacket - Anode Layout & Details - IFR | 12 | 2026-07-31 | 2026-08-18 | 33 | PTTME Office 5dx8h
STJ-2090 | WPA01 Jacket - Anode Layout & Details - IFA | 10 | 2026-09-02 | 2026-09-15 | 33 | PTTME Office 5dx8h
STJ-2100 | WPA01 Jacket - Anode Layout & Details - AFC | 10 | 2026-09-30 | 2026-10-14 | 33 | PTTME Office 5dx8h
STJ-2110 | WPA01 Jacket - Mudmat Layout & Details (2 Sheets) - IFR | 12 | 2026-07-31 | 2026-08-18 | 5 | PTTME Office 5dx8h
STJ-2120 | WPA01 Jacket - Mudmat Layout & Details (2 Sheets) - IFA | 10 | 2026-09-02 | 2026-09-15 | 33 | PTTME Office 5dx8h
STJ-2130 | WPA01 Jacket - Mudmat Layout & Details (2 Sheets) - AFC | 10 | 2026-09-30 | 2026-10-14 | 33 | PTTME Office 5dx8h
STJ-2140 | WPA01 Jacket - Lifting Configuration - IFR | 12 | 2026-08-04 | 2026-08-20 | 5 | PTTME Office 5dx8h
STJ-2150 | WPA01 Jacket - Lifting Configuration - IFA | 10 | 2026-09-04 | 2026-09-17 | 31 | PTTME Office 5dx8h
STJ-2160 | WPA01 Jacket - Lifting Configuration - AFC | 10 | 2026-10-02 | 2026-10-16 | 31 | PTTME Office 5dx8h
STJ-2170 | WPA01 Jacket - Lifting Padeye Details - IFR | 12 | 2026-08-04 | 2026-08-20 | 9 | PTTME Office 5dx8h
STJ-2180 | WPA01 Jacket - Lifting Padeye Details - IFA | 10 | 2026-09-04 | 2026-09-17 | 31 | PTTME Office 5dx8h
STJ-2190 | WPA01 Jacket - Lifting Padeye Details - AFC | 10 | 2026-10-02 | 2026-10-16 | 31 | PTTME Office 5dx8h
STJ-2200 | WPA01 Jacket - Lowering Sequence - IFR | 12 | 2026-08-04 | 2026-08-20 | 9 | PTTME Office 5dx8h
STJ-2210 | WPA01 Jacket - Lowering Sequence - IFA | 10 | 2026-09-04 | 2026-09-17 | 31 | PTTME Office 5dx8h
STJ-2220 | WPA01 Jacket - Lowering Sequence - AFC | 10 | 2026-10-02 | 2026-10-16 | 31 | PTTME Office 5dx8h
STJ-2230 | WPA01 - TAD Rig Clearance Check - IFR | 9 | 2026-08-10 | 2026-08-21 | 6 | PTTME Office 5dx8h
STJ-2240 | WPA01 - TAD Rig Clearance Check - IFA | 5 | 2026-09-07 | 2026-09-11 | 35 | PTTME Office 5dx8h
STJ-2250 | WPA01 - TAD Rig Clearance Check - AFC | 5 | 2026-09-28 | 2026-10-02 | 40 | PTTME Office 5dx8h
STJ-2260 | WPA02 Jacket Computer Modelling & Load Formulation Report - IFR | 10 | 2026-04-01 | 2026-04-20 | 142 | PTTME Office 5dx8h
STJ-2270 | WPA02 Jacket Computer Modelling & Load Formulation Report - IFA | 5 | 2026-05-06 | 2026-05-12 | 142 | PTTME Office 5dx8h
STJ-2280 | WPA02 Jacket Computer Modelling & Load Formulation Report - AFC | 5 | 2026-05-27 | 2026-06-04 | 142 | PTTME Office 5dx8h
STJ-2290 | WPA02 Jacket In-place Analysis Report - IFR | 12 | 2026-04-16 | 2026-05-04 | 70 | PTTME Office 5dx8h
STJ-2300 | WPA02 Jacket In-place Analysis Report - IFA | 5 | 2026-05-19 | 2026-05-25 | 103 | PTTME Office 5dx8h
STJ-2310 | WPA02 Jacket In-place Analysis Report - AFC | 5 | 2026-06-11 | 2026-06-17 | 108 | PTTME Office 5dx8h
STJ-2320 | WPA02 Jacket Dynamic Analysis Report - IFR | 15 | 2026-04-20 | 2026-05-11 | 128 | PTTME Office 5dx8h
STJ-2330 | WPA02 Jacket Dynamic Analysis Report - IFA | 5 | 2026-05-26 | 2026-06-02 | 128 | PTTME Office 5dx8h
STJ-2340 | WPA02 Jacket Dynamic Analysis Report - AFC | 5 | 2026-06-18 | 2026-06-24 | 128 | PTTME Office 5dx8h
STJ-2350 | WPA02 Platform Spectral Fatigue Analysis Report - IFR | 19 | 2026-05-18 | 2026-06-15 | 95 | PTTME Office 5dx8h
STJ-2360 | WPA02 Platform Spectral Fatigue Analysis Report - IFA | 10 | 2026-06-30 | 2026-07-13 | 95 | PTTME Office 5dx8h
STJ-2370 | WPA02 Platform Spectral Fatigue Analysis Report - AFC | 10 | 2026-07-31 | 2026-08-14 | 95 | PTTME Office 5dx8h
STJ-2380 | WPA02 Jacket On-bottom Stability Analysis & Mudmat Design Report - IFR | 20 | 2026-05-05 | 2026-06-02 | 103 | PTTME Office 5dx8h
STJ-2390 | WPA02 Jacket On-bottom Stability Analysis & Mudmat Design Report - IFA | 10 | 2026-06-18 | 2026-07-01 | 103 | PTTME Office 5dx8h
STJ-2400 | WPA02 Jacket On-bottom Stability Analysis & Mudmat Design Report - AFC | 10 | 2026-07-16 | 2026-08-03 | 103 | PTTME Office 5dx8h
STJ-2410 | WPA02 Topside and Jacket Seismic Analysis Report (Extreme Level Earthquake - ELE) - IFR | 19 | 2026-05-25 | 2026-06-22 | 90 | PTTME Office 5dx8h
STJ-2420 | WPA02 Topside and Jacket Seismic Analysis Report (Extreme Level Earthquake - ELE) - IFA | 10 | 2026-07-07 | 2026-07-20 | 90 | PTTME Office 5dx8h
STJ-2430 | WPA02 Topside and Jacket Seismic Analysis Report (Extreme Level Earthquake - ELE) - AFC | 10 | 2026-08-07 | 2026-08-21 | 90 | PTTME Office 5dx8h
STJ-2440 | WPA02 Topside and Jacket Seismic Analysis Report (Abnormal Level Earthquake - ALE) - IFR | 19 | 2026-06-02 | 2026-06-29 | 85 | PTTME Office 5dx8h
STJ-2450 | WPA02 Topside and Jacket Seismic Analysis Report (Abnormal Level Earthquake - ALE) - IFA | 10 | 2026-07-14 | 2026-07-27 | 85 | PTTME Office 5dx8h
STJ-2460 | WPA02 Topside and Jacket Seismic Analysis Report (Abnormal Level Earthquake - ALE) - AFC | 10 | 2026-08-17 | 2026-08-28 | 85 | PTTME Office 5dx8h
STJ-2470 | WPA02 Boat Impact Analysis - IFR | 21 | 2026-06-15 | 2026-07-13 | 49 | PTTME Office 5dx8h
STJ-2480 | WPA02 Boat Impact Analysis - IFA | 10 | 2026-07-31 | 2026-08-14 | 75 | PTTME Office 5dx8h
STJ-2490 | WPA02 Boat Impact Analysis - AFC | 10 | 2026-08-31 | 2026-09-11 | 75 | PTTME Office 5dx8h
STJ-2500 | WPA02 Non-Linear Static Pushover Analysis - IFR | 21 | 2026-06-22 | 2026-07-20 | 49 | PTTME Office 5dx8h
STJ-2510 | WPA02 Non-Linear Static Pushover Analysis - IFA | 10 | 2026-08-07 | 2026-08-21 | 70 | PTTME Office 5dx8h
STJ-2520 | WPA02 Non-Linear Static Pushover Analysis - AFC | 10 | 2026-09-07 | 2026-09-18 | 70 | PTTME Office 5dx8h
STJ-2530 | WPA02 Jacket Transportation Fatigue Analysis Report - IFR | 13 | 2026-07-20 | 2026-08-10 | 49 | PTTME Office 5dx8h
STJ-2540 | WPA02 Jacket Transportation Fatigue Analysis Report - IFA | 10 | 2026-08-26 | 2026-09-08 | 58 | PTTME Office 5dx8h
STJ-2550 | WPA02 Jacket Transportation Fatigue Analysis Report - AFC | 10 | 2026-09-23 | 2026-10-06 | 58 | PTTME Office 5dx8h
STJ-2560 | WPA02 Levelling Analysis Report - IFR | 12 | 2026-07-27 | 2026-08-17 | 49 | PTTME Office 5dx8h
STJ-2570 | WPA02 Levelling Analysis Report - IFA | 15 | 2026-09-01 | 2026-09-21 | 49 | PTTME Office 5dx8h
STJ-2580 | WPA02 Levelling Analysis Report - AFC | 10 | 2026-10-06 | 2026-10-20 | 49 | PTTME Office 5dx8h
STJ-2590 | WPA02 Pile Fatigue, Pile Handling, Stuck-Up and Pile Driving Analysis Report - IFR | 17 | 2026-04-16 | 2026-05-11 | 118 | PTTME Office 5dx8h
STJ-2600 | WPA02 Pile Fatigue, Pile Handling, Stuck-Up and Pile Driving Analysis Report - IFA | 10 | 2026-05-26 | 2026-06-10 | 118 | PTTME Office 5dx8h
STJ-2610 | WPA02 Pile Fatigue, Pile Handling, Stuck-Up and Pile Driving Analysis Report - AFC | 10 | 2026-06-25 | 2026-07-08 | 118 | PTTME Office 5dx8h
STJ-2620 | WPA02 Jacket Cathodic Protection Design Report - IFR | 16 | 2026-08-11 | 2026-09-02 | 42 | PTTME Office 5dx8h
STJ-2630 | WPA02 Jacket Cathodic Protection Design Report - IFA | 10 | 2026-09-17 | 2026-09-30 | 42 | PTTME Office 5dx8h
STJ-2640 | WPA02 Jacket Cathodic Protection Design Report - AFC | 10 | 2026-10-16 | 2026-10-30 | 42 | PTTME Office 5dx8h
STJ-2650 | WPA02 Jacket - Drawing Index - IFR | 17 | 2026-06-26 | 2026-07-20 | 59 | PTTME Office 5dx8h
STJ-2660 | WPA02 Jacket - Drawing Index - IFA | 10 | 2026-08-07 | 2026-08-21 | 60 | PTTME Office 5dx8h
STJ-2670 | WPA02 Jacket - Drawing Index - AFC | 10 | 2026-09-07 | 2026-09-18 | 60 | PTTME Office 5dx8h
STJ-2680 | WPA02 Jacket - Elevation Row A, B, 1, 2 - IFR | 17 | 2026-06-26 | 2026-07-20 | 70 | PTTME Office 5dx8h
STJ-2690 | WPA02 Jacket - Elevation Row A, B, 1, 2 - IFA | 10 | 2026-08-07 | 2026-08-21 | 70 | PTTME Office 5dx8h
STJ-2700 | WPA02 Jacket - Elevation Row A, B, 1, 2 - AFC | 10 | 2026-09-07 | 2026-09-18 | 70 | PTTME Office 5dx8h
STJ-2710 | WPA02 Jacket - Horizontal Framing Plan (4 Sheets) - IFR | 16 | 2026-07-06 | 2026-07-27 | 65 | PTTME Office 5dx8h
STJ-2720 | WPA02 Jacket - Horizontal Framing Plan (4 Sheets) - IFA | 10 | 2026-08-17 | 2026-08-28 | 65 | PTTME Office 5dx8h
STJ-2730 | WPA02 Jacket - Horizontal Framing Plan (4 Sheets) - AFC | 10 | 2026-09-14 | 2026-09-25 | 65 | PTTME Office 5dx8h
STJ-2740 | WPA02 Jacket - Sections - IFR | 15 | 2026-07-15 | 2026-08-07 | 59 | PTTME Office 5dx8h
STJ-2750 | WPA02 Jacket - Sections - IFA | 10 | 2026-08-25 | 2026-09-07 | 59 | PTTME Office 5dx8h
STJ-2760 | WPA02 Jacket - Sections - AFC | 10 | 2026-09-22 | 2026-10-05 | 59 | PTTME Office 5dx8h
STJ-2770 | WPA02 Jacket - Pile Make Up & Details (2 Sheets) - IFR | 15 | 2026-07-15 | 2026-08-07 | 59 | PTTME Office 5dx8h
STJ-2780 | WPA02 Jacket - Pile Make Up & Details (2 Sheets) - IFA | 10 | 2026-08-25 | 2026-09-07 | 59 | PTTME Office 5dx8h
STJ-2790 | WPA02 Jacket - Pile Make Up & Details (2 Sheets) - AFC | 10 | 2026-09-22 | 2026-10-05 | 59 | PTTME Office 5dx8h
STJ-2800 | WPA02 Jacket - Pile Marking Details - IFR | 15 | 2026-07-15 | 2026-08-07 | 59 | PTTME Office 5dx8h
STJ-2810 | WPA02 Jacket - Pile Marking Details - IFA | 10 | 2026-08-25 | 2026-09-07 | 59 | PTTME Office 5dx8h
STJ-2820 | WPA02 Jacket - Pile Marking Details - AFC | 10 | 2026-09-22 | 2026-10-05 | 59 | PTTME Office 5dx8h
STJ-2830 | WPA02 Jacket - Access Walkway Layout & Details (3 Sheets) - IFR | 12 | 2026-07-22 | 2026-08-11 | 57 | PTTME Office 5dx8h
STJ-2840 | WPA02 Jacket - Access Walkway Layout & Details (3 Sheets) - IFA | 10 | 2026-08-27 | 2026-09-09 | 57 | PTTME Office 5dx8h
STJ-2850 | WPA02 Jacket - Access Walkway Layout & Details (3 Sheets) - AFC | 10 | 2026-09-24 | 2026-10-07 | 57 | PTTME Office 5dx8h
STJ-2860 | WPA02 Jacket - Anode Layout & Details - IFR | 12 | 2026-07-31 | 2026-08-18 | 53 | PTTME Office 5dx8h
STJ-2870 | WPA02 Jacket - Anode Layout & Details - IFA | 10 | 2026-09-02 | 2026-09-15 | 53 | PTTME Office 5dx8h
STJ-2880 | WPA02 Jacket - Anode Layout & Details - AFC | 10 | 2026-09-30 | 2026-10-14 | 53 | PTTME Office 5dx8h
STJ-2890 | WPA02 Jacket - Mudmat Layout & Details (2 Sheets) - IFR | 12 | 2026-07-31 | 2026-08-18 | 53 | PTTME Office 5dx8h
STJ-2900 | WPA02 Jacket - Mudmat Layout & Details (2 Sheets) - IFA | 10 | 2026-09-02 | 2026-09-15 | 53 | PTTME Office 5dx8h
STJ-2910 | WPA02 Jacket - Mudmat Layout & Details (2 Sheets) - AFC | 10 | 2026-09-30 | 2026-10-14 | 53 | PTTME Office 5dx8h
STJ-2920 | WPA02 Jacket - Caisson Support Layout - IFR | 11 | 2026-08-10 | 2026-08-25 | 48 | PTTME Office 5dx8h
STJ-2930 | WPA02 Jacket - Caisson Support Layout - IFA | 10 | 2026-09-09 | 2026-09-22 | 48 | PTTME Office 5dx8h
STJ-2940 | WPA02 Jacket - Caisson Support Layout - AFC | 10 | 2026-10-07 | 2026-10-21 | 48 | PTTME Office 5dx8h
STJ-2950 | WPA02 Jacket - Caisson Support Section & Details - IFR | 11 | 2026-08-10 | 2026-08-25 | 48 | PTTME Office 5dx8h
STJ-2960 | WPA02 Jacket - Caisson Support Section & Details - IFA | 10 | 2026-09-09 | 2026-09-22 | 48 | PTTME Office 5dx8h
STJ-2970 | WPA02 Jacket - Caisson Support Section & Details - AFC | 10 | 2026-10-07 | 2026-10-21 | 48 | PTTME Office 5dx8h
STJ-2980 | WPA02 Jacket - Lifting Configuration - IFR | 11 | 2026-08-10 | 2026-08-25 | 5 | PTTME Office 5dx8h
STJ-2990 | WPA02 Jacket - Lifting Configuration - IFA | 10 | 2026-09-09 | 2026-09-22 | 48 | PTTME Office 5dx8h
STJ-3000 | WPA02 Jacket - Lifting Configuration - AFC | 10 | 2026-10-07 | 2026-10-21 | 48 | PTTME Office 5dx8h
STJ-3010 | WPA02 Jacket - Lifting Padeye Details - IFR | 11 | 2026-08-10 | 2026-08-25 | 5 | PTTME Office 5dx8h
STJ-3020 | WPA02 Jacket - Lifting Padeye Details - IFA | 10 | 2026-09-09 | 2026-09-22 | 48 | PTTME Office 5dx8h
STJ-3030 | WPA02 Jacket - Lifting Padeye Details - AFC | 10 | 2026-10-07 | 2026-10-21 | 48 | PTTME Office 5dx8h
STJ-3040 | WPA02 Jacket - Lowering Sequence - IFR | 11 | 2026-08-10 | 2026-08-25 | 5 | PTTME Office 5dx8h
STJ-3050 | WPA02 Jacket - Lowering Sequence - IFA | 10 | 2026-09-09 | 2026-09-22 | 48 | PTTME Office 5dx8h
STJ-3060 | WPA02 Jacket - Lowering Sequence - AFC | 10 | 2026-10-07 | 2026-10-21 | 48 | PTTME Office 5dx8h
STJ-3070 | WPA02 - TAD Rig Clearance Check - IFR | 12 | 2026-08-11 | 2026-08-27 | 5 | PTTME Office 5dx8h
STJ-3080 | WPA02 - TAD Rig Clearance Check - IFA | 10 | 2026-09-11 | 2026-09-24 | 46 | PTTME Office 5dx8h
STJ-3090 | WPA02 - TAD Rig Clearance Check - AFC | 10 | 2026-10-09 | 2026-10-26 | 46 | PTTME Office 5dx8h
STJ-3100 | WPA01 Jacket Weight Control Report - IFR | 15 | 2026-08-24 | 2026-09-11 | 5 | PTTME Office 5dx8h
STJ-3110 | WPA01 Jacket Weight Control Report - IFA | 10 | 2026-09-28 | 2026-10-09 | 25 | PTTME Office 5dx8h
STJ-3120 | WPA01 Jacket Weight Control Report - AFC | 10 | 2026-10-28 | 2026-11-10 | 25 | PTTME Office 5dx8h
STJ-3130 | WPA01 Jacket Primary Steel MTO - IFR | 7 | 2026-06-02 | 2026-06-11 | 77 | PTTME Office 5dx8h
STJ-3140 | WPA01 Jacket Primary Steel MTO - IFA | 5 | 2026-06-26 | 2026-07-02 | 92 | PTTME Office 5dx8h
STJ-3150 | WPA01 Jacket Primary Steel MTO - AFC | 5 | 2026-07-17 | 2026-07-23 | 97 | PTTME Office 5dx8h
STJ-3160 | WPA01 Jacket Secondary MTO and Tertiary Steel - IFR | 15 | 2026-10-05 | 2026-10-27 | 5 | PTTME Office 5dx8h
STJ-3170 | WPA01 Jacket Secondary MTO and Tertiary Steel - IFA | 10 | 2026-11-11 | 2026-11-24 | 5 | PTTME Office 5dx8h
STJ-3180 | WPA01 Jacket Secondary MTO and Tertiary Steel - AFC | 10 | 2026-12-11 | 2026-12-24 | 5 | PTTME Office 5dx8h
STJ-3190 | WPA02 Jacket Weight Control Report - IFR | 15 | 2026-08-24 | 2026-09-11 | 35 | PTTME Office 5dx8h
STJ-3200 | WPA02 Jacket Weight Control Report - IFA | 10 | 2026-09-28 | 2026-10-09 | 35 | PTTME Office 5dx8h
STJ-3210 | WPA02 Jacket Weight Control Report - AFC | 10 | 2026-10-28 | 2026-11-10 | 35 | PTTME Office 5dx8h
STJ-3220 | WPA02 Jacket Primary Steel MTO - IFR | 7 | 2026-06-02 | 2026-06-11 | 107 | PTTME Office 5dx8h
STJ-3230 | WPA02 Jacket Primary Steel MTO - IFA | 5 | 2026-06-26 | 2026-07-02 | 107 | PTTME Office 5dx8h
STJ-3240 | WPA02 Jacket Primary Steel MTO - AFC | 5 | 2026-07-17 | 2026-07-23 | 107 | PTTME Office 5dx8h
STJ-3250 | WPA02 Jacket Secondary MTO and Tertiary Steel - IFR | 15 | 2026-10-05 | 2026-10-27 | 5 | PTTME Office 5dx8h
STJ-3260 | WPA02 Jacket Secondary MTO and Tertiary Steel - IFA | 10 | 2026-11-11 | 2026-11-24 | 5 | PTTME Office 5dx8h
STJ-3270 | WPA02 Jacket Secondary MTO and Tertiary Steel - AFC | 10 | 2026-12-11 | 2026-12-24 | 5 | PTTME Office 5dx8h
STJ-3280 | Barge Motion Analysis Report - IFR | 19 | 2026-05-06 | 2026-06-02 | 112 | PTTME Office 5dx8h
STJ-3290 | Barge Motion Analysis Report - IFA | 10 | 2026-06-18 | 2026-07-01 | 112 | PTTME Office 5dx8h
STJ-3300 | Barge Motion Analysis Report - AFC | 10 | 2026-07-16 | 2026-08-03 | 112 | PTTME Office 5dx8h
PIPELINE&RISERENGINEERING |  | 128 | 2026-04-16 | 2026-10-22 | 56 | PTTME Office 5dx8h
RI-1000 | WPA01 Riser Clamp Design Report - IFR | 17 | 2026-04-16 | 2026-05-11 | 47 | PTTME Office 5dx8h
RI-1010 | WPA01 Riser Clamp Design Report - IFA | 10 | 2026-05-26 | 2026-06-10 | 118 | PTTME Office 5dx8h
RI-1020 | WPA01 Riser Clamp Design Report - AFC | 10 | 2026-06-25 | 2026-07-08 | 118 | PTTME Office 5dx8h
RI-1030 | WPA01 NPS 12 Hanger Flange Support Drawing - IFR | 15 | 2026-05-06 | 2026-05-26 | 47 | PTTME Office 5dx8h
RI-1040 | WPA01 NPS 12 Hanger Flange Support Drawing - IFA | 10 | 2026-06-12 | 2026-06-25 | 102 | PTTME Office 5dx8h
RI-1050 | WPA01 NPS 12 Hanger Flange Support Drawing - AFC | 10 | 2026-07-10 | 2026-07-23 | 102 | PTTME Office 5dx8h
RI-1060 | WPA01 NPS 12 Sliding Clamp Type 1 Drawing - IFR | 15 | 2026-05-06 | 2026-05-26 | 107 | PTTME Office 5dx8h
RI-1070 | WPA01 NPS 12 Sliding Clamp Type 1 Drawing - IFA | 10 | 2026-06-12 | 2026-06-25 | 107 | PTTME Office 5dx8h
RI-1080 | WPA01 NPS 12 Sliding Clamp Type 1 Drawing - AFC | 10 | 2026-07-10 | 2026-07-23 | 107 | PTTME Office 5dx8h
RI-1090 | WPA01 NPS 12 Sliding Clamp Type 2 Drawing - IFR | 15 | 2026-05-06 | 2026-05-26 | 107 | PTTME Office 5dx8h
RI-1100 | WPA01 NPS 12 Sliding Clamp Type 2 Drawing - IFA | 10 | 2026-06-12 | 2026-06-25 | 107 | PTTME Office 5dx8h
RI-1110 | WPA01 NPS 12 Sliding Clamp Type 2 Drawing - AFC | 10 | 2026-07-10 | 2026-07-23 | 107 | PTTME Office 5dx8h
RI-1120 | WPA01 NPS 12 Sliding Clamp Type 3 Drawing - IFR | 15 | 2026-05-06 | 2026-05-26 | 82 | PTTME Office 5dx8h
RI-1130 | WPA01 NPS 12 Sliding Clamp Type 3 Drawing - IFA | 10 | 2026-06-12 | 2026-06-25 | 107 | PTTME Office 5dx8h
RI-1140 | WPA01 NPS 12 Sliding Clamp Type 3 Drawing - AFC | 10 | 2026-07-10 | 2026-07-23 | 107 | PTTME Office 5dx8h
RI-1150 | WPA02 NPS 12 Hanger Flange Support Drawing - IFR | 16 | 2026-05-12 | 2026-06-04 | 47 | PTTME Office 5dx8h
RI-1160 | WPA02 NPS 12 Hanger Flange Support Drawing - IFA | 10 | 2026-06-19 | 2026-07-02 | 97 | PTTME Office 5dx8h
RI-1170 | WPA02 NPS 12 Hanger Flange Support Drawing - AFC | 10 | 2026-07-17 | 2026-08-04 | 97 | PTTME Office 5dx8h
RI-1180 | WPA02 NPS 12 Sliding Clamp Type 1 Drawing - IFR | 16 | 2026-05-12 | 2026-06-04 | 102 | PTTME Office 5dx8h
RI-1190 | WPA02 NPS 12 Sliding Clamp Type 1 Drawing - IFA | 10 | 2026-06-19 | 2026-07-02 | 102 | PTTME Office 5dx8h
RI-1200 | WPA02 NPS 12 Sliding Clamp Type 1 Drawing - AFC | 10 | 2026-07-17 | 2026-08-04 | 102 | PTTME Office 5dx8h
RI-1210 | WPA02 NPS 12 Sliding Clamp Type 2 Drawing - IFR | 16 | 2026-05-12 | 2026-06-04 | 102 | PTTME Office 5dx8h
RI-1220 | WPA02 NPS 12 Sliding Clamp Type 2 Drawing - IFA | 10 | 2026-06-19 | 2026-07-02 | 102 | PTTME Office 5dx8h
RI-1230 | WPA02 NPS 12 Sliding Clamp Type 2 Drawing - AFC | 10 | 2026-07-17 | 2026-08-04 | 102 | PTTME Office 5dx8h
RI-1240 | WPA02 NPS 12 Sliding Clamp Type 3 Drawing - IFR | 16 | 2026-05-12 | 2026-06-04 | 80 | PTTME Office 5dx8h
RI-1250 | WPA02 NPS 12 Sliding Clamp Type 3 Drawing - IFA | 10 | 2026-06-19 | 2026-07-02 | 102 | PTTME Office 5dx8h
RI-1260 | WPA02 NPS 12 Sliding Clamp Type 3 Drawing - AFC | 10 | 2026-07-17 | 2026-08-04 | 102 | PTTME Office 5dx8h
RI-1270 | WPA02 Riser Clamp Design Report - IFR | 20 | 2026-05-05 | 2026-06-02 | 47 | PTTME Office 5dx8h
RI-1280 | WPA02 Riser Clamp Design Report - IFA | 10 | 2026-06-18 | 2026-07-01 | 103 | PTTME Office 5dx8h
RI-1290 | WPA02 Riser Clamp Design Report - AFC | 10 | 2026-07-16 | 2026-08-03 | 103 | PTTME Office 5dx8h
RI-1300 | WPA02 NPS 20 Hanger Flange Support Drawing - IFR | 11 | 2026-05-20 | 2026-06-05 | 101 | PTTME Office 5dx8h
RI-1310 | WPA02 NPS 20 Hanger Flange Support Drawing - IFA | 10 | 2026-06-22 | 2026-07-03 | 110 | PTTME Office 5dx8h
RI-1320 | WPA02 NPS 20 Hanger Flange Support Drawing - AFC | 10 | 2026-07-20 | 2026-08-05 | 110 | PTTME Office 5dx8h
RI-1330 | WPA02 NPS 20 Sliding Clamp Type 1 Drawing - IFR | 11 | 2026-05-20 | 2026-06-05 | 110 | PTTME Office 5dx8h
RI-1340 | WPA02 NPS 20 Sliding Clamp Type 1 Drawing - IFA | 10 | 2026-06-22 | 2026-07-03 | 110 | PTTME Office 5dx8h
RI-1350 | WPA02 NPS 20 Sliding Clamp Type 1 Drawing - AFC | 10 | 2026-07-20 | 2026-08-05 | 110 | PTTME Office 5dx8h
RI-1360 | WPA02 NPS 20 Sliding Clamp Type 2 Drawing - IFR | 11 | 2026-05-20 | 2026-06-05 | 101 | PTTME Office 5dx8h
RI-1370 | WPA02 NPS 20 Sliding Clamp Type 2 Drawing - IFA | 10 | 2026-06-22 | 2026-07-03 | 101 | PTTME Office 5dx8h
RI-1380 | WPA02 NPS 20 Sliding Clamp Type 2 Drawing - AFC | 10 | 2026-07-20 | 2026-08-05 | 101 | PTTME Office 5dx8h
Datasheet-Pipeline&Riser |  | 50 | 2026-06-05 | 2026-08-19 | 92 | PTTME Office 5dx8h
A1000 | Datasheet for Pipeline Flanges - IFR | 10 | 2026-06-05 | 2026-06-18 | 47 | PTTME Office 5dx8h
A1010 | Datasheet for Pipeline Flanges - IFA | 5 | 2026-07-03 | 2026-07-09 | 102 | PTTME Office 5dx8h
A1020 | Datasheet for Pipeline Flanges - AFC | 5 | 2026-08-05 | 2026-08-11 | 97 | PTTME Office 5dx8h
A1030 | Datasheet for Barred Tee - IFR | 10 | 2026-06-19 | 2026-07-02 | 47 | PTTME Office 5dx8h
A1040 | Datasheet for Barred Tee - IFA | 5 | 2026-07-17 | 2026-07-23 | 92 | PTTME Office 5dx8h
A1050 | Datasheet for Barred Tee - AFC | 5 | 2026-08-13 | 2026-08-19 | 92 | PTTME Office 5dx8h
A1060 | Datasheet for Piggable Wye - IFR | 10 | 2026-06-19 | 2026-07-02 | 47 | PTTME Office 5dx8h
A1070 | Datasheet for Piggable Wye - IFA | 5 | 2026-07-17 | 2026-07-23 | 92 | PTTME Office 5dx8h
A1080 | Datasheet for Piggable Wye - AFC | 5 | 2026-08-13 | 2026-08-19 | 92 | PTTME Office 5dx8h
A1090 | Datasheet for Barrel Reducer - IFR | 10 | 2026-06-19 | 2026-07-02 | 47 | PTTME Office 5dx8h
A1100 | Datasheet for Barrel Reducer - IFA | 5 | 2026-07-17 | 2026-07-23 | 92 | PTTME Office 5dx8h
A1110 | Datasheet for Barrel Reducer - AFC | 5 | 2026-08-13 | 2026-08-19 | 92 | PTTME Office 5dx8h
MR-Pipeline&Riser |  | 85 | 2026-06-19 | 2026-10-22 | 47 | PTTME Office 5dx8h
A1120 | Material Requisition for Pipeline Flanges - IFR | 10 | 2026-06-19 | 2026-07-02 | 57 | PTTME Office 5dx8h
A1130 | Material Requisition for Pipeline Flanges - AFC | 5 | 2026-10-01 | 2026-10-07 | 57 | PTTME Office 5dx8h
A1140 | Material Requisition for Barred Tee - IFR | 10 | 2026-07-03 | 2026-07-16 | 47 | PTTME Office 5dx8h
A1150 | Material Requisition for Barred Tee - AFC | 5 | 2026-10-16 | 2026-10-22 | 47 | PTTME Office 5dx8h
A1160 | Material Requisition for Piggable Wye - IFR | 10 | 2026-07-03 | 2026-07-16 | 47 | PTTME Office 5dx8h
A1170 | Material Requisition for Piggable Wye - AFC | 5 | 2026-10-16 | 2026-10-22 | 47 | PTTME Office 5dx8h
A1180 | Material Requisition for Barrel Reducer - IFR | 10 | 2026-07-03 | 2026-07-16 | 47 | PTTME Office 5dx8h
A1190 | Material Requisition for Barrel Reducer - AFC | 5 | 2026-10-16 | 2026-10-22 | 47 | PTTME Office 5dx8h
TBE-Pipeline&Riser |  | 40 | 2026-08-05 | 2026-09-30 | 47 | PTTME Office 5dx8h
A1200 | Technical Bid Evaluation for Pipeline Flanges - IFR | 15 | 2026-08-05 | 2026-08-26 | 57 | PTTME Office 5dx8h
A1210 | Technical Bid Evaluation for Pipeline Flanges - AFC | 5 | 2026-09-10 | 2026-09-16 | 57 | PTTME Office 5dx8h
A1220 | Technical Bid Evaluation for Barred Tee - IFR | 15 | 2026-08-20 | 2026-09-09 | 47 | PTTME Office 5dx8h
A1230 | Technical Bid Evaluation for Barred Tee - AFC | 5 | 2026-09-24 | 2026-09-30 | 47 | PTTME Office 5dx8h
A1240 | Technical Bid Evaluation for Piggable Wye - IFR | 15 | 2026-08-20 | 2026-09-09 | 47 | PTTME Office 5dx8h
A1250 | Technical Bid Evaluation for Piggable Wye - AFC | 5 | 2026-09-24 | 2026-09-30 | 47 | PTTME Office 5dx8h
A1260 | Technical Bid Evaluation for Barrel Reducer - IFR | 15 | 2026-08-20 | 2026-09-09 | 47 | PTTME Office 5dx8h
A1270 | Technical Bid Evaluation for Barrel Reducer - AFC | 5 | 2026-09-24 | 2026-09-30 | 47 | PTTME Office 5dx8h
ELECTRICALENGINEERING |  | 151 | 2026-03-31 | 2026-11-13 | 32 | PTTME Office 5dx8h
EE-1000 | Electrical Basic of Design (offshore) - IFR | 10 | 2026-04-01 | 2026-04-20 | -45 | PTTME Office 5dx8h
EE-1010 | Electrical Basic of Design (offshore) - IFA | 5 | 2026-05-13 | 2026-05-19 | 33 | PTTME Office 5dx8h
EE-1020 | Electrical Basic of Design (offshore) - AFC | 5 | 2026-06-05 | 2026-06-11 | 33 | PTTME Office 5dx8h
EE-1030 | Electrical Load List & Load Analysis - WPA01 - IFR | 10 | 2026-04-08 | 2026-04-24 | 58 | PTTME Office 5dx8h
EE-1040 | Electrical Load List & Load Analysis - WPA01 - IFA | 10 | 2026-05-20 | 2026-06-04 | 82 | PTTME Office 5dx8h
EE-1050 | Electrical Load List & Load Analysis - WPA01 - AFC | 5 | 2026-06-19 | 2026-06-25 | 87 | PTTME Office 5dx8h
EE-1060 | Electrical Equipment Sizing Calculations - WPA01 - IFR | 10 | 2026-04-08 | 2026-04-24 | 83 | PTTME Office 5dx8h
EE-1070 | Electrical Equipment Sizing Calculations - WPA01 - IFA | 10 | 2026-05-20 | 2026-06-04 | 92 | PTTME Office 5dx8h
EE-1080 | Electrical Equipment Sizing Calculations - WPA01 - AFC | 5 | 2026-06-19 | 2026-06-25 | 97 | PTTME Office 5dx8h
EE-1090 | Electrical Cable Sizing Calculations - WPA01 - IFR | 15 | 2026-06-05 | 2026-06-25 | 32 | PTTME Office 5dx8h
EE-1100 | Electrical Cable Sizing Calculations - WPA01 - IFA | 10 | 2026-07-10 | 2026-07-23 | 67 | PTTME Office 5dx8h
EE-1110 | Electrical Cable Sizing Calculations - WPA01 - AFC | 5 | 2026-08-13 | 2026-08-19 | 87 | PTTME Office 5dx8h
EE-1120 | Electrical Cable Tray / Cable Ladder Sizing - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-1140 | Electrical Cable Tray / Cable Ladder Sizing - WPA01 - AFC | 5 | 2026-09-10 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-1150 | Electrical Cable Schedule - WPA01 - IFR | 15 | 2026-06-05 | 2026-06-25 | 72 | PTTME Office 5dx8h
EE-1160 | Electrical Cable Schedule - WPA01 - IFA | 10 | 2026-07-24 | 2026-08-11 | 67 | PTTME Office 5dx8h
EE-1170 | Electrical Cable Schedule - WPA01 - AFC | 5 | 2026-08-27 | 2026-09-02 | 72 | PTTME Office 5dx8h
EE-1180 | Illumination Calculations - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 42 | PTTME Office 5dx8h
EE-1190 | Illumination Calculations - WPA01 - IFA | 10 | 2026-08-05 | 2026-08-19 | 77 | PTTME Office 5dx8h
EE-1200 | Illumination Calculations - WPA01 - AFC | 5 | 2026-09-03 | 2026-09-09 | 77 | PTTME Office 5dx8h
EE-1210 | Electrical Equipment and Explosion Proof Equipment Schedule - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 42 | PTTME Office 5dx8h
EE-1220 | Electrical Equipment and Explosion Proof Equipment Schedule - WPA01 - IFA | 10 | 2026-08-05 | 2026-08-19 | 77 | PTTME Office 5dx8h
EE-1230 | Electrical Equipment and Explosion Proof Equipment Schedule - WPA01 - AFC | 5 | 2026-09-03 | 2026-09-09 | 77 | PTTME Office 5dx8h
EE-1240 | Electrical Power Generation Selection Report - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 57 | PTTME Office 5dx8h
EE-1250 | Electrical Power Generation Selection Report - WPA02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 62 | PTTME Office 5dx8h
EE-1260 | Electrical Power Generation Selection Report - WPA02 - AFC | 5 | 2026-09-03 | 2026-09-09 | 67 | PTTME Office 5dx8h
EE-1270 | Electrical Load List & Load Analysis - WPA02 - IFR | 10 | 2026-04-08 | 2026-04-24 | 58 | PTTME Office 5dx8h
EE-1280 | Electrical Load List & Load Analysis - WPA02 - IFA | 10 | 2026-05-20 | 2026-06-04 | 82 | PTTME Office 5dx8h
EE-1290 | Electrical Load List & Load Analysis - WPA02 - AFC | 5 | 2026-06-19 | 2026-06-25 | 97 | PTTME Office 5dx8h
EE-1300 | Electrical Equipment Sizing Calculations - WPA02 - IFR | 10 | 2026-04-08 | 2026-04-24 | 78 | PTTME Office 5dx8h
EE-1310 | Electrical Equipment Sizing Calculations - WPA02 - IFA | 10 | 2026-05-20 | 2026-06-04 | 102 | PTTME Office 5dx8h
EE-1320 | Electrical Equipment Sizing Calculations - WPA02 - AFC | 5 | 2026-06-19 | 2026-06-25 | 112 | PTTME Office 5dx8h
EE-1330 | Electrical Cable Sizing Calculations - WPA02 - IFR | 15 | 2026-06-05 | 2026-06-25 | 32 | PTTME Office 5dx8h
EE-1340 | Electrical Cable Sizing Calculations - WPA02 - IFA | 10 | 2026-07-10 | 2026-07-23 | 57 | PTTME Office 5dx8h
EE-1350 | Electrical Cable Sizing Calculations - WPA02 - AFC | 5 | 2026-08-13 | 2026-08-19 | 67 | PTTME Office 5dx8h
EE-1360 | Electrical Cable Tray / Cable Ladder Sizing - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 32 | PTTME Office 5dx8h
EE-1380 | Electrical Cable Tray / Cable Ladder Sizing - WPA02 - AFC | 5 | 2026-09-03 | 2026-09-09 | 57 | PTTME Office 5dx8h
EE-1390 | Electrical Cable Schedule - WPA02 - IFR | 15 | 2026-04-27 | 2026-05-18 | 58 | PTTME Office 5dx8h
EE-1400 | Electrical Cable Schedule - WPA02 - IFA | 10 | 2026-06-05 | 2026-06-18 | 82 | PTTME Office 5dx8h
EE-1410 | Electrical Cable Schedule - WPA02 - AFC | 5 | 2026-07-03 | 2026-07-09 | 92 | PTTME Office 5dx8h
EE-1420 | Illumination Calculations - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 77 | PTTME Office 5dx8h
EE-1430 | Illumination Calculations - WPA02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 77 | PTTME Office 5dx8h
EE-1440 | Illumination Calculations - WPA02 - AFC | 5 | 2026-09-03 | 2026-09-09 | 77 | PTTME Office 5dx8h
EE-1441 | Electrical Equipment and Explosion Proof Equipment Schedule - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 77 | PTTME Office 5dx8h
EE-1442 | Electrical Equipment and Explosion Proof Equipment Schedule - WPA01 - IFA | 10 | 2026-08-05 | 2026-08-19 | 77 | PTTME Office 5dx8h
EE-1443 | Electrical Equipment and Explosion Proof Equipment Schedule - WPA01 - AFC | 5 | 2026-09-03 | 2026-09-09 | 77 | PTTME Office 5dx8h
EE-1450 | Motor Starting Study - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 37 | PTTME Office 5dx8h
EE-1460 | Motor Starting Study - WPA02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 62 | PTTME Office 5dx8h
EE-1470 | Motor Starting Study - WPA02 - AFC | 5 | 2026-09-03 | 2026-09-09 | 67 | PTTME Office 5dx8h
EE-1480 | Project Particular Specification for AC and DC Distribution Boards/Panels - IFR | 15 | 2026-04-01 | 2026-04-27 | -45 | PTTME Office 5dx8h
EE-1490 | Project Particular Specification for AC and DC Distribution Boards/Panels - AFC | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
EE-1500 | Project Particular Specification for Solar power system - IFR | 15 | 2026-03-31 | 2026-04-24 | 0 | PTTME Office 5dx8h
EE-1510 | Project Particular Specification for Solar power system - AFC | 10 | 2026-05-27 | 2026-06-11 | 33 | PTTME Office 5dx8h
EE-1520 | Project Particular Specification for Navigation Aid system - IFR | 15 | 2026-04-01 | 2026-04-27 | -45 | PTTME Office 5dx8h
EE-1530 | Project Particular Specification for Navigation Aid system - AFC | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
EE-1540 | Project Particular Specification for External Battery Charger - IFR | 15 | 2026-04-01 | 2026-04-27 | -45 | PTTME Office 5dx8h
EE-1550 | Project Particular Specification for External Battery Charger - AFC | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
EE-1560 | Project Particular Specification for Electrical Cables - IFR | 15 | 2026-04-01 | 2026-04-27 | 87 | PTTME Office 5dx8h
EE-1570 | Project Particular Specification for Electrical Cables - AFC | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
EE-1580 | Project Particular Specification for Electrical Bulk Materials - IFR | 15 | 2026-04-01 | 2026-04-27 | 87 | PTTME Office 5dx8h
EE-1590 | Project Particular Specification for Electrical Bulk Materials - AFC | 10 | 2026-06-12 | 2026-06-25 | 112 | PTTME Office 5dx8h
EE-1595 | Project Particular Specification for FOG HORN - IFR | 15 | 2026-04-01 | 2026-04-27 | 147 | PTTME Office 5dx8h
EE-1596 | Project Particular Specification for FOG HORN - AFC | 10 | 2026-06-12 | 2026-06-25 | 127 | PTTME Office 5dx8h
EE-1600 | Project Particular Specification for AC Generator - IFR | 15 | 2026-04-01 | 2026-04-27 | 112 | PTTME Office 5dx8h
EE-1610 | Project Particular Specification for AC Generator - AFC | 10 | 2026-06-12 | 2026-06-25 | 117 | PTTME Office 5dx8h
EE-1620 | Project Particular Specification for Motor Control Center - IFR | 15 | 2026-04-01 | 2026-04-27 | 92 | PTTME Office 5dx8h
EE-1630 | Project Particular Specification for Motor Control Center - AFC | 10 | 2026-06-12 | 2026-06-25 | 117 | PTTME Office 5dx8h
EE-1640 | Project Particular Specification for Induction Motor - IFR | 15 | 2026-04-01 | 2026-04-27 | 147 | PTTME Office 5dx8h
EE-1650 | Project Particular Specification for Induction Motor - AFC | 10 | 2026-06-12 | 2026-06-25 | 127 | PTTME Office 5dx8h
EE-2110 | Electrical Symbols and Legends - IFR | 15 | 2026-04-01 | 2026-04-27 | 112 | PTTME Office 5dx8h
EE-2130 | Electrical Symbols and Legends - AFC | 5 | 2026-06-12 | 2026-06-18 | 122 | PTTME Office 5dx8h
EE-2140 | Electrical Typical Installation Details - Lighting and Small Power (3 Sheets) - IFR | 15 | 2026-04-21 | 2026-05-12 | 137 | PTTME Office 5dx8h
EE-2150 | Electrical Typical Installation Details - Lighting and Small Power (3 Sheets) - AFC | 10 | 2026-05-27 | 2026-06-11 | 137 | PTTME Office 5dx8h
EE-2160 | Electrical Typical Installation Details - Earthing (5 Sheets) - IFR | 15 | 2026-04-21 | 2026-05-12 | 137 | PTTME Office 5dx8h
EE-2170 | Electrical Typical Installation Details - Earthing (5 Sheets) - AFC | 10 | 2026-05-27 | 2026-06-11 | 137 | PTTME Office 5dx8h
EE-2180 | Electrical Typical Installation Details - Cable Ladder/ Tray (3 Sheets) - IFR | 15 | 2026-04-21 | 2026-05-12 | 137 | PTTME Office 5dx8h
EE-2190 | Electrical Typical Installation Details - Cable Ladder/ Tray (3 Sheets) - AFC | 10 | 2026-05-27 | 2026-06-11 | 137 | PTTME Office 5dx8h
EE-2200 | Electrical Typical Installation Details - Navigation Aid System (2 Sheets) - IFR | 15 | 2026-04-21 | 2026-05-12 | 137 | PTTME Office 5dx8h
EE-2210 | Electrical Typical Installation Details - Navigation Aid System (2 Sheets) - AFC | 10 | 2026-05-27 | 2026-06-11 | 137 | PTTME Office 5dx8h
EE-2220 | Electrical Typical Installation Details - Power (3 Sheets) - IFR | 15 | 2026-04-21 | 2026-05-12 | 137 | PTTME Office 5dx8h
EE-2230 | Electrical Typical Installation Details - Power (3 Sheets) - AFC | 10 | 2026-05-27 | 2026-06-11 | 137 | PTTME Office 5dx8h
EE-2240 | Electrical Typical Installation Details - Solar Panel - IFR | 15 | 2026-04-01 | 2026-04-27 | 147 | PTTME Office 5dx8h
EE-2250 | Electrical Typical Installation Details - Solar Panel - AFC | 10 | 2026-05-13 | 2026-05-26 | 147 | PTTME Office 5dx8h
EE-2260 | Electrical Drawing Index - WPA01 - IFR | 15 | 2026-04-28 | 2026-05-19 | 112 | PTTME Office 5dx8h
EE-2280 | Electrical Drawing Index - WPA01 - AFC | 10 | 2026-07-03 | 2026-07-16 | 112 | PTTME Office 5dx8h
EE-2290 | Electrical Power & Control System Block Diagram - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2300 | Electrical Power & Control System Block Diagram - WPA01 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-2310 | Electrical Power & Control System Block Diagram - WPA01 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-2320 | Equipment Location Plan - WPA01 (3 Sheets) - IFR | 15 | 2026-06-26 | 2026-07-16 | 42 | PTTME Office 5dx8h
EE-2340 | Equipment Location Plan - WPA01 (3 Sheets) - AFC | 10 | 2026-09-03 | 2026-09-16 | 52 | PTTME Office 5dx8h
EE-2350 | Solar Panel Layout - WPA01 - IFR | 15 | 2026-05-06 | 2026-05-26 | 92 | PTTME Office 5dx8h
EE-2360 | Solar Panel Layout - WPA01 - IFA | 10 | 2026-07-10 | 2026-07-23 | 77 | PTTME Office 5dx8h
EE-2370 | Solar Panel Layout - WPA01 - AFC | 10 | 2026-09-10 | 2026-09-23 | 57 | PTTME Office 5dx8h
EE-2380 | E&I Room Equipment Layout - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 42 | PTTME Office 5dx8h
EE-2390 | E&I Room Equipment Layout - WPA01 - IFA | 10 | 2026-08-13 | 2026-08-26 | 47 | PTTME Office 5dx8h
EE-2400 | E&I Room Equipment Layout - WPA01 - AFC | 10 | 2026-09-10 | 2026-09-23 | 47 | PTTME Office 5dx8h
EE-2410 | Electrical Multi Cable Transit Schedule- WPA01 (6 Sheets) - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2430 | Electrical Multi Cable Transit Schedule- WPA01 (6 Sheets) - AFC | 10 | 2026-09-10 | 2026-09-23 | 67 | PTTME Office 5dx8h
EE-2440 | Electrical Overall Earthing and Bonding Diagrams- WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2450 | Electrical Overall Earthing and Bonding Diagrams- WPA01 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-2460 | Electrical Overall Earthing and Bonding Diagrams- WPA01 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-2470 | Cable Trays/Ladders Layout Drawings - WPA01(4 Sheets) - IFR | 15 | 2026-07-17 | 2026-08-11 | 42 | PTTME Office 5dx8h
EE-2490 | Cable Trays/Ladders Layout Drawings - WPA01(4 Sheets) - AFC | 10 | 2026-09-24 | 2026-10-07 | 47 | PTTME Office 5dx8h
EE-2491 | Cables Routing Plan/Layout Drawings - WPA01(4 Sheets) - IFR | 15 | 2026-07-17 | 2026-08-11 | 57 | PTTME Office 5dx8h
EE-2495 | Cables Routing Plan/Layout Drawings - WPA01(4 Sheets) - AFC | 10 | 2026-09-24 | 2026-10-07 | 57 | PTTME Office 5dx8h
EE-2500 | Electrical Bulk Materials Take Off - WPA01 - IFR | 15 | 2026-08-13 | 2026-09-02 | 42 | PTTME Office 5dx8h
EE-2510 | Electrical Bulk Materials Take Off - WPA01 - IFA | 10 | 2026-09-17 | 2026-09-30 | 42 | PTTME Office 5dx8h
EE-2520 | Electrical Bulk Materials Take Off - WPA01 - AFC | 10 | 2026-10-16 | 2026-10-30 | 42 | PTTME Office 5dx8h
EE-2530 | Electrical AC Distribution Board Schedule - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2540 | Electrical AC Distribution Board Schedule - WPA01 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-2550 | Electrical AC Distribution Board Schedule - WPA01 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-2551 | Electrical DC Distribution Board Schedule - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2553 | Electrical DC Distribution Board Schedule - WPA01 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-2556 | Electrical DC Distribution Board Schedule - WPA01 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-2560 | Electrical I/O summary - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2570 | Electrical I/O summary - WPA01 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-2580 | Electrical I/O summary - WPA01 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-2590 | Lighting and Small Power Loop Diagram - WPA01 (3 Sheets) - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2610 | Lighting and Small Power Loop Diagram - WPA01 (3 Sheets) - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-2620 | Lighting and Small Power Plan - WPA01 Mezzanine Deck - IFR | 15 | 2026-07-17 | 2026-08-11 | 42 | PTTME Office 5dx8h
EE-2640 | Lighting and Small Power Plan - WPA01 Mezzanine Deck - AFC | 10 | 2026-09-24 | 2026-10-07 | 47 | PTTME Office 5dx8h
EE-2650 | Lighting and Small Power Plan - WPA01 Lower Deck - IFR | 15 | 2026-07-17 | 2026-08-11 | 42 | PTTME Office 5dx8h
EE-2670 | Lighting and Small Power Plan - WPA01 Lower Deck - AFC | 10 | 2026-09-24 | 2026-10-07 | 47 | PTTME Office 5dx8h
EE-2680 | Lighting and Small Power Plan - WPA01 Sump Deck and Boat Landing - IFR | 15 | 2026-07-17 | 2026-08-11 | 42 | PTTME Office 5dx8h
EE-2700 | Lighting and Small Power Plan - WPA01 Sump Deck and Boat Landing - AFC | 10 | 2026-09-24 | 2026-10-07 | 47 | PTTME Office 5dx8h
EE-2710 | Electrical Drawing Index - WPA02 - IFR | 15 | 2026-04-28 | 2026-05-19 | 112 | PTTME Office 5dx8h
EE-2730 | Electrical Drawing Index - WPA02 - AFC | 10 | 2026-07-03 | 2026-07-16 | 112 | PTTME Office 5dx8h
EE-2740 | Electrical Power & Control System Block Diagram - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2750 | Electrical Power & Control System Block Diagram - WPA02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-2760 | Electrical Power & Control System Block Diagram - WPA02 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-2770 | Equipment Location Plan - WPA02 (3 Sheets) - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2780 | Equipment Location Plan - WPA02 (3 Sheets) - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-2790 | Equipment Location Plan - WPA02 (3 Sheets) - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-2800 | Solar Panel Layout - WPA02 - IFR | 15 | 2026-05-06 | 2026-05-26 | 107 | PTTME Office 5dx8h
EE-2810 | Solar Panel Layout - WPA02 - IFA | 10 | 2026-07-10 | 2026-07-23 | 87 | PTTME Office 5dx8h
EE-2820 | Solar Panel Layout - WPA02 - AFC | 10 | 2026-09-10 | 2026-09-23 | 67 | PTTME Office 5dx8h
EE-2830 | E&I Room Equipment Layout - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2840 | E&I Room Equipment Layout - WPA02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-2850 | E&I Room Equipment Layout - WPA02 - AFC | 10 | 2026-09-10 | 2026-09-23 | 67 | PTTME Office 5dx8h
EE-2860 | Electrical Multi Cable Transit Schedule - WPA02 (6 Sheets) - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2880 | Electrical Multi Cable Transit Schedule - WPA02 (6 Sheets) - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-2890 | Electrical Overall Earthing and Bonding Diagrams - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-2900 | Electrical Overall Earthing and Bonding Diagrams - WPA02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-2910 | Electrical Overall Earthing and Bonding Diagrams - WPA02 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-2920 | Cable Trays/Ladders Layout Drawings - WPA02 (4 Sheets) - IFR | 15 | 2026-07-17 | 2026-08-11 | 57 | PTTME Office 5dx8h
EE-2940 | Cable Trays/Ladders Layout Drawings - WPA02 (4 Sheets) - AFC | 10 | 2026-09-24 | 2026-10-07 | 57 | PTTME Office 5dx8h
EE-2950 | Cables Routing Plan/Layout Drawings - WPA02 (4 Sheets) - IFR | 15 | 2026-07-17 | 2026-08-11 | 57 | PTTME Office 5dx8h
EE-2970 | Cables Routing Plan/Layout Drawings - WPA02 (4 Sheets) - AFC | 10 | 2026-09-24 | 2026-10-07 | 57 | PTTME Office 5dx8h
EE-2980 | Electrical Bulk Materials Take Off - WPA02 - IFR | 15 | 2026-08-13 | 2026-09-02 | 42 | PTTME Office 5dx8h
EE-2990 | Electrical Bulk Materials Take Off - WPA02 - IFA | 10 | 2026-09-17 | 2026-09-30 | 42 | PTTME Office 5dx8h
EE-3000 | Electrical Bulk Materials Take Off - WPA02 - AFC | 10 | 2026-10-16 | 2026-10-30 | 42 | PTTME Office 5dx8h
EE-3010 | Electrical AC Distribution Board Schedule - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-3020 | Electrical AC Distribution Board Schedule - WPA02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-3030 | Electrical AC Distribution Board Schedule - WPA02 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-3031 | Electrical DC Distribution Board Schedule - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-3033 | Electrical DC Distribution Board Schedule - WPA02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-3035 | Electrical DC Distribution Board Schedule - WPA02 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-3040 | Electrical I/O summary - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-3060 | Electrical I/O summary - WPA02 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-3070 | Lighting and Small Power Loop Diagram - WPA02 (3 Sheets) - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-3090 | Lighting and Small Power Loop Diagram - WPA02 (3 Sheets) - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-3100 | Lighting and Small Power Plan - WPA02 Mezzanine Deck - IFR | 15 | 2026-07-17 | 2026-08-11 | 57 | PTTME Office 5dx8h
EE-3120 | Lighting and Small Power Plan - WPA02 Mezzanine Deck - AFC | 10 | 2026-09-24 | 2026-10-07 | 57 | PTTME Office 5dx8h
EE-3130 | Lighting and Small Power Plan - WPA02 Lower Deck - IFR | 15 | 2026-07-17 | 2026-08-11 | 57 | PTTME Office 5dx8h
EE-3150 | Lighting and Small Power Plan - WPA02 Lower Deck - AFC | 10 | 2026-09-24 | 2026-10-07 | 57 | PTTME Office 5dx8h
EE-3160 | Lighting and Small Power Plan - WPA02 Sump Deck and Boat Landing - IFR | 15 | 2026-07-17 | 2026-08-11 | 57 | PTTME Office 5dx8h
EE-3180 | Lighting and Small Power Plan - WPA02 Sump Deck and Boat Landing - AFC | 10 | 2026-09-24 | 2026-10-07 | 57 | PTTME Office 5dx8h
EE-3190 | Electrical Key Single Line Diagram - WPA01 - IFR | 15 | 2026-06-05 | 2026-06-25 | 72 | PTTME Office 5dx8h
EE-3200 | Electrical Key Single Line Diagram - WPA01 - IFA | 10 | 2026-07-10 | 2026-07-23 | 77 | PTTME Office 5dx8h
EE-3210 | Electrical Key Single Line Diagram - WPA01 - AFC | 10 | 2026-08-13 | 2026-08-26 | 77 | PTTME Office 5dx8h
EE-3220 | Electrical Single Line Diagram - AC System- WPA01 - IFR | 15 | 2026-06-05 | 2026-06-25 | 72 | PTTME Office 5dx8h
EE-3230 | Electrical Single Line Diagram - AC System- WPA01 - IFA | 10 | 2026-07-10 | 2026-07-23 | 77 | PTTME Office 5dx8h
EE-3240 | Electrical Single Line Diagram - AC System- WPA01 - AFC | 10 | 2026-08-13 | 2026-08-26 | 77 | PTTME Office 5dx8h
EE-3250 | Electrical Single Line Diagram - DC System & Navigation Aids System -WPA01 - IFR | 15 | 2026-06-05 | 2026-06-25 | 72 | PTTME Office 5dx8h
EE-3260 | Electrical Single Line Diagram - DC System & Navigation Aids System -WPA01 - IFA | 10 | 2026-07-10 | 2026-07-23 | 77 | PTTME Office 5dx8h
EE-3270 | Electrical Single Line Diagram - DC System & Navigation Aids System -WPA01 - AFC | 10 | 2026-08-13 | 2026-08-26 | 77 | PTTME Office 5dx8h
EE-3280 | Electrical Wiring Interconnection for AC and Distribution System - WPA01 (2 Sheets) - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-3290 | Electrical Wiring Interconnection for AC and Distribution System - WPA01 (2 Sheets) - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-3300 | Electrical Wiring Interconnection for AC and Distribution System - WPA01 (2 Sheets) - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-3310 | Electrical Wiring Interconnection for DC Distribution System - WPA01 (2 Sheets) - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-3320 | Electrical Wiring Interconnection for DC Distribution System - WPA01 (2 Sheets) - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-3330 | Electrical Wiring Interconnection for DC Distribution System - WPA01 (2 Sheets) - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-3340 | Electrical Wiring Interconnection for Navigation Aid System - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-3350 | Electrical Wiring Interconnection for Navigation Aid System - WPA01 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-3360 | Electrical Wiring Interconnection for Navigation Aid System - WPA01 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-3370 | Electrical Key Single Line Diagram - WPA02 - IFR | 15 | 2026-06-05 | 2026-06-25 | 87 | PTTME Office 5dx8h
EE-3380 | Electrical Key Single Line Diagram - WPA02 - IFA | 10 | 2026-07-10 | 2026-07-23 | 87 | PTTME Office 5dx8h
EE-3390 | Electrical Key Single Line Diagram - WPA02 - AFC | 10 | 2026-08-13 | 2026-08-26 | 87 | PTTME Office 5dx8h
EE-3400 | Electrical Single Line Diagram - AC System - WPA02 - IFR | 15 | 2026-06-05 | 2026-06-25 | 87 | PTTME Office 5dx8h
EE-3410 | Electrical Single Line Diagram - AC System - WPA02 - IFA | 10 | 2026-07-10 | 2026-07-23 | 87 | PTTME Office 5dx8h
EE-3420 | Electrical Single Line Diagram - AC System - WPA02 - AFC | 10 | 2026-08-13 | 2026-08-26 | 87 | PTTME Office 5dx8h
EE-3430 | Electrical Single Line Diagram - DC System & Navigation Aids System - WPA02 - IFR | 15 | 2026-06-05 | 2026-06-25 | 87 | PTTME Office 5dx8h
EE-3440 | Electrical Single Line Diagram - DC System & Navigation Aids System - WPA02 - IFA | 10 | 2026-07-10 | 2026-07-23 | 87 | PTTME Office 5dx8h
EE-3450 | Electrical Single Line Diagram - DC System & Navigation Aids System - WPA02 - AFC | 10 | 2026-08-13 | 2026-08-26 | 87 | PTTME Office 5dx8h
EE-3460 | Electrical Wiring Interconnection for AC and Distribution System - WPA02 (2 Sheets) - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-3470 | Electrical Wiring Interconnection for AC and Distribution System - WPA02 (2 Sheets) - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-3480 | Electrical Wiring Interconnection for AC and Distribution System - WPA02 (2 Sheets) - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-3490 | Electrical Wiring Interconnection for DC Distribution System - WPA02 (2 Sheets) - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-3500 | Electrical Wiring Interconnection for DC Distribution System - WPA02 (2 Sheets) - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-3510 | Electrical Wiring Interconnection for DC Distribution System - WPA02 (2 Sheets) - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
EE-3520 | Electrical Wiring Interconnection for Navigation Aid System - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
EE-3530 | Electrical Wiring Interconnection for Navigation Aid System - WPA02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
EE-3540 | Electrical Wiring Interconnection for Navigation Aid System - WPA02 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
Datasheet-Electrical |  | 126 | 2026-03-31 | 2026-10-07 | 57 | PTTME Office 5dx8h
EE-1660 | Datasheet for AC and DC Distribution Boards/Panels - WPA01 - IFR | 15 | 2026-05-06 | 2026-05-26 | 36 | PTTME Office 5dx8h
EE-1670 | Datasheet for AC and DC Distribution Boards/Panels - WPA01 - IFA | 10 | 2026-06-12 | 2026-06-25 | 102 | PTTME Office 5dx8h
EE-1680 | Datasheet for AC and DC Distribution Boards/Panels - WPA01 - AFC | 10 | 2026-07-10 | 2026-07-23 | 102 | PTTME Office 5dx8h
EE-1690 | Datasheet for Solar power system - WPA01 - IFR | 15 | 2026-03-31 | 2026-04-24 | 0 | PTTME Office 5dx8h
EE-1700 | Datasheet for Solar power system - WPA01 - IFA | 10 | 2026-05-12 | 2026-05-25 | 34 | PTTME Office 5dx8h
EE-1710 | Datasheet for Solar power system - WPA01 - AFC | 10 | 2026-06-12 | 2026-06-25 | 33 | PTTME Office 5dx8h
EE-1720 | Datasheet for Navigation Aid system - WPA01 - IFR | 15 | 2026-05-06 | 2026-05-26 | 36 | PTTME Office 5dx8h
EE-1730 | Datasheet for Navigation Aid system - WPA01 - IFA | 10 | 2026-06-12 | 2026-06-25 | 102 | PTTME Office 5dx8h
EE-1740 | Datasheet for Navigation Aid system - WPA01 - AFC | 10 | 2026-07-10 | 2026-07-23 | 102 | PTTME Office 5dx8h
EE-1750 | Datasheet for External Battery Charger - WPA01 - IFR | 10 | 2026-04-20 | 2026-05-04 | -45 | PTTME Office 5dx8h
EE-1760 | Datasheet for External Battery Charger - WPA01 - IFA | 10 | 2026-05-19 | 2026-06-02 | 123 | PTTME Office 5dx8h
EE-1770 | Datasheet for External Battery Charger - WPA01 - AFC | 5 | 2026-06-26 | 2026-07-02 | 117 | PTTME Office 5dx8h
EE-1780 | Datasheet for Electrical Cables - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 47 | PTTME Office 5dx8h
EE-1800 | Datasheet for Electrical Cables - WPA01 - AFC | 10 | 2026-09-03 | 2026-09-16 | 67 | PTTME Office 5dx8h
EE-1810 | Datasheet for Electrical Bulk Materials - WPA01 - IFR | 15 | 2026-07-17 | 2026-08-11 | 32 | PTTME Office 5dx8h
EE-1830 | Datasheet for Electrical Bulk Materials - WPA01 - AFC | 10 | 2026-09-24 | 2026-10-07 | 52 | PTTME Office 5dx8h
EE-1833 | Datasheet for FOG HORN - WPA01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 47 | PTTME Office 5dx8h
EE-1835 | Datasheet for FOG HORN - WPA01 - IFA | 10 | 2026-08-05 | 2026-08-19 | 67 | PTTME Office 5dx8h
EE-1837 | Datasheet for FOG HORN - WPA01 - AFC | 10 | 2026-09-03 | 2026-09-16 | 67 | PTTME Office 5dx8h
EE-1840 | Datasheet for AC and DC Distribution Boards/Panels - WPA02 - IFR | 15 | 2026-05-06 | 2026-05-26 | 63 | PTTME Office 5dx8h
EE-1850 | Datasheet for AC and DC Distribution Boards/Panels - WPA02 - IFA | 10 | 2026-06-12 | 2026-06-25 | 102 | PTTME Office 5dx8h
EE-1860 | Datasheet for AC and DC Distribution Boards/Panels - WPA02 - AFC | 10 | 2026-07-10 | 2026-07-23 | 102 | PTTME Office 5dx8h
EE-1870 | Datasheet for Solar power system - WPA02 - IFR | 15 | 2026-03-31 | 2026-04-24 | 89 | PTTME Office 5dx8h
EE-1880 | Datasheet for Solar power system - WPA02 - IFA | 10 | 2026-05-12 | 2026-05-25 | 123 | PTTME Office 5dx8h
EE-1890 | Datasheet for Solar power system - WPA02 - AFC | 10 | 2026-06-11 | 2026-06-24 | 123 | PTTME Office 5dx8h
EE-1900 | Datasheet for Navigation Aid system - WPA02 - IFR | 15 | 2026-05-06 | 2026-05-26 | 36 | PTTME Office 5dx8h
EE-1910 | Datasheet for Navigation Aid system - WPA02 - IFA | 10 | 2026-06-12 | 2026-06-25 | 102 | PTTME Office 5dx8h
EE-1920 | Datasheet for Navigation Aid system - WPA02 - AFC | 10 | 2026-07-10 | 2026-07-23 | 102 | PTTME Office 5dx8h
EE-1930 | Datasheet for External Battery Charger - WPA02 - IFR | 10 | 2026-04-20 | 2026-05-04 | -45 | PTTME Office 5dx8h
EE-1940 | Datasheet for External Battery Charger - WPA02 - IFA | 10 | 2026-05-19 | 2026-06-02 | 6 | PTTME Office 5dx8h
EE-1950 | Datasheet for External Battery Charger - WPA02 - AFC | 10 | 2026-06-18 | 2026-07-01 | 6 | PTTME Office 5dx8h
EE-1960 | Datasheet for Electrical Cables - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 47 | PTTME Office 5dx8h
EE-1980 | Datasheet for Electrical Cables - WPA02 - AFC | 10 | 2026-09-03 | 2026-09-16 | 67 | PTTME Office 5dx8h
EE-1990 | Datasheet for Electrical Bulk Materials - WPA02 - IFR | 15 | 2026-07-17 | 2026-08-11 | 32 | PTTME Office 5dx8h
EE-2010 | Datasheet for Electrical Bulk Materials - WPA02 - AFC | 10 | 2026-09-24 | 2026-10-07 | 52 | PTTME Office 5dx8h
EE-2020 | Datasheet for AC Generator - WPA02 - IFR | 15 | 2026-07-17 | 2026-08-11 | 57 | PTTME Office 5dx8h
EE-2030 | Datasheet for AC Generator - WPA02 - IFA | 10 | 2026-08-27 | 2026-09-09 | 57 | PTTME Office 5dx8h
EE-2040 | Datasheet for AC Generator - WPA02 - AFC | 10 | 2026-09-24 | 2026-10-07 | 57 | PTTME Office 5dx8h
EE-2050 | Datasheet for Motor Control Center - WPA02 - IFR | 15 | 2026-07-17 | 2026-08-11 | 37 | PTTME Office 5dx8h
EE-2060 | Datasheet for Motor Control Center - WPA02 - IFA | 10 | 2026-08-27 | 2026-09-09 | 57 | PTTME Office 5dx8h
EE-2070 | Datasheet for Motor Control Center - WPA02 - AFC | 10 | 2026-09-24 | 2026-10-07 | 57 | PTTME Office 5dx8h
EE-2080 | Datasheet for Induction Motor - WPA02 - IFR | 15 | 2026-07-17 | 2026-08-11 | 57 | PTTME Office 5dx8h
EE-2090 | Datasheet for Induction Motor - WPA02 - IFA | 10 | 2026-08-27 | 2026-09-09 | 57 | PTTME Office 5dx8h
EE-2100 | Datasheet for Induction Motor - WPA02 - AFC | 10 | 2026-09-24 | 2026-10-07 | 57 | PTTME Office 5dx8h
EE-4042 | Datasheet for FOG HORN - WPA02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 47 | PTTME Office 5dx8h
EE-4044 | Datasheet for FOG HORN - WPA02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 67 | PTTME Office 5dx8h
EE-4046 | Datasheet for FOG HORN - WPA02 - AFC | 10 | 2026-09-03 | 2026-09-16 | 67 | PTTME Office 5dx8h
MR-Electrical |  | 133 | 2026-04-30 | 2026-11-13 | 32 | PTTME Office 5dx8h
EE-3550 | Material Requisition for AC & DC Distribution Boards/Panels - WPA01 - IFR | 15 | 2026-06-08 | 2026-06-26 | 63 | PTTME Office 5dx8h
EE-3560 | Material Requisition for AC & DC Distribution Boards/Panels - WPA01 - AFC | 5 | 2026-09-23 | 2026-09-29 | 63 | PTTME Office 5dx8h
EE-3570 | Material Requisition for Solar power system - WPA01 - IFR | 15 | 2026-04-30 | 2026-05-21 | 0 | PTTME Office 5dx8h
EE-3580 | Material Requisition for Solar power system - WPA01 - AFC | 5 | 2026-08-18 | 2026-08-24 | 0 | PTTME Office 5dx8h
EE-3590 | Material Requisition for Navigation Aid system - WPA01 - IFR | 15 | 2026-07-10 | 2026-08-04 | 36 | PTTME Office 5dx8h
EE-3600 | Material Requisition for Navigation Aid system - WPA01 - AFC | 5 | 2026-11-03 | 2026-11-09 | 36 | PTTME Office 5dx8h
EE-3610 | Material Requisition for External Battery Charger - WPA01 - IFR | 15 | 2026-05-26 | 2026-06-17 | 67 | PTTME Office 5dx8h
EE-3620 | Material Requisition for External Battery Charger - WPA01 - AFC | 5 | 2026-09-17 | 2026-09-23 | 67 | PTTME Office 5dx8h
EE-3630 | Material Requisition for Electrical Cables - WPA01 - IFR | 10 | 2026-07-17 | 2026-08-04 | 47 | PTTME Office 5dx8h
EE-3640 | Material Requisition for Electrical Cables - WPA01 - AFC | 5 | 2026-10-16 | 2026-10-22 | 47 | PTTME Office 5dx8h
EE-3650 | Material Requisition for Electrical Bulk Materials - WPA01 - IFR | 10 | 2026-08-13 | 2026-08-26 | 32 | PTTME Office 5dx8h
EE-3660 | Material Requisition for Electrical Bulk Materials - WPA01 - AFC | 5 | 2026-11-09 | 2026-11-13 | 32 | PTTME Office 5dx8h
EE-3661 | Material Requisition for FOG HORN - WPA01 - IFR | 10 | 2026-07-17 | 2026-08-04 | 47 | PTTME Office 5dx8h
EE-3665 | Material Requisition for FOG HORN - WPA01 - AFC | 5 | 2026-10-16 | 2026-10-22 | 47 | PTTME Office 5dx8h
EE-3670 | Material Requisition for AC & DC Distribution Boards/Panels - WPA02 - IFR | 15 | 2026-06-08 | 2026-06-26 | 63 | PTTME Office 5dx8h
EE-3680 | Material Requisition for AC & DC Distribution Boards/Panels - WPA02 - AFC | 5 | 2026-09-23 | 2026-09-29 | 63 | PTTME Office 5dx8h
EE-3690 | Material Requisition for Solar power system - WPA02 - IFR | 15 | 2026-04-30 | 2026-05-21 | 89 | PTTME Office 5dx8h
EE-3700 | Material Requisition for Solar power system - WPA02 - AFC | 5 | 2026-08-18 | 2026-08-24 | 89 | PTTME Office 5dx8h
EE-3710 | Material Requisition for Navigation Aid system - WPA02 - IFR | 15 | 2026-07-10 | 2026-08-04 | 36 | PTTME Office 5dx8h
EE-3720 | Material Requisition for Navigation Aid system - WPA02 - AFC | 5 | 2026-11-03 | 2026-11-09 | 36 | PTTME Office 5dx8h
EE-3730 | Material Requisition for External Battery Charger - WPA02 - IFR | 15 | 2026-05-26 | 2026-06-17 | -45 | PTTME Office 5dx8h
EE-3740 | Material Requisition for External Battery Charger - WPA02 - AFC | 5 | 2026-09-17 | 2026-09-23 | -45 | PTTME Office 5dx8h
EE-3750 | Material Requisition for Electrical Cables - WPA02 - IFR | 10 | 2026-07-17 | 2026-08-04 | 47 | PTTME Office 5dx8h
EE-3760 | Material Requisition for Electrical Cables - WPA02 - AFC | 5 | 2026-10-16 | 2026-10-22 | 47 | PTTME Office 5dx8h
EE-3770 | Material Requisition for Electrical Bulk Materials - WPA02 - IFR | 10 | 2026-08-13 | 2026-08-26 | 32 | PTTME Office 5dx8h
EE-3780 | Material Requisition for Electrical Bulk Materials - WPA02 - AFC | 5 | 2026-11-09 | 2026-11-13 | 32 | PTTME Office 5dx8h
EE-4048 | Material Requisition for FOG HORN - WPA02 - IFR | 10 | 2026-07-17 | 2026-08-04 | 47 | PTTME Office 5dx8h
EE-4050 | Material Requisition for FOG HORN - WPA02 - AFC | 5 | 2026-10-16 | 2026-10-22 | 47 | PTTME Office 5dx8h
EE-4056 | Material Requisition for Motor Control Center - WPA02 - IFR | 10 | 2026-07-24 | 2026-08-11 | 82 | PTTME Office 5dx8h
EE-4058 | Material Requisition for Motor Control Center - WPA02 - AFC | 5 | 2026-11-02 | 2026-11-06 | 37 | PTTME Office 5dx8h
TBE-Electrical |  | 92 | 2026-06-10 | 2026-10-22 | 32 | PTTME Office 5dx8h
EE-3790 | Technical Bid Evaluation for AC & DC Distribution Boards/Panels - WPA01 - IFR | 16 | 2026-07-22 | 2026-08-18 | 63 | PTTME Office 5dx8h
EE-3800 | Technical Bid Evaluation for AC & DC Distribution Boards/Panels - WPA01 - AFC | 5 | 2026-09-02 | 2026-09-08 | 63 | PTTME Office 5dx8h
EE-3810 | Technical Bid Evaluation for Solar power system - WPA01 - IFR | 20 | 2026-06-10 | 2026-07-07 | 0 | PTTME Office 5dx8h
EE-3820 | Technical Bid Evaluation for Solar power system - WPA01 - AFC | 5 | 2026-07-22 | 2026-07-31 | 0 | PTTME Office 5dx8h
EE-3830 | Technical Bid Evaluation for Navigation Aid system - WPA01 - IFR | 20 | 2026-08-28 | 2026-09-24 | 36 | PTTME Office 5dx8h
EE-3840 | Technical Bid Evaluation for Navigation Aid system - WPA01 - AFC | 5 | 2026-10-09 | 2026-10-16 | 36 | PTTME Office 5dx8h
EE-3850 | Technical Bid Evaluation for External Battery Charger - WPA01 - IFR | 12 | 2026-07-22 | 2026-08-11 | 67 | PTTME Office 5dx8h
EE-3860 | Technical Bid Evaluation for External Battery Charger - WPA01 - AFC | 5 | 2026-08-27 | 2026-09-02 | 67 | PTTME Office 5dx8h
EE-3870 | Technical Bid Evaluation for Electrical Cables - WPA01 - IFR | 15 | 2026-08-20 | 2026-09-09 | 47 | PTTME Office 5dx8h
EE-3880 | Technical Bid Evaluation for Electrical Cables - WPA01 - AFC | 5 | 2026-09-24 | 2026-09-30 | 47 | PTTME Office 5dx8h
EE-3890 | Technical Bid Evaluation for Electrical Bulk Materials - WPA01 - IFR | 15 | 2026-09-10 | 2026-09-30 | 32 | PTTME Office 5dx8h
EE-3900 | Technical Bid Evaluation for Electrical Bulk Materials - WPA01 - AFC | 5 | 2026-10-16 | 2026-10-22 | 32 | PTTME Office 5dx8h
EE-3905 | Technical Bid Evaluation for FOG HORN - WPA01- IFR | 15 | 2026-08-20 | 2026-09-09 | 47 | PTTME Office 5dx8h
EE-3908 | Technical Bid Evaluation for FOG HORN - WPA01 - AFC | 5 | 2026-09-24 | 2026-09-30 | 47 | PTTME Office 5dx8h
EE-3910 | Technical Bid Evaluation for AC & DC Distribution Boards/Panels - WPA02 - IFR | 16 | 2026-07-22 | 2026-08-18 | 63 | PTTME Office 5dx8h
EE-3920 | Technical Bid Evaluation for AC & DC Distribution Boards/Panels - WPA02 - AFC | 5 | 2026-09-02 | 2026-09-08 | 63 | PTTME Office 5dx8h
EE-3930 | Technical Bid Evaluation for Solar power system - WPA02 - IFR | 20 | 2026-06-10 | 2026-07-07 | 89 | PTTME Office 5dx8h
EE-3940 | Technical Bid Evaluation for Solar power system - WPA02 - AFC | 5 | 2026-07-22 | 2026-07-31 | 89 | PTTME Office 5dx8h
EE-3950 | Technical Bid Evaluation for Navigation Aid system - WPA02 - IFR | 20 | 2026-08-28 | 2026-09-24 | 36 | PTTME Office 5dx8h
EE-3960 | Technical Bid Evaluation for Navigation Aid system - WPA02 - AFC | 5 | 2026-10-09 | 2026-10-16 | 36 | PTTME Office 5dx8h
EE-3970 | Technical Bid Evaluation for External Battery Charger - WPA02 - IFR | 12 | 2026-07-22 | 2026-08-11 | -45 | PTTME Office 5dx8h
EE-3980 | Technical Bid Evaluation for External Battery Charger - WPA02 - AFC | 5 | 2026-08-27 | 2026-09-02 | -45 | PTTME Office 5dx8h
EE-3990 | Technical Bid Evaluation for Electrical Cables - WPA02 - IFR | 15 | 2026-08-20 | 2026-09-09 | 47 | PTTME Office 5dx8h
EE-4000 | Technical Bid Evaluation for Electrical Cables - WPA02 - AFC | 5 | 2026-09-24 | 2026-09-30 | 47 | PTTME Office 5dx8h
EE-4010 | Technical Bid Evaluation for Electrical Bulk Materials - WPA02 - IFR | 15 | 2026-09-10 | 2026-09-30 | 32 | PTTME Office 5dx8h
EE-4020 | Technical Bid Evaluation for Electrical Bulk Materials - WPA02 - AFC | 5 | 2026-10-16 | 2026-10-22 | 32 | PTTME Office 5dx8h
EE-4030 | Technical Bid Evaluation for Motor Control Center - IFR | 20 | 2026-08-27 | 2026-09-23 | 37 | PTTME Office 5dx8h
EE-4040 | Technical Bid Evaluation for Motor Control Center - AFC | 5 | 2026-10-08 | 2026-10-15 | 37 | PTTME Office 5dx8h
EE-4052 | Technical Bid Evaluation for FOG HORN - WPA02- IFR | 15 | 2026-08-20 | 2026-09-09 | 47 | PTTME Office 5dx8h
EE-4054 | Technical Bid Evaluation for FOG HORN - WPA02 - AFC | 5 | 2026-09-24 | 2026-09-30 | 47 | PTTME Office 5dx8h
INSTRUMENTANDCONTROLSYSTEMENGINEERING |  | 198 | 2026-03-10 | 2027-01-05 | 0 | PTTME Office 5dx8h
IN-1000 | Instrument Basis Of Design - IFR | 10 | 2026-03-10 | 2026-03-23 | 168 | PTTME Office 5dx8h
IN-1010 | Instrument Basis Of Design - AFC | 10 | 2026-06-30 | 2026-07-13 | 115 | PTTME Office 5dx8h
IN-1020 | Instrument / Control And Safety System Philosophy - IFR | 10 | 2026-03-16 | 2026-03-27 | 22 | PTTME Office 5dx8h
IN-1030 | Instrument / Control And Safety System Philosophy - IFA | 10 | 2026-04-17 | 2026-04-30 | 144 | PTTME Office 5dx8h
IN-1040 | Instrument / Control And Safety System Philosophy - AFC | 10 | 2026-06-30 | 2026-07-13 | 115 | PTTME Office 5dx8h
IN-1050 | Project Particular Specification For SCADA Systems and PLC Gateway - IFR | 10 | 2026-03-16 | 2026-03-27 | 22 | PTTME Office 5dx8h
IN-1060 | Project Particular Specification For SCADA Systems and PLC Gateway - AFC | 5 | 2026-05-04 | 2026-05-08 | 159 | PTTME Office 5dx8h
IN-1070 | Project Particular Specification For PLC Systems - IFR | 10 | 2026-03-17 | 2026-03-30 | 22 | PTTME Office 5dx8h
IN-1080 | Project Particular Specification For PLC Systems - AFC | 5 | 2026-05-05 | 2026-05-11 | 158 | PTTME Office 5dx8h
IN-1090 | Project Particular Specification For Wellhead Control Panel - IFR | 10 | 2026-03-17 | 2026-03-30 | 22 | PTTME Office 5dx8h
IN-1100 | Project Particular Specification For Wellhead Control Panel - AFC | 5 | 2026-05-05 | 2026-05-11 | 158 | PTTME Office 5dx8h
IN-1110 | Project Particular Specification For Instrument For Measurement - IFR | 10 | 2026-03-23 | 2026-04-03 | 22 | PTTME Office 5dx8h
IN-1120 | Project Particular Specification For Instrument For Measurement - AFC | 5 | 2026-05-11 | 2026-05-15 | 154 | PTTME Office 5dx8h
IN-1130 | Project Particular Specification For Instrument Cables - IFR | 10 | 2026-03-23 | 2026-04-03 | 22 | PTTME Office 5dx8h
IN-1140 | Project Particular Specification For Instrument Cables - AFC | 5 | 2026-05-11 | 2026-05-15 | 154 | PTTME Office 5dx8h
IN-1150 | Project Particular Specification For Instrument Bulk Material - IFR | 10 | 2026-04-08 | 2026-04-24 | 22 | PTTME Office 5dx8h
IN-1160 | Project Particular Specification For Instrument Bulk Material - AFC | 10 | 2026-05-12 | 2026-05-25 | 148 | PTTME Office 5dx8h
IN-1170 | Project Particular Specification For Actuated Choke Valves - IFR | 10 | 2026-04-08 | 2026-04-24 | 22 | PTTME Office 5dx8h
IN-1180 | Project Particular Specification For Actuated Choke Valves - AFC | 10 | 2026-05-12 | 2026-05-25 | 148 | PTTME Office 5dx8h
IN-1190 | Project Particular Specification For Actuated Ball Valves - IFR | 10 | 2026-04-09 | 2026-04-27 | 22 | PTTME Office 5dx8h
IN-1200 | Project Particular Specification For Actuated Ball Valves - AFC | 10 | 2026-05-13 | 2026-05-26 | 147 | PTTME Office 5dx8h
IN-1210 | Project Particular Specification For Acuated Compact Ball Valve - IFR | 10 | 2026-04-09 | 2026-04-27 | 22 | PTTME Office 5dx8h
IN-1220 | Project Particular Specification For Acuated Compact Ball Valve - AFC | 10 | 2026-05-13 | 2026-05-26 | 147 | PTTME Office 5dx8h
IN-1230 | Project Particular Specification For Control Valves And Self Actuated Pcv - IFR | 10 | 2026-04-17 | 2026-04-30 | 22 | PTTME Office 5dx8h
IN-1240 | Project Particular Specification For Control Valves And Self Actuated Pcv - AFC | 10 | 2026-05-18 | 2026-05-29 | 144 | PTTME Office 5dx8h
IN-1250 | Project Particular Specification For Relief Valves - IFR | 10 | 2026-04-17 | 2026-04-30 | 22 | PTTME Office 5dx8h
IN-1260 | Project Particular Specification For Relief Valves - AFC | 10 | 2026-05-18 | 2026-05-29 | 144 | PTTME Office 5dx8h
IN-1270 | Project Particular Specification For Coriolis Flow Meters - IFR | 10 | 2026-04-17 | 2026-04-30 | 22 | PTTME Office 5dx8h
IN-1280 | Project Particular Specification For Coriolis Flow Meters - AFC | 10 | 2026-05-18 | 2026-05-29 | 63 | PTTME Office 5dx8h
IN-1290 | Project Particular Specification For Vortex Flow Meters - IFR | 10 | 2026-04-21 | 2026-05-05 | 22 | PTTME Office 5dx8h
IN-1300 | Project Particular Specification For Vortex Flow Meters - AFC | 10 | 2026-05-20 | 2026-06-04 | 52 | PTTME Office 5dx8h
IN-1310 | Project Particular Specification For Fire & Gas Detectors - IFR | 10 | 2026-04-21 | 2026-05-05 | 22 | PTTME Office 5dx8h
IN-1320 | Project Particular Specification For Fire & Gas Detectors - AFC | 10 | 2026-05-20 | 2026-06-04 | 32 | PTTME Office 5dx8h
IN-1330 | Project Particular Specification For Installation Of Instrumentation And Control - IFR | 10 | 2026-04-21 | 2026-05-05 | 22 | PTTME Office 5dx8h
IN-1340 | Project Particular Specification For Installation Of Instrumentation And Control - AFC | 10 | 2026-05-20 | 2026-06-04 | 27 | PTTME Office 5dx8h
IN-1380 | Instrument Cable Block Diagram For SCADA System - IFR | 15 | 2026-04-28 | 2026-05-19 | 22 | PTTME Office 5dx8h
IN-1390 | Instrument Cable Block Diagram For SCADA System - IFA | 10 | 2026-06-05 | 2026-06-18 | 117 | PTTME Office 5dx8h
IN-1400 | Instrument Cable Block Diagram For SCADA System - AFC | 5 | 2026-07-03 | 2026-07-09 | 117 | PTTME Office 5dx8h
IN-1410 | Overall Instrument Earthing Diagram - IFR | 15 | 2026-04-28 | 2026-05-19 | 22 | PTTME Office 5dx8h
IN-1420 | Overall Instrument Earthing Diagram - IFA | 10 | 2026-06-05 | 2026-06-18 | 112 | PTTME Office 5dx8h
IN-1430 | Overall Instrument Earthing Diagram - AFC | 10 | 2026-07-03 | 2026-07-16 | 112 | PTTME Office 5dx8h
IN-1440 | Instrument Typical Installation Details - IFR | 15 | 2026-07-03 | 2026-07-23 | 37 | PTTME Office 5dx8h
IN-1450 | Instrument Typical Installation Details - AFC | 10 | 2026-11-10 | 2026-11-23 | 16 | PTTME Office 5dx8h
IN-1480 | Instrument Drawing Index -Wp01 - IFR | 15 | 2026-10-01 | 2026-10-22 | 12 | PTTME Office 5dx8h
IN-1490 | Instrument Drawing Index -Wp01 - IFA | 10 | 2026-11-25 | 2026-12-09 | 0 | PTTME Office 5dx8h
IN-1500 | Instrument Drawing Index -Wp01 - AFC | 5 | 2026-12-28 | 2027-01-05 | 0 | PTTME Office 5dx8h
IN-1510 | Instrument Index-Wp01 - IFR | 15 | 2026-04-28 | 2026-05-19 | 7 | PTTME Office 5dx8h
IN-1520 | Instrument Index-Wp01 - IFA | 10 | 2026-06-05 | 2026-06-18 | 47 | PTTME Office 5dx8h
IN-1530 | Instrument Index-Wp01 - AFC | 10 | 2026-07-03 | 2026-07-16 | 77 | PTTME Office 5dx8h
IN-1540 | Plc Input/Output List-Wp01 - IFR | 15 | 2026-04-28 | 2026-05-19 | 22 | PTTME Office 5dx8h
IN-1550 | Plc Input/Output List-Wp01 - IFA | 10 | 2026-06-05 | 2026-06-18 | 67 | PTTME Office 5dx8h
IN-1560 | Plc Input/Output List-Wp01 - AFC | 10 | 2026-07-03 | 2026-07-16 | 87 | PTTME Office 5dx8h
IN-1570 | Control System Block Diagram For-Wp01 - IFR | 15 | 2026-05-20 | 2026-06-11 | 22 | PTTME Office 5dx8h
IN-1580 | Control System Block Diagram For-Wp01 - IFA | 10 | 2026-06-26 | 2026-07-09 | 62 | PTTME Office 5dx8h
IN-1590 | Control System Block Diagram For-Wp01 - AFC | 5 | 2026-07-24 | 2026-08-04 | 82 | PTTME Office 5dx8h
IN-1600 | Instrument Cable Block Diagram Pcs/Esd/Fgs-Wp01 - IFR | 15 | 2026-05-20 | 2026-06-11 | 22 | PTTME Office 5dx8h
IN-1610 | Instrument Cable Block Diagram Pcs/Esd/Fgs-Wp01 - IFA | 10 | 2026-06-26 | 2026-07-09 | 67 | PTTME Office 5dx8h
IN-1620 | Instrument Cable Block Diagram Pcs/Esd/Fgs-Wp01 - AFC | 5 | 2026-07-24 | 2026-08-04 | 72 | PTTME Office 5dx8h
IN-2210 | Instrument Loop Diagram- Wp01 - IFR | 25 | 2026-07-03 | 2026-08-11 | 47 | PTTME Office 5dx8h
IN-2220 | Instrument Loop Diagram- Wp01 - AFC | 20 | 2026-09-24 | 2026-10-22 | 42 | PTTME Office 5dx8h
IN-2230 | Instrument Cable Tray Layout- Wp01 - IFR | 15 | 2026-06-12 | 2026-07-02 | 7 | PTTME Office 5dx8h
IN-2240 | Instrument Cable Tray Layout- Wp01 - IFA | 10 | 2026-09-14 | 2026-09-25 | 0 | PTTME Office 5dx8h
IN-2250 | Instrument Cable Tray Layout- Wp01 - AFC | 5 | 2026-11-03 | 2026-11-09 | 11 | PTTME Office 5dx8h
IN-2260 | Instrument Cable Routing Plan And Junction Boxes Layout- Wp01 - IFR | 15 | 2026-07-03 | 2026-07-23 | 7 | PTTME Office 5dx8h
IN-2270 | Instrument Cable Routing Plan And Junction Boxes Layout- Wp01 - IFA | 10 | 2026-09-28 | 2026-10-09 | 0 | PTTME Office 5dx8h
IN-2280 | Instrument Cable Routing Plan And Junction Boxes Layout- Wp01 - AFC | 5 | 2026-11-10 | 2026-11-16 | 11 | PTTME Office 5dx8h
IN-2290 | Instrument Cable Schedule- Wp01 - IFR | 15 | 2026-07-24 | 2026-08-19 | 7 | PTTME Office 5dx8h
IN-2300 | Instrument Cable Schedule- Wp01 - IFA | 10 | 2026-10-12 | 2026-10-27 | 0 | PTTME Office 5dx8h
IN-2310 | Instrument Cable Schedule- Wp01 - AFC | 5 | 2026-11-17 | 2026-11-23 | 11 | PTTME Office 5dx8h
IN-2320 | Instrument Multi Cable Transit Schedule- Wp01 - IFR | 15 | 2026-08-20 | 2026-09-09 | 7 | PTTME Office 5dx8h
IN-2330 | Instrument Multi Cable Transit Schedule- Wp01 - IFA | 10 | 2026-10-28 | 2026-11-10 | 0 | PTTME Office 5dx8h
IN-2340 | Instrument Multi Cable Transit Schedule- Wp01 - AFC | 5 | 2026-11-25 | 2026-12-01 | 10 | PTTME Office 5dx8h
IN-2341 | Instrument Location Plan - WP01 - IFR | 15 | 2026-05-20 | 2026-06-11 | 7 | PTTME Office 5dx8h
IN-2342 | Instrument Location Plan - WP01 - IFA | 10 | 2026-08-31 | 2026-09-11 | 0 | PTTME Office 5dx8h
IN-2343 | Instrument Location Plan - WP01 - AFC | 5 | 2026-10-27 | 2026-11-02 | 11 | PTTME Office 5dx8h
IN-2344 | Instrument Tubing Tray Laout - WP01 - IFR | 15 | 2026-06-12 | 2026-07-02 | 52 | PTTME Office 5dx8h
IN-2345 | Instrument Tubing Tray Laout - WP01 - IFA | 10 | 2026-09-14 | 2026-09-25 | 30 | PTTME Office 5dx8h
IN-2346 | Instrument Tubing Tray Laout - WP01 - AFC | 5 | 2026-11-03 | 2026-11-09 | 26 | PTTME Office 5dx8h
IN-2347 | Instrument Tubing Schedule - WP01 - IFR | 15 | 2026-07-03 | 2026-07-23 | 62 | PTTME Office 5dx8h
IN-2348 | Instrument Tubing Schedule - WP01 - IFA | 10 | 2026-09-28 | 2026-10-09 | 30 | PTTME Office 5dx8h
IN-2349 | Instrument Tubing Schedule - WP01 - AFC | 5 | 2026-11-10 | 2026-11-16 | 26 | PTTME Office 5dx8h
IN-2350 | Instrument Hook-Up Drawing - WP01 - IFR | 15 | 2026-06-12 | 2026-07-02 | 37 | PTTME Office 5dx8h
IN-2351 | Instrument Hook-Up Drawing - WP01 - IFA | 10 | 2026-09-14 | 2026-09-25 | 30 | PTTME Office 5dx8h
IN-2352 | Instrument Hook-Up Drawing - WP01 - AFC | 5 | 2026-11-03 | 2026-11-09 | 16 | PTTME Office 5dx8h
IN-2353 | Instrument Wiring Diagram (PCS AND SIS/FGS SYSTEM) - WP01 - IFR | 15 | 2026-06-12 | 2026-07-02 | 47 | PTTME Office 5dx8h
IN-2354 | Instrument Wiring Diagram (PCS AND SIS/FGS SYSTEM) - WP01 - IFA | 10 | 2026-07-17 | 2026-08-04 | 62 | PTTME Office 5dx8h
IN-2355 | Instrument Wiring Diagram (PCS AND SIS/FGS SYSTEM) - WP01 - AFC | 5 | 2026-08-20 | 2026-08-26 | 62 | PTTME Office 5dx8h
IN-2356 | Instrument Equipment And Explosion Proof Equipment Schedule- Wp01 - IFR | 15 | 2026-09-07 | 2026-09-25 | 20 | PTTME Office 5dx8h
IN-2357 | Instrument Equipment And Explosion Proof Equipment Schedule- Wp01 - IFA | 10 | 2026-10-12 | 2026-10-27 | 20 | PTTME Office 5dx8h
IN-2358 | Instrument Equipment And Explosion Proof Equipment Schedule- Wp01 - AFC | 5 | 2026-11-19 | 2026-11-25 | 19 | PTTME Office 5dx8h
IN-2359 | Fusible Plug And F&G Layout- Wp01 - IFR | 15 | 2026-07-10 | 2026-08-04 | 32 | PTTME Office 5dx8h
IN-2360 | Fusible Plug And F&G Layout- Wp01 - AFC | 10 | 2026-09-10 | 2026-09-23 | 62 | PTTME Office 5dx8h
IN-2370 | Instrument Bulk Material Take Off- Wp01 - IFR | 15 | 2026-09-10 | 2026-09-30 | 7 | PTTME Office 5dx8h
IN-2380 | Instrument Bulk Material Take Off- Wp01 - IFA | 10 | 2026-11-11 | 2026-11-24 | 0 | PTTME Office 5dx8h
IN-2390 | Instrument Bulk Material Take Off- Wp01 - AFC | 5 | 2026-12-11 | 2026-12-17 | 5 | PTTME Office 5dx8h
IN-2420 | Instrument Shiploose List For Offshore Installation- Wp01 - IFR | 15 | 2026-07-24 | 2026-08-19 | 42 | PTTME Office 5dx8h
IN-2430 | Instrument Shiploose List For Offshore Installation- Wp01 - AFC | 10 | 2026-09-03 | 2026-09-16 | 67 | PTTME Office 5dx8h
IN-2440 | Instrument Shiploose List Handover To Company Operation Team- Wp01 - IFR | 15 | 2026-07-24 | 2026-08-19 | 42 | PTTME Office 5dx8h
IN-2450 | Instrument Shiploose List Handover To Company Operation Team- Wp01 - AFC | 10 | 2026-09-03 | 2026-09-16 | 67 | PTTME Office 5dx8h
IN-2460 | Instrument Drawing Index -Wp02 - IFR | 15 | 2026-10-01 | 2026-10-22 | 22 | PTTME Office 5dx8h
IN-2470 | Instrument Drawing Index -Wp02 - IFA | 10 | 2026-11-25 | 2026-12-09 | 0 | PTTME Office 5dx8h
IN-2480 | Instrument Drawing Index -Wp02 - AFC | 5 | 2026-12-28 | 2027-01-05 | 0 | PTTME Office 5dx8h
IN-2490 | Instrument Index-Wp02 - IFR | 15 | 2026-04-28 | 2026-05-19 | 107 | PTTME Office 5dx8h
IN-2500 | Instrument Index-Wp02 - IFA | 10 | 2026-06-05 | 2026-06-18 | 107 | PTTME Office 5dx8h
IN-2510 | Instrument Index-Wp02 - AFC | 10 | 2026-07-03 | 2026-07-16 | 107 | PTTME Office 5dx8h
IN-2520 | Plc Input/Output List-Wp02 - IFR | 15 | 2026-04-28 | 2026-05-19 | 67 | PTTME Office 5dx8h
IN-2530 | Plc Input/Output List-Wp02 - IFA | 10 | 2026-06-05 | 2026-06-18 | 92 | PTTME Office 5dx8h
IN-2540 | Plc Input/Output List-Wp02 - AFC | 10 | 2026-07-03 | 2026-07-16 | 92 | PTTME Office 5dx8h
IN-2541 | Control System Block Diagram For-Wp02 - IFR | 15 | 2026-05-20 | 2026-06-11 | 102 | PTTME Office 5dx8h
IN-2542 | Control System Block Diagram For-Wp02 - IFA | 10 | 2026-06-26 | 2026-07-09 | 102 | PTTME Office 5dx8h
IN-2543 | Control System Block Diagram For-Wp02 - AFC | 5 | 2026-07-24 | 2026-08-04 | 102 | PTTME Office 5dx8h
IN-2544 | Instrument Cable Block Diagram Pcs/Esd/Fgs-Wp02 - IFR | 15 | 2026-05-20 | 2026-06-11 | 102 | PTTME Office 5dx8h
IN-2545 | Instrument Cable Block Diagram Pcs/Esd/Fgs-Wp02 - IFA | 10 | 2026-06-26 | 2026-07-09 | 102 | PTTME Office 5dx8h
IN-2546 | Instrument Cable Block Diagram Pcs/Esd/Fgs-Wp02 - AFC | 5 | 2026-07-24 | 2026-08-04 | 102 | PTTME Office 5dx8h
IN-3170 | Instrument Loop Diagram- Wp02 - IFR | 25 | 2026-07-03 | 2026-08-11 | 57 | PTTME Office 5dx8h
IN-3180 | Instrument Loop Diagram- Wp02 - AFC | 20 | 2026-09-24 | 2026-10-22 | 42 | PTTME Office 5dx8h
IN-3190 | Instrument Cable Tray Layout- Wp02 - IFR | 15 | 2026-06-12 | 2026-07-02 | 52 | PTTME Office 5dx8h
IN-3195 | Instrument Cable Tray Layout- Wp02 - IFA | 15 | 2026-09-07 | 2026-09-25 | 65 | PTTME Office 5dx8h
IN-3200 | Instrument Cable Tray Layout- Wp02 - AFC | 5 | 2026-11-03 | 2026-11-09 | 31 | PTTME Office 5dx8h
IN-3210 | Instrument Cable Routing Plan And Junction Boxes Layout- Wp02 - IFR | 15 | 2026-07-03 | 2026-07-23 | 32 | PTTME Office 5dx8h
IN-3220 | Instrument Cable Routing Plan And Junction Boxes Layout- Wp02 - IFA | 10 | 2026-09-28 | 2026-10-09 | 30 | PTTME Office 5dx8h
IN-3230 | Instrument Cable Routing Plan And Junction Boxes Layout- Wp02 - AFC | 5 | 2026-11-10 | 2026-11-16 | 26 | PTTME Office 5dx8h
IN-3240 | Instrument Cable Schedule- Wp02 - IFR | 15 | 2026-07-24 | 2026-08-19 | 17 | PTTME Office 5dx8h
IN-3250 | Instrument Cable Schedule- Wp02 - IFA | 10 | 2026-10-12 | 2026-10-27 | 20 | PTTME Office 5dx8h
IN-3260 | Instrument Cable Schedule- Wp02 - AFC | 5 | 2026-11-17 | 2026-11-23 | 21 | PTTME Office 5dx8h
IN-3270 | Instrument Multi Cable Transit Schedule- Wp02 - IFR | 15 | 2026-08-20 | 2026-09-09 | 7 | PTTME Office 5dx8h
IN-3280 | Instrument Multi Cable Transit Schedule- Wp02 - IFA | 10 | 2026-10-28 | 2026-11-10 | 10 | PTTME Office 5dx8h
IN-3290 | Instrument Multi Cable Transit Schedule- Wp02 - AFC | 5 | 2026-11-25 | 2026-12-01 | 15 | PTTME Office 5dx8h
IN-3291 | Instrument Location Plan- Wp02 - IFR | 15 | 2026-05-20 | 2026-06-11 | 47 | PTTME Office 5dx8h
IN-3292 | Instrument Location Plan- Wp02 - IFA | 10 | 2026-08-31 | 2026-09-11 | 50 | PTTME Office 5dx8h
IN-3293 | Instrument Location Plan- Wp02 - AFC | 5 | 2026-10-27 | 2026-11-02 | 36 | PTTME Office 5dx8h
IN-3294 | Instrument Tubing Tray Layout - Wp02 - IFR | 15 | 2026-06-12 | 2026-07-02 | 52 | PTTME Office 5dx8h
IN-3295 | Instrument Tubing Tray Layout - Wp02 - IFA | 10 | 2026-09-14 | 2026-09-25 | 40 | PTTME Office 5dx8h
IN-3296 | Instrument Tubing Tray Layout - Wp02 - AFC | 5 | 2026-11-03 | 2026-11-09 | 31 | PTTME Office 5dx8h
IN-3320 | Instrument Tubing Schedule- Wp02 - IFR | 15 | 2026-07-03 | 2026-07-23 | 62 | PTTME Office 5dx8h
IN-3330 | Instrument Tubing Schedule- Wp02 - IFA | 10 | 2026-09-28 | 2026-10-09 | 30 | PTTME Office 5dx8h
IN-3340 | Instrument Tubing Schedule- Wp02 - AFC | 5 | 2026-11-10 | 2026-11-16 | 26 | PTTME Office 5dx8h
IN-3380 | Instrument Hook-Up Drawings- Wp02 - IFR | 15 | 2026-06-12 | 2026-07-02 | 37 | PTTME Office 5dx8h
IN-3390 | Instrument Hook-Up Drawings- Wp02 - IFA | 10 | 2026-09-14 | 2026-09-25 | 30 | PTTME Office 5dx8h
IN-3400 | Instrument Hook-Up Drawings- Wp02 - AFC | 5 | 2026-11-03 | 2026-11-09 | 16 | PTTME Office 5dx8h
IN-3440 | Instrument Wiring Diagrams (PCS AND SIS/FGS SYSTEM) - Wp02 - IFR | 15 | 2026-06-12 | 2026-07-02 | 77 | PTTME Office 5dx8h
IN-3450 | Instrument Wiring Diagrams (PCS AND SIS/FGS SYSTEM) - Wp02 - IFA | 10 | 2026-07-17 | 2026-08-04 | 77 | PTTME Office 5dx8h
IN-3460 | Instrument Wiring Diagrams (PCS AND SIS/FGS SYSTEM) - Wp02 - AFC | 10 | 2026-08-20 | 2026-09-02 | 77 | PTTME Office 5dx8h
IN-3470 | Instrument Equipment And Explosion Proof Equipment Schedule- Wp02 - IFR | 15 | 2026-09-07 | 2026-09-25 | 20 | PTTME Office 5dx8h
IN-3480 | Instrument Equipment And Explosion Proof Equipment Schedule- Wp02 - IFA | 10 | 2026-10-12 | 2026-10-27 | 20 | PTTME Office 5dx8h
IN-3490 | Instrument Equipment And Explosion Proof Equipment Schedule- Wp02 - AFC | 10 | 2026-11-12 | 2026-11-25 | 19 | PTTME Office 5dx8h
IN-3500 | Fusible Plug And F&G Layout- Wp02 - IFR | 15 | 2026-07-10 | 2026-08-04 | 32 | PTTME Office 5dx8h
IN-3510 | Fusible Plug And F&G Layout- Wp02 - AFC | 10 | 2026-09-10 | 2026-09-23 | 62 | PTTME Office 5dx8h
IN-3520 | Instrument Bulk Material Take Off- Wp02 - IFR | 15 | 2026-09-10 | 2026-09-30 | 7 | PTTME Office 5dx8h
IN-3530 | Instrument Bulk Material Take Off- Wp02 - IFA | 10 | 2026-11-11 | 2026-11-24 | 0 | PTTME Office 5dx8h
IN-3540 | Instrument Bulk Material Take Off- Wp02 - AFC | 10 | 2026-12-11 | 2026-12-24 | 0 | PTTME Office 5dx8h
IN-3570 | Instrument Shiploose List For Offshore Installation- Wp02 - IFR | 15 | 2026-09-10 | 2026-09-30 | 22 | PTTME Office 5dx8h
IN-3580 | Instrument Shiploose List For Offshore Installation- Wp02 - AFC | 10 | 2026-10-16 | 2026-10-30 | 37 | PTTME Office 5dx8h
IN-3590 | Instrument Shiploose List Handover To Company Operation Team- Wp02 - IFR | 15 | 2026-09-10 | 2026-09-30 | 22 | PTTME Office 5dx8h
IN-3600 | Instrument Shiploose List Handover To Company Operation Team- Wp02 - AFC | 10 | 2026-10-16 | 2026-10-30 | 37 | PTTME Office 5dx8h
Datasheets-Instrument |  | 148 | 2026-04-09 | 2026-11-18 | 24 | PTTME Office 5dx8h
IN-1350 | Data Sheets For Supervisory Control And Data Acquisition System (Scada) - IFR | 15 | 2026-04-09 | 2026-05-05 | 22 | PTTME Office 5dx8h
IN-1360 | Data Sheets For Supervisory Control And Data Acquisition System (Scada) - IFA | 10 | 2026-05-20 | 2026-06-04 | 72 | PTTME Office 5dx8h
IN-1370 | Data Sheets For Supervisory Control And Data Acquisition System (Scada) - AFC | 5 | 2026-06-19 | 2026-06-25 | 72 | PTTME Office 5dx8h
IN-1630 | Data Sheets For Whcp-Wp01 - IFR | 15 | 2026-04-29 | 2026-05-20 | 0 | PTTME Office 5dx8h
IN-1640 | Data Sheets For Whcp-Wp01 - IFA | 10 | 2026-06-08 | 2026-06-19 | 96 | PTTME Office 5dx8h
IN-1650 | Data Sheets For Whcp-Wp01 - AFC | 5 | 2026-07-08 | 2026-07-14 | 104 | PTTME Office 5dx8h
IN-1660 | Data Sheet For Control Valves-Wp01 - IFR | 15 | 2026-07-17 | 2026-08-11 | 4 | PTTME Office 5dx8h
IN-1670 | Data Sheet For Control Valves-Wp01 - IFA | 10 | 2026-08-27 | 2026-09-09 | 42 | PTTME Office 5dx8h
IN-1680 | Data Sheet For Control Valves-Wp01 - AFC | 5 | 2026-10-21 | 2026-10-28 | 34 | PTTME Office 5dx8h
IN-1690 | Data Sheet For Self Actuated Pcv-Wp01 - IFR | 15 | 2026-07-27 | 2026-08-20 | 4 | PTTME Office 5dx8h
IN-1700 | Data Sheet For Self Actuated Pcv-Wp01 - IFA | 10 | 2026-09-04 | 2026-09-17 | 36 | PTTME Office 5dx8h
IN-1710 | Data Sheet For Self Actuated Pcv-Wp01 - AFC | 5 | 2026-10-27 | 2026-11-02 | 31 | PTTME Office 5dx8h
IN-1720 | Data Sheet For Actuated Choke Valves-Wp01 - IFR | 15 | 2026-04-24 | 2026-05-15 | 57 | PTTME Office 5dx8h
IN-1730 | Data Sheet For Actuated Choke Valves-Wp01 - IFA | 10 | 2026-06-02 | 2026-06-16 | 99 | PTTME Office 5dx8h
IN-1740 | Data Sheet For Actuated Choke Valves-Wp01 - AFC | 5 | 2026-07-03 | 2026-07-09 | 107 | PTTME Office 5dx8h
IN-1750 | Data Sheets For Actuated Ball Valves-Wp01 - IFR | 15 | 2026-05-29 | 2026-06-22 | 57 | PTTME Office 5dx8h
IN-1760 | Data Sheets For Actuated Ball Valves-Wp01 - IFA | 10 | 2026-07-07 | 2026-07-20 | 75 | PTTME Office 5dx8h
IN-1770 | Data Sheets For Actuated Ball Valves-Wp01 - AFC | 5 | 2026-08-27 | 2026-09-02 | 72 | PTTME Office 5dx8h
IN-1780 | Data Sheet For Actuated Compact Ball Valves-Wp01 - IFR | 15 | 2026-05-07 | 2026-05-27 | 0 | PTTME Office 5dx8h
IN-1790 | Data Sheet For Actuated Compact Ball Valves-Wp01 - IFA | 10 | 2026-06-15 | 2026-06-26 | 91 | PTTME Office 5dx8h
IN-1800 | Data Sheet For Actuated Compact Ball Valves-Wp01 - AFC | 5 | 2026-08-04 | 2026-08-10 | 88 | PTTME Office 5dx8h
IN-1810 | Data Sheet For Safety Relief Valves-Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 4 | PTTME Office 5dx8h
IN-1820 | Data Sheet For Safety Relief Valves-Wp01 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-1830 | Data Sheet For Safety Relief Valves-Wp01 - AFC | 5 | 2026-10-20 | 2026-10-27 | 35 | PTTME Office 5dx8h
IN-1840 | Data Sheet For Coriolis Flow Meters-Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 14 | PTTME Office 5dx8h
IN-1850 | Data Sheet For Coriolis Flow Meters-Wp01 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-1860 | Data Sheet For Coriolis Flow Meters-Wp01 - AFC | 5 | 2026-10-29 | 2026-11-04 | 29 | PTTME Office 5dx8h
IN-1870 | Data Sheets For Vortex Flow Meters-Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-1880 | Data Sheets For Vortex Flow Meters-Wp01 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-1890 | Data Sheets For Vortex Flow Meters-Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-1900 | Data Sheets For Flow Switch-Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-1910 | Data Sheets For Flow Switch-Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-1920 | Data Sheet For Pressure Gauges-Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-1930 | Data Sheet For Pressure Gauges-Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-1940 | Data Sheet For Pressure Transmitters-Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-1950 | Data Sheet For Pressure Transmitters-Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-1960 | Data Sheet For Temperature Gauge And Thermowell-Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-1970 | Data Sheet For Temperature Gauge And Thermowell-Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-1980 | Data Sheet For Temperature Transmitters And Thermowells-Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-1990 | Data Sheet For Temperature Transmitters And Thermowells-Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2000 | Data Sheets For Magnetic Level Gauge And Transmitters-Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2010 | Data Sheets For Magnetic Level Gauge And Transmitters-Wp01 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-2020 | Data Sheets For Magnetic Level Gauge And Transmitters-Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2030 | Data Sheet For Dip Tape Level Indicator-Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2040 | Data Sheet For Dip Tape Level Indicator-Wp01 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-2050 | Data Sheet For Dip Tape Level Indicator-Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2060 | Data Sheets For Level Switch-Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2070 | Data Sheets For Level Switch-Wp01 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-2080 | Data Sheets For Level Switch-Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2090 | Data Sheets For Dp Level Transmitters-Wp01 - IFR | 15 | 2026-07-06 | 2026-07-24 | 27 | PTTME Office 5dx8h
IN-2100 | Data Sheets For Dp Level Transmitters-Wp01 - AFC | 5 | 2026-10-08 | 2026-10-15 | 42 | PTTME Office 5dx8h
IN-2110 | Data Sheets For Restriction Orifice- Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 16 | PTTME Office 5dx8h
IN-2120 | Data Sheets For Restriction Orifice- Wp01 - AFC | 5 | 2026-10-08 | 2026-10-15 | 42 | PTTME Office 5dx8h
IN-2130 | Data Sheet For Fire & Gas Detectors- Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2140 | Data Sheet For Fire & Gas Detectors- Wp01 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-2150 | Data Sheet For Fire & Gas Detectors- Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2160 | Data Sheets For Position Limit Switches- Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2170 | Data Sheets For Position Limit Switches- Wp01 - IFA | 5 | 2026-09-21 | 2026-09-25 | 30 | PTTME Office 5dx8h
IN-2180 | Data Sheets For Position Limit Switches- Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2190 | Data Sheets For Pig Signaller - Wp01 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2200 | Data Sheets For Pig Signaller - Wp01 - AFC | 5 | 2026-11-11 | 2026-11-17 | 25 | PTTME Office 5dx8h
IN-2550 | Data Sheets For Whcp-Wp02 - IFR | 15 | 2026-04-29 | 2026-05-20 | 0 | PTTME Office 5dx8h
IN-2560 | Data Sheets For Whcp-Wp02 - IFA | 10 | 2026-06-08 | 2026-06-19 | 22 | PTTME Office 5dx8h
IN-2570 | Data Sheets For Whcp-Wp02 - AFC | 5 | 2026-07-08 | 2026-07-14 | 20 | PTTME Office 5dx8h
IN-2580 | Data Sheet For Control Valves-Wp02 - IFR | 15 | 2026-07-17 | 2026-08-11 | 19 | PTTME Office 5dx8h
IN-2590 | Data Sheet For Control Valves-Wp02 - IFA | 10 | 2026-08-27 | 2026-09-09 | 42 | PTTME Office 5dx8h
IN-2600 | Data Sheet For Control Valves-Wp02 - AFC | 5 | 2026-10-21 | 2026-10-28 | 34 | PTTME Office 5dx8h
IN-2610 | Data Sheet For Self Actuated Pcv-Wp02 - IFR | 15 | 2026-07-27 | 2026-08-20 | 16 | PTTME Office 5dx8h
IN-2620 | Data Sheet For Self Actuated Pcv-Wp02 - IFA | 10 | 2026-09-04 | 2026-09-17 | 36 | PTTME Office 5dx8h
IN-2630 | Data Sheet For Self Actuated Pcv-Wp02 - AFC | 5 | 2026-10-27 | 2026-11-02 | 31 | PTTME Office 5dx8h
IN-2640 | Data Sheet For Actuated Choke Valves-Wp02 - IFR | 15 | 2026-04-24 | 2026-05-15 | 93 | PTTME Office 5dx8h
IN-2650 | Data Sheet For Actuated Choke Valves-Wp02 - IFA | 10 | 2026-06-02 | 2026-06-16 | 99 | PTTME Office 5dx8h
IN-2660 | Data Sheet For Actuated Choke Valves-Wp02 - AFC | 5 | 2026-07-02 | 2026-07-08 | 108 | PTTME Office 5dx8h
IN-2670 | Data Sheets For Actuated Ball Valves-Wp02 - IFR | 15 | 2026-05-29 | 2026-06-22 | 57 | PTTME Office 5dx8h
IN-2680 | Data Sheets For Actuated Ball Valves-Wp02 - IFA | 10 | 2026-07-07 | 2026-07-20 | 75 | PTTME Office 5dx8h
IN-2690 | Data Sheets For Actuated Ball Valves-Wp02 - AFC | 5 | 2026-08-27 | 2026-09-02 | 72 | PTTME Office 5dx8h
IN-2700 | Data Sheet For Actuated Compact Ball Valves-Wp02 - IFR | 15 | 2026-05-07 | 2026-05-27 | 0 | PTTME Office 5dx8h
IN-2710 | Data Sheet For Actuated Compact Ball Valves-Wp02 - IFA | 10 | 2026-06-15 | 2026-06-26 | 38 | PTTME Office 5dx8h
IN-2720 | Data Sheet For Actuated Compact Ball Valves-Wp02 - AFC | 5 | 2026-08-04 | 2026-08-10 | 25 | PTTME Office 5dx8h
IN-2730 | Data Sheet For Safety Relief Valves-Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 4 | PTTME Office 5dx8h
IN-2740 | Data Sheet For Safety Relief Valves-Wp02 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-2750 | Data Sheet For Safety Relief Valves-Wp02 - AFC | 5 | 2026-11-12 | 2026-11-18 | 19 | PTTME Office 5dx8h
IN-2760 | Data Sheet For Coriolis Flow Meters-Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 14 | PTTME Office 5dx8h
IN-2770 | Data Sheet For Coriolis Flow Meters-Wp02 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-2780 | Data Sheet For Coriolis Flow Meters-Wp02 - AFC | 5 | 2026-10-29 | 2026-11-04 | 29 | PTTME Office 5dx8h
IN-2790 | Data Sheets For Vortex Flow Meters-Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2800 | Data Sheets For Vortex Flow Meters-Wp02 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-2810 | Data Sheets For Vortex Flow Meters-Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2820 | Data Sheets For Flow Switch-Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2830 | Data Sheets For Flow Switch-Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2840 | Data Sheet For Pressure Gauges-Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2850 | Data Sheet For Pressure Gauges-Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2860 | Data Sheets For Pressure Transmitters-Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2870 | Data Sheets For Pressure Transmitters-Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2880 | Data Sheet For Temperature Gauge And Thermowell-Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2890 | Data Sheet For Temperature Gauge And Thermowell-Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2900 | Data Sheet For Temperature Transmitters And Thermowells-Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2910 | Data Sheet For Temperature Transmitters And Thermowells-Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2920 | Data Sheets For Magnetic Level Gauge And Transmitters-Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2930 | Data Sheets For Magnetic Level Gauge And Transmitters-Wp02 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-2940 | Data Sheets For Magnetic Level Gauge And Transmitters-Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2950 | Data Sheet For Dip Tape Level Indicator-Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2960 | Data Sheet For Dip Tape Level Indicator-Wp02 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-2970 | Data Sheet For Dip Tape Level Indicator-Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-2980 | Data Sheets For Level Switch-Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-2990 | Data Sheets For Level Switch-Wp02 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-3000 | Data Sheets For Level Switch-Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-3010 | Data Sheet For Guided Wave Radar Level Transmitter - Wp02 - IFR | 15 | 2026-07-06 | 2026-07-24 | 27 | PTTME Office 5dx8h
IN-3020 | Data Sheet For Guided Wave Radar Level Transmitter - Wp02 - IFA | 10 | 2026-08-14 | 2026-08-27 | 51 | PTTME Office 5dx8h
IN-3030 | Data Sheet For Guided Wave Radar Level Transmitter - Wp02 - AFC | 5 | 2026-10-08 | 2026-10-15 | 42 | PTTME Office 5dx8h
IN-3040 | Data Sheets For Dp Level Transmitters-Wp02 - IFR | 15 | 2026-07-06 | 2026-07-24 | 27 | PTTME Office 5dx8h
IN-3050 | Data Sheets For Dp Level Transmitters-Wp02 - AFC | 5 | 2026-10-08 | 2026-10-15 | 42 | PTTME Office 5dx8h
IN-3060 | Data Sheets For Restriction Orifice- Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 16 | PTTME Office 5dx8h
IN-3070 | Data Sheets For Restriction Orifice- Wp02 - AFC | 5 | 2026-11-05 | 2026-11-11 | 24 | PTTME Office 5dx8h
IN-3080 | Data Sheet For Fire & Gas Detectors- Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-3090 | Data Sheet For Fire & Gas Detectors- Wp02 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-3100 | Data Sheet For Fire & Gas Detectors- Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-3110 | Data Sheets For Position Limit Switches- Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-3120 | Data Sheets For Position Limit Switches- Wp02 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-3130 | Data Sheets For Position Limit Switches- Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
IN-3140 | Data Sheet For Oil In Water Analyzer - Wp02 - IFR | 15 | 2026-08-17 | 2026-09-04 | 5 | PTTME Office 5dx8h
IN-3150 | Data Sheet For Oil In Water Analyzer - Wp02 - IFA | 10 | 2026-09-21 | 2026-10-02 | 25 | PTTME Office 5dx8h
IN-3160 | Data Sheet For Oil In Water Analyzer - Wp02 - AFC | 5 | 2026-11-11 | 2026-11-17 | 20 | PTTME Office 5dx8h
MR-Instrument |  | 160 | 2026-05-04 | 2026-12-28 | 4 | PTTME Office 5dx8h
IN-3610 | Material Requisition For Wellhead Control Panel - IFR | 10 | 2026-05-07 | 2026-05-20 | 0 | PTTME Office 5dx8h
IN-3620 | Material Requisition For Wellhead Control Panel - AFC | 5 | 2026-08-18 | 2026-08-24 | 0 | PTTME Office 5dx8h
IN-3630 | Material Requisition For SCADA - IFR | 10 | 2026-05-06 | 2026-05-19 | 90 | PTTME Office 5dx8h
IN-3640 | Material Requisition For SCADA - AFC | 5 | 2026-08-17 | 2026-08-21 | 90 | PTTME Office 5dx8h
IN-3650 | Material Requisition For PLC And SCADA System - IFR | 10 | 2026-05-06 | 2026-05-19 | 42 | PTTME Office 5dx8h
IN-3660 | Material Requisition For PLC And SCADA System - AFC | 5 | 2026-08-13 | 2026-08-19 | 42 | PTTME Office 5dx8h
IN-3670 | Material Requisition For Control Valves - IFR | 10 | 2026-08-18 | 2026-08-31 | 19 | PTTME Office 5dx8h
IN-3680 | Material Requisition For Control Valves - AFC | 5 | 2026-11-26 | 2026-12-02 | 19 | PTTME Office 5dx8h
IN-3690 | Material Requisition For Self Regulator Valves - IFR | 10 | 2026-08-21 | 2026-09-03 | 16 | PTTME Office 5dx8h
IN-3700 | Material Requisition For Self Regulator Valves - AFC | 5 | 2026-12-01 | 2026-12-08 | 16 | PTTME Office 5dx8h
IN-3710 | Material Requisition For Actuated Choke Valves - IFR | 10 | 2026-05-04 | 2026-05-15 | 93 | PTTME Office 5dx8h
IN-3720 | Material Requisition For Actuated Choke Valves - AFC | 5 | 2026-08-11 | 2026-08-18 | 93 | PTTME Office 5dx8h
IN-3730 | Material Requisition For Actuated Ball Valves - IFR | 10 | 2026-06-23 | 2026-07-06 | 57 | PTTME Office 5dx8h
IN-3740 | Material Requisition For Actuated Ball Valves - AFC | 5 | 2026-10-01 | 2026-10-07 | 57 | PTTME Office 5dx8h
IN-3750 | Material Requisition For Actuated Compact Ball Valves - IFR | 10 | 2026-05-27 | 2026-06-11 | 0 | PTTME Office 5dx8h
IN-3760 | Material Requisition For Actuated Compact Ball Valves - AFC | 5 | 2026-09-09 | 2026-09-15 | 0 | PTTME Office 5dx8h
IN-3770 | Material Requisition For Safety Relief Valves - IFR | 10 | 2026-09-08 | 2026-09-21 | 4 | PTTME Office 5dx8h
IN-3780 | Material Requisition For Safety Relief Valves - AFC | 5 | 2026-12-21 | 2026-12-28 | 4 | PTTME Office 5dx8h
IN-3790 | Material Requisition For Coriolis Flow Meters - IFR | 10 | 2026-08-25 | 2026-09-07 | 14 | PTTME Office 5dx8h
IN-3800 | Material Requisition For Coriolis Flow Meters - AFC | 5 | 2026-12-03 | 2026-12-11 | 14 | PTTME Office 5dx8h
IN-3810 | Material Requisition For Vortex Flow Meters - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-3820 | Material Requisition For Vortex Flow Meters - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-3830 | Material Requisition For Flow Switch - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-3840 | Material Requisition For Flow Switch - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-3850 | Material Requisition For Pressure Gauges - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-3860 | Material Requisition For Pressure Gauges - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-3870 | Material Requisition For Pressure Transmitters - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-3880 | Material Requisition For Pressure Transmitters - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-3890 | Material Requisition For Temperature Gauges - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-3900 | Material Requisition For Temperature Gauges - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-3910 | Material Requisition For Temperature Transmitters - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-3920 | Material Requisition For Temperature Transmitters - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-3930 | Material Requisition For Level Gauge And Transmitters - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-3940 | Material Requisition For Level Gauge And Transmitters - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-3950 | Material Requisition For Dip Tape Level Indicator - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-3960 | Material Requisition For Dip Tape Level Indicator - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-3970 | Material Requisition For Level Switch - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-3980 | Material Requisition For Level Switch - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-3990 | Material Requisition For Guided Wave Radar Level Transmitter - IFR | 10 | 2026-07-27 | 2026-08-13 | 27 | PTTME Office 5dx8h
IN-4000 | Material Requisition For Guided Wave Radar Level Transmitter - AFC | 5 | 2026-11-16 | 2026-11-20 | 27 | PTTME Office 5dx8h
IN-4010 | Material Requisition For Dp Level Transmitters - IFR | 10 | 2026-07-27 | 2026-08-13 | 27 | PTTME Office 5dx8h
IN-4020 | Material Requisition For Dp Level Transmitters - AFC | 5 | 2026-11-16 | 2026-11-20 | 27 | PTTME Office 5dx8h
IN-4030 | Material Requisition For Instrument Cables - IFR | 10 | 2026-09-08 | 2026-09-21 | 4 | PTTME Office 5dx8h
IN-4040 | Material Requisition For Instrument Cables - AFC | 5 | 2026-12-21 | 2026-12-28 | 4 | PTTME Office 5dx8h
IN-4050 | Material Requisition For Restriction Orifice - IFR | 10 | 2026-09-07 | 2026-09-18 | 16 | PTTME Office 5dx8h
IN-4060 | Material Requisition For Restriction Orifice - AFC | 5 | 2026-12-01 | 2026-12-08 | 16 | PTTME Office 5dx8h
IN-4070 | Material Requisition For Fire & Gas Detectors - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-4080 | Material Requisition For Fire & Gas Detectors - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-4090 | Material Requisition For Position Limit Switches - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-4100 | Material Requisition For Position Limit Switches - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-4110 | Material Requisition For Oil In Water Analyzer - Wp02 - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-4120 | Material Requisition For Oil In Water Analyzer - Wp02 - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-4130 | Material Requisition For Pig Signaller - IFR | 10 | 2026-09-07 | 2026-09-18 | 5 | PTTME Office 5dx8h
IN-4140 | Material Requisition For Pig Signaller - AFC | 5 | 2026-12-18 | 2026-12-24 | 5 | PTTME Office 5dx8h
IN-4150 | Material Requisition For Instrument Bulk Materials - IFR | 10 | 2026-09-17 | 2026-09-30 | 7 | PTTME Office 5dx8h
IN-4160 | Material Requisition For Instrument Bulk Materials - AFC | 5 | 2026-12-16 | 2026-12-22 | 7 | PTTME Office 5dx8h
TBE-Instrument |  | 124 | 2026-06-04 | 2026-12-02 | 4 | PTTME Office 5dx8h
IN-4170 | Technical Bid Evaluation For SCADA - IFR | 20 | 2026-06-09 | 2026-07-06 | 90 | PTTME Office 5dx8h
IN-4180 | Technical Bid Evaluation For SCADA - AFC | 5 | 2026-07-21 | 2026-07-27 | 90 | PTTME Office 5dx8h
IN-4190 | Technical Bid Evaluation For Wellhead Control Panel - IFR | 20 | 2026-06-10 | 2026-07-07 | 0 | PTTME Office 5dx8h
IN-4200 | Technical Bid Evaluation For Wellhead Control Panel - AFC | 5 | 2026-07-22 | 2026-07-31 | 0 | PTTME Office 5dx8h
IN-4210 | Technical Bid Evaluation For PLC And SCADA System - IFR | 20 | 2026-06-05 | 2026-07-02 | 42 | PTTME Office 5dx8h
IN-4220 | Technical Bid Evaluation For PLC And SCADA System - AFC | 5 | 2026-07-17 | 2026-07-23 | 42 | PTTME Office 5dx8h
IN-4230 | Technical Bid Evaluation For Control Valves - IFR | 18 | 2026-09-24 | 2026-10-20 | 19 | PTTME Office 5dx8h
IN-4240 | Technical Bid Evaluation For Control Valves - AFC | 5 | 2026-11-05 | 2026-11-11 | 19 | PTTME Office 5dx8h
IN-4250 | Technical Bid Evaluation For Self Regulator Valves - IFR | 18 | 2026-09-29 | 2026-10-26 | 16 | PTTME Office 5dx8h
IN-4260 | Technical Bid Evaluation For Self Regulator Valves - AFC | 5 | 2026-11-10 | 2026-11-16 | 16 | PTTME Office 5dx8h
IN-4270 | Technical Bid Evaluation For Actuated Choke Valves - IFR | 20 | 2026-06-04 | 2026-07-01 | 93 | PTTME Office 5dx8h
IN-4280 | Technical Bid Evaluation For Actuated Choke Valves - AFC | 5 | 2026-07-16 | 2026-07-22 | 93 | PTTME Office 5dx8h
IN-4290 | Technical Bid Evaluation For Actuated Ball Valves - IFR | 19 | 2026-07-27 | 2026-08-26 | 57 | PTTME Office 5dx8h
IN-4300 | Technical Bid Evaluation For Actuated Ball Valves - AFC | 5 | 2026-09-10 | 2026-09-16 | 57 | PTTME Office 5dx8h
IN-4310 | Technical Bid Evaluation For Actuated Compact Ball Valves - IFR | 17 | 2026-07-07 | 2026-08-03 | 0 | PTTME Office 5dx8h
IN-4320 | Technical Bid Evaluation For Actuated Compact Ball Valves - AFC | 5 | 2026-08-19 | 2026-08-25 | 0 | PTTME Office 5dx8h
IN-4330 | Technical Bid Evaluation For Safety Relief Valves - IFR | 19 | 2026-10-15 | 2026-11-11 | 4 | PTTME Office 5dx8h
IN-4340 | Technical Bid Evaluation For Safety Relief Valves - AFC | 5 | 2026-11-26 | 2026-12-02 | 4 | PTTME Office 5dx8h
IN-4350 | Technical Bid Evaluation For Coriolis Flow Meters - IFR | 19 | 2026-09-30 | 2026-10-28 | 14 | PTTME Office 5dx8h
IN-4360 | Technical Bid Evaluation For Coriolis Flow Meters - AFC | 5 | 2026-11-12 | 2026-11-18 | 14 | PTTME Office 5dx8h
IN-4370 | Technical Bid Evaluation For Vortex Flow Meters - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4380 | Technical Bid Evaluation For Vortex Flow Meters - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4390 | Technical Bid Evaluation For Flow Switch - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4400 | Technical Bid Evaluation For Flow Switch - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4410 | Technical Bid Evaluation For Pressure Gauges - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4420 | Technical Bid Evaluation For Pressure Gauges - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4430 | Technical Bid Evaluation For Pressure Transmitters - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4440 | Technical Bid Evaluation For Pressure Transmitters - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4450 | Technical Bid Evaluation For Temperature Gauges - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4460 | Technical Bid Evaluation For Temperature Gauges - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4470 | Technical Bid Evaluation For Temperature Transmitters - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4480 | Technical Bid Evaluation For Temperature Transmitters - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4490 | Technical Bid Evaluation For Level Gauge And Transmitters - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4500 | Technical Bid Evaluation For Level Gauge And Transmitters - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4510 | Technical Bid Evaluation For Dip Tape Level Indicator - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4520 | Technical Bid Evaluation For Dip Tape Level Indicator - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4530 | Technical Bid Evaluation For Level Switch - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4540 | Technical Bid Evaluation For Level Switch - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4550 | Technical Bid Evaluation For Guided Wave Radar Level Transmitter - IFR | 20 | 2026-09-10 | 2026-10-07 | 27 | PTTME Office 5dx8h
IN-4560 | Technical Bid Evaluation For Guided Wave Radar Level Transmitter - AFC | 5 | 2026-10-26 | 2026-10-30 | 27 | PTTME Office 5dx8h
IN-4570 | Technical Bid Evaluation For Dp Level Transmitters - IFR | 20 | 2026-09-10 | 2026-10-07 | 27 | PTTME Office 5dx8h
IN-4580 | Technical Bid Evaluation For Dp Level Transmitters - AFC | 5 | 2026-10-26 | 2026-10-30 | 27 | PTTME Office 5dx8h
IN-4590 | Technical Bid Evaluation For Instrument Cables - IFR | 19 | 2026-10-15 | 2026-11-11 | 4 | PTTME Office 5dx8h
IN-4600 | Technical Bid Evaluation For Instrument Cables - AFC | 5 | 2026-11-26 | 2026-12-02 | 4 | PTTME Office 5dx8h
IN-4610 | Technical Bid Evaluation For Restriction Orifice - IFR | 20 | 2026-10-06 | 2026-11-04 | 16 | PTTME Office 5dx8h
IN-4620 | Technical Bid Evaluation For Restriction Orifice - AFC | 3 | 2026-11-12 | 2026-11-16 | 16 | PTTME Office 5dx8h
IN-4630 | Technical Bid Evaluation For Fire & Gas Detectors - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4640 | Technical Bid Evaluation For Fire & Gas Detectors - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4650 | Technical Bid Evaluation For Position Limit Switches - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4660 | Technical Bid Evaluation For Position Limit Switches - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4670 | Technical Bid Evaluation For Oil In Water Analyzer - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4680 | Technical Bid Evaluation For Oil In Water Analyzer - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4690 | Technical Bid Evaluation For Pig Signaller - IFR | 19 | 2026-10-14 | 2026-11-10 | 5 | PTTME Office 5dx8h
IN-4700 | Technical Bid Evaluation For Pig Signaller - AFC | 5 | 2026-11-25 | 2026-12-01 | 5 | PTTME Office 5dx8h
IN-4710 | Technical Bid Evaluation For Instrument Bulk Materials - IFR | 15 | 2026-10-16 | 2026-11-06 | 7 | PTTME Office 5dx8h
IN-4720 | Technical Bid Evaluation For Instrument Bulk Materials - AFC | 5 | 2026-11-23 | 2026-11-27 | 7 | PTTME Office 5dx8h
TELECOMMUNICATIONENGINEERING |  | 180 | 2026-03-25 | 2026-12-22 | 7 | PTTME Office 5dx8h
TE-1000 | Telecommunication Basis Of Design - IFR | 10 | 2026-03-25 | 2026-04-08 | -10 | PTTME Office 5dx8h
TE-1010 | Telecommunication Basis Of Design - IFA | 10 | 2026-04-28 | 2026-05-12 | 142 | PTTME Office 5dx8h
TE-1020 | Telecommunication Basis Of Design - AFC | 5 | 2026-05-27 | 2026-06-04 | 142 | PTTME Office 5dx8h
TE-1030 | Whp Telecommunication System Philosophy - IFR | 10 | 2026-03-25 | 2026-04-08 | -10 | PTTME Office 5dx8h
TE-1040 | Whp Telecommunication System Philosophy - IFA | 5 | 2026-04-28 | 2026-05-05 | 28 | PTTME Office 5dx8h
TE-1050 | Whp Telecommunication System Philosophy - AFC | 5 | 2026-05-20 | 2026-05-26 | 28 | PTTME Office 5dx8h
TE-1060 | Project Specification For Telecommunication Package - IFR | 15 | 2026-04-09 | 2026-05-05 | -10 | PTTME Office 5dx8h
TE-1070 | Project Specification For Telecommunication Package - AFC | 5 | 2026-05-27 | 2026-06-04 | 28 | PTTME Office 5dx8h
TE-1080 | Project Specification For Marine Racon - IFR | 15 | 2026-04-09 | 2026-05-05 | 7 | PTTME Office 5dx8h
TE-1090 | Project Specification For Marine Racon - AFC | 5 | 2026-05-27 | 2026-06-04 | 87 | PTTME Office 5dx8h
TE-1100 | Vsat Location Options And Selection Report - IFR | 20 | 2026-05-06 | 2026-06-04 | 7 | PTTME Office 5dx8h
TE-1110 | Vsat Location Options And Selection Report - IFA | 10 | 2026-06-19 | 2026-07-02 | 42 | PTTME Office 5dx8h
TE-1120 | Vsat Location Options And Selection Report - AFC | 5 | 2026-07-17 | 2026-07-23 | 57 | PTTME Office 5dx8h
TE-1130 | Design Report For Communication Links - IFR | 20 | 2026-05-06 | 2026-06-04 | 7 | PTTME Office 5dx8h
TE-1140 | Design Report For Communication Links - IFA | 10 | 2026-06-19 | 2026-07-02 | 42 | PTTME Office 5dx8h
TE-1150 | Design Report For Communication Links - AFC | 5 | 2026-07-17 | 2026-07-23 | 57 | PTTME Office 5dx8h
TE-1160 | Design Report For Overall Transmission Media Requirements - IFR | 20 | 2026-05-20 | 2026-06-18 | 7 | PTTME Office 5dx8h
TE-1170 | Design Report For Overall Transmission Media Requirements - IFA | 10 | 2026-07-03 | 2026-07-16 | 32 | PTTME Office 5dx8h
TE-1180 | Design Report For Overall Transmission Media Requirements - AFC | 5 | 2026-08-05 | 2026-08-11 | 47 | PTTME Office 5dx8h
TE-1190 | Design Report For Telecommunication Equipment On Whp'S Safety Zone With Fire And Explosion Risk Analysis - IFR | 20 | 2026-05-20 | 2026-06-18 | 7 | PTTME Office 5dx8h
TE-1200 | Design Report For Telecommunication Equipment On Whp'S Safety Zone With Fire And Explosion Risk Analysis - IFA | 10 | 2026-07-03 | 2026-07-16 | 32 | PTTME Office 5dx8h
TE-1210 | Design Report For Telecommunication Equipment On Whp'S Safety Zone With Fire And Explosion Risk Analysis - AFC | 5 | 2026-08-05 | 2026-08-11 | 47 | PTTME Office 5dx8h
TE-1220 | Telecommuniction Equipment And Ex-Certificates List - IFR | 15 | 2026-06-19 | 2026-07-09 | 7 | PTTME Office 5dx8h
TE-1230 | Telecommuniction Equipment And Ex-Certificates List - IFA | 10 | 2026-07-24 | 2026-08-11 | 27 | PTTME Office 5dx8h
TE-1240 | Telecommuniction Equipment And Ex-Certificates List - AFC | 5 | 2026-08-27 | 2026-09-02 | 37 | PTTME Office 5dx8h
TE-1250 | Overall Telecommunication System Block Diagram - IFR | 15 | 2026-06-19 | 2026-07-09 | 62 | PTTME Office 5dx8h
TE-1260 | Overall Telecommunication System Block Diagram - IFA | 10 | 2026-07-24 | 2026-08-11 | 67 | PTTME Office 5dx8h
TE-1270 | Overall Telecommunication System Block Diagram - AFC | 10 | 2026-08-27 | 2026-09-09 | 67 | PTTME Office 5dx8h
TE-1490 | Telecommuniction Document Index - Wp01 - IFR | 15 | 2026-06-19 | 2026-07-09 | 7 | PTTME Office 5dx8h
TE-1500 | Telecommuniction Document Index - Wp01 - IFA | 10 | 2026-07-24 | 2026-08-11 | 27 | PTTME Office 5dx8h
TE-1510 | Telecommuniction Document Index - Wp01 - AFC | 10 | 2026-08-27 | 2026-09-09 | 32 | PTTME Office 5dx8h
TE-1520 | Telecommuniction Equipment List - Wp01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 7 | PTTME Office 5dx8h
TE-1530 | Telecommuniction Equipment List - Wp01 - IFA | 10 | 2026-08-13 | 2026-08-26 | 27 | PTTME Office 5dx8h
TE-1540 | Telecommuniction Equipment List - Wp01 - AFC | 10 | 2026-09-10 | 2026-09-23 | 32 | PTTME Office 5dx8h
TE-1550 | Telecommuniction Cable Schedule - Wp01 - IFR | 15 | 2026-06-26 | 2026-07-16 | 7 | PTTME Office 5dx8h
TE-1560 | Telecommuniction Cable Schedule - Wp01 - IFA | 10 | 2026-08-27 | 2026-09-09 | 27 | PTTME Office 5dx8h
TE-1570 | Telecommuniction Cable Schedule - Wp01 - AFC | 10 | 2026-09-24 | 2026-10-07 | 32 | PTTME Office 5dx8h
TE-1580 | Telecommuniction Power Cpnstruction And Heat Dissipation List - Wp01 - IFR | 20 | 2026-07-17 | 2026-08-19 | 7 | PTTME Office 5dx8h
TE-1590 | Telecommuniction Power Cpnstruction And Heat Dissipation List - Wp01 - IFA | 15 | 2026-09-03 | 2026-09-23 | 22 | PTTME Office 5dx8h
TE-1600 | Telecommuniction Power Cpnstruction And Heat Dissipation List - Wp01 - AFC | 15 | 2026-10-08 | 2026-10-30 | 22 | PTTME Office 5dx8h
TE-1610 | Telecommuniction Bulk Material Take -Off - Wp01 - IFR | 15 | 2026-08-20 | 2026-09-09 | 7 | PTTME Office 5dx8h
TE-1620 | Telecommuniction Bulk Material Take -Off - Wp01 - IFA | 10 | 2026-09-24 | 2026-10-07 | 22 | PTTME Office 5dx8h
TE-1630 | Telecommuniction Bulk Material Take -Off - Wp01 - AFC | 10 | 2026-10-26 | 2026-11-06 | 22 | PTTME Office 5dx8h
TE-1850 | Telecommuniction Document Index - Wp02 - IFR | 15 | 2026-06-19 | 2026-07-09 | 77 | PTTME Office 5dx8h
TE-1860 | Telecommuniction Document Index - Wp02 - IFA | 10 | 2026-07-24 | 2026-08-11 | 77 | PTTME Office 5dx8h
TE-1870 | Telecommuniction Document Index - Wp02 - AFC | 10 | 2026-08-27 | 2026-09-09 | 77 | PTTME Office 5dx8h
TE-1880 | Telecommuniction Equipment List - Wp02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
TE-1890 | Telecommuniction Equipment List - Wp02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
TE-1900 | Telecommuniction Equipment List - Wp02 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
TE-1910 | Telecommuniction Cable Schedule - Wp02 - IFR | 15 | 2026-06-26 | 2026-07-16 | 72 | PTTME Office 5dx8h
TE-1920 | Telecommuniction Cable Schedule - Wp02 - IFA | 10 | 2026-08-05 | 2026-08-19 | 72 | PTTME Office 5dx8h
TE-1930 | Telecommuniction Cable Schedule - Wp02 - AFC | 10 | 2026-09-03 | 2026-09-16 | 72 | PTTME Office 5dx8h
TE-1940 | Telecommuniction Power Cpnstruction And Heat Dissipation List - Wp02 - IFR | 20 | 2026-07-17 | 2026-08-19 | 22 | PTTME Office 5dx8h
TE-1950 | Telecommuniction Power Cpnstruction And Heat Dissipation List - Wp02 - IFA | 15 | 2026-09-03 | 2026-09-23 | 22 | PTTME Office 5dx8h
TE-1960 | Telecommuniction Power Cpnstruction And Heat Dissipation List - Wp02 - AFC | 15 | 2026-10-08 | 2026-10-30 | 22 | PTTME Office 5dx8h
TE-1970 | Telecommuniction Bulk Material Take -Off - Wp02 - IFR | 15 | 2026-08-20 | 2026-09-09 | 7 | PTTME Office 5dx8h
TE-1980 | Telecommuniction Bulk Material Take -Off - Wp02 - IFA | 10 | 2026-09-24 | 2026-10-07 | 22 | PTTME Office 5dx8h
TE-1990 | Telecommuniction Bulk Material Take -Off - Wp02 - AFC | 10 | 2026-10-26 | 2026-11-06 | 22 | PTTME Office 5dx8h
TE-2000 | Telecommuniction Drawing Index - Wp01 - IFR | 15 | 2026-06-19 | 2026-07-09 | 77 | PTTME Office 5dx8h
TE-2010 | Telecommuniction Drawing Index - Wp01 - IFA | 10 | 2026-07-24 | 2026-08-11 | 77 | PTTME Office 5dx8h
TE-2020 | Telecommuniction Drawing Index - Wp01 - AFC | 10 | 2026-08-27 | 2026-09-09 | 77 | PTTME Office 5dx8h
TE-2030 | Telecommuniction System Block Diagram - Wp01 - IFR | 15 | 2026-07-10 | 2026-08-04 | 62 | PTTME Office 5dx8h
TE-2040 | Telecommuniction System Block Diagram - Wp01 - IFA | 10 | 2026-08-20 | 2026-09-02 | 62 | PTTME Office 5dx8h
TE-2050 | Telecommuniction System Block Diagram - Wp01 - AFC | 10 | 2026-09-10 | 2026-09-23 | 67 | PTTME Office 5dx8h
TE-2060 | Telecommuniction Equipment Layout - Wp01 - IFR | 15 | 2026-07-17 | 2026-08-11 | 37 | PTTME Office 5dx8h
TE-2070 | Telecommuniction Equipment Layout - Wp01 - IFA | 10 | 2026-08-27 | 2026-09-09 | 37 | PTTME Office 5dx8h
TE-2080 | Telecommuniction Equipment Layout - Wp01 - AFC | 10 | 2026-09-24 | 2026-10-07 | 37 | PTTME Office 5dx8h
TE-2090 | Telecommuniction Cable Routing Plan - Wp01 - IFR | 15 | 2026-08-05 | 2026-08-26 | 37 | PTTME Office 5dx8h
TE-2100 | Telecommuniction Cable Routing Plan - Wp01 - IFA | 10 | 2026-09-10 | 2026-09-23 | 37 | PTTME Office 5dx8h
TE-2110 | Telecommuniction Cable Routing Plan - Wp01 - AFC | 10 | 2026-10-08 | 2026-10-22 | 37 | PTTME Office 5dx8h
TE-2120 | Telecommuniction Schematic Diagram - Wp01 - IFR | 15 | 2026-08-05 | 2026-08-26 | 37 | PTTME Office 5dx8h
TE-2130 | Telecommuniction Schematic Diagram - Wp01 - IFA | 10 | 2026-09-24 | 2026-10-07 | 37 | PTTME Office 5dx8h
TE-2140 | Telecommuniction Schematic Diagram - Wp01 - AFC | 10 | 2026-10-26 | 2026-11-06 | 37 | PTTME Office 5dx8h
TE-2150 | Telecommuniction System Wiring Diagram - Wp01 - IFR | 15 | 2026-08-20 | 2026-09-09 | 37 | PTTME Office 5dx8h
TE-2160 | Telecommuniction System Wiring Diagram - Wp01 - IFA | 10 | 2026-09-24 | 2026-10-07 | 37 | PTTME Office 5dx8h
TE-2170 | Telecommuniction System Wiring Diagram - Wp01 - AFC | 10 | 2026-10-26 | 2026-11-06 | 37 | PTTME Office 5dx8h
TE-2180 | Telecommuniction Installation And Mounting Detail - Wp01 - IFR | 15 | 2026-08-20 | 2026-09-09 | 37 | PTTME Office 5dx8h
TE-2190 | Telecommuniction Installation And Mounting Detail - Wp01 - IFA | 10 | 2026-09-24 | 2026-10-07 | 37 | PTTME Office 5dx8h
TE-2200 | Telecommuniction Installation And Mounting Detail - Wp01 - AFC | 10 | 2026-10-26 | 2026-11-06 | 37 | PTTME Office 5dx8h
TE-2210 | Telecommuniction Drawing Index - Wp02 - IFR | 15 | 2026-06-19 | 2026-07-09 | 77 | PTTME Office 5dx8h
TE-2220 | Telecommuniction Drawing Index - Wp02 - IFA | 10 | 2026-07-24 | 2026-08-11 | 77 | PTTME Office 5dx8h
TE-2230 | Telecommuniction Drawing Index - Wp02 - AFC | 10 | 2026-08-27 | 2026-09-09 | 77 | PTTME Office 5dx8h
TE-2240 | Telecommuniction System Block Diagram - Wp02 - IFR | 15 | 2026-07-10 | 2026-08-04 | 62 | PTTME Office 5dx8h
TE-2250 | Telecommuniction System Block Diagram - Wp02 - IFA | 10 | 2026-08-20 | 2026-09-02 | 62 | PTTME Office 5dx8h
TE-2260 | Telecommuniction System Block Diagram - Wp02 - AFC | 10 | 2026-09-17 | 2026-09-30 | 62 | PTTME Office 5dx8h
TE-2270 | Telecommuniction Equipment Layout - Wp02 - IFR | 15 | 2026-07-17 | 2026-08-11 | 57 | PTTME Office 5dx8h
TE-2280 | Telecommuniction Equipment Layout - Wp02 - IFA | 10 | 2026-08-27 | 2026-09-09 | 57 | PTTME Office 5dx8h
TE-2290 | Telecommuniction Equipment Layout - Wp02 - AFC | 10 | 2026-09-24 | 2026-10-07 | 57 | PTTME Office 5dx8h
TE-2300 | Telecommuniction Cable Routing Plan - Wp02 - IFR | 15 | 2026-08-05 | 2026-08-26 | 47 | PTTME Office 5dx8h
TE-2310 | Telecommuniction Cable Routing Plan - Wp02 - IFA | 10 | 2026-09-10 | 2026-09-23 | 47 | PTTME Office 5dx8h
TE-2320 | Telecommuniction Cable Routing Plan - Wp02 - AFC | 10 | 2026-10-08 | 2026-10-22 | 47 | PTTME Office 5dx8h
TE-2330 | Telecommuniction Schematic Diagram - Wp02 - IFR | 15 | 2026-08-05 | 2026-08-26 | 47 | PTTME Office 5dx8h
TE-2340 | Telecommuniction Schematic Diagram - Wp02 - IFA | 10 | 2026-09-24 | 2026-10-07 | 37 | PTTME Office 5dx8h
TE-2350 | Telecommuniction Schematic Diagram - Wp02 - AFC | 10 | 2026-10-26 | 2026-11-06 | 37 | PTTME Office 5dx8h
TE-2360 | Telecommuniction System Wiring Diagram - Wp02 - IFR | 15 | 2026-08-20 | 2026-09-09 | 37 | PTTME Office 5dx8h
TE-2370 | Telecommuniction System Wiring Diagram - Wp02 - IFA | 10 | 2026-09-24 | 2026-10-07 | 37 | PTTME Office 5dx8h
TE-2380 | Telecommuniction System Wiring Diagram - Wp02 - AFC | 10 | 2026-10-26 | 2026-11-06 | 37 | PTTME Office 5dx8h
TE-2390 | Telecommuniction Installation And Mounting Detail - Wp02 - IFR | 15 | 2026-08-20 | 2026-09-09 | 37 | PTTME Office 5dx8h
TE-2400 | Telecommuniction Installation And Mounting Detail - Wp02 - IFA | 10 | 2026-09-24 | 2026-10-07 | 37 | PTTME Office 5dx8h
TE-2410 | Telecommuniction Installation And Mounting Detail - Wp02 - AFC | 10 | 2026-10-26 | 2026-11-06 | 37 | PTTME Office 5dx8h
TE-2550 | Telecommunication Shiploose List For Offshore Installation - IFR | 15 | 2026-09-10 | 2026-09-30 | 42 | PTTME Office 5dx8h
TE-2560 | Telecommunication Shiploose List For Offshore Installation - AFC | 10 | 2026-10-26 | 2026-11-06 | 37 | PTTME Office 5dx8h
TE-2570 | Telecommunication Shiploose List Handover To Company Operation Team - IFR | 15 | 2026-09-10 | 2026-09-30 | 42 | PTTME Office 5dx8h
TE-2580 | Telecommunication Shiploose List Handover To Company Operation Team - AFC | 10 | 2026-10-26 | 2026-11-06 | 37 | PTTME Office 5dx8h
Datasheets-Telecommunication |  | 135 | 2026-05-06 | 2026-11-20 | 27 | PTTME Office 5dx8h
TE-1280 | Data Sheet For Wimax Radio - Wp01 - IFR | 15 | 2026-08-05 | 2026-08-26 | 7 | PTTME Office 5dx8h
TE-1290 | Data Sheet For Wimax Radio - Wp01 - IFA | 10 | 2026-09-10 | 2026-09-23 | 42 | PTTME Office 5dx8h
TE-1300 | Data Sheet For Wimax Radio - Wp01 - AFC | 10 | 2026-11-09 | 2026-11-20 | 22 | PTTME Office 5dx8h
TE-1310 | Data Sheet For Radar Beacon - Wp01 - IFR | 15 | 2026-08-05 | 2026-08-26 | 7 | PTTME Office 5dx8h
TE-1320 | Data Sheet For Radar Beacon - Wp01 - IFA | 10 | 2026-09-10 | 2026-09-23 | 42 | PTTME Office 5dx8h
TE-1330 | Data Sheet For Radar Beacon - Wp01 - AFC | 10 | 2026-11-09 | 2026-11-20 | 22 | PTTME Office 5dx8h
TE-1340 | Data Sheet For Automatic Identification System - Wp01 - IFR | 15 | 2026-08-05 | 2026-08-26 | 7 | PTTME Office 5dx8h
TE-1350 | Data Sheet For Automatic Identification System - Wp01 - IFA | 10 | 2026-09-10 | 2026-09-23 | 42 | PTTME Office 5dx8h
TE-1360 | Data Sheet For Automatic Identification System - Wp01 - AFC | 10 | 2026-11-09 | 2026-11-20 | 22 | PTTME Office 5dx8h
TE-1370 | Data Sheet For Vhf-Dmr - Wp01 - IFR | 15 | 2026-08-05 | 2026-08-26 | 7 | PTTME Office 5dx8h
TE-1380 | Data Sheet For Vhf-Dmr - Wp01 - IFA | 10 | 2026-09-10 | 2026-09-23 | 42 | PTTME Office 5dx8h
TE-1390 | Data Sheet For Vhf-Dmr - Wp01 - AFC | 10 | 2026-11-09 | 2026-11-20 | 22 | PTTME Office 5dx8h
TE-1400 | Data Sheet For Vhf-Fm - Wp01 - IFR | 15 | 2026-08-05 | 2026-08-26 | 7 | PTTME Office 5dx8h
TE-1410 | Data Sheet For Vhf-Fm - Wp01 - IFA | 10 | 2026-09-10 | 2026-09-23 | 42 | PTTME Office 5dx8h
TE-1420 | Data Sheet For Vhf-Fm - Wp01 - AFC | 10 | 2026-11-09 | 2026-11-20 | 22 | PTTME Office 5dx8h
TE-1430 | Data Sheet For Telephone - Wp01 - IFR | 10 | 2026-05-06 | 2026-05-19 | -10 | PTTME Office 5dx8h
TE-1440 | Data Sheet For Telephone - Wp01 - IFA | 10 | 2026-06-05 | 2026-06-18 | 5 | PTTME Office 5dx8h
TE-1450 | Data Sheet For Telephone - Wp01 - AFC | 10 | 2026-07-16 | 2026-08-03 | -1 | PTTME Office 5dx8h
TE-1460 | Data Sheet For Bulk Material - Wp01 - IFR | 10 | 2026-09-10 | 2026-09-23 | 7 | PTTME Office 5dx8h
TE-1470 | Data Sheet For Bulk Material - Wp01 - IFA | 10 | 2026-10-08 | 2026-10-22 | 22 | PTTME Office 5dx8h
TE-1480 | Data Sheet For Bulk Material - Wp01 - AFC | 10 | 2026-11-09 | 2026-11-20 | 22 | PTTME Office 5dx8h
TE-1640 | Data Sheet For Wimax Radio - Wp02 - IFR | 15 | 2026-08-05 | 2026-08-26 | 47 | PTTME Office 5dx8h
TE-1650 | Data Sheet For Wimax Radio - Wp02 - IFA | 10 | 2026-09-10 | 2026-09-23 | 47 | PTTME Office 5dx8h
TE-1660 | Data Sheet For Wimax Radio - Wp02 - AFC | 10 | 2026-11-09 | 2026-11-20 | 27 | PTTME Office 5dx8h
TE-1670 | Data Sheet For Radar Beacon - Wp02 - IFR | 15 | 2026-08-05 | 2026-08-26 | 47 | PTTME Office 5dx8h
TE-1680 | Data Sheet For Radar Beacon - Wp02 - IFA | 10 | 2026-09-10 | 2026-09-23 | 47 | PTTME Office 5dx8h
TE-1690 | Data Sheet For Radar Beacon - Wp02 - AFC | 10 | 2026-11-09 | 2026-11-20 | 27 | PTTME Office 5dx8h
TE-1700 | Data Sheet For Automatic Identification System - Wp02 - IFR | 15 | 2026-08-05 | 2026-08-26 | 47 | PTTME Office 5dx8h
TE-1710 | Data Sheet For Automatic Identification System - Wp02 - IFA | 10 | 2026-09-10 | 2026-09-23 | 47 | PTTME Office 5dx8h
TE-1720 | Data Sheet For Automatic Identification System - Wp02 - AFC | 10 | 2026-11-09 | 2026-11-20 | 27 | PTTME Office 5dx8h
TE-1730 | Data Sheet For Vhf-Dmr - Wp02 - IFR | 15 | 2026-08-05 | 2026-08-26 | 47 | PTTME Office 5dx8h
TE-1740 | Data Sheet For Vhf-Dmr - Wp02 - IFA | 10 | 2026-09-10 | 2026-09-23 | 47 | PTTME Office 5dx8h
TE-1750 | Data Sheet For Vhf-Dmr - Wp02 - AFC | 10 | 2026-11-09 | 2026-11-20 | 27 | PTTME Office 5dx8h
TE-1760 | Data Sheet For Vhf-Fm - Wp02 - IFR | 15 | 2026-08-05 | 2026-08-26 | 47 | PTTME Office 5dx8h
TE-1770 | Data Sheet For Vhf-Fm - Wp02 - IFA | 10 | 2026-09-10 | 2026-09-23 | 47 | PTTME Office 5dx8h
TE-1780 | Data Sheet For Vhf-Fm - Wp02 - AFC | 10 | 2026-11-09 | 2026-11-20 | 27 | PTTME Office 5dx8h
TE-1790 | Data Sheet For Telephone - Wp02 - IFR | 10 | 2026-05-06 | 2026-05-19 | -10 | PTTME Office 5dx8h
TE-1800 | Data Sheet For Telephone - Wp02 - IFA | 10 | 2026-06-05 | 2026-06-18 | 5 | PTTME Office 5dx8h
TE-1810 | Data Sheet For Telephone - Wp02 - AFC | 10 | 2026-07-16 | 2026-08-03 | -1 | PTTME Office 5dx8h
TE-1820 | Data Sheet For Bulk Material - Wp02 - IFR | 10 | 2026-09-10 | 2026-09-23 | 7 | PTTME Office 5dx8h
TE-1830 | Data Sheet For Bulk Material - Wp02 - IFA | 10 | 2026-10-08 | 2026-10-22 | 22 | PTTME Office 5dx8h
TE-1840 | Data Sheet For Bulk Material - Wp02 - AFC | 10 | 2026-11-09 | 2026-11-20 | 22 | PTTME Office 5dx8h
MR-Telecommunication |  | 153 | 2026-05-08 | 2026-12-22 | 7 | PTTME Office 5dx8h
TE-2420 | Material Requisition For Telecommunication System - IFR | 10 | 2026-05-08 | 2026-05-21 | -10 | PTTME Office 5dx8h
TE-2430 | Material Requisition For Telecommunication System - IFA | 10 | 2026-06-19 | 2026-07-02 | 5 | PTTME Office 5dx8h
TE-2440 | Material Requisition For Telecommunication System - AFC | 5 | 2026-08-11 | 2026-08-18 | -10 | PTTME Office 5dx8h
TE-2450 | Material Requisition For Marine Racon (Racon) - IFR | 15 | 2026-08-27 | 2026-09-16 | 7 | PTTME Office 5dx8h
TE-2460 | Material Requisition For Marine Racon (Racon) - AFC | 5 | 2026-12-16 | 2026-12-22 | 7 | PTTME Office 5dx8h
TE-2470 | Material Requisition For For Telecommunication Bulk Material - IFR | 10 | 2026-09-10 | 2026-09-23 | 7 | PTTME Office 5dx8h
TE-2480 | Material Requisition For For Telecommunication Bulk Material - AFC | 5 | 2026-12-16 | 2026-12-22 | 7 | PTTME Office 5dx8h
TBE-Telecommunication |  | 111 | 2026-06-18 | 2026-11-27 | 7 | PTTME Office 5dx8h
TE-2490 | Technical Bid Evaluation For Telecommunication System - IFR | 20 | 2026-06-18 | 2026-07-15 | -10 | PTTME Office 5dx8h
TE-2500 | Technical Bid Evaluation For Telecommunication System - AFC | 5 | 2026-08-04 | 2026-08-10 | -10 | PTTME Office 5dx8h
TE-2510 | Technical Bid Evaluation For Marine Racon (Racon) - IFR | 20 | 2026-10-08 | 2026-11-06 | 7 | PTTME Office 5dx8h
TE-2520 | Technical Bid Evaluation For Marine Racon (Racon) - AFC | 5 | 2026-11-23 | 2026-11-27 | 7 | PTTME Office 5dx8h
TE-2530 | Technical Bid Evaluation For Telecommunication Bulk Material - IFR | 20 | 2026-10-08 | 2026-11-06 | 7 | PTTME Office 5dx8h
TE-2540 | Technical Bid Evaluation For Telecommunication Bulk Material - AFC | 5 | 2026-11-23 | 2026-11-27 | 7 | PTTME Office 5dx8h
SAFETY |  | 180 | 2026-03-04 | 2026-11-27 | 22 | PTTME Office 5dx8h
SF-1000 | Safety Security Health and Environment Concept (SSHE) (Offshore) - IFR | 20 | 2026-03-04 | 2026-03-31 | 52 | PTTME Office 5dx8h
SF-1010 | Safety Security Health and Environment Concept (SSHE) (Offshore) - IFA | 10 | 2026-04-21 | 2026-05-05 | 142 | PTTME Office 5dx8h
SF-1020 | Safety Security Health and Environment Concept (SSHE) (Offshore) - AFC | 10 | 2026-05-20 | 2026-06-04 | 142 | PTTME Office 5dx8h
SF-1030 | FERA and QRA Assumption Register - IFR | 20 | 2026-03-31 | 2026-05-04 | 143 | PTTME Office 5dx8h
SF-1040 | FERA and QRA Assumption Register - AFC | 10 | 2026-05-19 | 2026-06-02 | 143 | PTTME Office 5dx8h
SF-1050 | Reliability, Availability and Maintainability (RAM) Study Assumption Register - IFR | 20 | 2026-03-30 | 2026-04-30 | 101 | PTTME Office 5dx8h
SF-1060 | Reliability, Availability and Maintainability (RAM) Study Assumption Register - AFC | 10 | 2026-05-18 | 2026-05-29 | 144 | PTTME Office 5dx8h
SF-1070 | Reliability, Availability and Maintainability (RAM) Study Report (for WHP) - IFR | 30 | 2026-05-21 | 2026-07-03 | 101 | PTTME Office 5dx8h
SF-1080 | Reliability, Availability and Maintainability (RAM) Study Report (for WHP) - AFC | 10 | 2026-07-20 | 2026-08-05 | 101 | PTTME Office 5dx8h
SF-1090 | HAZID TOR (Offshore) - IFR | 10 | 2026-04-09 | 2026-04-27 | 152 | PTTME Office 5dx8h
SF-1100 | HAZID TOR (Offshore) - AFC | 5 | 2026-05-13 | 2026-05-19 | 152 | PTTME Office 5dx8h
SF-1110 | HAZID Report (Offshore) - IFR | 10 | 2026-05-22 | 2026-06-08 | 105 | PTTME Office 5dx8h
SF-1120 | HAZID Report (Offshore) - AFC | 5 | 2026-06-23 | 2026-06-29 | 105 | PTTME Office 5dx8h
SF-1121 | HAZID Closed Out Report - IFI | 5 | 2026-06-30 | 2026-07-06 | 105 | PTTME Office 5dx8h
SF-1130 | HAZOP TOR (Offshore) - IFR | 10 | 2026-04-09 | 2026-04-27 | 152 | PTTME Office 5dx8h
SF-1140 | HAZOP TOR (Offshore) - AFC | 5 | 2026-05-13 | 2026-05-19 | 152 | PTTME Office 5dx8h
SF-1150 | HAZOP Report (Offshore) - IFR | 15 | 2026-06-12 | 2026-07-02 | 97 | PTTME Office 5dx8h
SF-1160 | HAZOP Report (Offshore) - AFC | 10 | 2026-07-17 | 2026-08-04 | 97 | PTTME Office 5dx8h
SF-1161 | HAZOP Closed Out Report - IFI | 5 | 2026-08-05 | 2026-08-11 | 97 | PTTME Office 5dx8h
SF-1170 | SIL TOR (Offshore) - IFR | 10 | 2026-05-06 | 2026-05-19 | 67 | PTTME Office 5dx8h
SF-1180 | SIL TOR (Offshore) - AFC | 5 | 2026-06-05 | 2026-06-11 | 132 | PTTME Office 5dx8h
SF-1190 | SIL Classification Report (Offshore) - IFR | 10 | 2026-06-23 | 2026-07-06 | 75 | PTTME Office 5dx8h
SF-1200 | SIL Classification Report (Offshore) - AFC | 10 | 2026-07-21 | 2026-08-06 | 90 | PTTME Office 5dx8h
SF-1210 | SIL Verification (Offshore) - IFR | 10 | 2026-07-07 | 2026-07-20 | 75 | PTTME Office 5dx8h
SF-1220 | SIL Verification (Offshore) - IFA | 5 | 2026-08-07 | 2026-08-14 | 75 | PTTME Office 5dx8h
SF-1230 | SIL Verification (Offshore) - AFC | 5 | 2026-08-31 | 2026-09-04 | 75 | PTTME Office 5dx8h
SF-1231 | SIL Closed Out Report - IFI | 5 | 2026-09-07 | 2026-09-11 | 75 | PTTME Office 5dx8h
SF-1240 | ALARP Study TOR (Offshore) - IFR | 10 | 2026-06-12 | 2026-06-25 | 52 | PTTME Office 5dx8h
SF-1250 | ALARP Study TOR (Offshore) - AFC | 5 | 2026-07-10 | 2026-07-16 | 112 | PTTME Office 5dx8h
SF-1260 | ALARP Study Report (Offshore) - IFR | 15 | 2026-08-27 | 2026-09-16 | 52 | PTTME Office 5dx8h
SF-1270 | ALARP Study Report (Offshore) - AFC | 10 | 2026-10-01 | 2026-10-15 | 52 | PTTME Office 5dx8h
SF-1280 | Vent Dispersion & Thermal Radiation Study - IFR | 15 | 2026-06-12 | 2026-07-02 | 82 | PTTME Office 5dx8h
SF-1290 | Vent Dispersion & Thermal Radiation Study - IFA | 10 | 2026-07-17 | 2026-08-04 | 82 | PTTME Office 5dx8h
SF-1300 | Vent Dispersion & Thermal Radiation Study - AFC | 10 | 2026-08-20 | 2026-09-02 | 82 | PTTME Office 5dx8h
SF-1310 | Dropped Object Study (DOS) (Topside & associate Pipelines) - IFR | 30 | 2026-05-18 | 2026-06-30 | 84 | PTTME Office 5dx8h
SF-1320 | Dropped Object Study (DOS) (Topside & associate Pipelines) - IFA | 10 | 2026-07-15 | 2026-07-31 | 84 | PTTME Office 5dx8h
SF-1330 | Dropped Object Study (DOS) (Topside & associate Pipelines) - AFC | 10 | 2026-09-10 | 2026-09-23 | 67 | PTTME Office 5dx8h
SF-1340 | Fire and Explosion Risk Analysis Report (FERA) - IFR | 40 | 2026-05-11 | 2026-07-07 | 79 | PTTME Office 5dx8h
SF-1350 | Fire and Explosion Risk Analysis Report (FERA) - IFA | 10 | 2026-07-22 | 2026-08-07 | 79 | PTTME Office 5dx8h
SF-1360 | Fire and Explosion Risk Analysis Report (FERA) - AFC | 10 | 2026-08-25 | 2026-09-07 | 79 | PTTME Office 5dx8h
SF-1370 | Qualitative Risk Assessment (QRA) - IFR | 30 | 2026-07-15 | 2026-08-31 | 44 | PTTME Office 5dx8h
SF-1380 | Qualitative Risk Assessment (QRA) - IFA | 10 | 2026-09-15 | 2026-09-28 | 44 | PTTME Office 5dx8h
SF-1390 | Qualitative Risk Assessment (QRA) - AFC | 10 | 2026-10-14 | 2026-10-28 | 44 | PTTME Office 5dx8h
SF-1400 | Escape, Evacuation and Rescue Analysis (EERA) - IFR | 30 | 2026-07-15 | 2026-08-31 | 44 | PTTME Office 5dx8h
SF-1410 | Escape, Evacuation and Rescue Analysis (EERA) - IFA | 10 | 2026-09-15 | 2026-09-28 | 44 | PTTME Office 5dx8h
SF-1420 | Escape, Evacuation and Rescue Analysis (EERA) - AFC | 10 | 2026-10-14 | 2026-10-28 | 44 | PTTME Office 5dx8h
SF-1430 | Design Safety Critical Element and Performance Standard (SCE PS) - IFR | 40 | 2026-06-09 | 2026-08-06 | 60 | PTTME Office 5dx8h
SF-1440 | Design Safety Critical Element and Performance Standard (SCE PS) - IFA | 10 | 2026-08-24 | 2026-09-04 | 60 | PTTME Office 5dx8h
SF-1450 | Design Safety Critical Element and Performance Standard (SCE PS) - AFC | 10 | 2026-09-21 | 2026-10-02 | 60 | PTTME Office 5dx8h
SF-1460 | Safety Engineering Action Tracking Monitoring System (SEAMS) Report (monthly report) - IFR | 15 | 2026-06-12 | 2026-07-02 | 82 | PTTME Office 5dx8h
SF-1470 | Safety Engineering Action Tracking Monitoring System (SEAMS) Report (monthly report) - IFA | 10 | 2026-07-17 | 2026-08-04 | 82 | PTTME Office 5dx8h
SF-1480 | Safety Engineering Action Tracking Monitoring System (SEAMS) Report (monthly report) - AFC | 10 | 2026-08-20 | 2026-09-02 | 82 | PTTME Office 5dx8h
SF-1490 | Bow-Tie Diagrams for MAE/high risk hazards Analysis - IFR | 20 | 2026-06-09 | 2026-07-06 | 80 | PTTME Office 5dx8h
SF-1500 | Bow-Tie Diagrams for MAE/high risk hazards Analysis - IFA | 10 | 2026-07-21 | 2026-08-06 | 80 | PTTME Office 5dx8h
SF-1510 | Bow-Tie Diagrams for MAE/high risk hazards Analysis - AFC | 10 | 2026-08-24 | 2026-09-04 | 80 | PTTME Office 5dx8h
SF-1520 | Design Safety Case - IFR | 30 | 2026-09-17 | 2026-10-30 | 22 | PTTME Office 5dx8h
SF-1530 | Design Safety Case - AFC | 10 | 2026-11-16 | 2026-11-27 | 22 | PTTME Office 5dx8h
SF-1531 | Exhaust Plume Study Report - IFR | 15 | 2026-06-12 | 2026-07-02 | 102 | PTTME Office 5dx8h
SF-1532 | Exhaust Plume Study Report - AFC | 10 | 2026-07-17 | 2026-08-04 | 102 | PTTME Office 5dx8h
SF-1540 | Specification for Firefighting Equipment - IFR | 20 | 2026-04-01 | 2026-05-05 | 52 | PTTME Office 5dx8h
SF-1550 | Specification for Firefighting Equipment - IFA | 10 | 2026-05-20 | 2026-06-04 | 117 | PTTME Office 5dx8h
SF-1560 | Specification for Firefighting Equipment - AFC | 5 | 2026-06-19 | 2026-06-25 | 117 | PTTME Office 5dx8h
SF-1570 | Specification for Lifesaving Equipment and Safety Equipment - IFR | 20 | 2026-04-01 | 2026-05-05 | 52 | PTTME Office 5dx8h
SF-1580 | Specification for Lifesaving Equipment and Safety Equipment - AFC | 10 | 2026-05-20 | 2026-06-04 | 132 | PTTME Office 5dx8h
SF-1590 | Specification for Safety Signs - IFR | 20 | 2026-04-01 | 2026-05-05 | 52 | PTTME Office 5dx8h
SF-1600 | Specification for Safety Signs - AFC | 10 | 2026-05-20 | 2026-06-04 | 132 | PTTME Office 5dx8h
SF-1670 | Firefighting, Lifesaving Equipment and Safety Equipment List - IFR | 15 | 2026-05-20 | 2026-06-11 | 27 | PTTME Office 5dx8h
SF-1680 | Firefighting, Lifesaving Equipment and Safety Equipment List - IFA | 10 | 2026-06-26 | 2026-07-09 | 97 | PTTME Office 5dx8h
SF-1690 | Firefighting, Lifesaving Equipment and Safety Equipment List - AFC | 10 | 2026-07-24 | 2026-08-11 | 97 | PTTME Office 5dx8h
SF-1700 | Hazardous Equipment Schedule (Normal operations, SIMOPS) - IFR | 10 | 2026-04-28 | 2026-05-12 | 102 | PTTME Office 5dx8h
SF-1710 | Hazardous Equipment Schedule (Normal operations, SIMOPS) - IFA | 10 | 2026-05-29 | 2026-06-15 | 105 | PTTME Office 5dx8h
SF-1720 | Hazardous Equipment Schedule (Normal operations, SIMOPS) - AFC | 5 | 2026-06-30 | 2026-07-06 | 110 | PTTME Office 5dx8h
SF-1730 | Hazardous Area Classification Drawing (Normal operations) WP01 (10Sheets) - IFR | 15 | 2026-05-13 | 2026-06-04 | 102 | PTTME Office 5dx8h
SF-1740 | Hazardous Area Classification Drawing (Normal operations) WP01 (10Sheets) - IFA | 10 | 2026-06-19 | 2026-07-02 | 102 | PTTME Office 5dx8h
SF-1750 | Hazardous Area Classification Drawing (Normal operations) WP01 (10Sheets) - AFC | 10 | 2026-07-17 | 2026-08-04 | 102 | PTTME Office 5dx8h
SF-1760 | Hazardous Area Classification Drawing (SIMOPS) Index WP01 (10Sheets) - IFR | 15 | 2026-05-13 | 2026-06-04 | 102 | PTTME Office 5dx8h
SF-1770 | Hazardous Area Classification Drawing (SIMOPS) Index WP01 (10Sheets) - IFA | 10 | 2026-06-19 | 2026-07-02 | 102 | PTTME Office 5dx8h
SF-1780 | Hazardous Area Classification Drawing (SIMOPS) Index WP01 (10Sheets) - AFC | 10 | 2026-07-17 | 2026-08-04 | 102 | PTTME Office 5dx8h
SF-1790 | Hazardous Area Classification Drawing (Normal operations) WP02 (10Sheets) - IFR | 15 | 2026-05-13 | 2026-06-04 | 102 | PTTME Office 5dx8h
SF-1800 | Hazardous Area Classification Drawing (Normal operations) WP02 (10Sheets) - IFA | 10 | 2026-06-19 | 2026-07-02 | 102 | PTTME Office 5dx8h
SF-1810 | Hazardous Area Classification Drawing (Normal operations) WP02 (10Sheets) - AFC | 10 | 2026-07-17 | 2026-08-04 | 102 | PTTME Office 5dx8h
SF-1820 | Hazardous Area Classification Drawing (SIMOPS) Index WP02 (10Sheets) - IFR | 15 | 2026-05-13 | 2026-06-04 | 102 | PTTME Office 5dx8h
SF-1830 | Hazardous Area Classification Drawing (SIMOPS) Index WP02 (10Sheets) - IFA | 10 | 2026-06-19 | 2026-07-02 | 102 | PTTME Office 5dx8h
SF-1840 | Hazardous Area Classification Drawing (SIMOPS) Index WP02 (10Sheets) - AFC | 10 | 2026-07-17 | 2026-08-04 | 102 | PTTME Office 5dx8h
SF-1850 | Escape Routes, Lifesaving Equipment & Safety Equipment Layout Drawing WP01 (6 Sheets) - IFR | 15 | 2026-05-27 | 2026-06-18 | 92 | PTTME Office 5dx8h
SF-1860 | Escape Routes, Lifesaving Equipment & Safety Equipment Layout Drawing WP01 (6 Sheets) - IFA | 10 | 2026-07-10 | 2026-07-23 | 87 | PTTME Office 5dx8h
SF-1870 | Escape Routes, Lifesaving Equipment & Safety Equipment Layout Drawing WP01 (6 Sheets) - AFC | 10 | 2026-09-10 | 2026-09-23 | 67 | PTTME Office 5dx8h
SF-1880 | Escape Routes, Lifesaving Equipment & Safety Equipment Layout Drawing WP02 (6 Sheets) - IFR | 15 | 2026-05-27 | 2026-06-18 | 92 | PTTME Office 5dx8h
SF-1890 | Escape Routes, Lifesaving Equipment & Safety Equipment Layout Drawing WP02 (6 Sheets) - IFA | 10 | 2026-07-10 | 2026-07-23 | 87 | PTTME Office 5dx8h
SF-1900 | Escape Routes, Lifesaving Equipment & Safety Equipment Layout Drawing WP02 (6 Sheets) - AFC | 10 | 2026-09-10 | 2026-09-23 | 67 | PTTME Office 5dx8h
SF-1910 | Firefighting Equipment Layout Drawing WP01 (6 Sheets) - IFR | 15 | 2026-05-27 | 2026-06-18 | 32 | PTTME Office 5dx8h
SF-1920 | Firefighting Equipment Layout Drawing WP01 (6 Sheets) - IFA | 10 | 2026-07-10 | 2026-07-23 | 77 | PTTME Office 5dx8h
SF-1930 | Firefighting Equipment Layout Drawing WP01 (6 Sheets) - AFC | 10 | 2026-09-10 | 2026-09-23 | 67 | PTTME Office 5dx8h
SF-1940 | Firefighting Equipment Layout Drawing WP02 (6 Sheets) - IFR | 15 | 2026-05-27 | 2026-06-18 | 77 | PTTME Office 5dx8h
SF-1950 | Firefighting Equipment Layout Drawing WP02 (6 Sheets) - IFA | 10 | 2026-07-10 | 2026-07-23 | 77 | PTTME Office 5dx8h
SF-1960 | Firefighting Equipment Layout Drawing WP02 (6 Sheets) - AFC | 10 | 2026-09-10 | 2026-09-23 | 67 | PTTME Office 5dx8h
SF-1970 | Safety Signs Layout Drawing WP01 (6 Sheets) - IFR | 15 | 2026-06-19 | 2026-07-09 | 32 | PTTME Office 5dx8h
SF-1980 | Safety Signs Layout Drawing WP01 (6 Sheets) - IFA | 10 | 2026-07-24 | 2026-08-11 | 77 | PTTME Office 5dx8h
SF-1990 | Safety Signs Layout Drawing WP01 (6 Sheets) - AFC | 10 | 2026-08-27 | 2026-09-09 | 77 | PTTME Office 5dx8h
SF-2000 | Safety Signs Layout Drawing WP02 (6 Sheets) - IFR | 15 | 2026-06-19 | 2026-07-09 | 77 | PTTME Office 5dx8h
SF-2010 | Safety Signs Layout Drawing WP02 (6 Sheets) - IFA | 10 | 2026-07-24 | 2026-08-11 | 77 | PTTME Office 5dx8h
SF-2020 | Safety Signs Layout Drawing WP02 (6 Sheets) - AFC | 10 | 2026-08-27 | 2026-09-09 | 77 | PTTME Office 5dx8h
SF-2030 | Fire and Gas Detector Layout Drawing WP01 (6 Sheets) - IFR | 15 | 2026-06-19 | 2026-07-09 | 32 | PTTME Office 5dx8h
SF-2040 | Fire and Gas Detector Layout Drawing WP01 (6 Sheets) - IFA | 10 | 2026-07-24 | 2026-08-11 | 62 | PTTME Office 5dx8h
SF-2050 | Fire and Gas Detector Layout Drawing WP01 (6 Sheets) - AFC | 10 | 2026-08-27 | 2026-09-09 | 62 | PTTME Office 5dx8h
SF-2060 | Fire and Gas Detector Layout Drawing WP02 (6 Sheets) - IFR | 15 | 2026-06-19 | 2026-07-09 | 32 | PTTME Office 5dx8h
SF-2070 | Fire and Gas Detector Layout Drawing WP02 (6 Sheets) - IFA | 10 | 2026-07-24 | 2026-08-11 | 62 | PTTME Office 5dx8h
SF-2080 | Fire and Gas Detector Layout Drawing WP02 (6 Sheets) - AFC | 10 | 2026-08-27 | 2026-09-09 | 62 | PTTME Office 5dx8h
Datasheets-Safety |  | 85 | 2026-06-12 | 2026-10-15 | 52 | PTTME Office 5dx8h
SF-1610 | Datasheet for Firefighting Equipment - IFR | 15 | 2026-06-12 | 2026-07-02 | 27 | PTTME Office 5dx8h
SF-1620 | Datasheet for Firefighting Equipment - AFC | 10 | 2026-10-01 | 2026-10-15 | 52 | PTTME Office 5dx8h
SF-1630 | Datasheet for Lifesaving Equipment and Safety Equipment - IFR | 15 | 2026-06-12 | 2026-07-02 | 27 | PTTME Office 5dx8h
SF-1640 | Datasheet for Lifesaving Equipment and Safety Equipment - AFC | 10 | 2026-10-01 | 2026-10-15 | 52 | PTTME Office 5dx8h
SF-1650 | Datasheet for Safety Signs - IFR | 15 | 2026-06-12 | 2026-07-02 | 27 | PTTME Office 5dx8h
SF-1660 | Datasheet for Safety Signs - AFC | 10 | 2026-10-01 | 2026-10-15 | 52 | PTTME Office 5dx8h
MR-Safety |  | 95 | 2026-07-03 | 2026-11-20 | 27 | PTTME Office 5dx8h
SF-2090 | Material Requisition for Firefighting Equipment - IFR | 10 | 2026-07-03 | 2026-07-16 | 27 | PTTME Office 5dx8h
SF-2100 | Material Requisition for Firefighting Equipment - AFC | 5 | 2026-11-16 | 2026-11-20 | 27 | PTTME Office 5dx8h
SF-2110 | Material Requisition for Lifesaving Equipment and Safety Equipment - IFR | 10 | 2026-07-03 | 2026-07-16 | 27 | PTTME Office 5dx8h
SF-2120 | Material Requisition for Lifesaving Equipment and Safety Equipment - AFC | 5 | 2026-11-16 | 2026-11-20 | 27 | PTTME Office 5dx8h
SF-2130 | Material Requisition for Safety Signs - IFR | 10 | 2026-07-03 | 2026-07-16 | 27 | PTTME Office 5dx8h
SF-2140 | Material Requisition for Safety Signs - AFC | 5 | 2026-11-16 | 2026-11-20 | 27 | PTTME Office 5dx8h
TBE-Safety |  | 60 | 2026-08-20 | 2026-11-13 | 27 | PTTME Office 5dx8h
SF-2150 | Technical Bid Evaluation For Firefighting Equipment - IFR | 20 | 2026-08-20 | 2026-09-16 | 27 | PTTME Office 5dx8h
SF-2160 | Technical Bid Evaluation For Firefighting Equipment - IFA | 10 | 2026-10-01 | 2026-10-15 | 27 | PTTME Office 5dx8h
SF-2170 | Technical Bid Evaluation For Firefighting Equipment - AFC | 10 | 2026-11-02 | 2026-11-13 | 27 | PTTME Office 5dx8h
SF-2180 | Technical Bid Evaluation For Lifesaving Equipment and Safety Equipment - IFR | 20 | 2026-08-20 | 2026-09-16 | 27 | PTTME Office 5dx8h
SF-2190 | Technical Bid Evaluation For Lifesaving Equipment and Safety Equipment - IFA | 10 | 2026-10-01 | 2026-10-15 | 27 | PTTME Office 5dx8h
SF-2200 | Technical Bid Evaluation For Lifesaving Equipment and Safety Equipment - AFC | 10 | 2026-11-02 | 2026-11-13 | 27 | PTTME Office 5dx8h
SF-2210 | Technical Bid Evaluation For Safety Signs - IFR | 20 | 2026-08-20 | 2026-09-16 | 27 | PTTME Office 5dx8h
SF-2220 | Technical Bid Evaluation For Safety Signs - IFA | 10 | 2026-10-01 | 2026-10-15 | 27 | PTTME Office 5dx8h
SF-2230 | Technical Bid Evaluation For Safety Signs - AFC | 10 | 2026-11-02 | 2026-11-13 | 27 | PTTME Office 5dx8h
Datasheets-Mechanical |  | 10 | 2026-05-25 | 2026-06-09 | 99 | PTTME Office 5dx8h
ME-1510_X_ | Mechanical Datasheet for Material Handling Equipment - IFR_X_ | 10 | 2026-05-25 | 2026-06-09 | 99 | PTTME Office 5dx8h

## Before Award (hidden)
ZM167 PTTEPI ASK Procurement Plan - Before Award
[8 empty] | LA |  |  | 1 | 5 | 1 | 5 |  |  | 10 | 20 | 3 | 10 | 2 | 57 | [17 empty] | 2 | 4 | 5
[8 empty] | LB |  |  | 1 | 5 | 1 | 5 |  |  | 10 | 20 | 3 | 10 | 2 | 57 | [17 empty] | 2 | 4 | 5
[8 empty] | LC |  |  | 3 | 10 | 1 | 10 |  |  | 10 | 15 | 10 | 10 | 2 | 71 | [17 empty] | 2 | 2 | 5
[8 empty] | LD |  |  | 3 | 5 | 1 | 3 |  |  | 5 | 7 | 2 | 5 | 2 | 33 | [17 empty] | 2 | 2 | 5
No. | MR.No | RFQ No. | Package Name | PO NO. | Discripline | Long Lead Item (Y/N) | Criticality Rating | Priority Level |  | Bidder List Approval | MR Issued | MR Approved | RFQ Issued | RFQ Approved | Bidding Duration | CFT Issuance | Bid Closing Date | TBE Issued | TBE Approved | PO Issued | Vendor Acknowledgement | Delivery Duration (Weeks) | Delivery Date | Lead Time (Days) | ROS date | Earlier ROS date | Float (Day) | 2010-05-31 | 2010-06-30 | 2010-07-31 | 2010-08-31 | 2010-09-30 | 2010-10-31 | 2010-11-30 | 2010-12-31 | 2011-01-31 | 2011-02-28 | 2026-07-28 |  | Final&Best Proposal Submission | TJE CBE approval (LOI Issue) | MRP | Transportation time
1 |  | RFQ-001 | Pedestal Crane |  | Mechanical | N |  | LA | Plan | 2026-04-28 | 2026-04-29 | 2026-05-06 | 2026-05-07 | 2026-05-14 | 76 |  | 2026-05-28 | 2026-06-25 | 2026-06-30 | 2026-07-14 | 2026-07-16 | 50 | 2027-06-29 | 350 | 2027-06-29 | 2027-06-29 | 0 | [11 empty] | 14 | #REF! | #REF! | #REF! | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-001 | Pedestal Crane |  |  |  |  | LA | Forecast | 2026-04-28 | 2026-04-29 | 2026-05-06 | 2026-05-07 | 2026-05-14 |  |  | 2026-05-28 | 2026-06-25 | 2026-06-30 | 2026-07-14 | 2026-07-16 |  | 2027-06-29 | [15 empty] | 14 | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-001 | Pedestal Crane |  |  |  |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
2 |  | RFQ-002 | Material Handling Equipment |  | Mechanical | N |  | LC | Plan | 2026-10-01 | 2026-10-06 | 2026-10-20 | 2026-10-21 | 2026-11-04 | 92 |  | 2026-11-18 | 2026-12-09 | 2026-12-23 | 2027-01-06 | 2027-01-08 | 25 | 2027-06-30 | 175 | 2027-06-30 | 2027-06-30 | 0 | [11 empty] | 14 | #REF! | #REF! | #REF! | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-002 | Material Handling Equipment |  |  | N |  | LC | Forecast | 2026-10-01 | 2026-10-06 | 2026-10-20 | 2026-10-21 | 2026-11-04 |  |  | 2026-11-18 | 2026-12-09 | 2026-12-23 | 2027-01-06 | 2027-01-08 |  | 2027-06-30 | [15 empty] | 14 | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-002 | Material Handling Equipment |  |  | N |  | LC | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
3 |  | RFQ-003 | Instrument Gas Filter Coalescer |  | Mechanical | Y |  | LA | Plan | 2026-07-06 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-22 | 76 |  | 2026-08-05 | 2026-09-02 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 25.7143 | 2027-03-20 | 180 | 2027-03-20 | 2027-03-20 | 0 | [11 empty] | 14 | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-003 | Instrument Gas Filter Coalescer |  |  | Y |  | LA | Forecast | 2026-07-06 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-22 |  |  | 2026-08-05 | 2026-09-02 | 2026-09-07 | 2026-09-21 | 2026-09-23 |  | 2027-03-20 | [15 empty] | 14 | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-003 | Instrument Gas Filter Coalescer |  |  | Y |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
4 |  | RFQ-004 | Production & Test Seperator |  | Mechanical | N |  | LA | Plan | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-15 | 2026-07-20 | 71 |  | 2026-08-03 | 2026-08-31 | 2026-09-03 | 2026-09-18 | 2026-09-25 | 26 | 2027-03-20 | 182 | 2027-03-20 | 2027-03-20 | 0 | [11 empty] | 15 | 2026-09-07 | 2026-09-11 | 2026-09-11 | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-004 | Production & Test Seperator |  |  | N |  | LA | Forecast | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-15 | 2026-07-20 |  |  | 2026-08-03 | 2026-08-31 | 2026-09-03 | 2026-09-18 | 2026-09-25 |  | 2027-03-20 | [15 empty] | 15 | 2026-09-07 | 2026-09-11 | 2026-09-18 |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-004 | Production & Test Seperator |  |  | N |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
5 |  | RFQ-005 | Pig Launcher and Receiver |  | Piping | Y |  | LA | Plan | 2026-06-03 | 2026-06-04 | 2026-06-09 | 2026-06-10 | 2026-06-15 | 71 |  | 2026-06-29 | 2026-07-27 | 2026-07-30 | 2026-08-14 | 2026-08-21 | 32 | 2027-03-26 | 224 | 2027-03-26 | 2027-03-26 | 0 | [11 empty] | 15 | 2026-08-03 | 2026-08-07 | 2026-08-07 | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-005 | Pig Launcher and Receiver |  | Piping | Y |  | LA | Forecast | 2026-06-03 | 2026-06-04 | 2026-06-09 | 2026-06-10 | 2026-06-15 |  |  | 2026-06-29 | 2026-07-27 | 2026-07-30 | 2026-08-14 | 2026-08-21 |  | 2027-03-26 | [15 empty] | 15 | 2026-08-03 | 2026-08-07 | 2026-08-14 |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-005 | Pig Launcher and Receiver |  | Piping | Y |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
6 |  | RFQ-006 | Corrosion Inhibitor Injection Pump |  | Mechanical | N |  | LA | Plan | 2026-05-01 | 2026-05-04 | 2026-05-11 | 2026-05-12 | 2026-05-19 | 74 |  | 2026-06-02 | 2026-06-30 | 2026-07-03 | 2026-07-17 | 2026-07-21 | 32 | 2027-02-26 | 224 | 2027-02-26 | 2027-02-26 | 0 | [11 empty] | 14 | #REF! | #REF! | #REF! | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-006 |  |  |  | N |  | LA | Forecast | 2026-05-01 | 2026-05-04 | 2026-05-11 | 2026-05-12 | 2026-05-19 |  |  | 2026-06-02 | 2026-06-30 | 2026-07-03 | 2026-07-17 | 2026-07-21 |  | 2027-02-26 | [15 empty] | 14 | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-006 |  |  |  | N |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
7 |  | RFQ-007 | Demulsifier/Water Clarifier Injection Pump |  | Mechanical | N |  | LA | Plan | 2026-06-03 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 76 |  | 2026-07-03 | 2026-07-31 | 2026-08-05 | 2026-08-19 | 2026-08-21 | 32 | 2027-03-31 | 224 | 2027-03-31 | 2027-03-31 | 0 | [11 empty] | 14 | #REF! | #REF! | #REF! | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-007 | Demulsifier/Water Clarifier Injection Pump |  |  | N |  | LA | Forecast | 2026-06-03 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 |  |  | 2026-07-03 | 2026-07-31 | 2026-08-05 | 2026-08-19 | 2026-08-21 |  | 2027-03-31 | [15 empty] | 14 | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-007 | Demulsifier/Water Clarifier Injection Pump |  |  | N |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
8 |  | RFQ-008 | De-Oiler Hydrocyclone |  | Mechanical | N |  |  | Plan | 2026-05-20 | 2026-05-21 | 2026-05-26 | 2026-05-27 | 2026-06-01 | 71 |  | 2026-06-15 | 2026-07-13 | 2026-07-16 | 2026-07-31 | 2026-08-07 | 26 | 2027-01-29 | 182 | 2027-01-29 | 2027-01-29 | 0 | [11 empty] | 15 | 2026-07-20 | 2026-07-24 | 2026-07-24 | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-008 | De-Oiler Hydrocyclone |  |  | N |  |  | Forecast | 2026-05-20 | 2026-05-21 | 2026-05-26 | 2026-05-27 | 2026-06-01 |  |  | 2026-06-15 | 2026-07-13 | 2026-07-16 | 2026-07-31 | 2026-08-07 |  | 2027-01-29 | [15 empty] | 15 | 2026-07-20 | 2026-07-24 | 2026-07-31 |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-008 | De-Oiler Hydrocyclone |  |  | N |  |  | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
9 |  | RFQ-009 | Degasser |  | Mechanical | N |  | LA | Plan | 2026-05-20 | 2026-05-21 | 2026-05-26 | 2026-05-27 | 2026-06-01 | 71 |  | 2026-06-15 | 2026-07-13 | 2026-07-16 | 2026-07-31 | 2026-08-07 | 26 | 2027-01-29 | 182 | 2027-01-29 | 2027-01-29 | 0 | [11 empty] | 15 | 2026-07-20 | 2026-07-24 | 2026-07-24 | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-009 | Degasser |  |  | N |  | LA | Forecast | 2026-05-20 | 2026-05-21 | 2026-05-26 | 2026-05-27 | 2026-06-01 |  |  | 2026-06-15 | 2026-07-13 | 2026-07-16 | 2026-07-31 | 2026-08-07 |  | 2027-01-29 | [15 empty] | 15 | 2026-07-20 | 2026-07-24 | 2026-07-31 |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-009 | Degasser |  |  | N |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
10 |  | RFQ-010 | Skim Tank Vessel |  | Mechanical | N |  | LA | Plan | 2026-05-20 | 2026-05-21 | 2026-05-26 | 2026-05-27 | 2026-06-01 | 71 |  | 2026-06-15 | 2026-07-13 | 2026-07-16 | 2026-07-31 | 2026-08-07 | 26 | 2027-01-29 | 182 | 2027-01-29 | 2027-01-29 | 0 | [11 empty] | 15 | 2026-07-20 | 2026-07-24 | 2026-07-24 | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-010 | Skim Tank Vessel |  |  | N |  | LA | Forecast | 2026-05-20 | 2026-05-21 | 2026-05-26 | 2026-05-27 | 2026-06-01 |  |  | 2026-06-15 | 2026-07-13 | 2026-07-16 | 2026-07-31 | 2026-08-07 |  | 2027-01-29 | [15 empty] | 15 | 2026-07-20 | 2026-07-24 | 2026-07-31 |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-010 | Skim Tank Vessel |  |  | N |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
11 |  | RFQ-011 | Closed Drain Sump Vessel |  | Mechanical | Y |  | LA | Plan | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-17 | 2026-06-22 | 71 |  | 2026-07-06 | 2026-08-03 | 2026-08-06 | 2026-08-21 | 2026-08-28 | 26 | 2027-02-19 | 182 | 2027-02-19 | 2026-12-30 | 0 | [11 empty] | 15 | 2026-08-10 | 2026-08-14 | 2026-08-14 | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-011 | Closed Drain Sump Vessel |  |  | Y |  | LA | Forecast | 2026-06-10 | 2026-06-11 | 2026-06-16 | 2026-06-17 | 2026-06-22 |  |  | 2026-07-06 | 2026-08-03 | 2026-08-06 | 2026-08-21 | 2026-08-28 |  | 2027-02-19 | [15 empty] | 15 | 2026-08-10 | 2026-08-14 | 2026-08-21 |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-011 | Closed Drain Sump Vessel |  |  | Y |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
12 |  | RFQ-012 | Storage Tote Tank |  | Mechanical | N |  | LA | Plan | 2026-07-01 | 2026-07-02 | 2026-07-07 | 2026-07-08 | 2026-07-13 | 71 |  | 2026-07-27 | 2026-08-24 | 2026-08-27 | 2026-09-11 | 2026-09-18 | 20 | 2027-01-29 | 140 | 2027-01-29 | 2027-01-29 | 0 | [11 empty] | 15 | 2026-08-31 | 2026-09-04 | 2026-09-04 | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-012 | Storage Tote Tank |  |  | N |  | LA | Forecast | 2026-07-01 | 2026-07-02 | 2026-07-07 | 2026-07-08 | 2026-07-13 |  |  | 2026-07-27 | 2026-08-24 | 2026-08-27 | 2026-09-11 | 2026-09-18 |  | 2027-01-29 | [15 empty] | 15 | 2026-08-31 | 2026-09-04 | 2026-09-11 |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-012 | Storage Tote Tank |  |  | N |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
13 |  | RFQ-013 | Storage Tank |  | Mechanical | N |  | LA | Plan | 2026-08-06 | 2026-08-07 | 2026-08-12 | 2026-08-13 | 2026-08-18 | 73 |  | 2026-09-01 | 2026-09-29 | 2026-10-02 | 2026-10-19 | 2026-10-26 | 20 | 2027-03-08 | 140 | 2027-03-08 | 2027-01-29 | 0 | [11 empty] | 17 | 2026-10-06 | 2026-10-12 | 2026-10-12 | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-013 | Storage Tank |  |  | N |  | LA | Forecast | 2026-08-06 | 2026-08-07 | 2026-08-12 | 2026-08-13 | 2026-08-18 |  |  | 2026-09-01 | 2026-09-29 | 2026-10-02 | 2026-10-19 | 2026-10-26 |  | 2027-03-08 | [15 empty] | 17 | 2026-10-06 | 2026-10-12 | 2026-10-19 |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-013 | Storage Tank |  |  | N |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
14 |  | RFQ-014 | Closed Drain Sump Pump |  | Mechanical | N |  | LA | Plan | 2026-04-21 | 2026-04-22 | 2026-04-29 | 2026-04-30 | 2026-05-07 | 76 |  | 2026-05-21 | 2026-06-18 | 2026-06-23 | 2026-07-07 | 2026-07-09 | 32 | 2027-02-16 | 224 | 2027-02-16 | 2026-12-30 | 0 | [11 empty] | 14 | #REF! | #REF! | #REF! | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-014 | Closed Drain Sump Pump |  |  | N |  | LA | Forecast | 2026-04-21 | 2026-04-22 | 2026-04-29 | 2026-04-30 | 2026-05-07 |  |  | 2026-05-21 | 2026-06-18 | 2026-06-23 | 2026-07-07 | 2026-07-09 |  | 2027-02-16 | [15 empty] | 14 | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-014 | Closed Drain Sump Pump |  |  | N |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
15 |  | RFQ-015 | Diesel Transfer Pump |  | Mechanical | N |  | LA | Plan | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-04 | 74 |  | 2026-08-18 | 2026-09-15 | 2026-09-18 | 2026-10-02 | 2026-10-06 | 32 | 2027-05-14 | 224 | 2027-05-14 | 2027-05-14 | 0 | [11 empty] | 14 | #REF! | #REF! | #REF! | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-015 | Diesel Transfer Pump |  |  | N |  | LA | Forecast | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-04 |  |  | 2026-08-18 | 2026-09-15 | 2026-09-18 | 2026-10-02 | 2026-10-06 |  | 2027-05-14 | [15 empty] | 14 | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-015 | Diesel Transfer Pump |  |  | N |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
16 |  | RFQ-016 | Open Drain Caisson Pump |  | Mechanical | N |  | LA | Plan | 2026-06-03 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 76 |  | 2026-07-03 | 2026-07-31 | 2026-08-05 | 2026-08-19 | 2026-08-21 | 32 | 2027-03-31 | 224 | 2027-03-31 | 2027-03-31 | 0 | [11 empty] | 14 | #REF! | #REF! | #REF! | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-016 | Open Drain Caisson Pump |  |  | N |  | LA | Forecast | 2026-06-03 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 |  |  | 2026-07-03 | 2026-07-31 | 2026-08-05 | 2026-08-19 | 2026-08-21 |  | 2027-03-31 | [15 empty] | 14 | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-016 | Open Drain Caisson Pump |  |  | N |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
17 |  | RFQ-017 | DC Distribution Board |  | Electrical | N |  | LB | Plan | 2026-06-17 | 2026-06-18 | 2026-06-25 | 2026-06-26 | 2026-07-03 | 76 |  | 2026-07-17 | 2026-08-14 | 2026-08-19 | 2026-09-02 | 2026-09-04 | 34 | 2027-04-28 | 238 | 2027-04-28 | 2027-04-28 | 0 | [11 empty] | 14 | #REF! | #REF! | #REF! | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-017 | DC Distribution Board |  |  | N |  | LB | Forecast | 2026-06-17 | 2026-06-18 | 2026-06-25 | 2026-06-26 | 2026-07-03 |  |  | 2026-07-17 | 2026-08-14 | 2026-08-19 | 2026-09-02 | 2026-09-04 |  | 2027-04-28 | [15 empty] | 14 | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-017 | DC Distribution Board |  |  | N |  | LB | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
18 |  | RFQ-018 | Solar Power System |  | Electrical | N |  | LA | Plan | 2026-05-06 | 2026-05-07 | 2026-05-14 | 2026-05-15 | 2026-05-22 | 76 |  | 2026-06-05 | 2026-07-03 | 2026-07-08 | 2026-07-22 | 2026-07-24 | 36 | 2027-03-31 | 252 | 2027-03-31 | 2027-03-31 | 0 | [11 empty] | 14 | #REF! | #REF! | #REF! | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-018 | Solar Power System |  |  | N |  | LA | Forecast | 2026-05-06 | 2026-05-07 | 2026-05-14 | 2026-05-15 | 2026-05-22 |  |  | 2026-06-05 | 2026-07-03 | 2026-07-08 | 2026-07-22 | 2026-07-24 |  | 2027-03-31 | [15 empty] | 14 | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-018 | Solar Power System |  |  | N |  | LA | Actual | [29 empty] | 0 | [6 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
19 |  | RFQ-019 | Navigation Aid System |  | Electrical | Y |  | LB | Plan | 2026-06-24 | 2026-06-25 | 2026-07-02 | 2026-07-03 | 2026-07-10 | 76 |  | 2026-07-24 | 2026-08-21 | 2026-08-26 | 2026-09-09 | 2026-09-11 | 42 | 2027-06-30 | 294 | 2027-06-30 | 2027-07-30 | 0 | [11 empty] | 14 | #REF! | #REF! | #REF! | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-019 | Navigation Aid System |  |  | Y |  | LB | Forecast | 2026-06-24 | 2026-06-25 | 2026-07-02 | 2026-07-03 | 2026-07-10 |  |  | 2026-07-24 | 2026-08-21 | 2026-08-26 | 2026-09-09 | 2026-09-11 |  | 2027-06-30 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-019 | Navigation Aid System |  |  | Y |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
20 |  | RFQ-020 | External Battery Charger |  | Electrical | Y |  | LC | Plan | 2026-06-01 | 2026-06-04 | 2026-06-18 | 2026-06-19 | 2026-07-03 | 92 |  | 2026-07-17 | 2026-08-07 | 2026-08-21 | 2026-09-04 | 2026-09-08 | 36 | 2027-05-14 | 252 | 2027-05-14 | 2027-05-14 | 0 | [12 empty] | #REF! | #REF! | #REF! | 14 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-020 | External Battery Charger |  |  | Y |  | LC | Forecast | 2026-06-01 | 2026-06-04 | 2026-06-18 | 2026-06-19 | 2026-07-03 |  |  | 2026-07-17 | 2026-08-07 | 2026-08-21 | 2026-09-04 | 2026-09-08 |  | 2027-05-14 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-020 | External Battery Charger |  |  | Y |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
21 |  | RFQ-021 | Control Valve |  | Instrument | N |  | LB | Plan | 2026-08-24 | 2026-08-25 | 2026-09-01 | 2026-09-02 | 2026-09-09 | 76 |  | 2026-09-23 | 2026-10-21 | 2026-10-26 | 2026-11-09 | 2026-11-11 | 28.5714 | 2027-05-28 | 200 | 2027-05-28 | 2027-05-28 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-021 | Control Valve |  | Instrument | N |  | LB | Forecast | 2026-08-24 | 2026-08-25 | 2026-09-01 | 2026-09-02 | 2026-09-09 |  |  | 2026-09-23 | 2026-10-21 | 2026-10-26 | 2026-11-09 | 2026-11-11 |  | 2027-05-28 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-021 | Control Valve |  | Instrument | N |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
22 |  | RFQ-022 | Self Regulator Valve |  | Instrument | N |  | LB | Plan | 2026-08-27 | 2026-08-28 | 2026-09-04 | 2026-09-07 | 2026-09-14 | 76 |  | 2026-09-28 | 2026-10-26 | 2026-10-29 | 2026-11-12 | 2026-11-16 | 28.5714 | 2027-05-31 | 200 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-022 | Self Regulator Valve |  | Instrument | N |  | LB | Forecast | 2026-08-27 | 2026-08-28 | 2026-09-04 | 2026-09-07 | 2026-09-14 |  |  | 2026-09-28 | 2026-10-26 | 2026-10-29 | 2026-11-12 | 2026-11-16 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-022 | Self Regulator Valve |  | Instrument | N |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
23 |  | RFQ-023 | Actuated Choke Valve |  | Instrument | N |  | LA | Plan | 2026-05-11 | 2026-05-12 | 2026-05-19 | 2026-05-20 | 2026-05-27 | 76 |  | 2026-06-10 | 2026-07-08 | 2026-07-13 | 2026-07-27 | 2026-07-29 | 44 | 2027-05-31 | 308 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-023 | Actuated Choke Valve |  | Instrument | N |  | LA | Forecast | 2026-05-11 | 2026-05-12 | 2026-05-19 | 2026-05-20 | 2026-05-27 |  |  | 2026-06-10 | 2026-07-08 | 2026-07-13 | 2026-07-27 | 2026-07-29 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-023 | Actuated Choke Valve |  | Instrument | N |  | LA | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
24 |  | RFQ-024 | Actuated Ball Valve |  | Instrument | N |  | LB | Plan | 2026-07-06 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-22 | 76 |  | 2026-08-05 | 2026-09-02 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 36 | 2027-05-31 | 252 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-024 | Actuated Ball Valve |  | Instrument | N |  | LB | Forecast | 2026-07-06 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-22 |  |  | 2026-08-05 | 2026-09-02 | 2026-09-07 | 2026-09-21 | 2026-09-23 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-024 | Actuated Ball Valve |  | Instrument | N |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
25 |  | RFQ-025 | Actuated Compact Ball Valve |  | Instrument | N |  | LB | Plan | 2026-06-08 | 2026-06-09 | 2026-06-16 | 2026-06-17 | 2026-06-24 | 76 |  | 2026-07-08 | 2026-08-05 | 2026-08-10 | 2026-08-24 | 2026-08-26 | 40 | 2027-05-31 | 280 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-025 | Actuated Compact Ball Valve |  | Instrument | N |  | LB | Forecast | 2026-06-08 | 2026-06-09 | 2026-06-16 | 2026-06-17 | 2026-06-24 |  |  | 2026-07-08 | 2026-08-05 | 2026-08-10 | 2026-08-24 | 2026-08-26 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-025 | Actuated Compact Ball Valve |  | Instrument | N |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
26 |  | RFQ-026 | Safety Relief Valves |  | Instrument | N |  | LB | Plan | 2026-09-14 | 2026-09-15 | 2026-09-22 | 2026-09-23 | 2026-09-30 | 76 |  | 2026-10-14 | 2026-11-11 | 2026-11-16 | 2026-11-30 | 2026-12-02 | 26.2857 | 2027-05-31 | 184 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-026 | Safety Relief Valves |  | Instrument | N |  | LB | Forecast | 2026-09-14 | 2026-09-15 | 2026-09-22 | 2026-09-23 | 2026-09-30 |  |  | 2026-10-14 | 2026-11-11 | 2026-11-16 | 2026-11-30 | 2026-12-02 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-026 | Safety Relief Valves |  | Instrument | N |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
27 |  | RFQ-027 | Coriolis Flow Meters |  | Instrument | N |  | LC | Plan | 2026-10-01 | 2026-10-06 | 2026-10-20 | 2026-10-21 | 2026-11-04 | 92 |  | 2026-11-18 | 2026-12-09 | 2026-12-23 | 2027-01-06 | 2027-01-08 | 20.7143 | 2027-05-31 | 145 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-027 | Coriolis Flow Meters |  | Instrument | N |  | LC | Forecast | 2026-10-01 | 2026-10-06 | 2026-10-20 | 2026-10-21 | 2026-11-04 |  |  | 2026-11-18 | 2026-12-09 | 2026-12-23 | 2027-01-06 | 2027-01-08 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-027 | Coriolis Flow Meters |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
28 |  | RFQ-028 | Wellhead Control Panel (WHCP) |  | Instrument | Y |  | LA | Plan | 2026-05-05 | 2026-05-06 | 2026-05-13 | 2026-05-14 | 2026-05-21 | 76 |  | 2026-06-04 | 2026-07-02 | 2026-07-07 | 2026-07-21 | 2026-07-23 | 36 | 2027-03-30 | 252 | 2027-03-30 | 2027-01-29 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-028 | Wellhead Control Panel (WHCP) |  | Instrument | Y |  | LA | Forecast | 2026-05-05 | 2026-05-06 | 2026-05-13 | 2026-05-14 | 2026-05-21 |  |  | 2026-06-04 | 2026-07-02 | 2026-07-07 | 2026-07-21 | 2026-07-23 |  | 2027-03-30 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-028 | Wellhead Control Panel (WHCP) |  | Instrument | Y |  | LA | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
29 |  | RFQ-029 | Pressure Gauge |  | Instrument | N |  | LC | Plan | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 | 94 |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 | 18 | 2027-05-31 | 126 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-029 | Pressure Gauge |  | Instrument | N |  | LC | Forecast | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 |  |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-029 | Pressure Gauge |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
30 |  | RFQ-030 | Pressure Transmitter |  | Instrument | N |  | LC | Plan | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 | 94 |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 | 18 | 2027-05-31 | 126 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-030 | Pressure Transmitter |  | Instrument | N |  | LC | Forecast | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 |  |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-030 | Pressure Transmitter |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
31 |  | RFQ-031 | Temperature Gauge |  | Instrument | N |  | LC | Plan | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 | 94 |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 | 18 | 2027-05-31 | 126 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-031 | Temperature Gauge |  | Instrument | N |  | LC | Forecast | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 |  |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-031 | Temperature Gauge |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
32 |  | RFQ-032 | Temperature Transmitter |  | Instrument | N |  | LC | Plan | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 | 94 |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 | 18 | 2027-05-31 | 126 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-032 | Temperature Transmitter |  | Instrument | N |  | LC | Forecast | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 |  |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-032 | Temperature Transmitter |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
33 |  | RFQ-033 | Vortex Flow Meter |  | Instrument | N |  | LC | Plan | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 | 94 |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 | 18 | 2027-05-31 | 126 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-033 | Vortex Flow Meter |  | Instrument | N |  | LC | Forecast | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 |  |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-033 | Vortex Flow Meter |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
34 |  | RFQ-034 | Level Transmitter and Gauge |  | Instrument | N |  | LC | Plan | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 | 94 |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 | 18 | 2027-05-31 | 126 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-034 | Level Transmitter and Gauge |  | Instrument | N |  | LC | Forecast | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 |  |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-034 | Level Transmitter and Gauge |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
35 |  | RFQ-035 | Pig Signaller |  | Instrument | N |  | LC | Plan | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 | 94 |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 | 18 | 2027-05-31 | 126 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-035 | Pig Signaller |  | Instrument | N |  | LC | Forecast | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 |  |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-035 | Pig Signaller |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
36 |  | RFQ-036 | Rrestriction Orifice |  | Instrument | N |  | LC | Plan | 2026-09-22 | 2026-09-25 | 2026-10-09 | 2026-10-12 | 2026-10-26 | 94 |  | 2026-11-09 | 2026-11-30 | 2026-12-14 | 2026-12-28 | 2026-12-30 | 22 | 2027-05-31 | 154 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-036 | Rrestriction Orifice |  | Instrument | N |  | LC | Forecast | 2026-09-22 | 2026-09-25 | 2026-10-09 | 2026-10-12 | 2026-10-26 |  |  | 2026-11-09 | 2026-11-30 | 2026-12-14 | 2026-12-28 | 2026-12-30 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-036 | Rrestriction Orifice |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
37 |  | RFQ-037 | PLC System |  | Instrument | N |  | LB | Plan | 2026-07-06 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-22 | 76 |  | 2026-08-05 | 2026-09-02 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 36 | 2027-05-31 | 252 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-037 | PLC System |  | Instrument | N |  | LB | Forecast | 2026-07-06 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-22 |  |  | 2026-08-05 | 2026-09-02 | 2026-09-07 | 2026-09-21 | 2026-09-23 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-037 | PLC System |  | Instrument | N |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
38 |  | RFQ-038 | Fire and Gas Detector |  | Instrument | N |  | LC | Plan | 2026-10-15 | 2026-10-20 | 2026-11-03 | 2026-11-04 | 2026-11-18 | 92 |  | 2026-12-02 | 2026-12-23 | 2027-01-06 | 2027-01-20 | 2027-01-22 | 18.7143 | 2027-05-31 | 131 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-038 | Fire and Gas Detector |  | Instrument | N |  | LC | Forecast | 2026-10-15 | 2026-10-20 | 2026-11-03 | 2026-11-04 | 2026-11-18 |  |  | 2026-12-02 | 2026-12-23 | 2027-01-06 | 2027-01-20 | 2027-01-22 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-038 | Fire and Gas Detector |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
39 |  | RFQ-039 | Dip Tape Level Indicator |  | Instrument | N |  | LC | Plan | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 | 94 |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 | 18 | 2027-05-31 | 126 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-039 | Dip Tape Level Indicator |  | Instrument | N |  | LC | Forecast | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 |  |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-039 | Dip Tape Level Indicator |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
40 |  | RFQ-040 | Position Limit Switches |  | Instrument | N |  | LC | Plan | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 | 94 |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 | 18 | 2027-05-31 | 126 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-040 | Position Limit Switches |  | Instrument | N |  | LC | Forecast | 2026-10-20 | 2026-10-23 | 2026-11-06 | 2026-11-09 | 2026-11-23 |  |  | 2026-12-07 | 2026-12-28 | 2027-01-11 | 2027-01-25 | 2027-01-27 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-040 | Position Limit Switches |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
41 |  | RFQ-041 | Guided Wave Radar Level Transmitter |  | Instrument | N |  | LC | Plan | 2026-07-28 | 2026-07-31 | 2026-08-14 | 2026-08-17 | 2026-08-31 | 94 |  | 2026-09-14 | 2026-10-05 | 2026-10-19 | 2026-11-02 | 2026-11-04 | 30 | 2027-05-31 | 210 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-041 | Guided Wave Radar Level Transmitter |  | Instrument | N |  | LC | Forecast | 2026-07-28 | 2026-07-31 | 2026-08-14 | 2026-08-17 | 2026-08-31 |  |  | 2026-09-14 | 2026-10-05 | 2026-10-19 | 2026-11-02 | 2026-11-04 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-041 | Guided Wave Radar Level Transmitter |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
42 |  | RFQ-042 | Oil in Water Analyzer |  | Instrument | N |  | LC | Plan | 2026-09-08 | 2026-09-11 | 2026-09-25 | 2026-09-28 | 2026-10-12 | 94 |  | 2026-10-26 | 2026-11-16 | 2026-11-30 | 2026-12-14 | 2026-12-16 | 24 | 2027-05-31 | 168 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-042 | Oil in Water Analyzer |  | Instrument | N |  | LC | Forecast | 2026-09-08 | 2026-09-11 | 2026-09-25 | 2026-09-28 | 2026-10-12 |  |  | 2026-10-26 | 2026-11-16 | 2026-11-30 | 2026-12-14 | 2026-12-16 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-042 | Oil in Water Analyzer |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
43 |  | RFQ-043 | Level Switch |  | Instrument | N |  | LC | Plan | 2026-12-25 | 2026-12-30 | 2027-01-13 | 2027-01-14 | 2027-01-28 | 92 |  | 2027-02-11 | 2027-03-04 | 2027-03-18 | 2027-04-01 | 2027-04-05 | 8.5714 | 2027-05-31 | 60 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-043 | Level Switch |  | Instrument | N |  | LC | Forecast | 2026-12-25 | 2026-12-30 | 2027-01-13 | 2027-01-14 | 2027-01-28 |  |  | 2027-02-11 | 2027-03-04 | 2027-03-18 | 2027-04-01 | 2027-04-05 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-043 | Level Switch |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
44 |  | RFQ-044 | Flow Switch |  | Instrument | N |  | LC | Plan | 2026-12-25 | 2026-12-30 | 2027-01-13 | 2027-01-14 | 2027-01-28 | 92 |  | 2027-02-11 | 2027-03-04 | 2027-03-18 | 2027-04-01 | 2027-04-05 | 8.5714 | 2027-05-31 | 60 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-044 | Flow Switch |  | Instrument | N |  | LC | Forecast | 2026-12-25 | 2026-12-30 | 2027-01-13 | 2027-01-14 | 2027-01-28 |  |  | 2027-02-11 | 2027-03-04 | 2027-03-18 | 2027-04-01 | 2027-04-05 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-044 | Flow Switch |  | Instrument | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
45 |  | RFQ-045 | SCADA System |  | Electrical | N |  | LB | Plan | 2026-07-06 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-22 | 76 |  | 2026-08-05 | 2026-09-02 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 36 | 2027-05-31 | 252 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-045 | SCADA System |  | Electrical | N |  | LB | Forecast | 2026-07-06 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-22 |  |  | 2026-08-05 | 2026-09-02 | 2026-09-07 | 2026-09-21 | 2026-09-23 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-045 | SCADA System |  | Electrical | N |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
46 |  | RFQ-046 | Telecommunication System (WiMAX, Telephone, Marine Radio) |  | Telecommunication | Y |  | LC | Plan | 2026-05-05 | 2026-05-08 | 2026-05-22 | 2026-05-25 | 2026-06-08 | 94 |  | 2026-06-22 | 2026-07-13 | 2026-07-27 | 2026-08-10 | 2026-08-12 | 42 | 2027-05-31 | 294 | 2027-05-31 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-046 | Telecommunication System (WiMAX, Telephone, Marine Radio) |  | Telecommunication | Y |  | LC | Forecast | 2026-05-05 | 2026-05-08 | 2026-05-22 | 2026-05-25 | 2026-06-08 |  |  | 2026-06-22 | 2026-07-13 | 2026-07-27 | 2026-08-10 | 2026-08-12 |  | 2027-05-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-046 | Telecommunication System (WiMAX, Telephone, Marine Radio) |  | Telecommunication | Y |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
47 |  | RFQ-047 | Marine Racon |  | Telecommunication | N |  | LC | Plan | 2026-09-03 | 2026-09-08 | 2026-09-22 | 2026-09-23 | 2026-10-07 | 92 |  | 2026-10-21 | 2026-11-11 | 2026-11-25 | 2026-12-09 | 2026-12-11 | 16 | 2027-03-31 | 112 | 2027-03-31 | 2027-03-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-047 | Marine Racon |  | Telecommunication | N |  | LC | Forecast | 2026-09-03 | 2026-09-08 | 2026-09-22 | 2026-09-23 | 2026-10-07 |  |  | 2026-10-21 | 2026-11-11 | 2026-11-25 | 2026-12-09 | 2026-12-11 |  | 2027-03-31 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-047 | Marine Racon |  | Telecommunication | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
48 |  | RFQ-048 | BALL VALVE (FLANGE END) |  | Piping | N |  | LC | Plan | 2026-05-26 | 2026-05-29 | 2026-06-12 | 2026-06-15 | 2026-06-29 | 93 |  | 2026-07-13 | 2026-08-03 | 2026-08-17 | 2026-08-30 | 2026-09-01 | 26.1429 | 2027-03-01 | 183 | 2027-03-01 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-048 | BALL VALVE (FLANGE END) |  | Piping | N |  | LC | Forecast | 2026-05-26 | 2026-05-29 | 2026-06-12 | 2026-06-15 | 2026-06-29 |  |  | 2026-07-13 | 2026-08-03 | 2026-08-17 | 2026-08-30 | 2026-09-01 |  | 2027-03-01 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-048 | BALL VALVE (FLANGE END) |  | Piping | N |  | LC | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
49 |  | RFQ-049 | GLOBE VALVE (FLANGE END) |  | Piping | N |  | LB | Plan | 2026-06-15 | 2026-06-16 | 2026-06-23 | 2026-06-24 | 2026-07-01 | 75 |  | 2026-07-15 | 2026-08-12 | 2026-08-17 | 2026-08-30 | 2026-09-01 | 26.1429 | 2027-03-01 | 183 | 2027-03-01 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-049 | GLOBE VALVE (FLANGE END) |  | Piping | N |  | LB | Forecast | 2026-06-15 | 2026-06-16 | 2026-06-23 | 2026-06-24 | 2026-07-01 |  |  | 2026-07-15 | 2026-08-12 | 2026-08-17 | 2026-08-30 | 2026-09-01 |  | 2027-03-01 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-049 | GLOBE VALVE (FLANGE END) |  | Piping | N |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
50 |  | RFQ-050 | GLOBE VALVE (WELDED END) |  | Piping | N |  | LB | Plan | 2026-06-15 | 2026-06-16 | 2026-06-23 | 2026-06-24 | 2026-07-01 | 75 |  | 2026-07-15 | 2026-08-12 | 2026-08-17 | 2026-08-30 | 2026-09-01 | 26.1429 | 2027-03-01 | 183 | 2027-03-01 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-050 | GLOBE VALVE (WELDED END) |  | Piping | N |  | LB | Forecast | 2026-06-15 | 2026-06-16 | 2026-06-23 | 2026-06-24 | 2026-07-01 |  |  | 2026-07-15 | 2026-08-12 | 2026-08-17 | 2026-08-30 | 2026-09-01 |  | 2027-03-01 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-050 | GLOBE VALVE (WELDED END) |  | Piping | N |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
51 |  | RFQ-051 | CHECK VALVE (FLANGE END) |  | Piping | N |  | LB | Plan | 2026-06-15 | 2026-06-16 | 2026-06-23 | 2026-06-24 | 2026-07-01 | 75 |  | 2026-07-15 | 2026-08-12 | 2026-08-17 | 2026-08-30 | 2026-09-01 | 26.1429 | 2027-03-01 | 183 | 2027-03-01 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-051 | CHECK VALVE (FLANGE END) |  | Piping | N |  | LB | Forecast | 2026-06-15 | 2026-06-16 | 2026-06-23 | 2026-06-24 | 2026-07-01 |  |  | 2026-07-15 | 2026-08-12 | 2026-08-17 | 2026-08-30 | 2026-09-01 |  | 2027-03-01 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-051 | CHECK VALVE (FLANGE END) |  | Piping | N |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
52 |  | RFQ-052 | CHECK VALVE (WELDED END) |  | Piping | N |  | LB | Plan | 2026-06-15 | 2026-06-16 | 2026-06-23 | 2026-06-24 | 2026-07-01 | 75 |  | 2026-07-15 | 2026-08-12 | 2026-08-17 | 2026-08-30 | 2026-09-01 | 26.1429 | 2027-03-01 | 183 | 2027-03-01 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-052 | CHECK VALVE (WELDED END) |  | Piping | N |  | LB | Forecast | 2026-06-15 | 2026-06-16 | 2026-06-23 | 2026-06-24 | 2026-07-01 |  |  | 2026-07-15 | 2026-08-12 | 2026-08-17 | 2026-08-30 | 2026-09-01 |  | 2027-03-01 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-052 | CHECK VALVE (WELDED END) |  | Piping | N |  | LB | Actual | [36 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
53 |  | RFQ-053 | COMPACT CHECK VALVE (WELDED END) |  | Piping | N |  | LB | Plan | 2026-05-18 | 2026-05-19 | 2026-05-26 | 2026-05-27 | 2026-06-03 | 76 |  | 2026-06-17 | 2026-07-15 | 2026-07-20 | 2026-08-03 | 2026-08-05 | 30 | 2027-03-01 | 210 | 2027-03-01 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-053 | COMPACT CHECK VALVE (WELDED END) |  | Piping | N |  | LB | Forecast | 2026-05-18 | 2026-05-19 | 2026-05-26 | 2026-05-27 | 2026-06-03 |  |  | 2026-06-17 | 2026-07-15 | 2026-07-20 | 2026-08-03 | 2026-08-05 |  | 2027-03-01 | [16 empty] | #REF! | #REF! | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  | RFQ-053 | COMPACT CHECK VALVE (WELDED END) |  | Piping | N |  | LB | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | Primary Steel - Plates for topside |  | Structural | Y |  | LA | Plan | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-23 | 2026-03-24 | 24 |  | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-12 | 2026-04-14 | 17.1429 | 2026-08-10 | 120 | 2026-08-10 | 2026-08-10 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | Primary Steel - Plate |  |  | Y |  | LA | Forecast | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-23 | 2026-03-24 |  |  | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-12 | 2026-04-13 |  | 2026-08-10 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | Primary Steel - Plate |  |  | Y |  | LA | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | Primary Steel - Joint Connection for Topside |  | Structural | Y |  | LA | Plan | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-23 | 2026-03-24 | 24 |  | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-12 | 2026-04-14 | 17.1429 | 2026-08-10 | 120 | 2026-08-10 | 2026-08-10 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
[6 empty] | Y |  | LA | Forecast | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-23 | 2026-03-24 |  |  | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-12 | 2026-04-13 |  | 2026-08-10 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
[6 empty] | Y |  | LA | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | Primary Steel - Beam for topside (Standard) |  | Structural | Y |  | LA | Plan | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 23 |  | 2026-04-17 | 2026-04-20 | 2026-04-21 | 2026-04-30 | 2026-05-04 | 19 | 2026-09-10 | 133 | 2026-09-10 | 2026-08-10 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | Primary Steel - Beam |  |  | Y |  | LA | Forecast | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 |  |  | 2026-04-17 | 2026-04-20 | 2026-04-21 | 2026-04-30 | 2026-05-01 |  | 2026-09-10 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | Primary Steel - Beam |  |  | Y |  | LA | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | Primary Steel - Beam for topside (non-standard) |  | Structural | Y |  | LA | Plan | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-23 | 2026-03-24 | 24 |  | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-12 | 2026-04-14 | 17.1429 | 2026-08-10 | 120 | 2026-08-10 |  | 0
|  |  | Primary Steel - Beam |  |  | Y |  | LA | Forecast | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-23 | 2026-03-24 |  |  | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-12 | 2026-04-13 |  | 2026-08-10
|  |  | Primary Steel - Beam |  |  | Y |  | LA | Actual
|  |  | Primary Steel - Seamless Pipe for topside |  | Structural | Y |  | LA | Plan | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-25 | 23 |  | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-12 | 2026-06-16 | 12.8571 | 2026-09-10 | 90 | 2026-09-10 |  | 0
|  |  | Primary Steel - Seamless Pipe |  |  | Y |  | LA | Forecast | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-25 |  |  | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-12 | 2026-06-15 |  | 2026-09-10
|  |  | Primary Steel - Seamless Pipe |  |  | Y |  | LA | Actual
|  |  | Primary Steel - Tubular for topside |  | Structural | Y |  | LA | Plan | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 23 |  | 2026-04-10 | 2026-04-13 | 2026-04-14 | 2026-04-23 | 2026-04-27 | 22.8571 | 2026-09-30 | 160 | 2026-09-30 |  | 0
[6 empty] | Y |  | LA | Forecast | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 |  |  | 2026-04-10 | 2026-04-13 | 2026-04-14 | 2026-04-23 | 2026-04-24 |  | 2026-09-30
[6 empty] | Y |  | LA | Actual
|  |  | Primary Steel - Plates for jacket |  | Structural | Y |  | LA | Plan | 2026-04-10 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 23 |  | 2026-04-23 | 2026-04-24 | 2026-04-27 | 2026-05-06 | 2026-05-08 | 17.1429 | 2026-09-03 | 120 | 2026-09-03 |  | 0 | [17 empty] | 2026-10-27
|  |  | Primary Steel - Plate |  |  | Y |  | LA | Forecast | 2026-04-10 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 |  |  | 2026-04-23 | 2026-04-24 | 2026-04-27 | 2026-05-06 | 2026-05-07 |  | 2026-09-03 | [20 empty] | 2026-09-17
|  |  | Primary Steel - Plate |  |  | Y |  | LA | Actual
|  |  | Primary Steel -Beam for jacket |  | Structural | Y |  | LA | Plan | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-18 | 2026-05-19 | 23 |  | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-06-06 | 2026-06-09 | 19 | 2026-10-17 | 133 | 2026-10-17 |  | 0
[6 empty] | Y |  | LA | Forecast | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-18 | 2026-05-19 |  |  | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-06-06 | 2026-06-08 |  | 2026-10-17
[6 empty] | Y |  | LA | Actual
|  |  | Primary Steel -Tubular for jacket (column) |  | Structural | Y |  | LA | Plan | 2026-04-24 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 23 |  | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-20 | 2026-05-22 | 22.8571 | 2026-10-27 | 160 | 2026-10-27 |  | 0
[6 empty] | Y |  | LA | Forecast | 2026-04-24 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 |  |  | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-20 | 2026-05-21 |  | 2026-10-27
[6 empty] | Y |  | LA | Actual
|  |  | Primary Steel -Tubular for jacket (bracing) |  | Structural | Y |  | LA | Plan | 2026-04-24 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 23 |  | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-20 | 2026-05-22 | 22.8571 | 2026-10-27 | 160 | 2026-10-27 |  | 0
[6 empty] | Y |  | LA | Forecast | 2026-04-24 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 |  |  | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-20 | 2026-05-21 |  | 2026-10-27
[6 empty] | Y |  | LA | Actual
|  |  | Primary Steel - Plates for Pile |  | Structural | Y |  | LA | Plan | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 25 |  | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-12 | 2026-10-14 | 17.1429 | 2027-02-09 | 120 | 2027-02-09 |  | 0
|  |  | Primary Steel - Plate |  |  | Y |  | LA | Forecast | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 |  |  | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-12 | 2026-10-13 |  | 2027-02-09
|  |  | Primary Steel - Plate |  |  | Y |  | LA | Actual
|  |  | Primary Steel -Tubular for Pile |  | Structural | Y |  | LA | Plan | 2026-10-02 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 23 |  | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-28 | 2026-10-30 | 22.8571 | 2027-04-06 | 160 | 2027-04-06 |  | 0
[6 empty] | Y |  | LA | Forecast | 2026-10-02 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 |  |  | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-28 | 2026-10-29 |  | 2027-04-06
[6 empty] | Y |  | LA | Actual
|  |  | Special items |  | Piping | N |  | LA | Plan | 2026-01-08 | 2026-01-09 | 2026-01-16 | 2026-01-19 | 2026-01-26 | 76 |  | 2026-02-09 | 2026-03-09 | 2026-03-12 | 2026-03-26 | 2026-03-30 | 24 | 2026-09-10 | 168 | 2026-09-10 | 2027-05-31 | 2 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
[5 empty] | Piping | N |  | LA | Forecast | 2026-01-08 | 2026-01-09 | 2026-01-16 | 2026-01-19 | 2026-01-26 |  |  | 2026-02-09 | 2026-03-09 | 2026-03-12 | 2026-03-24 | 2026-03-26 |  | 2026-09-08 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
[5 empty] | Piping | N |  | LA | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | SPECIAL PIPE SUPPORT |  | Piping | N |  | LA | Plan | 2026-04-27 | 2026-04-28 | 2026-05-05 | 2026-05-06 | 2026-05-13 | 74 |  | 2026-05-27 | 2026-06-24 | 2026-06-29 | 2026-07-11 | 2026-07-14 | 24 | 2026-12-26 | 168 | 2026-12-26 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | SPECIAL PIPE SUPPORT |  | Piping | N |  | LA | Forecast | 2026-04-27 | 2026-04-28 | 2026-05-05 | 2026-05-06 | 2026-05-13 |  |  | 2026-05-27 | 2026-06-24 | 2026-06-29 | 2026-07-11 | 2026-07-14 |  | 2026-12-26 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | SPECIAL PIPE SUPPORT |  | Piping | N |  | LA | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | CS Fitting |  | Piping | N |  | LD | Plan | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 | 39 |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 | 12.8571 | 2026-12-26 | 90 | 2026-12-26 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | CS Fitting |  | Piping | N |  | LD | Forecast | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 |  |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 |  | 2026-12-26 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | CS Fitting |  | Piping | N |  | LD | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | SS & DSS Fitting |  | Piping | N |  | LD | Plan | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 | 39 |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 | 12.8571 | 2026-12-26 | 90 | 2026-12-26 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | SS & DSS Fitting |  | Piping | N |  | LD | Forecast | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 |  |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 |  | 2026-12-26 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | SS & DSS Fitting |  | Piping | N |  | LD | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | CS Flange |  | Piping | N |  | LD | Plan | 2026-05-27 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-12 | 38 |  | 2026-06-19 | 2026-06-30 | 2026-07-02 | 2026-07-09 | 2026-07-13 | 24.2857 | 2026-12-26 | 170 | 2026-12-26 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | CS Flange |  | Piping | N |  | LD | Forecast | 2026-05-27 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-12 |  |  | 2026-06-19 | 2026-06-30 | 2026-07-02 | 2026-07-09 | 2026-07-13 |  | 2026-12-26 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | CS Flange |  | Piping | N |  | LD | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | SS & DSS Flange |  | Piping | N |  | LD | Plan | 2026-05-27 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-12 | 38 |  | 2026-06-19 | 2026-06-30 | 2026-07-02 | 2026-07-09 | 2026-07-13 | 24.2857 | 2026-12-26 | 170 | 2026-12-26 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | SS & DSS Flange |  | Piping | N |  | LD | Forecast | 2026-05-27 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-12 |  |  | 2026-06-19 | 2026-06-30 | 2026-07-02 | 2026-07-09 | 2026-07-13 |  | 2026-12-26 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | SS & DSS Flange |  | Piping | N |  | LD | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | SAW Welded Pipe |  | Piping | N |  | LD | Plan | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 | 39 |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 | 12.8571 | 2026-12-26 | 90 | 2026-12-26 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | SAW Welded Pipe |  | Piping | N |  | LD | Forecast | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 |  |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 |  | 2026-12-26 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | SAW Welded Pipe |  | Piping | N |  | LD | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | CS Pipe |  | Piping | N |  | LD | Plan | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 | 39 |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 | 12.8571 | 2026-12-26 | 90 | 2026-12-26 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | CS Pipe |  | Piping | N |  | LD | Forecast | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 |  |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 |  | 2026-12-26 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | CS Pipe |  | Piping | N |  | LD | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | DSS Pipes |  | Piping | N |  | LD | Plan | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 | 39 |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 | 12.8571 | 2026-12-26 | 90 | 2026-12-26 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | DSS Pipes |  | Piping | N |  | LD | Forecast | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 |  |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 |  | 2026-12-26 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | DSS Pipes |  | Piping | N |  | LD | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | Steamless SS pipes |  | Piping | N |  | LD | Plan | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 | 39 |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 | 12.8571 | 2026-12-26 | 90 | 2026-12-26 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | Steamless SS pipes |  | Piping | N |  | LD | Forecast | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-01 |  |  | 2026-09-08 | 2026-09-17 | 2026-09-21 | 2026-09-27 | 2026-09-29 |  | 2026-12-26 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | Steamless SS pipes |  | Piping | N |  | LD | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | Bolts & Nuts |  | Piping | N |  | LD | Plan | 2026-07-16 | 2026-07-21 | 2026-07-28 | 2026-07-29 | 2026-08-03 | 38 |  | 2026-08-10 | 2026-08-19 | 2026-08-21 | 2026-08-28 | 2026-09-01 | 17.1429 | 2026-12-26 | 120 | 2026-12-26 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | Bolts & Nuts |  | Piping | N |  | LD | Forecast | 2026-07-16 | 2026-07-21 | 2026-07-28 | 2026-07-29 | 2026-08-03 |  |  | 2026-08-10 | 2026-08-19 | 2026-08-21 | 2026-08-28 | 2026-09-01 |  | 2026-12-26 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | Bolts & Nuts |  | Piping | N |  | LD | Actual | bar: 2010-05-31 to 2026-07-28
|  |  | Gasket |  | Piping | N |  | LD | Plan | 2026-07-16 | 2026-07-21 | 2026-07-28 | 2026-07-29 | 2026-08-03 | 38 |  | 2026-08-10 | 2026-08-19 | 2026-08-21 | 2026-08-28 | 2026-09-01 | 17.1429 | 2026-12-26 | 120 | 2026-12-26 | 2027-05-31 | 0 | [12 empty] | #REF! | #REF! | #REF! | 7 | bar: 2010-05-31 to 2026-07-28
|  |  | Gasket |  | Piping | N |  | LD | Forecast | 2026-07-16 | 2026-07-21 | 2026-07-28 | 2026-07-29 | 2026-08-03 |  |  | 2026-08-10 | 2026-08-19 | 2026-08-21 | 2026-08-28 | 2026-09-01 |  | 2026-12-26 | [16 empty] | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | Gasket |  | Piping | N |  | LD | Actual | bar: 2010-05-31 to 2026-07-28

## After Award (hidden)
ZM167 PTTEPI ASK Procurement Status Report (PSR) - After Award
[8 empty] | LA | Most complexity RFQ | [8 empty] | 20 | 10 |  |  | 5 | 5 | 5 | 2 | 10
date | - Forecast later than Plan | [6 empty] | LB | High complexity RFQ | [8 empty] | 20 | 10 |  |  | 5 | 5 | 5 | 2 | 10
date | - Two weeks forecasted activities | [6 empty] | LC | Normal complexity RFQ | [8 empty] | 15 | 10 |  |  | 5 | 5 | 5 | 2 | 10
date | - Overdue activities | [6 empty] | LD | Low complexity RFQ |  |  | 74.7% | [5 empty] | 10 | 10 |  |  | 5 | 5 | 5 | 2 | 10
No. | Remark | PIC | DIS | RFQ No. | LLI | Vendors | Description | Criticality Rating | MRQ No. | weight | weight | weight | weight | weight | weight | P/F/A | KOM | VDR Submission | Approval of Key Vendor Documents | Delivery of Major Materials | Start Production | FAT | Ready for Shipment | Receipt at WORKSITE | Punch List Clearance | Approval of Final Documentation | Delivery Date | Delivery Condition | Transportation time | Lead Time | ETA Date | ROS date | ROS date (input) | Improved time for ROS date | Float | PO No. | Awarded Supplier | 2010-05-31 | 2010-06-30 | 2010-07-31 | 2010-08-31 | 2010-09-30 | 2010-10-31 | 2010-11-30 | 2010-12-31 | 2011-01-31 | 2011-02-28 | 2026-07-28
Y/N
[16 empty] | Matrix | TJE QA/QC | PTTEPI | PTTEPI | TJE PRC | Bidder | TJE ENG | PTTEPI | Bidder | TJE PRC | PTTEPI | Vendor | [21 empty] | #REF!
[16 empty] | Progress | [10 empty] | 95%
1 | Use FEED deliverables | TBA | MEC | RFQ-001 | N | FAVELLE FAVCO OIL STATES SCM | Pedestal Crane | LA |  | 2% | [5 empty] | P | 2026-07-19 | #REF! | #REF! | #REF! |  | 2027-05-25 |  |  |  |  | 2027-06-29 | DDP ZHJT Yard | 14 | 350 | #REF! | 2027-06-29 | 2027-04-30 | 60 | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-001 | N |  | Pedestal Crane | LA |  |  | 2% |  |  |  |  | F | 2026-07-19 | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-001 | N |  | Pedestal Crane | LA |  |  |  | 2% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
2 |  | TBA | MEC | RFQ-002 | N | Yale Excellift Crosby KITO | Material Handling Equipment | LA |  | 7% | [5 empty] | P | 2027-01-11 | #REF! | #REF! | #REF! |  | 2027-05-26 |  |  |  |  | 2027-06-30 | DDP ZHJT Yard | 14 | 175 | #REF! | 2027-06-30 | 2027-06-30 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-002 | N |  | Material Handling Equipment | LA |  |  | 7% |  |  |  |  | F | 2027-01-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-002 | N |  | Material Handling Equipment | LA |  |  |  | 7% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
3 | AVL Approval for ZHJT Yard and lead time is TBC | TBA | MEC | RFQ-003 | Y | Pall Crest ZHJT | Instrument Gas Filter Coalescer | LA |  | 15% | [5 empty] | P | 2026-09-26 | #REF! | #REF! | #REF! |  | 2027-02-13 |  |  |  |  | 2027-03-20 | DDP ZHJT Yard | 7 | 180 | #REF! | 2027-02-01 | 2027-02-01 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-003 | Y |  | Instrument Gas Filter Coalescer | LA |  |  | 15% |  |  |  |  | F | 2026-09-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-003 | Y |  | Instrument Gas Filter Coalescer | LA |  |  |  | 15% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
4 | AVL Approval for ZHJT Yard to reduce by 2 months To study installation sequence | TBA | MEC | RFQ-004 | N | AMC ALPHA ECC Zhuhai Jutal | Production & Test Seperator | LA |  | 2% | [5 empty] | P | 2026-09-23 | #REF! | #REF! | #REF! |  | 2027-02-13 |  |  |  |  | 2027-03-20 | DDP ZHJT Yard | 14 | 336 | #REF! | 2027-01-29 | 2027-01-30 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-004 | N |  | Production & Test Seperator | LA |  |  | 2% |  |  |  |  | F | 2026-09-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-004 | N |  | Production & Test Seperator | LA |  |  |  | 2% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
5 | AVL Approval for ZHJT Yard to reduce by 2 months To study installation sequence | TBA | PIP | RFQ-005 | Y | AMC ALPHA ECC APPLIED ENGINEERING Zhuhai Jutal | Pig Launcher and Receiver | LA |  | 2% | [5 empty] | P | 2026-08-19 | #REF! | #REF! | #REF! |  | 2027-02-19 |  |  |  |  | 2027-03-26 | DDP ZHJT Yard | 14 | 294 | #REF! | 2026-11-13 | 2026-11-15 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-005 | Y |  | Pig Launcher and Receiver | LA |  |  | 2% |  |  |  |  | F | 2026-08-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-005 | Y |  | Pig Launcher and Receiver | LA |  |  |  | 2% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
6 | AVL Approval for WASCO and lead time is 28 weeks Early issuance of Datasheet | TBA | MEC | RFQ-006 | Y | WILLIAM (under MILTON ROY) （Packager: Multiphase) WILLIAM (under MILTON ROY) （Packager: Ashburn International Trade (Tianjin) Co., Ltd) TEXSTEAM (under Dresser) | Corrosion Inhibitor Injection Pump | LA |  | 1% | [5 empty] | P | 2026-07-22 | #REF! | #REF! | #REF! |  | 2027-01-22 |  |  |  |  | 2027-02-26 | DDP ZHJT Yard | 14 | 224 | #REF! | 2027-02-26 | 2027-02-28 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-006 | Y |  | Corrosion Inhibitor Injection Pump | LA |  |  | 1% |  |  |  |  | F | 2026-07-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-006 | Y |  | Corrosion Inhibitor Injection Pump | LA |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
7 |  | TBA | MEC | RFQ-007 | N | WILLIAM (under MILTON ROY) （Packager: Multiphase) WILLIAM (under MILTON ROY) （Packager: Ashburn International Trade (Tianjin) Co., Ltd) TEXSTEAM (under Dresser) | Demulsifier/Water Clarifier Injection Pump | LA |  | 2% | [5 empty] | P | 2026-08-24 | #REF! | #REF! | #REF! |  | 2027-02-24 |  |  |  |  | 2027-03-31 | DDP ZHJT Yard | 14 | 224 | #REF! | 2027-03-31 | 2027-03-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-007 | N |  | Demulsifier/Water Clarifier Injection Pump | LA |  |  | 2% |  |  |  |  | F | 2026-08-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-007 | N |  | Demulsifier/Water Clarifier Injection Pump | LA |  |  |  | 2% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
8 | Mitigation required, ZJHT approval required to reduce the lead time by 40 days To study installation sequence | TBA | MEC | RFQ-008 | N | Sulzer Zhuhai Jutal (FMC internal) Burgess Manning (under CECO) ALPHA ECC (FMC internal) | De-Oiler Hydrocyclone | LA |  | 1% | [5 empty] | P | 2026-08-05 | #REF! | #REF! | #REF! |  | 2026-12-25 |  |  |  |  | 2027-01-29 | DDP ZHJT Yard | 14 | 280 | #REF! | 2027-01-29 | 2027-01-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-008 | N |  | De-Oiler Hydrocyclone | LA |  |  | 1% |  |  |  |  | F | 2026-08-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-008 | N |  | De-Oiler Hydrocyclone | LA |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
9 | Mitigation requied, ZJHT approval required to reduce the lead time by 40 days To study installation sequence | TBA | MEC | RFQ-009 | N | Sulzer Zhuhai Jutal (FMC internal) Burgess Manning (under CECO) ALPHA ECC (FMC internal) | Degasser | LA |  | 4% | [5 empty] | P | 2026-08-05 | #REF! | #REF! | #REF! |  | 2026-12-25 |  |  |  |  | 2027-01-29 | DDP ZHJT Yard | 14 | 280 | #REF! | 2027-01-29 | 2027-01-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-009 | N |  | Degasser | LA |  |  | 4% |  |  |  |  | F | 2026-08-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-009 | N |  | Degasser | LA |  |  |  | 4% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
10 | Mitigation requied, ZJHT approval required to reduce the lead time by 2 months To study installation sequence | TBA | MEC | RFQ-010 | N | AMC ALPHA ECC Zhuhai Jutal | Skim Tank Vessel | LA |  | 1% | [5 empty] | P | 2026-08-05 | #REF! | #REF! | #REF! |  | 2026-12-25 |  |  |  |  | 2027-01-29 | DDP ZHJT Yard | 14 | 294 | #REF! | 2027-01-29 | 2027-01-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-010 | N |  | Skim Tank Vessel | LA |  |  | 1% |  |  |  |  | F | 2026-08-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-010 | N |  | Skim Tank Vessel | LA |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
11 | Mitigation requied, ZJHT approval required to reduce the lead time by 2 months To study installation sequence | TBA | MEC | RFQ-011 | Y | AMC ALPHA ECC Zhuhai Jutal | Closed Drain Sump Vessel | LA |  | 1% | [5 empty] | P | 2026-08-26 | #REF! | #REF! | #REF! |  | 2027-01-15 |  |  |  |  | 2027-02-19 | DDP ZHJT Yard | 14 | 294 | #REF! | 2026-12-30 | 2026-12-30 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-011 | Y |  | Closed Drain Sump Vessel | LA |  |  | 1% |  |  |  |  | F | 2026-08-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-011 | Y |  | Closed Drain Sump Vessel | LA |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
12 | Mitigation requied, ZJHT approval required to reduce the lead time by 1 months | TBA | MEC | RFQ-012 | N | AMC ALPHA ECC Zhuhai Jutal | Diesel Storage Tote Tank | LA |  | 1% | [5 empty] | P | 2026-09-16 | #REF! | #REF! | #REF! |  | 2026-12-25 |  |  |  |  | 2027-01-29 | DDP ZHJT Yard | 14 | 238 | #REF! | 2027-01-29 | 2027-01-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-012 | N |  | Diesel Storage Tote Tank | LA |  |  | 1% |  |  |  |  | F | 2026-09-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-012 | N |  | Diesel Storage Tote Tank | LA |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
13 | Mitigation requied, ZJHT approval required to reduce the lead time by 1 months | TBA | MEC | RFQ-013 | N | AMC ALPHA ECC Zhuhai Jutal | Corrosion Inhibitor Storage Tank | LA |  | 0.1% | [5 empty] | P | 2026-10-24 | #REF! | #REF! | #REF! |  | 2027-02-01 |  |  |  |  | 2027-03-08 | DDP ZHJT Yard | 14 | 238 | #REF! | 2027-01-29 | 2027-01-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-013 | N |  | Corrosion Inhibitor Storage Tank | LA |  |  | 0.1% |  |  |  |  | F | 2026-10-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-013 | N |  | Corrosion Inhibitor Storage Tank | LA |  |  |  | 0.1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
14 | AVL approval for WASCO (20 weeks lead time) To study installation sequence | TBA | MEC | RFQ-014 | N | Mc FARLAND HASKEL (Package: Ashburn International Trade (Tianjin) Co., Ltd) | Closed Drain Sump Pump | LA |  | 1% | [5 empty] | P | 2026-07-12 | #REF! | #REF! | #REF! |  | 2027-01-12 |  |  |  |  | 2027-02-16 | DDP ZHJT Yard | 14 | 224 | #REF! | 2026-12-30 | 2026-12-30 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-014 | N |  | Closed Drain Sump Pump | LA |  |  | 1% |  |  |  |  | F | 2026-07-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-014 | N |  | Closed Drain Sump Pump | LA |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
15 |  | TBA | MEC | RFQ-015 | N | WILDEN （C/O Multiphase) ARO (Under INGERSOLL RAND）(C/O Shanghai Shuyi Machine Engineering & Equipment Co.,Ltd） SANDPIPER (C/O SHANGHAI YIZHI FLOW CONTROL EQUIPMENT CO., LTD ) | Diesel Transfer Pump | LA |  | 1% | [5 empty] | P | 2026-10-07 | #REF! | #REF! | #REF! |  | 2027-04-09 |  |  |  |  | 2027-05-14 | DDP ZHJT Yard | 14 | 224 | #REF! | 2027-05-14 | 2027-05-15 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-015 | N |  | Diesel Transfer Pump | LA |  |  | 1% |  |  |  |  | F | 2026-10-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-015 | N |  | Diesel Transfer Pump | LA |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
16 |  | TBA | MEC | RFQ-016 | N | ARO (Under INGERSOLL RAND）(C/O Shanghai Shuyi Machine Engineering & Equipment Co.,Ltd） SANDPIPER (C/O SHANGHAI YIZHI FLOW CONTROL EQUIPMENT CO., LTD ) | Open Drain Caisson Pump | LA |  | 0.05% | [5 empty] | P | 2026-08-24 | #REF! | #REF! | #REF! |  | 2027-02-24 |  |  |  |  | 2027-03-31 | DDP ZHJT Yard | 14 | 224 | #REF! | 2027-03-31 | 2027-03-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-016 | N |  | Open Drain Caisson Pump | LA |  |  | 0.05% |  |  |  |  | F | 2026-08-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MEC | RFQ-016 | N |  | Open Drain Caisson Pump | LA |  |  |  | 0.05% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
17 |  | TBA | ELE | RFQ-017 | N | STAHL Swift Energy Beijing Talented Electrical Sets Co., Ltd. Anhui Schutten Solar Energy Co.,ltd Semitech Control & Engineering PTE Ltd | DC Distribution Board | LC |  | 0.1% | [5 empty] | P | 2026-09-07 | #REF! | #REF! | #REF! |  | 2027-03-24 |  |  |  |  | 2027-04-28 | DDP ZHJT Yard | 14 | 238 | #REF! | 2027-04-28 | 2027-04-28 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-017 | N |  | DC Distribution Board | LC |  |  | 0.1% |  |  |  |  | F | 2026-09-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-017 | N |  | DC Distribution Board | LC |  |  |  | 0.1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
18 | PVL approval for Beijing Talented / Warom to reduce the lead time (60 days) To study installation sequence | TBA | ELE | RFQ-018 | N | Swift Energy Beijing Talented Electrical Sets Co., Ltd. Anhui Schutten Solar Energy Co.,ltd Semitech Control & Engineering PTE Ltd MDS (Orga) | Solar Power System | LB |  | 0.1% | [5 empty] | P | 2026-07-27 | #REF! | #REF! | #REF! |  | 2027-02-24 |  |  |  |  | 2027-03-31 | DDP ZHJT Yard | 14 | 252 | #REF! | 2027-03-31 | 2027-03-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-018 | N |  | Solar Power System | LB |  |  | 0.1% |  |  |  |  | F | 2026-07-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-018 | N |  | Solar Power System | LB |  |  |  | 0.1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
19 |  | TBA | ELE | RFQ-019 | N | Swift Energy MDS (Orga) | Navigation Aid System | LB |  | 0.15% | [5 empty] | P | 2026-09-14 | #REF! | #REF! | #REF! |  | 2027-05-26 |  |  |  |  | 2027-06-30 | DDP ZHJT Yard | 14 | 294 | #REF! | 2027-07-30 | 2027-07-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-019 | N |  | Navigation Aid System | LB |  |  | 0.15% |  |  |  |  | F | 2026-09-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-019 | N |  | Navigation Aid System | LB |  |  |  | 0.15% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
20 |  | TBA | ELE | RFQ-020 | Y | Swift Energy MDS (Orga) | External Battery Charger | LC |  | 0.05% | [5 empty] | P | 2026-09-09 | #REF! | #REF! | #REF! |  | 2027-04-09 |  |  |  |  | 2027-05-14 | DDP ZHJT Yard | 14 | 252 | #REF! | 2027-05-14 | 2027-05-15 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-020 | Y |  | External Battery Charger | LC |  |  | 0.05% |  |  |  |  | F | 2026-09-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-020 | Y |  | External Battery Charger | LC |  |  |  | 0.05% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
21 |  | TBA | INS | RFQ-021 | N | FISHER CCI FLOWSERVE | Control Valve | LB |  | 1% | [5 empty] | P | 2026-11-14 | #REF! | #REF! | #REF! |  | 2027-04-23 |  |  |  |  | 2027-05-28 | DDP ZHJT Yard | 7 | 200 | #REF! | 2027-05-28 | 2027-05-30 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-021 | N |  | Control Valve | LB |  |  | 1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-021 | N |  | Control Valve | LB |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
22 |  | TBA | INS | RFQ-022 | N | FISHER CCI FLOWSERVE | Self Regulator Valve | LB |  | 1% | [5 empty] | P | 2026-11-17 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 200 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-022 | N |  | Self Regulator Valve | LB |  |  | 1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-022 | N |  | Self Regulator Valve | LB |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
23 |  | TBA | INS | RFQ-023 | N | CCI CAMERON(SLB) MASTER FLO MOKVELD | Actuated Choke Valve | LB |  | 1% | [5 empty] | P | 2026-08-01 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 308 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-023 | N |  | Actuated Choke Valve | LB |  |  | 1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-023 | N |  | Actuated Choke Valve | LB |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
24 |  | TBA | INS | RFQ-024 | N | COMBET Flowserve | Actuated Ball Valve | LB |  | 1% | [5 empty] | P | 2026-09-26 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 252 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-024 | N |  | Actuated Ball Valve | LB |  |  | 1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-024 | N |  | Actuated Ball Valve | LB |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
25 |  | TBA | INS | RFQ-025 | N | TechnipFMC COMBET Flowserve | Actuated Compact Ball Valve | LB |  | 1% | [5 empty] | P | 2026-08-29 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 280 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-025 | N |  | Actuated Compact Ball Valve | LB |  |  | 1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-025 | N |  | Actuated Compact Ball Valve | LB |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
26 |  | TBA | INS | RFQ-026 | N | CROSBY DRESSER / CONSOLIDATED IMI FARRIS | Safety Relief Valves | LB |  | 2% | [5 empty] | P | 2026-12-05 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 184 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-026 | N |  | Safety Relief Valves | LB |  |  | 2% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-026 | N |  | Safety Relief Valves | LB |  |  |  | 2% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
27 |  | TBA | INS | RFQ-027 | N | Yokogawa MICRO MOTIONS (EMERSON) | Coriolis Flow Meters | LC |  | 4% | [5 empty] | P | 2027-01-11 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 145 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-027 | N |  | Coriolis Flow Meters | LC |  |  | 4% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-027 | N |  | Coriolis Flow Meters | LC |  |  |  | 4% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
28 | MitigationTBC Consider FEED Doc. | TBA | INS | RFQ-028 | Y | wilmax FST IVS Matorly | Wellhead Control Panel (WHCP) | LB |  | 3% | [5 empty] | P | 2026-07-26 | #REF! | #REF! | #REF! |  | 2027-02-23 |  |  |  |  | 2027-03-30 | DDP ZHJT Yard | 7 | 252 | #REF! | 2027-01-29 | 2027-01-30 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-028 | Y |  | Wellhead Control Panel (WHCP) | LB |  |  | 3% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-028 | Y |  | Wellhead Control Panel (WHCP) | LB |  |  |  | 3% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
29 |  | TBA | INS | RFQ-029 | N | ASHCROFT BOUDON HASEM WIKA | Pressure Gauge | LC |  | 3.4% | [5 empty] | P | 2027-01-30 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 126 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-029 | N |  | Pressure Gauge | LC |  |  | 3.4% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-029 | N |  | Pressure Gauge | LC |  |  |  | 3.4% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
30 |  | TBA | INS | RFQ-030 | N | Yokogawa EMERSON E+H | Pressure Transmitter | LC |  | 1% | [5 empty] | P | 2027-01-30 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 126 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-030 | N |  | Pressure Transmitter | LC |  |  | 1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-030 | N |  | Pressure Transmitter | LC |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
31 |  | TBA | INS | RFQ-031 | N | ASCHROFT WIKA EMERSON | Temperature Gauge | LC |  | 1% | [5 empty] | P | 2027-01-30 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 126 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-031 | N |  | Temperature Gauge | LC |  |  | 1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-031 | N |  | Temperature Gauge | LC |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
32 |  | TBA | INS | RFQ-032 | N | EMERSON YOKOGAWA HONEYWELL | Temperature Transmitter | LC |  | 2% | [5 empty] | P | 2027-01-30 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 126 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-032 | N |  | Temperature Transmitter | LC |  |  | 2% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-032 | N |  | Temperature Transmitter | LC |  |  |  | 2% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
33 |  | TBA | INS | RFQ-033 | N | Yokogawa EMERSON | Vortex Flow Meter | LC |  | 4% | [5 empty] | P | 2027-01-30 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 126 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-033 | N |  | Vortex Flow Meter | LC |  |  | 4% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-033 | N |  | Vortex Flow Meter | LC |  |  |  | 4% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
34 |  | TBA | INS | RFQ-034 | N | Magnetrol WIKA | Level Transmitter and Gauge | LC |  | 1% | [5 empty] | P | 2027-01-30 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 126 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-034 | N |  | Level Transmitter and Gauge | LC |  |  | 1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-034 | N |  | Level Transmitter and Gauge | LC |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
35 |  | TBA | INS | RFQ-035 | N | EMERSON Shenyang Yongye T.D. Williamson | Pig Signaller | LC |  | 0.5% | [5 empty] | P | 2027-01-30 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 126 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-035 | N |  | Pig Signaller | LC |  |  | 0.5% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-035 | N |  | Pig Signaller | LC |  |  |  | 0.5% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
36 |  | TBA | INS | RFQ-036 | N | EMERSON WIKA | Rrestriction Orifice | LC |  | 0.5% | [5 empty] | P | 2027-01-02 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 154 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-036 | N |  | Rrestriction Orifice | LC |  |  | 0.5% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-036 | N |  | Rrestriction Orifice | LC |  |  |  | 0.5% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
37 |  | TBA | INS | RFQ-037 | N | Rockwell China Rockwell Thailand | PLC System | LB |  | 0.5% | [5 empty] | P | 2026-09-26 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 252 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-037 | N |  | PLC System | LB |  |  | 0.5% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-037 | N |  | PLC System | LB |  |  |  | 0.5% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
38 |  | TBA | INS | RFQ-038 | N | Draeger Honeywell | Fire and Gas Detector | LC |  | 0.5% | [5 empty] | P | 2027-01-25 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 131 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-038 | N |  | Fire and Gas Detector | LC |  |  | 0.5% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-038 | N |  | Fire and Gas Detector | LC |  |  |  | 0.5% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
39 |  | TBA | INS | RFQ-039 | N | MAC Yokogawa | Dip Tape Level Indicator | LC |  | 0.5% | [5 empty] | P | 2027-01-30 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 126 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-039 | N |  | Dip Tape Level Indicator | LC |  |  | 0.5% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-039 | N |  | Dip Tape Level Indicator | LC |  |  |  | 0.5% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
40 |  | TBA | INS | RFQ-040 | N | TOPWORX-GO SWITCH WESTLOCK (MAGNUM SERIES) | Position Limit Switches | LC |  | 0.5% | [5 empty] | P | 2027-01-30 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 126 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-040 | N |  | Position Limit Switches | LC |  |  | 0.5% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-040 | N |  | Position Limit Switches | LC |  |  |  | 0.5% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
41 |  | TBA | INS | RFQ-041 | N | VEGA Krohne EMERSON | Guided Wave Radar Level Transmitter | LC |  | 0.5% | [5 empty] | P | 2026-11-07 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 210 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-041 | N |  | Guided Wave Radar Level Transmitter | LC |  |  | 0.5% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-041 | N |  | Guided Wave Radar Level Transmitter | LC |  |  |  | 0.5% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
42 |  | TBA | INS | RFQ-042 | N | E+H EMERSON | Oil in Water Analyzer | LC |  | 0.2% | [5 empty] | P | 2026-12-19 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 168 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-042 | N |  | Oil in Water Analyzer | LC |  |  | 0.2% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-042 | N |  | Oil in Water Analyzer | LC |  |  |  | 0.2% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
43 |  | TBA | INS | RFQ-043 | N | MAGNETROL EMERSON VEGA | Level Switch | LC |  | 0.5% | [5 empty] | P | 2027-04-06 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 60 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-043 | N |  | Level Switch | LC |  |  | 0.5% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-043 | N |  | Level Switch | LC |  |  |  | 0.5% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
44 |  | TBA | INS | RFQ-044 | N | E+H VEGA | Flow Switch | LC |  | 0.5% | [5 empty] | P | 2027-04-06 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 60 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-044 | N |  | Flow Switch | LC |  |  | 0.5% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-044 | N |  | Flow Switch | LC |  |  |  | 0.5% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
45 |  | TBA | INS | RFQ-045 | N | Rockwell China Rockwell Thailand | SCADA System | LB |  | 0.2% | [5 empty] | P | 2026-09-26 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 252 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-045 | N |  | SCADA System | LB |  |  | 0.2% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-045 | N |  | SCADA System | LB |  |  |  | 0.2% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
46 |  | TBA | INS | RFQ-046 | Y | Excel OMEGA Fusion | Telecommunication System (WiMAX, Telephone, Marine Radio) | LC |  | 0.2% | [5 empty] | P | 2026-08-15 | #REF! | #REF! | #REF! |  | 2027-04-26 |  |  |  |  | 2027-05-31 | DDP ZHJT Yard | 7 | 294 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-046 | Y |  | Telecommunication System (WiMAX, Telephone, Marine Radio) | LC |  |  | 0.2% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-046 | Y |  | Telecommunication System (WiMAX, Telephone, Marine Radio) | LC |  |  |  | 0.2% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
47 |  | TBA | INS | RFQ-047 | N | MDS | Marine Racon | LC |  | 0.1% | [5 empty] | P | 2026-12-14 | #REF! | #REF! | #REF! |  | 2027-02-24 |  |  |  |  | 2027-03-31 | DDP ZHJT Yard | 7 | 112 | #REF! | 2027-03-31 | 2027-03-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-047 | N |  | Marine Racon | LC |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-047 | N |  | Marine Racon | LC |  |  |  | 0.1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
48 |  | TBA | PIP | RFQ-048 | N | YDF Neway VALVITALIA | BALL VALVE (FLANGE END) | LC |  | 0.1% | [5 empty] | P | 2026-09-04 | #REF! | #REF! | #REF! |  | 2027-01-25 |  |  |  |  | 2027-03-01 | DDP ZHJT Yard | 7 | 183 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-048 | N |  | BALL VALVE (FLANGE END) | LC |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-048 | N |  | BALL VALVE (FLANGE END) | LC |  |  |  | 0.1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
49 |  | TBA | PIP | RFQ-049 | N | YDF Neway VALVITALIA | GLOBE VALVE (FLANGE END) | LC |  | 1% | [5 empty] | P | 2026-09-04 | #REF! | #REF! | #REF! |  | 2027-01-25 |  |  |  |  | 2027-03-01 | DDP ZHJT Yard | 7 | 183 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-049 | N |  | GLOBE VALVE (FLANGE END) | LC |  |  | 1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-049 | N |  | GLOBE VALVE (FLANGE END) | LC |  |  |  | 1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
50 |  | TBA | PIP | RFQ-050 | N | YDF Neway VALVITALIA | GLOBE VALVE (WELDED END) | LC |  | 0.05% | [5 empty] | P | 2026-09-04 | #REF! | #REF! | #REF! |  | 2027-01-25 |  |  |  |  | 2027-03-01 | DDP ZHJT Yard | 7 | 183 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-050 | N |  | GLOBE VALVE (WELDED END) | LC |  |  | 0.05% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-050 | N |  | GLOBE VALVE (WELDED END) | LC |  |  |  | 0.05% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
51 |  | TBA | PIP | RFQ-051 | N | YDF Neway VALVITALIA | CHECK VALVE (FLANGE END) | LC |  | 0.1% | [5 empty] | P | 2026-09-04 | #REF! | #REF! | #REF! |  | 2027-01-25 |  |  |  |  | 2027-03-01 | DDP ZHJT Yard | 7 | 183 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-051 | N |  | CHECK VALVE (FLANGE END) | LC |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-051 | N |  | CHECK VALVE (FLANGE END) | LC |  |  |  | 0.1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
52 |  | TBA | INS | RFQ-052 | N | YDF Neway VALVITALIA | CHECK VALVE (WELDED END) | LC |  | 0.1% | [5 empty] | P | 2026-09-04 | #REF! | #REF! | #REF! |  | 2027-01-25 |  |  |  |  | 2027-03-01 | DDP ZHJT Yard | 7 | 183 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-052 | N |  | CHECK VALVE (WELDED END) | LC |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INS | RFQ-052 | N |  | CHECK VALVE (WELDED END) | LC |  |  |  | 0.1% |  |  |  | A | [32 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
53 |  | TBA | PIP | RFQ-053 | N | YDF Neway VALVITALIA | COMPACT CHECK VALVE (WELDED END) | LB |  | 0.1% | [5 empty] | P | 2026-08-08 | #REF! | #REF! | #REF! |  | 2027-01-25 |  |  |  |  | 2027-03-01 | DDP ZHJT Yard | 7 | 183 | #REF! | 2027-05-31 | 2027-05-31 |  | #REF! | [13 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-053 | N |  | COMPACT CHECK VALVE (WELDED END) | LB |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [21 empty] | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-053 | N |  | COMPACT CHECK VALVE (WELDED END) | LB |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
54 | Place Order 70% preliminary FEED MTO | TBA | STR | RFQ-054 | N |  | Primary Steel - Plate | LA |  | 0.1% | [5 empty] | P | 2026-04-17 | #REF! | #REF! | #REF! |  | 2026-07-06 |  |  |  |  | 2026-08-10 | DDP ZHJT Yard | 7 | 84 | #REF! | 2026-08-10 | 2026-08-10 |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | STR | RFQ-054 | N |  | Primary Steel - Plate | LA |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | STR | RFQ-054 | N |  | Primary Steel - Plate | LA |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
55 | Place Order 70% preliminary FEED MTO | TBA | STR | RFQ-054 | N |  | Primary Steel - Beam | LA |  | 0.1% | [5 empty] | P | 2026-04-17 | #REF! | #REF! | #REF! |  | 2026-07-06 |  |  |  |  | 2026-08-10 | DDP ZHJT Yard | 7 | 133 | #REF! | 2026-08-10 | 2026-08-10 |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | STR | RFQ-054 | N |  | Primary Steel - Beam | LA |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | STR | RFQ-054 | N |  | Primary Steel - Beam | LA |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
56 | Place Order 70% preliminary FEED MTO | TBA | STR | RFQ-054 | N |  | Primary Steel - Seamless | LA |  | 0.1% | [5 empty] | P | 2026-05-05 | #REF! | #REF! | #REF! |  | 2026-08-06 |  |  |  |  | 2026-09-10 | DDP ZHJT Yard | 7 | 192 | #REF! | 2026-08-10 | 2026-08-10 |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | STR | RFQ-054 | N |  | Primary Steel - Seamless | LA |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | STR | RFQ-054 | N |  | Primary Steel - Seamless | LA |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
57 | Place Order 70% preliminary FEED MTO | TBA | ELE | RFQ-054 | N |  | Primary Steel - Welding | LA |  | 0.1% | [5 empty] | P | #REF! | #REF! | #REF! | #REF! |  | #REF! |  |  |  |  | #REF! | DDP ZHJT Yard | 7 | 141 | #REF! |  |  |  | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | Primary Steel - Welding | LA |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | Primary Steel - Welding | LA |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
58 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | JUNCTION BOX AND RECEPTACLES | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 175 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | JUNCTION BOX AND RECEPTACLES | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | JUNCTION BOX AND RECEPTACLES | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
59 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | CABLE GLAND | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 123 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | CABLE GLAND | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | CABLE GLAND | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
60 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | ELECTRICAL CABLE LADDER / TRAY | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 175 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | ELECTRICAL CABLE LADDER / TRAY | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | ELECTRICAL CABLE LADDER / TRAY | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
61 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | EARTHING SYSTEM | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | EARTHING SYSTEM | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | EARTHING SYSTEM | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
62 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | MULTI-CABLE TRANSIT (MCT) | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 123 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | MULTI-CABLE TRANSIT (MCT) | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | MULTI-CABLE TRANSIT (MCT) | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
63 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | ELECTRICAL CABLE | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 104 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | ELECTRICAL CABLE | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | ELECTRICAL CABLE | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
64 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | NAVIGATIONAL AIDS LANTERN AND FOG HORN | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | NAVIGATIONAL AIDS LANTERN AND FOG HORN | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | NAVIGATIONAL AIDS LANTERN AND FOG HORN | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
65 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | FLASHING BEACON AND WARNING SIREN | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | FLASHING BEACON AND WARNING SIREN | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | FLASHING BEACON AND WARNING SIREN | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
66 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | PRESERVATION AND SEA-FASTENING MATERIAL | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | PRESERVATION AND SEA-FASTENING MATERIAL | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | PRESERVATION AND SEA-FASTENING MATERIAL | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
67 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | PIPING SURPPORT | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 69 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | PIPING SURPPORT | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | PIPING SURPPORT | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
68 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | Strainer | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 151 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | Strainer | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | Strainer | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
69 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | BOLT & NUTS | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 100 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | BOLT & NUTS | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | BOLT & NUTS | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
70 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | CS FITTING | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 100 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | CS FITTING | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | CS FITTING | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
71 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | SS & DSS FITTING | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 100 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | SS & DSS FITTING | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | SS & DSS FITTING | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
72 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | Welding Electrode | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | Welding Electrode | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | Welding Electrode | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
73 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | Cable Ladder/Tray-GRP | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | Cable Ladder/Tray-GRP | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | Cable Ladder/Tray-GRP | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
74 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | Flameproof Enclosure (Ex'd) | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | Flameproof Enclosure (Ex'd) | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | Flameproof Enclosure (Ex'd) | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
75 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | Pushbutton | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | Pushbutton | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | Pushbutton | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
76 | TBC with Yard | TBA | INT | RFQ-054 | N |  | ESD Button / Station | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | INT | RFQ-054 | N |  | ESD Button / Station | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INT | RFQ-054 | N |  | ESD Button / Station | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
77 | TBC with Yard | TBA | INT | RFQ-054 | N |  | Tube Clamp (Anti Corrosion Type) | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 121 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | INT | RFQ-054 | N |  | Tube Clamp (Anti Corrosion Type) | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INT | RFQ-054 | N |  | Tube Clamp (Anti Corrosion Type) | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
78 | TBC with Yard | TBA | INT | RFQ-054 | N |  | TUBE | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 121 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | INT | RFQ-054 | N |  | TUBE | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INT | RFQ-054 | N |  | TUBE | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
79 | TBC with Yard | TBA | INT | RFQ-054 | N |  | Instrument Cable Glands | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 121 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | INT | RFQ-054 | N |  | Instrument Cable Glands | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INT | RFQ-054 | N |  | Instrument Cable Glands | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
80 | TBC with Yard | TBA | INT | RFQ-054 | N |  | Instrument cables | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 121 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | INT | RFQ-054 | N |  | Instrument cables | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | INT | RFQ-054 | N |  | Instrument cables | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
81 | TBC with Yard | TBA | ELE | RFQ-054 | N |  | AC Distribution Pane | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 100 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | ELE | RFQ-054 | N |  | AC Distribution Pane | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | ELE | RFQ-054 | N |  | AC Distribution Pane | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
82 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | SS & DSS FITTING | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 100 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | SS & DSS FITTING | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | SS & DSS FITTING | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
83 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | SS & DSS Fitting | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 100 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | SS & DSS Fitting | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | SS & DSS Fitting | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
84 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | CS FLANGES | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 100 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | CS FLANGES | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | CS FLANGES | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
85 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | DSS & SS FLANGES | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 100 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | DSS & SS FLANGES | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | DSS & SS FLANGES | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
86 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | GASKETS | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 100 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | GASKETS | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | GASKETS | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
87 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | SEAMLESS CS PIPE | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 100 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | SEAMLESS CS PIPE | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | SEAMLESS CS PIPE | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
88 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | SEAMLESS SS & DSS STEEL | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 100 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | SEAMLESS SS & DSS STEEL | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | SEAMLESS SS & DSS STEEL | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
89 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | CLAMP Type Connectors | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 121 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | CLAMP Type Connectors | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | CLAMP Type Connectors | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
90 | TBC with Yard | TBA | STR | RFQ-054 | N |  | Painting | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 75 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | STR | RFQ-054 | N |  | Painting | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | STR | RFQ-054 | N |  | Painting | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
91 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | Fire fighting | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 121 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | Fire fighting | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | Fire fighting | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
92 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | Life saving | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 121 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | Life saving | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | Life saving | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
93 | TBC with Yard | TBA | PIP | RFQ-054 | N |  | SAFETY SIGNS | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 | 121 | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | PIP | RFQ-054 | N |  | SAFETY SIGNS | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | PIP | RFQ-054 | N |  | SAFETY SIGNS | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
94 | TBC with Yard | TBA | STR | RFQ-054 | N |  | Jacket Anode | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | STR | RFQ-054 | N |  | Jacket Anode | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | STR | RFQ-054 | N |  | Jacket Anode | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
95 | TBC with Yard | TBA | STR | RFQ-054 | N |  | Steel Grating | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | STR | RFQ-054 | N |  | Steel Grating | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | STR | RFQ-054 | N |  | Steel Grating | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
96 | TBC with Yard | TBA | MIS | RFQ-054 | N |  | Welding Electrode | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  | MIS | RFQ-054 | N |  | Welding Electrode | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  | MIS | RFQ-054 | N |  | Welding Electrode | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
75 |  | TBA |  | RFQ-054 | N |  |  | LD |  | 0.1% | [5 empty] | P |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | DDP ZHJT Yard | 7 |  | #REF! |  |  |  | #REF! |  |  | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
|  |  |  | RFQ-054 | N |  |  | LD |  |  | 0.1% |  |  |  |  | F |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2010-05-31 to 2026-07-28
|  |  |  | RFQ-054 | N |  |  | LD |  |  |  | 0.1% |  |  |  | A | bar: 2010-05-31 to 2026-07-28
`

## Thai Holidays
Date | Holiday Name
2025-12-05 | Father's Day
2025-12-10 | Constitution Day
2025-12-29 | New Year's Day
2025-12-30 | New Year's Day
2025-12-31 | New Year's Day
2026-01-01 | New Year's Day
2026-01-02 | New Year's Day
2026-02-12 | The Buddha Day
2026-04-06 | Kutkuri Dynasty Memorial Day
2026-04-13 | Songkran Festival
2026-04-14 | Songkran Festival
2026-04-15 | Songkran Festival
2026-04-16 | Songkran Festival
2026-04-17 | Songkran Festival
2026-05-01 | International Workers' Day
2026-05-04 | The anniversary of the King's accession to the throne
2026-06-01
2026-06-03
2026-07-28
2026-07-29
2026-08-12 | Mother's Day
2026-10-13 | The anniversary of the death of the 9th King
2026-10-23 | The anniversary of the death of the 5th King Father's Day
2026-12-07 | Father's Day
2026-12-31 | New Year's Day
2027-01-01 | New Year's Day
2027-01-02
2027-02-21 | The Buddha Day | 佛历节日，日期为预测
2027-02-22
2027-04-06 | Kutkuri Dynasty Memorial Day
2027-04-13 | Songkran Festival
2027-04-14 | Songkran Festival
2027-04-15 | Songkran Festival
2027-05-01 | International Workers' Day
2027-05-04 | The anniversary of the King's accession to the throne
2027-05-20 | Vesak Festival | 佛历节日，日期为预测
2027-06-03 | The Birthday Anniversary of the Queen
2027-08-12 | 母亲节
2027-10-13 | 九世王逝世纪念日
2027-10-23 | 五世王逝世纪念日
2027-10-25
2027-12-05 | 父亲节
2027-12-06
2027-12-10 | 宪法纪念日
2027-12-31 | 新年前夜
2028-01-01 | 新年元旦
2028-02-08 | 万佛节 | 佛历节日，日期为预测
2028-04-06 | 却克里王朝纪念日
2028-04-13 | 宋干节
2028-04-14 | 宋干节
2028-04-15 | 宋干节
2028-05-01 | 劳动节
2028-05-05 | 泰王登基纪念日
2028-06-08 | 卫塞节 | 佛历节日，日期为预测
2028-06-03 | 王后诞辰纪念日
2028-07-24 | 守夏节 | 佛历节日，日期为预测
2028-08-12 | 母亲节
2028-10-13 | 九世王逝世纪念日
2028-10-23 | 五世王逝世纪念日
2028-12-05 | 父亲节
2028-12-10 | 宪法纪念日
2028-12-31 | 新年前夜

## China Holidays
Date | Holiday Name
2026-01-01 | New Year's Day
2026-01-02 | New Year's Day
2026-01-03 | New Year's Day
2026-02-15 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2026-02-16 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2026-02-17 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2026-02-18 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2026-02-19 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2026-02-20 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2026-02-21 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2026-04-04 | Qingming Festival
2026-04-05 | Qingming Festival
2026-04-06 | Qingming Festival
2026-05-01 | International Workers' Day
2026-05-02 | International Workers' Day
2026-05-03 | International Workers' Day
2026-06-19 | Dragon Boat Festival
2026-06-20 | Dragon Boat Festival
2026-06-21 | Dragon Boat Festival
2026-09-25
2026-10-01 | National Day
2026-10-02 | National Day
2026-10-03 | National Day
2026-10-04 | National Day
2026-10-05 | National Day
2026-10-06 | National Day
2026-10-07 | National Day
2027-01-01 | New Year's Day
2027-01-02 | New Year's Day
2027-01-03 | New Year's Day
2027-02-06 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2027-02-07 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2027-02-08 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2027-02-09 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2027-02-10 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2027-02-11 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2027-02-12 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2027-04-03 | Qingming Festival
2027-04-04 | Qingming Festival
2027-04-05 | Qingming Festival
2027-05-01 | International Workers' Day
2027-05-02 | International Workers' Day
2027-05-03 | International Workers' Day
2027-06-11 | Dragon Boat Festival
2027-06-12 | Dragon Boat Festival
2027-06-13 | Dragon Boat Festival
2027-06-14 | Dragon Boat Festival
2027-09-15
2027-10-01 | National Day
2027-10-02 | National Day
2027-10-03 | National Day
2027-10-04 | National Day
2027-10-05 | National Day
2027-10-06 | National Day
2027-10-07 | National Day
2028-01-01 | New Year's Day
2028-01-02 | New Year's Day
2028-01-03 | New Year's Day
2028-01-25 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2028-01-26 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2028-01-27 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2028-01-28 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2028-01-29 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2028-01-30 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2028-01-31 | Spring Festival 元旦 元旦 春节 春节 春节 春节 春节 春节 春节 清明节 清明节 清明节 劳动节 劳动节 劳动节 端午节 端午节 端午节
2028-04-04 | Qingming Festival
2028-04-05 | Qingming Festival
2028-04-06 | Qingming Festival
2028-05-01 | International Workers' Day
2028-05-02 | International Workers' Day
2028-05-03 | International Workers' Day
2028-05-31 | Dragon Boat Festival
2028-06-01 | Dragon Boat Festival
2028-06-02 | Dragon Boat Festival
2028-10-01 | National Day
2028-10-02 | National Day
2028-10-03 | National Day
2028-10-04 | National Day
2028-10-05 | National Day
2028-10-06 | National Day
2028-10-07 | National Day