## PSR
PROVISION OF ENGINEERING, PROCUREMENT, CONSTRUCTION AND COMMISSIONING FOR WELLHEAD PLATFORMS, ASSOCIATED PIPLINES AND BROWNFIELD MODIFICATIONS FOR ZAWTIKA DEVELOPMENT PROJECT PHASE 1F
Procurement Plan
[10 empty] | LA | Most complexity RFQ |  |  |  | 1 | 10 | 0 | 0 | 10 | 17 | 10 |  | 9 | 2 | 5 | 20 | 10 | [15 empty] | 3 |  | 10 | 2
[10 empty] | LB | High complexity RFQ |  |  |  | 1 | 10 | 0 | 0 | 10 | 17 | 10 |  | 9 | 2 | 5 | 20 | 10 | [15 empty] | 3 |  | 10 | 2
[10 empty] | LC | Normal complexity RFQ |  |  |  | 1 | 10 | 0 | 0 | 10 | 13 | 10 |  | 9 | 2 | 5 | 15 | 10 | [15 empty] | 3 |  | 10 | 2
Contract no: MMC25-5001 | [9 empty] | LD | Low complexity RFQ |  |  |  | 1 | 10 | 0 | 0 | 5 | 7 | 10 |  | 5 | 2 | 5 | 10 | 10 | [14 empty] | Update:14-Aug-2026 | 2 |  | 5 | 2
No. | MR No. | RFQ No. | Package Name | Tag No. | Q'ty | CODE | DIS | LLI (Y/N) | CR | Priority Level | PO description | Owner | P/F/A | Bidder list Approval | MR Issued (IFR) | MR Approved | RFQ Issued | RFQ Approved | Bid Closing Date | TBE Issued | TBE Approved | LOA issued | PO Issued | Vendor Acknowledgement | KOM | VDB Submission | Approval of Key VP | Main Material Arrived | PIM | Start Production | FAT | Ready for Shipment | Receipt at WORKSITE | Punch List Clearance(all punch clearance before Tag Equipment Ready for Shipping ) | Approval of Final Documentation (To be confirmed later) | Delivery Duration (Weeks) | days | Delivery Date(1st Batch for ZWP21) | ROS Date | Float | Responder | Remarks | 2010-05-31 | 2010-06-30 | 2010-07-31 | 2010-08-31 | 2010-09-30 | 2010-10-31 | 2010-11-30 | 2010-12-31 | 2011-01-31 | 2011-02-28 | 2026-08-18
[13 empty] | Matrix | PTTEP | ENG | PTTEP | TJE PRC | PTTEP | TJE PRC | ENG | PTTEP | TJE PRC | TJE PRC | BIDDER | TJE PRC | Vendor | ENG | Vendor | TJE QA/QC | Vendor | TJE QA/QC | Vendor | THE Worksite | TJE QA/QC | TJE PRC |  |  | TJE PRC
[13 empty] | Holiday | China | Thai | Thai | China | Thai | China | Thai | Thai | China | China | China | China | China | Thai | [15 empty] | Thai |  | China | China
1 | MM-ZTK-1F-GEN-MEC-MR-0001 | RFQ-MA-001 | Offshore Pedestal Crane | CR7001 | 1*4 | 4-2 | MA | Y | L2 | LA | Favelle Favco | SH | P | 2026-04-21 | 2026-04-21 | 2026-04-24 | 2026-04-27 | 2026-05-06 | 2026-05-17 | 2026-06-11 | 2026-06-25 |  | 2026-07-08 | 2026-07-10 | 2026-07-17 | 2026-08-14 | 2026-08-28 | 2026-11-26 | 2026-12-01 | 2026-12-04 | 2027-04-24 | 2027-05-24 | 2027-06-23 | 2027-06-26 | 2027-07-23 | 50 | 350 | 2027-06-23 | 2027-06-29 | 394 | Sun liheng | 2026.4.16: Issued RFQ 2026.4.28-5.1: Received Bid 2026.5.7: TC 2026.5.19: Vendor will reply TC 2026.2.26-27 Hold TC meeting (ZWP21)1st Unit of Pedestal Adaptor = 42 Weeks after LOA (3-May-2027) (ZWP21)1st Unit of 100RL = 46 Weeks after LOA (31-May-2027) (ZWP23)2nd Unit of Pedestal Adaptor = 45 Weeks after LOA (24-May-2027) (ZWP23)2nd Unit of 100RL = 49 Weeks after LOA (21-Jun-2027) (ZWP22)3rd Unit of Pedestal Adaptor = 48 Weeks after LOA (14-Jun-2027) (ZWP22)3rd Unit of 100RL = 52 Weeks after LOA (12-Jul-2027) (ZWP20)4th Unit of Pedestal Adaptor = 51 Weeks after LOA (5-Jul-2027) (ZWP20)4th Unit of 100RL = 55 Weeks after LOA (2-Aug-2027) 2026.8.9 Expedite drawings by e-mail | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0001 | RFQ-MA-001 | Offshore Pedestal Crane |  |  | 4-2 | MA | Y | L2 | LA | ZM169-WP1-PO-MEC-001 | SH | F | [13 empty] | 2026-08-28 | 2026-11-26 | 2026-12-01 | 2026-12-04 | 2027-04-24 | 2026-05-24 | 2026-06-07 | 2027-06-26 | 2027-07-23 | 46 | 322 | 2026-05-31 |  |  | CIF Zhuhai Port |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0001 | RFQ-MA-001 | Offshore Pedestal Crane |  |  | 4-2 | MA | Y | L2 | LA |  | SH | A | 2026-04-08 | 2026-04-13 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 2026-05-01 | 2026-06-19 | 2026-07-13 | 2026-07-13 | 2026-07-17 | 2026-07-24 | 2026-07-17 | 2026-08-14 | [16 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2 | MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-1 | Closed Drain Sump Vessel | V-5001 | 1*4 | 4-10 | MA | Y | L3 | LA | Zhuhai Jutal | SH | P | 2026-05-25 | 2026-05-26 | 2026-06-04 | 2026-06-05 | 2026-06-12 | 2026-06-24 | 2026-06-24 | 2026-07-08 |  | 2026-07-15 | 2026-07-17 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2027-01-21 | 2027-02-05 | 2027-02-15 | 2027-02-18 | 2027-03-17 | 26 | 182 | 2027-02-15 | 2027-02-20 | 5 | HuangWei | 2026.5.6 Issued RFQ to Zhuhai yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-1 | Closed Drain Sump Vessel |  |  | 4-10 | MA | Y | L3 | LA | ZM169-WP1-PO-MEC-002 | SH | F | [13 empty] | 2026-08-25 | 2026-10-24 | 2026-10-26 | 2026-10-28 | 2027-01-30 | 2027-02-14 | 2027-02-15 | 2027-02-18 | 2027-03-17 |  |  | 2027-02-15 |  |  | DDP Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-1 | Closed Drain Sump Vessel |  |  | 4-10 | MA | Y | L3 | LA |  | SH | A |  | 2026-04-17 | 2026-05-01 | 2026-05-06 | 2026-05-06 | 2026-06-10 | 2026-06-27 | 2026-07-08 | N/A | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-08-10 | [16 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3 | MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-2 | Test Separator | V-1001 | 1*4 | 4-8 | MA | Y | L2 | LA | Zhuhai Jutal | SH | P | 2026-04-23 | 2026-04-24 | 2026-05-05 | 2026-05-06 | 2026-05-13 | 2026-06-24 | 2026-06-24 | 2026-07-08 |  | 2026-07-15 | 2026-07-17 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2027-02-11 | 2027-02-26 | 2027-03-03 | 2027-03-06 | 2027-04-02 | 33 | 231 | 2027-03-03 | 2027-03-20 | -9 | HuangWei | 2026.5.6 Issued RFQ to Zhuhai yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-2 | Test Separator |  |  | 4-8 | MA | Y | L2 | LA | ZM169-WP1-PO-MEC-002 | SH | F | [13 empty] | 2026-08-21 | 2026-12-04 | 2026-12-06 | 2026-12-08 | 2027-03-14 | 2027-03-29 | 2027-03-29 | 2027-03-06 | 2027-04-02 |  |  | 2027-03-29 |  |  | DDP Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-2 | Test Separator |  |  | 4-8 | MA | Y | L2 | LA |  | SH | A |  | 2026-04-17 | 2026-05-01 | 2026-05-06 | 2026-05-06 | 2026-06-10 | 2026-06-27 | 2026-07-08 | N/A | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-08-06 | [16 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4 | MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-3 | Instrument Gas Filter Coalescer | V-3001 | 1*4 | 4-11 | MA | Y | L2 | LA | Zhuhai Jutal | SH | P | 2026-06-04 | 2026-06-05 | 2026-06-12 | 2026-06-15 | 2026-06-22 | 2026-06-24 | 2026-06-24 | 2026-07-08 |  | 2026-07-15 | 2026-07-17 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2027-01-21 | 2027-02-05 | 2027-02-20 | 2027-02-23 | 2027-03-22 | 26 | 180 | 2027-02-20 | 2027-03-20 | 28 | HuangWei | 2026.5.6 Issued RFQ to Zhuhai yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-3 | Instrument Gas Filter Coalescer |  |  | 4-11 | MA | Y | L2 | LA | ZM169-WP1-PO-MEC-002 | SH | F | [12 empty] | 2026-08-21 | 2026-09-04 | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2027-01-21 | 2027-02-05 | 2027-02-20 | 2027-02-23 | 2027-03-22 |  |  | 2027-02-20 |  |  | DDP Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-3 | Instrument Gas Filter Coalescer |  |  | 4-11 | MA | Y | L2 | LA |  | SH | A |  | 2026-04-29 | 2026-05-01 | 2026-05-06 | 2026-05-06 | 2026-06-18 | 2026-06-27 | 2026-07-08 | N/A | 2026-07-14 | 2026-07-15 | 2026-07-17 | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5 | MM-ZTK-1F-GEN-MEC-MR-0003 | RFQ-MA-003 | Closed Drain Sump Pump skids |  | 1*4 | 4-18 | MA | Y | L3 | LA | Multipahse | SH | P | 2026-04-28 | 2026-04-29 | 2026-05-08 | 2026-05-11 | 2026-05-18 | 2026-05-26 | 2026-06-22 | 2026-07-06 |  | 2026-07-17 | 2026-07-21 | 2026-07-28 | 2026-08-25 | 2026-09-08 | 2026-12-07 | 2026-12-07 | 2026-12-10 | 2027-01-14 | 2027-01-29 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 32 | 224 | 2027-02-26 | 2027-03-30 | 12 | Sun liheng | 2026.5.6 Issued RFQ bid due day:22-May | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0003 | RFQ-MA-003 | Closed Drain Sump Pump skids |  |  | 4-18 | MA | Y | L3 | LA | ZM169-WP1-PO-MEC-003 | SH | F | [10 empty] | 2026-08-20 |  | 2026-08-25 | 2026-09-08 | 2026-12-07 | 2026-12-07 | 2026-12-10 | 2027-02-10 | 2027-02-25 | 2027-03-25 | 2027-03-01 | 2027-03-28 | 32 | 224 | 2027-03-18 |  |  | CIF Zhuhai Port |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0003 | RFQ-MA-003 | Closed Drain Sump Pump skids |  |  | 4-18 | MA | Y | L3 | LA |  | SH | A | 2026-04-21 | 2026-04-18 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 2026-05-22 | 2026-07-03 | 2026-07-17 | 2026-08-04 | 2026-08-11 |  | 2026-08-07 | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6 | MM-ZTK-1F-GEN-MEC-MR-0004 | RFQ-MA-004 | Chemical injection pump skids |  | 1*4 | 4-4 | MA | Y | L3 | LA | Multipahse | SH | P | 2026-04-28 | 2026-04-29 | 2026-05-08 | 2026-05-11 | 2026-05-18 | 2026-05-26 | 2026-06-22 | 2026-07-06 |  | 2026-07-17 | 2026-07-21 | 2026-07-28 | 2026-08-25 | 2026-09-08 | 2026-12-07 | 2026-12-07 | 2026-12-10 | 2027-02-06 | 2027-02-21 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 34 | 238 | 2027-03-12 | 2027-03-18 | 46268 | Sun liheng | 2026.5.6 Issued RFQ bid due day:22-May 2025.5.31-6.5 TC | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0004 | RFQ-MA-004 | Chemical injection pump skids |  |  | 4-4 | MA | Y | L3 | LA | ZM169-WP1-PO-MEC-003 | SH | F | [10 empty] | 2026-08-20 |  | 2026-08-25 | 2026-09-08 | 2026-12-07 | 2026-12-07 | 2026-12-10 | 1900-06-08 | 1900-06-23 | 1900-07-21 | 2027-03-15 | 2027-04-11 | 28 | 196 | 1900-07-14 |  |  | CIF Zhuhai Port |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0004 | RFQ-MA-004 | Chemical injection pump skids |  |  | 4-4 | MA | Y | L3 | LA |  | SH | A | 2026-04-21 | 2026-04-18 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 2026-05-22 | 2026-06-29 | 2026-08-07 | 2026-08-04 | 2026-08-11 |  | 2026-08-07 | [17 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7 | MM-ZTK-1F-GEN-MEC-MR-0005 | RFQ-MA-005 | Chemical storage tank |  | 2*4 | 4-39 | MA | Y | L3 | LA | Zhuhai Jutal | SH | P | 2026-05-11 | 2026-05-12 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-06-30 | 2026-06-30 | 2026-07-14 |  | 2026-07-27 | 2026-07-29 | 2026-08-05 | 2026-09-02 | 2026-09-16 | 2026-10-16 | 2026-10-19 | 2026-10-22 | 2026-12-31 | 2027-01-10 | 2027-01-11 | 2027-01-14 | 2027-02-10 | 24 | 168 | 2027-01-11 | 2027-02-15 | -4 | HuangWei | 2026.5.6 Issued RFQ to Zhuhai yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0005 | RFQ-MA-005 | Chemical storage tank |  |  | 4-39 | MA | Y | L3 | LA | ZM169-WP1-PO-MEC-005 | SH | F | [13 empty] | 2026-08-24 | 2026-10-16 | 2026-10-19 | 2026-10-22 | 2027-02-09 | 2027-02-19 | 2027-02-19 | 2027-01-14 | 2027-02-10 |  |  | 2027-02-19 |  |  | DDP Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0005 | RFQ-MA-005 | Chemical storage tank |  |  | 4-39 | MA | Y | L3 | LA |  | SH | A |  | 2026-04-21 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-06-08 | 2026-07-01 | 2026-07-08 | N/A | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-08-07 | [16 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8 | MM-ZTK-1F-GEN-MEC-MR-0006 | RFQ-MA-006 | Material Handling Equipment |  | 6*4 | 4-7 | MA | N | L4 | LC |  | SH | P | 2026-06-09 | 2026-06-09 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-30 | 2026-07-09 | 2026-07-23 |  | 2026-08-25 | 2026-08-27 | 2026-08-27 | 2026-09-10 | 2026-09-30 | 2026-10-30 | 2026-11-02 | 2026-11-05 | 2027-01-04 | 2027-01-19 | 2027-02-16 | 2027-02-19 | 2027-03-18 | 25 | 175 | 2027-02-16 | 2027-03-23 | 35 | Sun liheng |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | DDP : 24 weeks
| MM-ZTK-1F-GEN-MEC-MR-0006 | RFQ-MA-006 | Material Handling Equipment |  | 4 | 4-7 | MA | N | L4 | LC |  | SH | F | [8 empty] | 2026-08-21 | 2026-08-25 | 2026-08-27 | 2026-08-27 | 2026-09-10 | 2026-09-24 | 2026-10-24 | 2026-10-27 | 2026-10-30 | 2027-01-04 | 2027-01-19 | 2027-02-16 | 2027-02-19 | 2027-03-18 |  |  | 2027-02-16 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2 | DDP : 25 weeks
| MM-ZTK-1F-GEN-MEC-MR-0006 | RFQ-MA-006 | Material Handling Equipment |  |  | 4-7 | MA | N | L4 | LC |  | SH | A | 2026-06-19 | 2026-05-12 | 2026-05-28 | 2026-06-23 | 2026-06-23 | 2026-06-30 | 2026-07-17 | 2026-08-12 | [21 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9 | MM-ZTK-1F-GEN-SAF-MR-0001 | RFQ-SA-001 | Fire Fighting, Safety Equipment (Including Lifesaving) |  |  | 4-38 | SA | N | L3 | LD |  | SH | P | 2026-07-10 | 2026-06-28 | 2026-07-10 | 2026-09-18 | 2026-09-18 | 2026-09-25 | 2026-10-08 | 2026-10-23 |  | 2026-10-30 | 2026-11-03 | 2026-11-03 | 2026-11-17 | 2026-12-01 | 2027-01-30 | 2027-01-30 | 2027-02-02 | 2027-04-13 | 2027-04-28 | 2027-05-28 | 2027-05-31 | 2027-06-27 | 30 | 210 | 2027-05-28 | 2027-06-30 | 50 | Sun liheng |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-SAF-MR-0001 | RFQ-SA-001 | Fire Fighting, Safety Equipment (Including Lifesaving) |  |  | 4-38 | SA | N | L3 | LD |  | SH | F | [6 empty] | 2026-09-08 | 2026-09-22 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-30 | 2027-01-30 | 2027-02-02 | 2027-04-13 | 2027-04-28 | 2027-05-28 | 2027-05-31 | 2027-06-27 |  |  | 2027-05-11 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-SAF-MR-0001 | RFQ-SA-001 | Fire Fighting, Safety Equipment (Including Lifesaving) |  |  | 4-38 | SA | N | L3 | LD |  | SH | A | 2026-07-27 | 2026-06-10 | 2026-06-24 | 2026-07-28 | 2026-07-28 | 2026-08-14 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
10 | MM-ZTK-1F-GEN-SAF-MR-0002 | RFQ-SA-002 | Safety Signs |  |  | 4-38 | SA | N | L3 | LD |  | ZH | P | 2026-12-25 | 2026-12-25 | 2027-01-12 | 2027-01-12 | 2027-01-12 | 2027-01-19 | 2027-01-28 | 2027-02-11 |  | 2027-02-19 | 2027-02-23 | 2027-03-02 | 2027-03-16 | 2027-03-30 | 2027-04-14 | 2027-04-14 | 2027-04-16 | 2027-05-16 | 2027-05-18 | 2027-05-23 | 2027-05-26 | 2027-06-22 | 5 | 35 | 2027-05-23 | 2027-06-30 | 260 | Kuang Cuichang | 2026.6.10 Issued RFQ to Zhuhai yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-SAF-MR-0002 | RFQ-SA-002 | Safety Signs |  |  | 4-38 | SA | N | L3 | LD |  | ZH | F | [6 empty] | 2026-08-18 | 2026-09-01 |  | 2026-09-08 | 2026-09-10 | 2026-09-17 | 2026-10-09 | 2026-10-27 | 2026-11-11 | 2026-11-11 | 2026-11-13 | 2026-12-13 | 2026-12-15 | 2026-12-20 | 2027-05-26 | 2027-06-22 |  |  | 2026-10-13 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-SAF-MR-0002 | RFQ-SA-002 | Safety Signs |  |  | 4-38 | SA | N | L3 | LD |  | ZH | A | 2026-07-14 | 2026-06-01 | 2026-06-09 | 2026-07-27 | 2026-07-27 | 2026-08-06 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-001 | Ball Valve (Flange End) | 150#-148 | 355 | 4-19 | PI | N | L3 | LC | BOTELI | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-03-30 | 25 | Lin Yazhen |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-001 | Ball Valve (Flange End) | 600#-207 |  | 4-19 | PI | N | L3 | LC | ZM169-WP1-PO-PIP-001 | SH | F | [7 empty] | 2026-08-19 |  | 2026-08-21 | 2026-08-25 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-11-08 | 2026-11-11 | 2026-11-14 | 2027-02-11 | 2027-02-26 | 2027-03-05 | 2027-03-01 | 2027-03-28 |  |  | 2027-03-05 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-001 | Ball Valve (Flange End) |  |  | 4-19 | PI | N | L3 | LC |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-01 | 2026-06-01 | 2026-06-18 | C1:2026/7/16 C2:2026/8/14 | [22 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-021 | Ball Valve (Welded End) | 800#-521 | 649 | 4-19 | PI | N | L3 | LC | DHV | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-03-30 | 36 | Lin Yazhen |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-021 | Ball Valve (Welded End) | 2500#-128 |  | 4-19 | PI | N | L3 | LC | ZM169-WP1-PO-PIP-002 | SH | F | [9 empty] | 2026-08-21 | 2026-08-25 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-11-08 | 2026-11-11 | 2026-11-14 | 2027-01-31 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-28 | 22 | 154 | 2027-02-22 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-021 | Ball Valve (Welded End) |  |  | 4-19 | PI | N | L3 | LC | VALVITALIA,STARLINE | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-01 | 2026-06-01 | 2026-06-27 | C1:2026/7/16 C2:2026/8/14 | 2026-08-06 | 2026-08-14 | [20 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-002 | Globe Valve (without equal percentage) |  | 6*4 | 4-21 | PI | N | L3 | LC | DHV | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-03-30 | 25 | Liu Lei |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-002 | Globe Valve (without equal percentage) |  |  | 4-21 | PI | N | L3 | LC | ZM169-WP1-PO-PIP-002 | SH | F | [9 empty] | 2026-08-21 | 2026-08-25 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-11-08 | 2026-11-11 | 2026-11-14 | 2027-02-11 | 2027-02-26 | 2027-03-05 | 2027-03-01 | 2027-03-28 |  |  | 2027-03-05 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-002 | Globe Valve (without equal percentage) |  |  | 4-21 | PI | N | L3 | LC |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-05 | 2026-06-05 | 2026-06-25 | 2026-07-16 | 2026-08-11 | 2026-08-14 | [20 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-028 | Globe Valve (with equal percentage) |  | 5*4 | 4-21 | PI | N | L3 | LC | New package split from PIP-002 | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-03-30 | 25 | Lin Yazhen |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | 24 weeks after PO
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-028 | Globe Valve (withequal percentage) |  |  | 4-21 | PI | N | L3 | LC |  | SH | F | [8 empty] | 2026-08-19 | 2026-08-21 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2204-01-30 | 2204-02-29 | 2204-03-03 | 2204-03-06 | 2027-02-11 | 2027-02-26 | 2027-03-05 | 2027-03-01 | 2027-03-28 |  |  | 2027-03-05 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2 | 28 weeks after PO
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-028 | Globe Valve (withequal percentage) |  |  | 4-21 | PI | N | L3 | LC |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-05 | 2026-06-05 | 2026-06-25 | 2026-07-16 | 2026-08-11 | [21 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-003 | Check Valve (Swing) |  | 1*4 | 4-22 | PI | N | L3 | LC | Combined with Check Wafer | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-03-30 | 32 | Liu Lei |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-003 | Check Valve (Swing) |  |  | 4-22 | PI | N | L3 | LC |  | SH | F | [6 empty] | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 |  |  | 2027-02-26 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-003 | Check Valve (Swing) |  |  | 4-22 | PI | N | L3 | LC |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-29 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-029 | Check Valve (Position) |  | 1*4 | 4-22 | PI | N | L3 | LC | Combined with Check Wafer | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-03-30 | 32 | Liu Lei |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-029 | Check Valve (Position) |  |  | 4-22 | PI | N | L3 | LC |  | SH | F | [6 empty] | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 |  |  | 2027-02-26 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-029 | Check Valve (Position) |  |  | 4-22 | PI | N | L3 | LC |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-29 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
15 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-030 | Check Valve (Wafer) |  | 7*4 | 4-22 | PI | N | L3 | LC | BOTELI | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-03-30 | 36 | Liu Lei |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-030 | Check Valve (Wafer) |  |  | 4-22 | PI | N | L3 | LC | ZM169-WP1-PO-PIP-001 | SH | F | [9 empty] | 2026-08-21 | 2026-08-25 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-01-31 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-28 | 22 | 154 | 2027-02-22 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-030 | Check Valve (Wafer) |  |  | 4-22 | PI | N | L3 | LC |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-29 | 2026-07-16 | 2026-08-11 | 2026-08-14 | [20 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
16 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-004 | Check valve (Compact) |  | 16*4 | 4-41 | PI | N | L2 | LB | KCON | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-04 | 2026-06-18 | 2026-07-13 | 2026-07-27 |  | 2026-08-10 | 2026-08-12 | 2026-08-19 | 2026-09-16 | 2026-09-30 | 2026-10-30 | 2026-11-02 | 2026-11-05 | 2027-02-02 | 2027-02-17 | 2027-02-22 | 2027-02-25 | 2027-03-24 | 28 | 196 | 2027-02-22 | 2027-03-20 | 26 | Lin Yazhen |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-004 | Check valve (Compact) |  |  | 4-41 | PI | N | L2 | LB | ZM169-WP1-PO-PIP-004 | SH | F | [12 empty] | 2026-09-03 | 2026-09-17 | 2026-10-17 | 2026-10-20 | 2026-10-23 | 2027-02-07 | 2027-02-17 | 2027-02-22 | 2027-02-25 | 2027-03-24 | 28 | 196 | 2027-02-22 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-004 | Check valve (Compact) |  |  | 4-41 | PI | N | L2 | LB |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-01 | 2026-06-01 | 2026-06-15 | 2026-07-10 | 2026-08-07 | 2026-08-07 | 2026-08-14: 2026-08-10; 2026-08-18: 2026-08-12; 2026-08-25: 2026-08-06 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
17 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-020 | ButterflyValve |  | 1*4 | 4-22 | PI | N | L3 | LC | BOTELI | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-24 | 2026-07-31 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-03-30 | 67 | Liu Lei | 2026.6.8 Short bidder list to CPY for approval | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-020 | ButterflyValve |  |  | 4-22 | PI | N | L3 | LC | ZM169-WP1-PO-PIP-001 | SH | F | [9 empty] | 2026-08-21 | 2026-08-25 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-01-05 | 2027-01-15 | 2027-01-22 | 2027-03-01 | 2027-03-28 | 22 | 154 | 2027-01-22 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-020 | ButterflyValve |  |  | 4-22 | PI | N | L3 | LC | Combined with Globe valve | SH | A | 2026-06-10 | 2026-05-06 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-29 | 2026-07-16 | 2026-08-11 | 2026-08-14 | [20 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
18 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-006 | Special items-Chemical Injection Quill | SP-01B/C | 2*4 | 5-5 | PI | N | L3 | LA |  | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-24 | 2026-07-31 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-01-14 | 2027-01-24 | 2027-01-29 | 2027-02-01 | 2027-02-28 | 24 | 168 | 2027-01-29 | 2027-04-08 | 48 | Liu Lei |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | 22weeks DDP Zhuhai after after drawing approval
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-006 | Special items-Chemical Injection Quill | SP-02B/C | 2*4 | 5-5 | PI | N | L3 | LA |  | SH | F | [6 empty] | 2026-08-21 | 2026-09-04 |  | 2026-09-04 | 2026-09-08 | 2026-09-15 | 2026-10-21 | 2026-11-05 | 2026-11-28 | 2026-11-28 | 2026-12-01 | 2027-02-04 | 2027-02-14 | 2027-02-19 | 2027-02-01 | 2027-02-28 |  |  | 2027-02-19 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2 | 16 weeks from receipt of customer approval of drawings. DDP Zhuhai
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-006 | Special items-Chemical Injection Quill | SP-13A/B | 2*4 | 5-5 | PI | N | L3 | LA |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-24 | 2026-06-09 | 2026-06-12 | 2026-07-21 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder3 | 28 weeks DDP Zhuhai after after drawing approval
19 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-023 | Special items-Hoses and Connections | SP-41/42 | 2 | 5-5 | PI | N | L3 | LA |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2027-02-03 | 2027-02-23 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 24 | 168 | 2027-03-25 | 2027-04-08 | 48 | Liu Lei | 2026.6.10 Short bidder list to CPY for approval | [11 empty] | Bidder1
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-023 | Special items-Hoses and Connections | SP-43(Future) |  | 5-5 | PI | N | L3 | LA |  | SH | F | [6 empty] | 2026-08-21 | 2026-09-04 |  | 2026-09-04 | 2026-09-08 | 2026-09-15 | 2026-10-21 | 2026-11-05 | 2026-12-05 | 2026-12-05 | 2026-12-05 | 2026-12-31 | 2027-01-20 | 2027-02-19 | 2027-03-28 | 2027-04-24 |  |  | 2027-02-19 | [15 empty] | Bidder2 | 12 weeks DDP Zhuhai after after drawing approval
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-023 | Special items-Hoses and Connections |  |  | 5-5 | PI | N | L3 | LA |  | SH | A | 2026-06-11 | 2026-05-06 | 2026-05-24 | 2026-06-12 | 2026-06-12 | 2026-06-26 | [34 empty] | Bidder3 | 12 weeks DDP Zhuhai after after drawing approval
20 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-022 | Special items-Liquid trap | SP-70 | 1 | 5-5 | PI | N | L3 | LA |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2027-02-03 | 2027-02-23 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 24 | 168 | 2027-03-25 | 2027-04-08 | 48 | Liu Lei | [12 empty] | Bidder1
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-022 | Special items-Liquid trap | SP-71 | 1 | 5-5 | PI | N | L3 | LA |  | SH | F | [6 empty] | 2026-08-21 | 2026-09-04 |  | 2026-09-04 | 2026-09-08 | 2026-09-15 | 2026-10-21 | 2026-11-05 | 2026-12-05 | 2026-12-05 | 2026-12-05 | 2026-12-31 | 2027-01-20 | 2027-02-19 | 2027-03-28 | 2027-04-24 |  |  | 2027-02-19 | [15 empty] | Bidder2
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-022 | Special items-Liquid trap |  |  | 5-5 | PI | N | L3 | LA |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-24 | 2026-06-10 | 2026-06-10 | 2026-06-26 | [34 empty] | Bidder3 | 10 weeks weeks DDP Zhuhai after after drawing approval
21 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-032 | Special items-Clamp Type Connector and Target Tee with Clamp Type Connector | SP-*A002/A001 | 32+32 | 5-5 | PI | N | L3 | LA |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2027-02-03 | 2027-02-23 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 24 | 168 | 2027-03-25 | 2027-04-08 | 48 | Liu Lei | 2026.6.10 Short bidder list to CPY for approval | [11 empty] | Bidder1 | 36 weeks DDP Zhuhai after after drawing approval
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-032 | Special items-Clamp Type Connector and Target Tee with Clamp Type Connector | SP-*A003/004 | 32+32 | 5-5 | PI | N | L3 | LA |  | SH | F | [6 empty] | 2026-08-21 | 2026-09-04 |  | 2026-09-04 | 2026-09-08 | 2026-09-15 | 2026-10-21 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-12-31 | 2027-01-20 | 2027-02-19 | 2027-03-28 | 2027-04-24 |  |  | 2027-02-19 | [15 empty] | Bidder2
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-032 | Special items-Clamp Type Connector and Target Tee with Clamp Type Connector |  |  | 5-5 | PI | N | L3 | LA |  | SH | A | 2026-06-11 | 2026-05-06 | 2026-05-24 | 2026-06-12 | 2026-06-12 | 2026-07-21 | [34 empty] | Bidder3
22 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-031 | Special items-Corrosion Probe & Coupon | SP-21/31/32 | 4+1+2 | 5-5 | PI | N | L3 | LA | Combine with chemical Injection quill | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2027-02-03 | 2027-02-23 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 24 | 168 | 2027-03-25 | 2027-04-08 | 48 | Liu Lei
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-031 | Special items-Corrosion Probe & Coupon | SP-31(Future) |  | 5-5 | PI | N | L3 | LA |  | SH | F | [6 empty] | 2026-08-21 | 2026-09-04 |  | 2026-09-04 | 2026-09-08 | 2026-09-15 | 2026-10-21 | 2026-11-05 | 2026-12-05 | 2026-12-05 | 2026-12-07 | 2026-12-31 | 2027-01-20 | 2027-02-19 | 2027-03-28 | 2027-04-24 |  |  | 2027-02-19
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-031 | Special items-Corrosion Probe & Coupon |  |  | 5-5 | PI | N | L3 | LA |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-24 | 2026-06-12 | 2026-06-12 | 2026-07-22
23 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-024 | Special items-Portable Valve Actuator |  | 2 | 5-5 | PI | N | L3 | LA |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-09-21 | 2026-09-28 |  | 2026-10-12 | 2026-10-16 | 2026-10-23 | 2026-11-20 | 2026-12-04 | 2027-01-03 | 2027-01-03 | 2027-01-05 | 2027-04-04 | 2027-04-24 | 2027-05-24 | 2027-05-27 | 2027-06-23 | 24 | 168 | 2027-03-25 | 2027-06-30 | 93 | Liu Lei
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-024 | Special items-Portable Valve Actuator |  |  | 5-5 | PI | N | L3 | LA |  | SH | F | [5 empty] | 2026-08-24 | 2026-09-21 | 2026-09-28 |  | 2026-10-12 | 2026-10-16 | 2026-10-23 | 2026-11-20 | 2026-12-04 | 2027-01-03 | 2027-01-03 | 2027-01-05 | 2027-04-04 | 2027-04-24 | 2027-05-24 | 2027-05-27 | 2027-06-23 |  |  | 2027-03-29
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-024 | Special items-Portable Valve Actuator |  |  | 5-5 | PI | N | L3 | LA |  | SH | A | 2026-08-17 | 2026-05-06 | 2026-05-24 | 2026-08-17 | 2026-08-17
24 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-019 | Special items-Strainers | SP-50 | 1 | 5-5 | PI | N | L3 | LA |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2027-02-03 | 2027-02-23 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 32 | 224 | 2027-03-25 | 2027-04-08 | -7 | Liu Lei | [12 empty] | Bidder1 | 14 weeks weeks EX WORK
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-019 | Special items-Strainers | SP-11 | 1 | 5-5 | PI | N | L3 | LA |  | SH | F | [6 empty] | 2026-08-21 | 2026-08-21 |  | 2026-09-03 | 2026-09-07 | 2026-09-14 | 2026-10-20 | 2026-11-04 | 2026-12-04 | 2026-12-04 | 2026-12-06 | 2027-02-24 | 2027-03-16 | 2027-04-15 | 2027-03-28 | 2027-04-24 |  |  | 2027-04-15 | [15 empty] | Bidder2
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-019 | Special items-Strainers |  |  | 5-5 | PI | N | L3 | LA |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-24 | 2026-06-10 | 2026-06-10 | 2026-07-22 | [34 empty] | Bidder3 | 14 weeks weeks CIF Zhuhai after after PO
25 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barred Tees | SP-05/06 | 2 | 5-5 | PI | N | L3 | LA |  | SH | P | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-05 | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 28 | 196 | 2027-04-27 | 2027-05-08 | 11 | Liu Lei | 2026.6.8 Short bidder list to CPY for approval | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | 24 weeks FCA from approval of manufacturing drawing and procedures (Summer / Christmas shutdown excluded)
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barred Tees | SP-07/08 | 2 | 5-5 | PI | N | L3 | LA |  | SH | F | [6 empty] | 2026-09-16 | 2026-09-30 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-13 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 |  |  | 2027-04-27 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2 | 12/14 WORKING WEEKS FROM PIM DATE.(Working weeks means by excluding 2 weeks of August and 2 weeks of Christmas shut-down)
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barred Tees | SP-09 | 1 | 5-5 | PI | N | L3 | LA |  | SH | A | 2026-06-11 | 2026-05-06 | 2026-05-24 | 2026-06-11 | 2026-06-11 | 2026-06-22 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder3 | EXW Italy 24-32 weeks after PO
26 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barrel Reducer (For PIG L&R) | SP-12 | 4 | 5-5 | PI | N | L3 | LA | Combine with Barred tee | SH | P | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-05 | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 28 | 196 | 2027-04-27 | 2027-05-08 | 11 | Liu Lei |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | 24 weeks FCA from approval of manufacturing drawing and procedures (Summer / Christmas shutdown excluded)
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barrel Reducer (For PIG L&R) | SP-13 | 1 | 5-5 | PI | N | L3 | LA |  | SH | F | [6 empty] | 2026-09-16 | 2026-09-30 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-13 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 |  |  | 2027-04-27 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2 | 12/14 WORKING WEEKS FROM PIM DATE.(Working weeks means by excluding 2 weeks of August and 2 weeks of Christmas shut-down)
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barrel Reducer (For PIG L&R) | SP-14 | 2 | 5-5 | PI | N | L3 | LA |  | SH | A | 2026-06-11 | 2026-05-06 | 2026-05-24 | 2026-06-11 | 2026-06-11 | 2026-06-22 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder3 | EXW Italy 24-32 weeks after PO
27 | MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-026 | PIPELINE BULK (B31.8)-3D Bend | Export line | 24 | 5-5 | PI | N | L2 | LA |  | SH | P | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-05 | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 28 | 196 | 2027-04-27 | 2027-05-08 | 11 | Liu Lei |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | Delivery time FCA Italy : 24-30 weeks, from approval of manufacturing drawing and procedures |  | (Summer / Christmas shutdown excluded)
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-026 | PIPELINE BULK (B31.8)-3D Bend | Import line | 18 | 5-5 | PI | N | L2 | LA |  | SH | F | [5 empty] | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 |  |  | 2027-04-27 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-026 | PIPELINE BULK (B31.8)-3D Bend |  |  | 5-5 | PI | N | L2 | LA |  | SH | A | 2026-07-28 | 2026-07-14 | 2026-07-28 | 2026-07-28 | 2026-07-28 | [24 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder3 | FCA SIMAS workshop, 42-44 working weeks after PO receipt and documents approval
28 | MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Flanges |  |  | 5-5 | PI | N | L2 | LA |  | ZH | P | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-05 | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 28 | 196 | 2027-04-27 | 2027-05-08 | 26 | Kuang Yuanna
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Flanges |  |  | 5-5 | PI | N | L2 | LA |  | ZH | F | [5 empty] | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 |  |  | 2027-04-27
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Flanges |  |  | 5-5 | PI | N | L2 | LA |  | ZH | A | 2026-08-16 | 2026-07-14 | 2026-07-28 | 2026-08-16 | 2026-08-16
29 | MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Pipes (include material B31.3 for PIG L&R) |  |  | 5-5 | PI | N | L2 | LA | B31.8 only more than 70m, so no vendor submit bid | ZH | P | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-05 | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 28 | 196 | 2027-04-27 | 2027-05-08 | 26 | Wei Chuanfang
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Pipes (include material B31.3 for PIG L&R) |  |  | 5-5 | PI | N | L2 | LA |  | ZH | F | [5 empty] | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 |  |  | 2027-04-27
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Pipes (include material B31.3 for PIG L&R) |  |  | 5-5 | PI | N | L2 | LA |  | ZH | A | 2026-08-16 | 2026-07-14 | 2026-07-28 | 2026-08-16 | 2026-08-16 | No vendor reply
|  | RFQ-PIP-007 | SPECIAL PIPE SUPPORT |  |  | 5-5 | PI | N | L4 | LC | As dicussed with ENG, it mabe has no special support. So it will confirm later | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-24 | 2026-07-31 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-10-29 | 2026-11-01 | 2027-01-12 | 2027-01-22 | 2027-01-29 | 2027-02-01 | 2027-02-28 | 24 | 168 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | RFQ-PIP-007 | SPECIAL PIPE SUPPORT |  |  | 5-5 | PI | N | L4 | LC |  | SH | F | 2026-06-20 | 2026-06-10 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-07-01 | 2026-07-10 | 2026-07-24 |  | 2026-07-31 | 2026-08-04 | 2026-08-11 | 2026-08-26 | 2026-09-09 | 2026-10-09 | 2026-10-09 | 2026-10-12 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | RFQ-PIP-007 | SPECIAL PIPE SUPPORT |  |  | 5-5 | PI | N | L4 | LC |  | SH | A | [29 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
30 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-008 | CS Fitting |  |  | 5-5 | PI | N | L3 | LD |  | ZH | P | 2026-06-16 | 2026-06-19 | 2026-06-26 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 2026-07-20 | 2026-07-22 |  | 2026-07-29 | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-09-04 | 2026-09-11 | 2026-09-11 | 2026-09-13 | 2026-10-17 | 2026-10-22 | 2026-10-27 | 2026-10-30 | 2026-11-26 | 12.8571 | 90 | 2026-10-27 | 2026-12-08 | 20 | Kuang Yuanna |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-008 | CS Fitting |  |  | 5-5 | PI | N | L3 | LD |  | ZH | F | [9 empty] | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-14 | 2026-09-28 | 2026-10-05 | 2026-10-05 | 2026-10-07 | 2026-11-08 | 2026-11-13 | 2026-11-18 | 2026-10-30 | 2026-11-26 |  |  | 2026-11-18 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-008 | CS Fitting |  |  | 5-5 | PI | N | L3 | LD |  | ZH | A | 2026-06-11 | 2026-05-06 | 2026-05-23 | 2026-06-11 | 2026-06-11 | 2026-07-10 | 2026-07-27 | 2026-08-12 | Waiting for TBE APPR | [20 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 2026-10-13 to 2027-05-27
31 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-009 | SS & DSS Fitting |  |  | 5-5 | PI | N | L2 | LC |  | ZH | P | 2026-05-26 | 2026-05-29 | 2026-06-09 | 2026-06-10 | 2026-06-17 | 2026-07-02 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-14 | 2026-09-28 | 2026-10-28 | 2026-10-28 | 2026-10-30 | 2026-12-24 | 2026-12-29 | 2027-01-28 | 2027-01-31 | 2027-02-27 | 24 | 168 | 2027-01-28 | 2027-02-08 | 4 | Kuang Yuanna | 2026.5.31 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-009 | SS & DSS Fitting |  |  | 5-5 | PI | N | L2 | LC |  | ZH | F | [9 empty] | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2026-12-31 | 2027-01-05 | 2027-02-04 | 2027-01-31 | 2027-02-27 |  |  | 2027-02-04 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-009 | SS & DSS Fitting |  |  | 5-5 | PI | N | L2 | LC |  | ZH | A | 2026-06-11 | 2026-05-06 | 2026-05-23 | 2026-06-11 | 2026-06-11 | 2026-07-11 | 2026-07-27 | 2026-08-11 | Waiting for TBE APPR | [20 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 2026-10-13 to 2027-05-27
32 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-010 | CS Flange |  |  | 5-5 | PI | N | L3 | LD |  | ZH | P | 2026-08-20 | 2026-08-25 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-14 | 2026-09-23 | 2026-09-25 |  | 2026-10-09 | 2026-10-13 | 2026-10-20 | 2026-11-03 | 2026-11-17 | 2026-11-27 | 2026-11-27 | 2026-11-29 | 2026-12-29 | 2027-01-03 | 2027-01-07 | 2027-01-10 | 2027-02-06 | 12.8571 | 90 | 2027-01-07 | 2027-01-23 | 66 | Kuang Yuanna |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-010 | CS Flange |  |  | 5-5 | PI | N | L3 | LD |  | ZH | F | [9 empty] | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-14 | 2026-09-28 | 2026-10-08 | 2026-10-08 | 2026-10-10 | 2026-11-09 | 2026-11-14 | 2026-11-18 | 2027-01-10 | 2027-02-06 |  |  | 2026-11-18 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-010 | CS Flange |  |  | 5-5 | PI | N | L3 | LD |  | ZH | A | 2026-06-11 | 2026-05-06 | 2026-05-23 | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-27 | 2026-08-12 | Waiting for TBE APPR | [20 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 2026-08-20 to 2027-02-06
33 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-011 | SS & DSS Flange |  |  | 5-5 | PI | N | L2 | LC |  | ZH | P | 2026-06-18 | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-09 | 2026-07-23 | 2026-08-18 | 2026-08-21 |  | 2026-09-04 | 2026-09-08 | 2026-09-15 | 2026-10-14 | 2026-10-29 | 2026-11-28 | 2026-11-28 | 2026-11-30 | 2026-11-29 09:36 | 2026-12-04 09:36 | 2027-01-03 09:36 | 2027-01-06 09:36 | 2027-02-02 09:36 | 17.2 | 120.4 | 2027-01-03 09:36 | 2027-02-08 | 50.6 | Kuang Yuanna | 2026.5.31 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-011 | SS & DSS Flange |  |  | 5-5 | PI | N | L2 | LC |  | ZH | F | [9 empty] | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2026-11-14 09:36 | 2026-11-19 09:36 | 2026-12-19 09:36 | 2027-01-06 09:36 | 2027-02-02 09:36 |  |  | 2026-12-19 09:36 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-011 | SS & DSS Flange |  |  | 5-5 | PI | N | L2 | LC |  | ZH | A | 2026-06-11 | 2026-05-06 | 2026-05-23 | 2026-06-11 | 2026-06-11 | 2026-06-26 | 2026-07-17 | 2026-08-12 | Waiting for TBE APPR | [20 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 2026-08-20 to 2027-02-02 09:36
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-012 | SAW Welded Pipe (include material B31.8 for PIG L&R) |  |  | 5-5 | PI | N | L3 | LD | Merge with CS pipes | ZH | P | 2026-06-26 | 2026-07-01 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-21 | 2026-08-03 | 2026-08-05 |  | 2026-08-12 | 2026-08-14 | 2026-08-21 | 2026-09-04 | 2026-09-18 | 2026-09-28 | 2026-09-28 | 2026-09-30 | 2026-10-29 | 2026-11-03 | 2026-11-10 | 2026-11-13 | 2026-12-10 | 12.8571 | 90 | 2026-11-10 | 2026-12-08 | 22 |  | To apply for changing to seamless pipes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-012 | SAW Welded Pipe (include material B31.8 for PIG L&R) |  |  | 5-5 | PI | N | L3 | LD |  | ZH | F | [5 empty] | 2026-08-20 | 2026-08-03 | 2026-08-18 |  | 2026-08-18 | 2026-08-20 | 2026-08-27 | 2026-09-10 | 2026-09-24 | 2026-10-04 | 2026-10-04 | 2026-10-06 | 2026-11-04 | 2026-11-09 | 2026-11-16 | 2026-11-13 | 2026-12-10 |  |  | 2026-11-16 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-012 | SAW Welded Pipe (include material B31.8 for PIG L&R) |  |  | 5-5 | PI | N | L3 | LD |  | ZH | A | 2026-06-12 | 2026-05-06 | 2026-05-23 | 2026-06-24 | 2026-06-24 | [24 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
34 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-013 | CS Pipe |  |  | 5-5 | PI | N | L3 | LD | include SAW Welded Pipe and seamless pipe | ZH | P | 2026-06-16 | 2026-06-19 | 2026-06-26 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 2026-07-20 | 2026-07-22 |  | 2026-07-29 | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-09-04 | 2026-09-14 | 2026-09-14 | 2026-09-16 | 2026-10-18 | 2026-10-23 | 2026-10-27 | 2026-10-30 | 2026-11-26 | 12.8571 | 90 | 2026-10-27 | 2026-11-21 | 4 | Wei Chuanfang |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-013 | CS Pipe |  |  | 5-5 | PI | N | L3 | LD |  | ZH | F | [7 empty] | 2026-08-19 |  | 2026-08-19 | 2026-08-21 | 2026-08-28 | 2026-09-11 | 2026-09-25 | 2026-10-05 | 2026-10-05 | 2026-10-07 | 2026-11-08 | 2026-11-13 | 2026-11-17 | 2026-10-30 | 2026-11-26 |  |  | 2026-11-17 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-013 | CS Pipe |  |  | 5-5 | PI | N | L3 | LD |  | ZH | A | 2026-06-12 | 2026-05-06 | 2026-05-23 | 2026-06-24 | 2026-06-24 | 2026-07-09 | C1:2026/7/27 C2:2026/8/17 | [22 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
35 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-014 | DSS Pipes and Seamless SS pipes |  |  | 5-5 | PI | N | L3 | LC |  | ZH | P | 2026-05-26 | 2026-05-29 | 2026-06-09 | 2026-06-10 | 2026-06-17 | 2026-07-02 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-14 | 2026-09-28 | 2026-10-28 | 2026-10-28 | 2026-10-30 | 2026-12-24 | 2026-12-29 | 2027-01-28 | 2027-01-31 | 2027-02-27 | 24 | 168 | 2027-01-28 | 2027-02-08 | -8 | Wei Chuanfang | 2026.5.31 MR issued yard 2026.8.9 Domestic sullier cannot meet hot drawn requirement.Sourcing other vendors. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-014 | DSS Pipes and Seamless SS pipes |  |  | 5-5 | PI | N | L3 | LC |  | ZH | F | [6 empty] | 2026-08-18 | 2026-09-01 |  | 2026-09-01 | 2026-09-03 | 2026-09-10 | 2026-10-09 | 2026-10-27 | 2026-11-26 | 2026-11-26 | 2026-11-28 | 2027-01-12 | 2027-01-17 | 2027-02-16 | 2027-01-31 | 2027-02-27 |  |  | 2027-02-16 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-014 | DSS Pipes and Seamless SS pipes |  |  | 5-5 | PI | N | L3 | LC |  | ZH | A | 2026-06-11 | 2026-05-06 | 2026-05-23 | 2026-06-12 | 2026-06-12 | 2026-07-06 | wait for TBE update | [22 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-015 | Seamless SS pipes |  |  | 5-5 | PI | N | L3 | LD | merged with DSS pipes | ZH | P | 2026-06-26 | 2026-07-01 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-21 | 2026-08-03 | 2026-08-05 |  | 2026-08-12 | 2026-08-14 | 2026-08-21 | 2026-09-04 | 2026-09-18 | 2026-10-08 | 2026-10-08 | 2026-10-10 | 2026-10-31 | 2026-11-05 | 2026-11-10 | 2026-11-13 | 2026-12-10 | 12.8571 | 90 | 2026-11-10 | 2026-12-08 | 22 |  | 2026.5.31 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-015 | Seamless SS pipes |  |  | 5-5 | PI | N | L3 | LD |  | ZH | F | [6 empty] | 2026-08-03 | 2026-08-18 |  | 2026-08-18 | 2026-08-20 | 2026-08-27 | 2026-09-10 | 2026-09-24 | 2026-10-14 | 2026-10-14 | 2026-10-16 | 2026-11-06 | 2026-11-11 | 2026-11-16 | 2026-11-13 | 2026-12-10 |  |  | 2026-11-16 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-015 | Seamless SS pipes |  |  | 5-5 | PI | N | L3 | LD |  | ZH | A | 2026-06-12 | 2026-05-06 | 2026-05-23 | 2026-06-18 | 2026-06-18 | 2026-06-26 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
36 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-034 | UPVC Pipes, Fitting and Flanges |  |  | 5-5 | PI | N | L3 | LC |  | ZH | P | 2026-07-28 | 2026-05-29 | 2026-06-09 | 2026-07-30 | 2026-07-29 | 2026-08-04 | 2026-08-24 | 2026-09-07 |  | 2026-09-18 | 2026-09-22 | 2026-09-30 | 2026-10-28 | 2026-11-11 | 2026-12-11 | 2026-12-11 | 2026-12-13 | 2026-11-12 | 2026-11-17 | 2026-12-17 | 2027-01-31 | 2027-02-27 | 12.8571 | 90 | 2027-01-28 | 2027-02-08 | 53 | Wei Chuanfang | 2026.7.17 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-034 | UPVC Pipes, Fitting and Flanges |  |  | 5-5 | PI | N | L3 | LC |  | ZH | F | [6 empty] | 2026-08-28 | 2026-09-11 |  | 2026-09-18 | 2026-09-22 | 2026-09-30 | 2026-10-28 | 2026-11-11 | 2026-12-11 | 2026-12-11 | 2026-12-13 | 2026-11-12 | 2026-11-17 | 2026-12-17 | 2027-01-31 | 2027-02-27 |  |  | 2026-12-17 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-034 | UPVC Pipes, Fitting and Flanges |  |  | 5-5 | PI | N | L3 | LC |  | ZH | A | 2026-06-12 | 2026-05-06 | 2026-05-23 | 2026-07-19 | 2026-07-19 | 2026-08-10 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-SPE-0002 | RFQ-PIP-018-1 | Pig launcher and receiver | SP-22 | 1*4 | 4-6 | PI | N | L2 | LA | no separate procurement item for the Pig Launcher and Receiver. The Pig Launcher/Receiver will be procured as individual components, including loose piping (RFQ-PIP-013), pipeline (Saw Welded Pipe, RFQ-PIP-012), Quick Opening Closure (RFQ-PIP-018), and barrel reducers. | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-09 | 2026-11-12 | 2026-11-15 | 2027-02-23 | 2027-03-10 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 32 | 224 | 2027-03-25 | 2027-04-23 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-SPE-0002 | RFQ-PIP-018-1 | Pig launcher and receiver | SP-23 (ZWP20,23) | 2 | 4-6 | PI | N | L2 | LA |  | SH | F | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-09 | 2026-11-12 | 2026-11-15 | 2027-02-28 | 2027-03-15 | 2027-03-30 | 2027-03-28 | 2027-04-24 |  |  | 2027-03-30 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-SPE-0002 | RFQ-PIP-018-1 | Pig launcher and receiver | SP-24 (ZWP-21,22) | 2 | 4-6 | PI | N | L2 | LA |  | SH | A | [29 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
37 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-018-2 | Special irems-Quick Opening Closure (For PIG L&R) | SP-22 | 1*4 | 4-6 | PI | N | L2 | LA | G.D.ENGINEERING | ZH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-09 | 2026-11-12 | 2026-11-15 | 2027-02-23 | 2027-03-10 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 32 | 224 | 2027-03-25 | 2027-04-23 | 22 | Zahng Xiaorui | 2026.6.9 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-018-2 | Special irems-Quick Opening Closure (For PIG L&R) | SP-23 (ZWP20,23) | 2 | 4-6 | PI | N | L2 | LA |  | ZH | F | [9 empty] | 2026-08-20 | 2026-08-24 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-07 | 2026-11-10 | 2027-03-02 | 2027-03-17 | 2027-04-01 | 2027-03-28 | 2027-04-24 |  |  | 2027-04-01 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-018-2 | Special irems-Quick Opening Closure (For PIG L&R) | SP-24 (ZWP-21,22) | 2 | 4-6 | PI | N | L2 | LA |  | ZH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-10 | 2026-06-10 | 2026-06-25 | C1:2026/7/25 C2:2026/8/17 | 2026-08-11 | 2026-08-11 | 2026-08-20: Waiting for TBE APPR | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
38 |  | RFQ-PIP-027 | Coating |  |  | 5-4 | PI | N | L4 | LD |  | ZH | P | 2026-07-21 | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-13 | 2026-08-27 |  | 2026-09-04 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-15 |  |  |  |  | 2026-10-25 | 2026-10-30 | 2026-11-02 | 2026-11-29 | 8 | 56 | 2026-10-30 | 2026-11-16 | 17 | Zheng Hanliang
|  | RFQ-PIP-027 | Coating |  |  | 5-4 | PI | N | L4 | LD |  | ZH | F | [5 empty] | 2026-08-20 | 2026-08-31 | 2026-09-14 |  | 2026-09-21 | 2026-09-23 | 2026-10-08 | 2026-10-22 | 2026-11-06 |  |  |  |  | 2026-10-25 | 2026-10-30 | 2026-11-02 | 2026-11-29 |  |  | 2026-10-30
|  | RFQ-PIP-027 | Coating |  |  | 5-4 | PI | N | L4 | LD |  | ZH | A | 2026-07-14 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27
39 | MM-ZTK-1F-GEN-ELE-MR-0001 | RFQ-EL-001 | Solar Power System | SP-440ABCD | 4 | 4-26 | EL | N | L3 | LA | Swift | SH | P | 2026-04-24 | 2026-04-27 | 2026-05-06 | 2026-05-07 | 2026-05-14 | 2026-05-28 | 2026-06-29 | 2026-07-02 |  | 2026-07-16 | 2026-07-20 | 2026-07-27 | 2026-08-24 | 2026-09-07 | 2026-09-27 | 2026-09-27 | 2026-09-30 | 2027-02-28 | 2027-03-15 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 36 | 252 | 2027-03-25 | 2027-04-15 | 46268 | Liu Lei | 2026.4.30 Issued RFQ bid due day:22-May | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | Ex-work 26 weeks
| MM-ZTK-1F-GEN-ELE-MR-0001 | RFQ-EL-001 | Solar Power System | VR-440 | 4 | 4-26 | EL | N | L3 | LA | ZM169-WP1-PO-ELE-001 | SH | F | [10 empty] | 2026-08-20 |  | 2026-08-24 | 2026-09-07 | 2026-09-27 | 2026-09-27 | 2026-09-30 | 1900-07-12 | 1900-08-01 | 1900-08-11 | 2027-03-28 | 2027-04-24 | 32 | 224 | 1900-08-11 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2 | DDP 34-36 weeks
| MM-ZTK-1F-GEN-ELE-MR-0001 | RFQ-EL-001 | Solar Power System | BAT-440ABC | 12 | 4-26 | EL | N | L3 | LA |  | SH | A | 2026-04-21 | 2026-04-24 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-22 | 2026-07-02 | 2026-07-04 | 2026-07-24 | 2026-08-20: 2026-08-07; 2026-08-31: 2026-07-30 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder3 | Ex-work 28 weeks
40 | MM-ZTK-1F-GEN-ELE-MR-0002 | RFQ-EL-002 | DC Distribution Boards | ACDB-440 | 4 |  | EL | Y | L3 | LB | Swift | SH | P | 2026-04-24 | 2026-04-27 | 2026-05-06 | 2026-05-07 | 2026-05-14 | 2026-05-28 | 2026-06-29 | 2026-07-02 |  | 2026-07-16 | 2026-07-20 | 2026-07-27 | 2026-08-24 | 2026-09-07 | 2026-09-27 | 2026-09-27 | 2026-09-30 | 2027-03-23 | 2027-04-12 | 2027-04-22 | 2027-04-25 | 2027-05-22 | 40 | 280 | 2027-04-16 | 2027-04-21 | 46274 | Liu Lei | 2026.4.30 Issued RFQ bid due day:22-May | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | 34 to 36 weeks after drawing approval DDP
| MM-ZTK-1F-GEN-ELE-MR-0002 | RFQ-EL-002 | DC Distribution Boards | ACDB-420 | 4 |  | EL | Y | L3 | LB | ZM169-WP1-PO-ELE-001 | SH | F | [10 empty] | 2026-08-20 |  | 2026-08-24 | 2026-09-07 | 2026-09-27 | 2026-09-27 | 2026-09-30 | 1900-07-12 | 1900-08-01 | 1900-08-11 | 2027-04-19 | 2027-05-16 | 32 | 224 | 1900-08-11 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2 | DDP 28 weeks( after drawing) with Code 2 within 2 weeks.
| MM-ZTK-1F-GEN-ELE-MR-0002 | RFQ-EL-002 | DC Distribution Boards |  |  |  | EL | Y | L3 | LB |  | SH | A | 2026-04-21 | 2026-04-28 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-22 | 2026-07-07 | 2026-07-08 | 2026-07-24 | 2026-08-20: 2026-08-07; 2026-08-31: 2026-07-30 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder3 | 32 weeks after drawing approval DDP
41 | MM-ZTK-1F-GEN-ELE-MR-0003 | RFQ-EL-003 | AC Distribution Boards | ACDB-410 | 4 | 4-24 | EL | Y | L3 | LB | Swift | SH | P | 2026-04-24 | 2026-04-27 | 2026-05-06 | 2026-05-07 | 2026-05-14 | 2026-05-28 | 2026-06-29 | 2026-07-02 |  | 2026-07-16 | 2026-07-20 | 2026-07-27 | 2026-08-24 | 2026-09-07 | 2026-09-27 | 2026-09-27 | 2026-09-30 | 2027-03-23 | 2027-04-12 | 2027-04-22 | 2027-04-25 | 2027-05-22 | 40 | 280 | 2027-04-16 | 2027-04-21 | 46274 | Liu Lei | 2026.4.30 Issued RFQ bid due day:22-May | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | 34 to 36 weeks after drawing approval DDP
| MM-ZTK-1F-GEN-ELE-MR-0003 | RFQ-EL-003 | AC Distribution Boards |  |  | 4-24 | EL | Y | L3 | LB | ZM169-WP1-PO-ELE-001 | SH | F | [10 empty] | 2026-08-20 |  | 2026-08-24 | 2026-09-07 | 2026-09-27 | 2026-09-27 | 2026-09-30 | 1900-07-12 | 1900-08-01 | 1900-08-11 | 2027-04-19 | 2027-05-16 | 32 | 224 | 1900-08-11 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2 | DDP 28 weeks( after drawing) with Code 2 within 2 weeks.
| MM-ZTK-1F-GEN-ELE-MR-0003 | RFQ-EL-003 | AC Distribution Boards |  |  | 4-24 | EL | Y | L3 | LB |  | SH | A | 2026-04-21 | 2026-04-28 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-22 | 2026-07-07 | 2026-07-12 | 2026-07-24 | 2026-08-20: 2026-08-07; 2026-08-31: 2026-07-30 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder3 | 32 weeks after drawing approval DDP
42 | MM-ZTK-1F-GEN-ELE-MR-0004 | RFQ-EL-004 | Navigation Aid, Red Lantern, Flashing Beacon, Warning Siren and Fog Horn | NAV-421/422 PC-420, RL-421 SR-421/422 | 24 | 4-25 | EL | Y | L4 | LB | Swift | SH | P | 2026-05-07 | 2026-05-08 | 2026-05-15 | 2026-05-18 | 2026-05-25 | 2026-06-08 | 2026-07-06 | 2026-07-09 |  | 2026-07-23 | 2026-07-27 | 2026-08-03 | 2026-08-31 | 2026-09-14 | 2026-10-14 | 2026-10-14 | 2026-10-17 | 2027-03-24 | 2027-04-13 | 2027-05-13 | 2027-05-16 | 2027-06-12 | 42 | 294 | 2027-05-13 | 2027-05-23 | 46306 | Liu Lei | 2026.4.30 Issued RFQ bid due day:22-May Bidder 1: Received bid on 17 May | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | Ex-work UK : 16weeks Transit time is 8 weeks Custom clerance: 4 weeks
| MM-ZTK-1F-GEN-ELE-MR-0004 | RFQ-EL-004 | Navigation Aid, Red Lantern, Flashing Beacon, Warning Siren and Fog Horn | FB-421/422/423 | 12 | 4-25 | EL | Y | L4 | LB | ZM169-WP1-PO-ELE-001 | SH | F | [10 empty] | 2026-08-20 |  | 2026-08-31 | 2026-08-31 | 2026-09-30 | 2026-09-30 | 2026-10-03 | 1900-06-22 | 1900-07-12 | 1900-08-11 | 2027-05-16 | 2027-06-12 | 32 | 224 | 1900-08-11 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2 | DDP 28 week with condition drawing to be approved within 2 weeks
| MM-ZTK-1F-GEN-ELE-MR-0004 | RFQ-EL-004 | Navigation Aid, Red Lantern, Flashing Beacon, Warning Siren and Fog Horn | FHCP-421&FH-421, FHD-421 | 8 | 4-25 | EL | Y | L4 | LB |  | SH | A | 2026-04-21 | 2026-04-30 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-21 | 2026-07-10 | 2026-08-02 | 2026-08-02 | 2026-08-20: 2026-08-07; 2026-08-31: 2026-07-30 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder3 | 26 weeks after drawing approval DDP
43 | MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-005 | EL Cable |  |  | 5-7 | EL | N | L3 | LD |  | ZH | P | 2026-08-28 | 2026-08-24 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-23 | 2026-10-07 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16 | 2027-05-17 | 121 | Kuang Yuena | 2026.6.4 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-005 | EL Cable |  |  | 5-7 | EL | N | L3 | LD |  | ZH | F | [6 empty] | 2026-09-23 | 2026-10-07 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-16 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-005 | EL Cable |  |  | 5-7 | EL | N | L3 | LD |  | ZH | A | 2026-06-16 | 2026-05-18 | 2026-06-15 | 2026-06-17 | 2026-06-17 | 2026-07-09 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
44 | MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-006 | E&I Cable Gland |  |  | 5-7 | EL | N | L4 | LD |  | ZH | P | 2026-08-28 | 2026-08-24 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-23 | 2026-10-07 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16 | 2027-05-23 | 127
| MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-006 | E&I Cable Gland |  |  | 5-7 | EL | N | L4 | LD |  | ZH | F | 2026-08-28 | 2026-08-24 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-23 | 2026-10-07 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-16
| MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-006 | E&I Cable Gland |  |  | 5-7 | EL | N | L4 | LD |  | ZH | A
45 | MM-ZTK-1F-GEN-ELE-MR-0006 | RFQ-EL-007 | Electrical Lighting Fixtures |  | 38*4 | 5-7 | EL | N | L4 | LD |  | ZH | P | 2026-06-03 | 2026-05-26 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-16 | 2026-07-23 | 2026-08-06 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-07 | 2026-09-22 | 2026-10-02 | 2026-10-02 | 2026-10-04 | 2027-02-10 | 2027-02-20 | 2027-02-25 | 2027-02-28 | 2027-03-27 | 28 | 196 | 2027-01-28 | 2027-04-15 | 41 | Kuang Yuena | 2026.5.15 MR issued yard
| MM-ZTK-1F-GEN-ELE-MR-0006 | RFQ-EL-007 | Electrical Lighting Fixtures |  |  | 5-7 | EL | N | L4 | LD |  | ZH | F | [9 empty] | 2026-08-21 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-29 | 2026-10-09 | 2026-10-09 | 2026-10-11 | 2027-02-18 | 2027-02-28 | 2027-03-05 | 2027-01-31 | 2027-02-27 |  |  | 2027-03-05
| MM-ZTK-1F-GEN-ELE-MR-0006 | RFQ-EL-007 | Electrical Lighting Fixtures |  |  | 5-7 | EL | N | L4 | LD |  | ZH | A | 2026-06-16 | 2026-04-30 | 2026-05-18 | 2026-06-17 | 2026-06-17 | 2026-06-29 | 2026-08-05 | 2026-08-07
46 | MM-ZTK-1F-GEN-ELE-MR-0007 | RFQ-EL-008 | E&I Cable Tray |  |  | 5-7 | EL | N | L4 | LD |  | ZH | P | 2026-08-28 | 2026-08-24 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-23 | 2026-10-07 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16 | 2027-04-09 | 83
| MM-ZTK-1F-GEN-ELE-MR-0007 | RFQ-EL-008 | E&I Cable Tray |  |  | 5-7 | EL | N | L4 | LD |  | ZH | F | 2026-08-28 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-23 | 2026-10-07 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-16
| MM-ZTK-1F-GEN-ELE-MR-0007 | RFQ-EL-008 | E&I Cable Tray |  |  | 5-7 | EL | N | L4 | LD |  | ZH | A |  | 2026-06-21 | 2026-07-07
47 | MM-ZTK-1F-GEN-ELE-MR-0008 | RFQ-EL-009 | E&I Multi-Cable Transits (MCT) |  |  | 5-7 | EL | N | L4 | LD |  | ZH | P | 2026-08-13 | 2026-08-04 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-26 | 2026-09-04 | 2026-09-18 |  | 2026-09-28 | 2026-09-30 | 2026-10-14 | 2026-10-28 | 2026-11-11 | 2026-11-26 | 2026-11-26 | 2026-11-28 | 2027-01-04 | 2027-01-13 | 2027-01-18 | 2027-01-21 | 2027-02-17 | 16 | 112 | 2027-01-18 | 2027-04-09 | 44
| MM-ZTK-1F-GEN-ELE-MR-0008 | RFQ-EL-009 | E&I Multi-Cable Transits (MCT) |  |  | 5-7 | EL | N | L4 | LD |  | ZH | F | 2026-08-13 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-26 | 2026-09-04 | 2026-09-18 |  | 2026-09-28 | 2026-09-30 | 2026-10-14 | 2026-10-28 | 2026-11-11 | 2026-11-26 | 2026-11-26 | 2026-11-28 | 2027-01-04 | 2027-01-13 | 2027-01-18 | 2027-01-21 | 2027-02-17 |  |  | 2027-01-18
| MM-ZTK-1F-GEN-ELE-MR-0008 | RFQ-EL-009 | E&I Multi-Cable Transits (MCT) |  |  | 5-7 | EL | N | L4 | LD |  | ZH | A |  | 2026-06-12 | 2026-06-28
48 | MM-ZTK-1F-GEN-ELE-MR-0009 | RFQ-EL-010 | POWER SOCKET/PLUG, JUNCTION BOXES, EARH BAR AND CABLE GLAND |  |  | 5-7 | EL | N | L4 | LD |  | ZH | P | 2026-08-13 | 2026-08-04 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-26 | 2026-09-04 | 2026-09-18 |  | 2026-09-28 | 2026-09-30 | 2026-10-14 | 2026-10-28 | 2026-11-11 | 2026-11-26 | 2026-11-26 | 2026-11-28 | 2027-01-03 | 2027-01-13 | 2027-01-18 | 2027-01-21 | 2027-02-17 | 16 | 112 | 2027-01-18 | 2027-04-09 | 81
| MM-ZTK-1F-GEN-ELE-MR-0009 | RFQ-EL-010 | POWER SOCKET/PLUG, JUNCTION BOXES, EARH BAR AND CABLE GLAND |  |  | 5-7 | EL | N | L4 | LD |  | ZH | F | 2026-08-13 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-26 | 2026-09-04 | 2026-09-18 |  | 2026-09-28 | 2026-09-30 | 2026-10-14 | 2026-10-28 | 2026-11-11 | 2026-11-26 | 2026-11-26 | 2026-11-28 | 2027-01-03 | 2027-01-13 | 2027-01-18 | 2027-01-21 | 2027-02-17 |  |  | 2027-01-18
| MM-ZTK-1F-GEN-ELE-MR-0009 | RFQ-EL-010 | POWER SOCKET/PLUG, JUNCTION BOXES, EARH BAR AND CABLE GLAND |  |  | 5-7 | EL | N | L4 | LD |  | ZH | A |  | 2026-06-18 | 2026-07-04
49 | MM-ZTK-1F-GEN-INS-MR-0001 | RFQ-IN-001 | Actuated Choke Valve |  | 32 | 4-20 | IN | Y | L3 | LA | MASTER FLO | SH | P | 2026-04-17 | 2026-04-18 | 2026-04-27 | 2026-04-28 | 2026-05-05 | 2026-05-12 | 2026-05-21 | 2026-05-25 |  | 2026-06-01 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-09 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2027-02-14 | 2027-03-06 | 2027-04-05 | 2027-04-08 | 2027-05-05 | 44 | 308 | 2027-04-05 | 2027-05-08 | 61 | Lin Yazhen | 2026.5.9 Issued RFQ(no MR) bid due day:20-May 2026.6.12:TECHNICAL BID EVALUATION FOR ACTUATED CHOKE VALVES(C1) 2026.8.9 Expedite drawings by e-mail | [11 empty] | Masterflo | CIF 36 weeks CIF Zhuhai Seaport, P.R. China
| MM-ZTK-1F-GEN-INS-MR-0001 | RFQ-IN-001 | Actuated Choke Valve |  |  | 4-20 | IN | Y | L3 | LA | ZM169-WP1-PO-IN-001 | SH | F | [13 empty] | 2026-08-24 | 2026-10-23 | 2026-10-25 | 2026-10-27 | 2026-01-19 | 2026-02-08 | 2027-03-08 | 2027-04-08 | 2027-05-05 | 36 | 252 | 2027-03-08 |  |  | CIF Zhuhai port | [13 empty] | Custom clerance: 4 weeks
| MM-ZTK-1F-GEN-INS-MR-0001 | RFQ-IN-001 | Actuated Choke Valve |  |  | 4-20 | IN | Y | L3 | LA |  | SH | A | 2026-04-21 | 2026-04-10 | 2026-04-28 | 2026-05-09 | 2026-05-09 | 2026-05-22 | 2026-06-12 | 2026-06-18 | 2026-06-30 | 2026-09-28: 2026-07-03; 2026-09-30: 2026-07-17; 2026-10-14: 2026-07-10; 2026-10-28: 2026-08-14
50 | MM-ZTK-1F-GEN-INS-MR-0002 | RFQ-IN-002 | Actuated ball valve | ZWP20,21,22 | 9*3 | 4-19 | IN | N | L3 | LB | KCON | SH | P | 2026-04-29 | 2026-04-30 | 2026-05-11 | 2026-05-12 | 2026-05-19 | 2026-06-02 | 2026-07-01 | 2026-07-06 |  | 2026-07-20 | 2026-07-22 | 2026-07-29 | 2026-08-26 | 2026-09-09 | 2026-11-08 | 2026-11-08 | 2026-11-10 | 2027-02-02 | 2027-02-27 | 2027-03-29 | 2027-04-01 | 2027-04-28 | 36 | 252 | 2027-03-29 | 2027-04-30 | 67 | Lin Yazhen | 2026.5.25 Issued RFQ bid due day:2-Jun
| MM-ZTK-1F-GEN-INS-MR-0002 | RFQ-IN-002 | Actuated ball valve | ZWP23 | 11 | 4-19 | IN | N | L3 | LB | ZM169-WP1-PO-IN-002 | SH | F | [8 empty] | 2026-08-20 | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-29 | 2026-10-14 | 2026-12-13 | 2026-12-13 | 2026-12-15 | 2026-12-29 | 2027-01-23 | 2027-02-22 | 2027-04-01 | 2027-04-28 |  |  | 2027-02-22 |  |  | DDP yard
| MM-ZTK-1F-GEN-INS-MR-0002 | RFQ-IN-002 | Actuated ball valve |  |  | 4-19 | IN | N | L3 | LB |  | SH | A | 2026-05-22 | 2026-04-21 | 2026-05-11 | 2026-05-25 | 2026-05-25 | 2026-06-06 | 2026-07-27 | 2026-08-02
51 | MM-ZTK-1F-GEN-INS-MR-0003 | RFQ-IN-003 | Actuated Compact Ball Valve |  | 64 | 4-40 | IN | Y | L2 | LA | OIL STATE | SH | P | 2026-04-28 | 2026-04-29 | 2026-05-08 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-30 | 2026-07-03 |  | 2026-07-17 | 2026-07-21 | 2026-07-28 | 2026-08-25 | 2026-09-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2027-03-04 | 2027-03-24 | 2027-04-23 | 2027-04-26 | 2027-05-23 | 40 | 280 | 2027-04-23 | 2027-04-30 | 69 | Lin Yazhen | 2026.5.9 Issued RFQ 2026.5.15 MR issued to bidders bid due day:20-May | [13 empty] | Ex-work 33
| MM-ZTK-1F-GEN-INS-MR-0003 | RFQ-IN-003 | Actuated Compact Ball Valve |  |  | 4-40 | IN | Y | L2 | LA | ZM169-WP1-PO-IN-003 | SH | F | [10 empty] | 2026-08-20 |  | 2026-08-25 | 2026-09-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2027-01-01 | 2027-01-21 | 2027-02-20 | 2027-04-26 | 2027-05-23 |  |  | 2027-02-20 |  |  | CIF Zhuhai Airport
| MM-ZTK-1F-GEN-INS-MR-0003 | RFQ-IN-003 | Actuated Compact Ball Valve |  |  | 4-40 | IN | Y | L2 | LA |  | SH | A | 2026-04-21 | 2026-04-21 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-06-05 | 2026-07-14 | 2026-07-27 | 2026-07-21 | 2026-07-31 |  | 2026-07-31
52 | MM-ZTK-1F-GEN-INS-MR-0004 | RFQ-IN-004 | Safety Relief Valves |  |  | 4-30 | IN | N | L3 | LB |  | SH | P | 2026-06-03 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-08-04 | 2026-08-07 |  | 2026-08-21 | 2026-08-25 | 2026-09-01 | 2026-09-30 | 2026-10-15 | 2026-12-14 | 2026-12-14 | 2026-12-16 | 2027-02-16 | 2027-03-03 | 2027-04-02 | 2027-04-05 | 2027-05-02 | 32 | 224 | 2027-04-02 | 2027-04-30 | 28 | Lin Yazhen | 2026.5.25 Issued RFQ bid due day:2-Jun | [11 empty] | Bidder1 | DDP 18 weeks( after PO)
| MM-ZTK-1F-GEN-INS-MR-0004 | RFQ-IN-004 | Safety Relief Valves |  |  | 4-30 | IN | N | L3 | LB |  | SH | F | [9 empty] | 2026-08-21 | 2026-08-25 | 2026-09-01 | 2026-09-30 | 2026-10-15 | 2026-12-14 | 2026-12-14 | 2026-12-16 | 2027-02-16 | 2027-03-03 | 2027-04-02 | 2027-04-05 | 2027-05-02 |  |  | 2027-04-02 | [15 empty] | Bidder2 | DDP 24 weeks( after PO)
| MM-ZTK-1F-GEN-INS-MR-0004 | RFQ-IN-004 | Safety Relief Valves |  |  | 4-30 | IN | N | L3 | LB |  | SH | A | 2026-05-22 | 2026-04-13 | 2026-05-05 | 2026-05-28 | 2026-05-28 | 2026-06-10 | 2026-07-24 | 2026-08-02 | [32 empty] | Bidder3 | DDP 30 weeks( after PO)
53 | MM-ZTK-1F-GEN-INS-MR-0005 | RFQ-IN-005 | Coriolis Flow Meters | FT-1018 | 1*4 | 4-32 | IN | N | L3 | LC |  | SH | P | 2026-08-06 | 2026-08-09 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-09-07 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-24 | 2026-12-24 | 2026-12-26 | 2027-02-22 23:17 | 2027-03-04 23:17 | 2027-03-14 23:17 | 2027-03-17 23:17 | 2027-04-13 23:17 | 20.71 | 144.97 | 2027-03-14 23:17 | 2027-04-30 | 46.03
| MM-ZTK-1F-GEN-INS-MR-0005 | RFQ-IN-005 | Coriolis Flow Meters |  |  | 4-32 | IN | N | L3 | LC |  | SH | F | [5 empty] | 2026-08-24 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-24 | 2026-12-24 | 2026-12-26 | 2027-02-22 23:17 | 2027-03-04 23:17 | 2027-03-14 23:17 | 2027-03-17 23:17 | 2027-04-13 23:17 |  |  | 2027-03-14 23:17
| MM-ZTK-1F-GEN-INS-MR-0005 | RFQ-IN-005 | Coriolis Flow Meters |  |  | 4-32 | IN | N | L3 | LC |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30 | 2026-08-14 | 2026-08-14
54 | MM-ZTK-1F-GEN-INS-MR-0006 | RFQ-IN-006 | Wellhead Control Panel |  |  | 4-28 | IN | Y | L2 | LA | Wilmax | SH | P | 2026-04-23 | 2026-04-24 | 2026-05-05 | 2026-05-06 | 2026-05-13 | 2026-05-27 | 2026-06-26 | 2026-07-01 |  | 2026-07-15 | 2026-07-17 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-10-14 | 2026-10-14 | 2026-10-16 | 2027-02-22 | 2027-03-14 | 2027-03-24 | 2027-03-27 | 2027-04-23 | 32 | 252 | 2027-03-23 | 2027-03-23 | 373 | Sun Liheng | 2026.5.9 Issued RFQ(No MR) bid due day:20-May | [12 empty] | 1st Batch: 32 Weeks (drawings approved within 4 weeks from LOA/PO date)
| MM-ZTK-1F-GEN-INS-MR-0006 | RFQ-IN-006 | Wellhead Control Panel |  |  | 4-28 | IN | Y | L2 | LA | ZM169-WP1-PO-IN-006 | SH | F | [13 empty] | 2026-08-24 | 2026-10-03 | 2026-10-03 | 2026-10-05 | 2027-02-21 | 2027-03-13 | 2027-03-23 | 2027-03-26 | 2027-04-22 |  |  | 2026-03-15 |  |  | CIF Zhuhai port | [13 empty] | 2nd Batch: 33 Weeks (drawings approved within 4 weeks from LOA/PO date)
| MM-ZTK-1F-GEN-INS-MR-0006 | RFQ-IN-006 | Wellhead Control Panel |  |  | 4-28 | IN | Y | L2 | LA |  | SH | A | 2026-04-21 | 2026-04-21 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-27 | 2026-07-14 | 2026-07-14 | 2026-07-23 | 2026-07-31 | 2026-08-13 | 2026-07-31 | 2026-08-07
55 | MM-ZTK-1F-GEN-INS-MR-0008 | RFQ-IN-007 | PLC system |  |  | 4-27 | IN | N | L3 | LB |  | SH | P | 2026-05-26 | 2026-05-27 | 2026-06-05 | 2026-06-08 | 2026-06-15 | 2026-06-30 | 2026-07-30 | 2026-08-04 |  | 2026-08-18 | 2026-08-20 | 2026-08-27 | 2026-09-24 | 2026-10-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 36 | 252 | 2027-04-27 | 2027-05-08 | 5 | Liu Lei | [12 empty] | Rockwell | 30 to 34 weeks after order and receipt of full and final design information.
| MM-ZTK-1F-GEN-INS-MR-0008 | RFQ-IN-007 | PLC system |  |  | 4-27 | IN | N | L3 | LB |  | SH | F | [8 empty] | 2026-08-18 | 2026-08-24 | 2026-08-26 | 2026-09-02 | 2026-10-08 | 2026-10-26 | 2026-11-25 | 2026-11-25 | 2026-11-27 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 |  |  | 2027-05-03
| MM-ZTK-1F-GEN-INS-MR-0008 | RFQ-IN-007 | PLC system |  |  | 4-27 | IN | N | L3 | LB |  | SH | A | 2026-04-21 | 2026-04-22 | 2026-05-13 | 2026-06-04 | 2026-06-04 | 2026-06-15 | 2026-07-31 | 2026-08-03
56 | MM-ZTK-1F-ZPQ-INS-MR-0001 | RFQ-IN-009 | SCADA |  |  | 4-27 | IN | N | L3 | LB |  | SH | P | 2026-05-26 | 2026-05-27 | 2026-06-05 | 2026-06-08 | 2026-06-15 | 2026-06-30 | 2026-09-03 | 2026-09-13 |  | 2026-09-18 | 2026-09-20 | 2026-09-19 | 2026-10-26 | 2026-11-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 33 | 231 | 2027-04-27 | 2027-05-08 | 1 | Liu Lei | [12 empty] | Rockwell | 30 to 34 weeks after order and receipt of full and final design information.
| MM-ZTK-1F-ZPQ-INS-MR-0001 | RFQ-IN-009 | SCADA |  |  | 4-27 | IN | N | L3 | LB |  | SH | F | [5 empty] | 2026-08-19 | 2026-09-03 | 2026-09-13 |  | 2026-09-18 | 2026-09-20 | 2026-09-19 | 2026-10-26 | 2026-11-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 |  |  | 2027-05-07
| MM-ZTK-1F-ZPQ-INS-MR-0001 | RFQ-IN-009 | SCADA |  |  | 4-27 | IN | N | L3 | LB |  | SH | A | 2026-04-21 | 2026-07-31 | 2026-08-05 | 2026-08-05 | 2026-08-05
57 | MM-ZTK-1F-GEN-INS-MR-0009 | RFQ-IN-008-1 | Control valve | LV-1017 | 1*4 | 4-5 | IN | N | L2 | LB |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-12-04 | 2026-12-04 | 2026-12-06 | 2027-03-07 | 2027-03-22 | 2027-04-01 | 2027-04-04 | 2027-05-01 | 33 | 231 | 2027-04-01 | 2027-04-30 | 17 | Lin Yazhen | 2026.5.25 Issued RFQ bid due day:2-Jun | [11 empty] | Bidder1 | DDP 24 weeks (after PO)
| MM-ZTK-1F-GEN-INS-MR-0009 | RFQ-IN-008-1 | Control valve | PV-1001/1015 | 2*4 | 4-5 | IN | N | L2 | LB |  | SH | F | [8 empty] | 2026-08-21 | 2026-08-25 | 2026-08-27 | 2026-09-03 | 2026-10-09 | 2026-10-27 | 2026-12-26 | 2026-12-26 | 2026-12-28 | 2027-03-07 | 2027-03-22 | 2027-04-01 | 2027-04-04 | 2027-05-01 |  |  | 2027-04-13 | [15 empty] | Bidder2 | DDP 24 weeks( after PO)
| MM-ZTK-1F-GEN-INS-MR-0009 | RFQ-IN-008-1 | Control valve |  |  | 4-5 | IN | N | L2 | LB |  | SH | A | 2026-04-21 | 2026-04-22 | 2026-05-13 | 2026-05-25 | 2026-05-25 | 2026-06-15 | 2026-07-31 | 2026-08-06
58 | MM-ZTK-1F-GEN-INS-MR-0010 | RFQ-IN-008-2 | Self-Actuated Pressure Control Valves | PCV-3003A/B | 2*4 | 4-5 | IN | N | L3 | LB | Combined with control valve (fisher) | SH | P | 2026-06-03 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-08-04 | 2026-08-07 |  | 2026-08-21 | 2026-08-25 | 2026-09-01 | 2026-09-30 | 2026-10-15 | 2026-12-14 | 2026-12-14 | 2026-12-16 | 2027-03-08 | 2027-03-23 | 2027-04-02 | 2027-04-05 | 2027-04-30 | 32 | 224 | 2027-04-02 | 2027-04-30 | 24 | Lin Yazhen | 2026.5.25 Issued RFQ bid due day:2-Jun
| MM-ZTK-1F-GEN-INS-MR-0010 | RFQ-IN-008-2 | Self-Actuated Pressure Control Valves |  |  | 4-5 | IN | N | L3 | LB |  | SH | F | [8 empty] | 2026-08-21 | 2026-08-25 | 2026-08-27 | 2026-09-03 | 2026-10-09 | 2026-10-27 | 2026-12-26 | 2026-12-26 | 2026-12-28 | 2027-03-08 | 2027-03-23 | 2027-04-02 | 2027-04-05 | 2027-04-30 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0010 | RFQ-IN-008-2 | Self-Actuated Pressure Control Valves |  |  | 4-5 | IN | N | L3 | LB |  | SH | A | No need | 2026-04-21 | 2026-05-11 | 2026-05-25 | 2026-05-25 | 2026-06-15 | 2026-07-24 | 2026-08-02
59 | MM-ZTK-1F-GEN-INS-MR-0011 | RFQ-IN-010 | Fire & Gas Detectors | AGD-0001/0002 | 2*4 | 4-8 | IN | N | L3 | LC |  | SH | P | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-03 | 2026-09-17 | 2026-10-08 | 2026-10-14 |  | 2026-10-28 | 2026-10-30 | 2026-11-06 | 2026-11-27 | 2026-12-14 | 2027-01-03 | 2027-01-03 | 2027-01-05 | 2027-02-13 | 2027-02-28 | 2027-03-10 | 2027-03-13 | 2027-04-09 | 19 | 133 | 2027-03-10 | 2027-04-30 | 51
| MM-ZTK-1F-GEN-INS-MR-0011 | RFQ-IN-010 | Fire & Gas Detectors | HS-9006/9020-26 | 8*4 | 4-8 | IN | N | L3 | LC |  | SH | F | [5 empty] | 2026-08-20 | 2026-09-08 | 2026-09-22 |  | 2026-10-28 | 2026-10-30 | 2026-11-06 | 2026-11-27 | 2026-12-14 | 2027-01-03 | 2027-01-03 | 2027-01-05 | 2027-02-13 | 2027-02-28 | 2027-03-10 | 2027-03-13 | 2027-04-09 |  |  | 2027-03-10
| MM-ZTK-1F-GEN-INS-MR-0011 | RFQ-IN-010 | Fire & Gas Detectors |  |  | 4-8 | IN | N | L3 | LC |  | SH | A | 2026-08-07 | 2026-05-09 | 2026-05-24 | 2026-08-10 | 2026-08-10
60 | MM-ZTK-1F-GEN-INS-MR-0012 | RFQ-IN-011 | IN Junction Box |  |  | 5-8 | IN | N | L3 | LD |  | ZH | P | 2026-10-27 | 2026-10-18 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-09 | 2026-11-18 | 2026-12-02 |  | 2026-12-09 | 2026-12-11 | 2026-12-18 | 2027-01-04 | 2027-01-18 | 2027-02-02 | 2027-02-02 | 2027-02-04 | 2027-03-06 | 2027-03-21 | 2027-03-31 | 2027-04-03 | 2027-04-30 | 16 | 112 | 2027-03-31 | 2027-04-15 | 86 | Zhang Jianwei
| MM-ZTK-1F-GEN-INS-MR-0012 | RFQ-IN-011 | IN Junction Box |  |  | 5-8 | IN | N | L3 | LD |  | ZH | F | 2026-08-19 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-27 | 2026-09-07 | 2026-09-21 |  | 2026-09-29 | 2026-10-08 | 2026-10-15 | 2026-10-29 | 2026-11-12 | 2026-11-27 | 2026-11-27 | 2026-11-29 | 2027-03-06 | 2027-03-21 | 2027-03-31 | 2027-04-03 | 2027-04-30 |  |  | 2027-01-19
| MM-ZTK-1F-GEN-INS-MR-0012 | RFQ-IN-011 | IN Junction Box |  |  | 5-8 | IN | N | L3 | LD |  | ZH | A |  | 2026-04-28 | 2026-05-08
61 | MM-ZTK-1F-GEN-INS-MR-0013 | RFQ-IN-012 | Position Limit Switch | ZSL-A02~R02 | 16*4 | 4-36 | IN | N | L3 | LC |  | SH | P | 2026-08-13 | 2026-08-18 | 2026-08-25 | 2026-08-26 | 2026-09-02 | 2026-09-16 | 2026-10-07 | 2026-10-12 |  | 2026-10-26 | 2026-10-28 | 2026-11-04 | 2026-11-25 | 2026-12-10 | 2026-12-25 | 2026-12-25 | 2026-12-27 | 2027-02-04 | 2027-02-19 | 2027-03-01 | 2027-03-04 | 2027-03-31 | 18 | 126 | 2027-03-01 | 2027-04-23 | 53
| MM-ZTK-1F-GEN-INS-MR-0013 | RFQ-IN-012 | Position Limit Switch | ZSL-A03~R03 | 16*4 | 4-36 | IN | N | L3 | LC |  | SH | F |  |  |  | 2026-08-26 | 2026-08-26 | 2026-09-09 | 2026-10-02 | 2026-10-19 |  | 2026-10-26 | 2026-10-28 | 2026-11-04 | 2026-11-25 | 2026-12-10 | 2026-12-25 | 2026-12-25 | 2026-12-27 | 2027-02-04 | 2027-02-19 | 2027-03-01 | 2027-03-04 | 2027-03-31 |  |  | 2027-03-01
| MM-ZTK-1F-GEN-INS-MR-0013 | RFQ-IN-012 | Position Limit Switch |  |  | 4-36 | IN | N | L3 | LC |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-24
62 | MM-ZTK-1F-GEN-INS-MR-0014 | RFQ-IN-013 | Pressure Gauges | PG-1008/2008/2009/2018/2028/2029/2030/3023/3039/5005/5007 | 11*4 | 4-35 | IN | N | L4 | LC |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-30 | 73
| MM-ZTK-1F-GEN-INS-MR-0014 | RFQ-IN-013 | Pressure Gauges |  |  | 4-35 | IN | N | L4 | LC |  | SH | F | [5 empty] | 2026-08-20 | 2026-09-08 | 2026-09-22 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-12 | 2026-11-26 | 2026-12-11 | 2026-12-11 | 2026-12-13 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-02-16
| MM-ZTK-1F-GEN-INS-MR-0014 | RFQ-IN-013 | Pressure Gauges |  |  | 4-35 | IN | N | L4 | LC |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-24 | 2026-08-12 | 2026-08-12
63 | MM-ZTK-1F-GEN-INS-MR-0015 | RFQ-IN-014 | Pressure Gauges (Wireless Type) | PG-A05~R05 | 16*4 | 4-35 | IN | N | L4 | LC |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-30 | 24
| MM-ZTK-1F-GEN-INS-MR-0015 | RFQ-IN-014 | Pressure Gauges (Wireless Type) | PG-A08~R08 | 16*4 | 4-35 | IN | N | L4 | LC |  | SH | F |  |  |  | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0015 | RFQ-IN-014 | Pressure Gauges (Wireless Type) | PG-A14~R14 | 16*4 | 4-35 | IN | N | L4 | LC |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30
64 | MM-ZTK-1F-GEN-INS-MR-0016 | RFQ-IN-015 | Temperature Gauges and Thermowells | TG-1005 | 1*4 | 4-35 | IN | N | L3 | LC |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-30 | 71
| MM-ZTK-1F-GEN-INS-MR-0016 | RFQ-IN-015 | Temperature Gauges and Thermowells |  |  | 4-35 | IN | N | L3 | LC |  | SH | F | [5 empty] | 2026-08-24 | 2026-09-10 | 2026-09-24 |  | 2026-10-15 | 2026-10-19 | 2026-10-26 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-12-15 | 2026-12-17 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-02-18
| MM-ZTK-1F-GEN-INS-MR-0016 | RFQ-IN-015 | Temperature Gauges and Thermowells |  |  | 4-35 | IN | N | L3 | LC |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30 | 2026-08-13 | 2026-08-13
65 | MM-ZTK-1F-GEN-INS-MR-0017 | RFQ-IN-016 | Temperature Transmitters and Thermowells | TT-1013 | 1*4 | 4-35 | IN | N | L3 | LC |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-30 | 71
| MM-ZTK-1F-GEN-INS-MR-0017 | RFQ-IN-016 | Temperature Transmitters and Thermowells |  |  | 4-35 | IN | N | L3 | LC |  | SH | F | [5 empty] | 2026-08-24 | 2026-09-10 | 2026-09-24 |  | 2026-10-15 | 2026-10-19 | 2026-10-26 | 2026-11-16 | 2026-11-30 | 2026-12-15 | 2026-12-15 | 2026-12-17 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-02-18
| MM-ZTK-1F-GEN-INS-MR-0017 | RFQ-IN-016 | Temperature Transmitters and Thermowells |  |  | 4-35 | IN | N | L3 | LC |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30 | 2026-08-13 | 2026-08-13
66 | MM-ZTK-1F-GEN-INS-MR-0018 | RFQ-IN-017 | Temperature Transmitters (Pipe Clamp) Wireless Type | TT-A10~R10 | 16*4 | 4-35 | IN | N | L3 | LC |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-30 | 24
| MM-ZTK-1F-GEN-INS-MR-0018 | RFQ-IN-017 | Temperature Transmitters (Pipe Clamp) Wireless Type | TT-2003/3024 | 2*4 | 4-35 | IN | N | L3 | LC |  | SH | F |  |  |  | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0018 | RFQ-IN-017 | Temperature Transmitters (Pipe Clamp) Wireless Type |  |  | 4-35 | IN | N | L3 | LC |  | SH | A | 2026-08-12 | 2026-05-12 | 2026-06-09
67 | MM-ZTK-1F-GEN-INS-MR-0019 | RFQ-IN-018 | Pressure Transmitters | PT-A09~R09 | 16*4 | 4-35 | IN | N | L3 | LC |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-30 | 73
| MM-ZTK-1F-GEN-INS-MR-0019 | RFQ-IN-018 | Pressure Transmitters | PT-1001/1007/1010/2001/2003/3004/3031/5003/5006 | 9*4 | 4-35 | IN | N | L3 | LC |  | SH | F | [5 empty] | 2026-08-20 | 2026-09-08 | 2026-09-22 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-12 | 2026-11-26 | 2026-12-11 | 2026-12-11 | 2026-12-13 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-02-16
| MM-ZTK-1F-GEN-INS-MR-0019 | RFQ-IN-018 | Pressure Transmitters |  |  | 4-35 | IN | N | L3 | LC |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30 | 2026-08-10 | 2026-08-10
68 | MM-ZTK-1F-GEN-INS-MR-0020 | RFQ-IN-019 | Pressure Transmitters (Wireless Type) | PT-0001 | 1*4 | 4-35 | IN | N | L3 | LC |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-30 | 24
| MM-ZTK-1F-GEN-INS-MR-0020 | RFQ-IN-019 | Pressure Transmitters (Wireless Type) | PT-A07~R07 | 15*4 | 4-35 | IN | N | L3 | LC |  | SH | F |  |  |  | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0020 | RFQ-IN-019 | Pressure Transmitters (Wireless Type) | WGW-9001 | 1*4 | 4-35 | IN | N | L3 | LC |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30
69 | MM-ZTK-1F-GEN-INS-MR-0021 | RFQ-IN-020 | Magnetic Level Gauges and Transmitters |  |  | 4-35 | IN | N | L3 | LC |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-30 | 73
| MM-ZTK-1F-GEN-INS-MR-0021 | RFQ-IN-020 | Magnetic Level Gauges and Transmitters |  |  | 4-35 | IN | N | L3 | LC |  | SH | F | [6 empty] | 2026-09-08 | 2026-09-22 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-12 | 2026-11-26 | 2026-12-11 | 2026-12-11 | 2026-12-13 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-02-16
| MM-ZTK-1F-GEN-INS-MR-0021 | RFQ-IN-020 | Magnetic Level Gauges and Transmitters |  |  | 4-35 | IN | N | L3 | LC |  | SH | A | 2026-07-27 | 2026-04-21 | 2026-05-11 | 2026-07-29 | 2026-07-29 | 2026-08-14
70 | MM-ZTK-1F-GEN-INS-MR-0023 | RFQ-IN-022 | DP Level Transmitters | LT-9065/9066 | 2*4 | 4-35 | IN | N | L3 | LC |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-30 | 73
| MM-ZTK-1F-GEN-INS-MR-0023 | RFQ-IN-022 | DP Level Transmitters |  |  | 4-35 | IN | N | L3 | LC |  | SH | F | [5 empty] | 2026-08-20 | 2026-09-08 | 2026-09-22 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-12 | 2026-11-26 | 2026-12-11 | 2026-12-11 | 2026-12-13 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-02-16
| MM-ZTK-1F-GEN-INS-MR-0023 | RFQ-IN-022 | DP Level Transmitters |  |  | 4-35 | IN | N | L3 | LC |  | SH | A | 2026-08-06 | 2026-05-09 | 2026-05-30 | 2026-08-10 | 2026-08-10
71 | MM-ZTK-1F-GEN-INS-MR-0024 | RFQ-IN-023 | Restriction Orifices | RO-0010/1020 | 2*4 | 4-42 | IN | N | L4 | LC |  | SH | P | 2026-08-06 | 2026-08-08 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-09-07 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-03-09 | 2027-03-19 | 2027-03-24 | 2027-03-27 | 2027-04-23 | 22 | 154 | 2027-03-24 | 2027-04-30 | 45
| MM-ZTK-1F-GEN-INS-MR-0024 | RFQ-IN-023 | Restriction Orifices | RO-3028/4001 | 2*4 | 4-42 | IN | N | L4 | LC |  | SH | F | [5 empty] | 2026-08-20 | 2026-09-08 | 2026-09-22 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-12 | 2026-11-26 | 2026-12-11 | 2026-12-11 | 2026-12-13 | 2027-03-09 | 2027-03-19 | 2027-03-24 | 2027-03-27 | 2027-04-23 |  |  | 2027-03-16
| MM-ZTK-1F-GEN-INS-MR-0024 | RFQ-IN-023 | Restriction Orifices |  |  | 4-42 | IN | N | L4 | LC |  | SH | A | 2026-08-12 | 2026-05-09 | 2026-05-18 | 2026-08-14 | 2026-08-14
72 | MM-ZTK-1F-GEN-INS-MR-0025 | RFQ-IN-024 | Vortex Flow Meters | FT-1012 | 1*4 | 4-32 | IN | N | L3 | LC |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-30 | 73
| MM-ZTK-1F-GEN-INS-MR-0025 | RFQ-IN-024 | Vortex Flow Meters |  |  | 4-32 | IN | N | L3 | LC |  | SH | F | [5 empty] | 2026-08-20 | 2026-09-08 | 2026-09-22 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-12 | 2026-11-26 | 2026-12-11 | 2026-12-11 | 2026-12-13 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-02-16
| MM-ZTK-1F-GEN-INS-MR-0025 | RFQ-IN-024 | Vortex Flow Meters |  |  | 4-32 | IN | N | L3 | LC |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-31 | 2026-08-14 | 2026-08-14
73 | MM-ZTK-1F-GEN-INS-MR-0026 | RFQ-IN-025 | Non-Intrusive Sand Monitoring System (Acoustic Type) | XT-0014 | 1*4 | 4-34 | IN | N | L3 | LC |  | SH | P | 2026-06-22 | 2026-06-22 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-20 | 2026-08-10 | 2026-08-25 |  | 2026-09-07 | 2026-09-09 | 2026-09-16 | 2026-10-15 | 2026-10-30 | 2026-11-29 | 2026-11-29 | 2026-12-01 | 2027-02-14 | 2027-03-06 | 2027-04-05 | 2027-04-08 | 2027-05-05 | 30 | 210 | 2027-04-05 | 2027-04-30 | -6
| MM-ZTK-1F-GEN-INS-MR-0026 | RFQ-IN-025 | Non-Intrusive Sand Monitoring System (Acoustic Type) |  |  | 4-34 | IN | N | L3 | LC |  | SH | F | [5 empty] | 2026-08-25 | 2026-09-17 | 2026-10-01 |  | 2026-10-08 | 2026-10-12 | 2026-10-19 | 2026-11-09 | 2026-11-23 | 2026-12-23 | 2026-12-23 | 2026-12-25 | 2027-02-14 | 2027-03-06 | 2027-04-05 | 2027-04-08 | 2027-05-05 |  |  | 2027-05-06
| MM-ZTK-1F-GEN-INS-MR-0026 | RFQ-IN-025 | Non-Intrusive Sand Monitoring System (Acoustic Type) |  |  | 4-34 | IN | N | L3 | LC |  | SH | A | 2026-08-17 | 2026-05-08 | 2026-05-31 | 2026-08-17 | 2026-08-17
| MM-ZTK-1F-GEN-INS-MR-0033 | RFQ-IN-026 | on-Intrusive Wireless Sand Monitoring System (Ultrasonic Type) | XT-A13A/B/C~R13A/B/C | 16*3*4 | 4-34 | IN | N | L3 | LC | Remove from Scope of supply | SH | P | 2026-06-22 | 2026-06-22 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-20 | 2026-08-10 | 2026-08-25 |  | 2026-09-07 | 2026-09-09 | 2026-09-16 | 2026-10-15 | 2026-10-30 | 2026-11-29 | 2026-11-29 | 2026-12-01 | 2027-02-14 | 2027-03-06 | 2027-04-05 | 2027-04-08 | 2027-05-05 | 30 | 210 | 2027-04-05 | 2027-04-30 | 25
| MM-ZTK-1F-GEN-INS-MR-0033 | RFQ-IN-026 | on-Intrusive Wireless Sand Monitoring System (Ultrasonic Type) |  |  | 4-34 | IN | N | L3 | LC |  | SH | F | 2026-07-13 |  |  | 2026-07-13 | 2026-07-13 | 2026-07-27 | 2026-08-10 | 2026-08-25 |  | 2026-09-07 | 2026-09-09 | 2026-09-16 | 2026-10-15 | 2026-10-30 | 2026-11-29 | 2026-11-29 | 2026-12-01 | 2027-02-14 | 2027-03-06 | 2027-04-05 | 2027-04-08 | 2027-05-05 |  |  | 2027-04-05
| MM-ZTK-1F-GEN-INS-MR-0033 | RFQ-IN-026 | on-Intrusive Wireless Sand Monitoring System (Ultrasonic Type) |  |  | 4-34 | IN | N | L3 | LC |  | SH | A |  | 2026-05-08 | 2026-05-31
74 | MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-027 | IN Cable |  |  | 5-8 | IN | N | L4 | LD |  | ZH | P | 2026-08-28 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-16 | 2026-09-30 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16 | 2027-04-09 | 83 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-027 | IN Cable |  |  | 5-8 | IN | N | L4 | LD |  | ZH | F | 2026-08-28 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-16 | 2026-09-30 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-16 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-027 | IN Cable |  |  | 5-8 | IN | N | L4 | LD |  | ZH | A | [29 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-028 | IN Cable Tray |  |  | 5-8 | IN | N | L4 | LD | Combine with EL Cable Tray | ZH | P | 2026-08-28 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-16 | 2026-09-30 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16 | 2027-04-09 | 83
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-028 | IN Cable Tray |  |  | 5-8 | IN | N | L4 | LD |  | ZH | F | 2026-08-28 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-16 | 2026-09-30 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-16
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-028 | IN Cable Tray |  |  | 5-8 | IN | N | L4 | LD |  | ZH | A
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-029 | IN Cable Gland |  |  | 5-8 | IN | N | L4 | LD | Combine with EL Cable Gland | ZH | P | 2026-08-28 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-16 | 2026-09-30 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16 | 2027-04-09 | 83
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-029 | IN Cable Gland |  |  | 5-8 | IN | N | L4 | LD |  | ZH | F | 2026-08-28 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-16 | 2026-09-30 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-16
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-029 | IN Cable Gland |  |  | 5-8 | IN | N | L4 | LD |  | ZH | A
75 | MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-030 | IN Bulk Material including of Fitting, Tubing, isolated valve(small), fusible plug, STAUFF clamps |  |  | 5-8 | IN | N | L3 | LD |  | ZH | P | 2026-09-07 | 2026-09-05 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-28 | 2026-10-07 | 2026-10-22 |  | 2026-10-29 | 2026-11-02 | 2026-11-09 | 2026-11-23 | 2026-12-08 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-03-06 | 2027-03-13 | 2027-03-18 | 2027-03-21 | 2027-04-17 | 20 | 140 | 2027-03-18 | 2027-05-23 | 66
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-030 | IN Bulk Material including of Fitting, Tubing, isolated valve(small), fusible plug, STAUFF clamps |  |  | 5-8 | IN | N | L3 | LD |  | ZH | F | 2026-09-07 | 2026-09-05 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-28 | 2026-10-07 | 2026-10-22 |  | 2026-10-29 | 2026-11-02 | 2026-11-09 | 2026-11-23 | 2026-12-08 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-03-06 | 2027-03-13 | 2027-03-18 | 2027-03-21 | 2027-04-17 |  |  | 2027-03-18
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-030 | IN Bulk Material including of Fitting, Tubing, isolated valve(small), fusible plug, STAUFF clamps |  |  | 5-8 | IN | N | L3 | LD |  | ZH | A
76 | MM-ZTK-1F-GEN-TEL-MR-0001~0005 | RFQ-TEL-001 | Telecom materials(SCADA radio, Trunk Radio, Explosion Proof Telephone,Marine Racon,VHF FM Marine Radio System) | ANT-502-001 MR-502-001 SA-502-001 MR-502-001A LAN-502-001 TCAB-500-001 | 4*4 4*4 4*4 4*4 5*4 4*4 | 4-37 | TEL | N | L3 | LC |  | SH | P | 2026-07-15 | 2026-07-14 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-08-13 | 2026-09-01 | 2026-09-15 |  | 2026-09-29 | 2026-10-08 | 2026-10-15 | 2026-11-05 | 2026-11-19 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-18 | 2027-02-28 | 2027-03-30 | 2027-04-02 | 2027-04-29 | 26 | 182 | 2027-03-30 | 2027-04-23 | -5
| MM-ZTK-1F-GEN-TEL-MR-0001~0005 | RFQ-TEL-001 | Telecom materials(SCADA radio, Trunk Radio, Explosion Proof Telephone,Marine Racon,VHF FM Marine Radio System) | Trunk Radio Ex Telephone Marine Racon | 118*4 8*4 13*3 | 4-37 | TEL | N | L3 | LC |  | SH | F |  |  |  | 2026-08-28 | 2026-08-28 | 2026-09-11 | 2026-09-30 | 2026-10-15 |  | 2026-10-28 | 2026-10-30 | 2026-11-06 | 2026-11-27 | 2026-12-14 | 2027-01-13 | 2027-01-13 | 2027-01-15 | 2027-02-18 | 2027-02-28 | 2027-03-30 | 2027-04-02 | 2027-04-29 |  |  | 2027-04-28
| MM-ZTK-1F-GEN-TEL-MR-0001~0005 | RFQ-TEL--001 | Telecom materials(SCADA radio, Trunk Radio, Explosion Proof Telephone,Marine Racon,VHF FM Marine Radio System) | VHFF-510-001 ANT-510-001 TCAB-510-001 SA-510-001 | 4*3 4*3 4*3 5*3 | 4-37 | TEL | N | L3 | LC |  | SH | A | 2026-07-08 | 2026-05-18 | 2026-06-13
77 | MM-ZTK-1F-GEN-STR-MR-1021 | RFQ-STR-001 | Topside Primary Steel- Plate |  |  | 5-1 | STR | Y | L2 | LA | Total: 1068T | ZH | P | 2026-05-04 | 2026-06-05 | 2026-06-20 | 2026-06-23 | 2026-06-26 | 2026-06-29 | 2026-07-02 | 2026-07-05 |  | 2026-07-13 | 2026-07-15 | 2026-04-20 | 2026-04-23 | 2026-05-11 | 2026-07-28 | 2026-08-12 | 2026-08-14 | 2026-08-27 12:00 | 2026-09-03 12:00 | 2026-09-08 | 2026-09-11 | 2026-10-10 12:00 | 8.5 | 59.5 | 2026-09-08 | 2026-09-09 | 15 | Huang liudong
| MM-ZTK-1F-GEN-STR-MR-1021 | RFQ-STR-001 | Topside Primary Steel- Plate |  |  | 5-1 | STR | Y | L2 | LA | 121 pic in stock(wait for SRN) | ZH | F | [9 empty] | 2027-02-18: 2026-08-21; 2027-02-28: 2026-08-23; 2027-03-30: 2026-08-25; 2027-04-02: 2026-09-11; 2027-04-29: 2026-10-10 12:00 |  |  | 2026-08-25
| MM-ZTK-1F-GEN-STR-MR-1021 | RFQ-STR-001 | Topside Primary Steel- Plate |  |  | 5-1 | STR | Y | L2 | LA |  | ZH | A | 2026-04-08 | 2026-05-20 | 2026-05-22 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-07-03 | 2026-07-07 |  | 2026-07-07 | 2026-07-07 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-07-30 | 2026-07-30 | 2026-08-02
78 | MM-ZTK-1F-GEN-STR-MR-1011 | RFQ-STR-002 | Topside Primary Steel-Beam |  |  | 5-1 | STR | Y | L2 | LA |  | ZH | P | 2026-04-22 | 2026-05-29 | 2026-06-20 | 2026-06-23 | 2026-06-26 | 2026-06-29 | 2026-07-02 | 2026-07-05 |  | 2026-07-13 | 2026-07-15 | 2026-07-24 | 2026-08-21 | 2026-09-04 |  | 2026-09-09 | 2026-09-11 | 2026-10-09 02:24 | 2026-10-16 02:24 | 2026-10-21 02:24 | 2026-10-24 | 2026-11-10 02:24 | 14.3 | 100.1 | 2026-10-21 | 2026-10-21 | 0 | Wei kefang | MATERIAL REQUISITION FOR TOPSIDES HIGH STRENGTHHOT-ROLLED STEEL SECTIONS (SHAPE STR) MATERIAL REQUISITION FOR TOPSIDES SECONDARY ANDTERTIARY HOT-ROLLED STEEL
| MM-ZTK-1F-GEN-STR-MR-1011 | RFQ-STR-002 | Topside Primary Steel-Beam |  |  | 5-1 | STR | Y | L2 | LA |  | ZH | F | [12 empty] | 2026-08-21 | 2026-09-04 |  | 2026-09-09 | 2026-09-11 | 2026-10-09 | 2026-10-16 | 2026-10-21 | 2026-10-24 | 2026-11-10 |  |  | 2026-10-21
| MM-ZTK-1F-GEN-STR-MR-1011 | RFQ-STR-002 | Topside Primary Steel-Beam |  |  | 5-1 | STR | Y | L2 | LA |  | ZH | A | 2026-04-24 | 2026-05-23 | 2026-05-25 | 2026-06-22 | 2026-06-22 | 2026-06-24 | 2026-07-10 | 2026-07-13 |  | 2026-10-28: 2026-07-14; 2026-10-30: 2026-07-15; 2026-11-06: 2026-06-29
79 | MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-003 | Topside Primary Steel- Seamless |  |  | 5-1 | STR | Y | L2 | LA |  | ZH | P | 2026-04-22 | 2026-05-29 | 2026-06-20 | 2026-06-23 | 2026-06-26 | 2026-06-29 | 2026-07-02 | 2026-07-05 |  | 2026-07-13 | 2026-07-15 | 2026-07-24 | 2026-08-21 | 2026-09-04 |  | 2026-09-09 | 2026-09-11 | 2026-10-09 02:24 | 2026-10-16 02:24 | 2026-10-21 02:24 | 2026-10-24 | 2026-11-10 02:24 | 14.3 | 100.1 | 2026-10-21 | 2026-10-27 | 46221.9 | Wei Chunfang | MATERIAL REOUISITION FOR TOPSIDES HIGH STRENGTHSTRTUBULAR STEEL MATERIAL REQUISITION FOR TOPSIDES SECONDARY ANDTERTIARY TUBULAR STEEL
| MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-003 | Topside Primary Steel- Seamless |  |  | 5-1 | STR | Y | L2 | LA |  | ZH | F | [12 empty] | 2026-08-21 | 2026-09-04 |  | 2026-09-09 | 2026-09-11 | 2026-10-09 02:24 | 2026-10-16 02:24 | 2026-10-21 02:24 | 2026-10-24 | 2026-11-10 02:24 |  |  | 1900-04-09 02:24
| MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-003 | Topside Primary Steel- Seamless |  |  | 5-1 | STR | Y | L2 | LA |  | ZH | A | 2026-04-24 | 2026-05-04 | 2026-05-15 | 2026-06-22 | 2026-06-22 | 2026-06-24 | 2026-07-03 | 2026-07-10 |  | 2026-10-28: 2026-07-10; 2026-10-30: 2026-07-10; 2026-11-06: 2026-07-16
80 | MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-016 | Topside Primary Steel- Tubular |  |  | 5-1 | STR | Y | L2 | LA |  | ZH | P | 2026-04-22 | 2026-07-15 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-08-05 | 2026-08-14 | 2026-08-30 |  | 2026-09-08 | 2026-09-10 | 2026-09-14 | 2026-09-17 | 2026-10-10 | 2026-09-19 | 2026-09-20 | 2026-09-24 | 2026-10-21 | 2026-10-28 | 2026-11-02 | 2026-11-05 | 2026-12-02 | 7.8571 | 55 | 2026-11-02 | 2026-11-25 | 23 | Tang Jiahe
| MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-016 | Topside Primary Steel- Tubular |  |  | 5-1 | STR | Y | L2 | LA |  | ZH | F | [7 empty] | 2026-08-30 |  | 2026-09-08 | 2026-09-10 | 2026-09-14 | 2026-09-17 | 2026-10-10 | 2026-09-19 | 2026-09-20 | 2026-09-24 | 2026-10-21 | 2026-10-28 | 2026-11-02 | 2026-11-05 | 2026-12-02 |  |  | 2026-11-02
| MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-016 | Topside Primary Steel- Tubular |  |  | 5-1 | STR | Y | L2 | LA |  | ZH | A | 2026-04-24 | 2026-05-04 | 2026-05-15 | 2026-06-10 | 2026-06-10 | 2026-06-12 | 2026-07-24
81 | MM-ZTK-1F-GEN-STR-MR-1002 | RFQ-STR-004 | Topside Secondary Steel(W) |  |  | 5-4 | STR | N | L3 | LA | Laigang | ZH | P | 2026-04-28 | 2026-04-29 | 2026-05-08 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-07-28 | 2026-08-11 |  | 2026-08-07 | 2026-08-11 | 2026-08-18 | 2026-09-15 | 2026-09-29 |  | 2026-10-04 | 2026-10-06 | 2026-11-03 02:24 | 2026-11-10 02:24 | 2026-11-15 02:24 | 2026-11-18 02:24 | 2026-12-15 02:24 | 14.3 | 100.1 | 2026-11-15 02:24 | 2026-11-25 | 46250.9 | Chen Yang
| MM-ZTK-1F-GEN-STR-MR-1002 | RFQ-STR-004 | Topside Secondary Steel(W) |  |  | 5-4 | STR | N | L3 | LA |  | ZH | F | [12 empty] | 2026-09-15 | 2026-09-29 |  | 2026-10-04 | 2026-10-06 | 2026-11-03 02:24 | 2026-11-10 02:24 | 2026-11-15 02:24 | 2026-11-18 02:24 | 2026-12-15 02:24 |  |  | 1900-04-09 02:24
| MM-ZTK-1F-GEN-STR-MR-1002 | RFQ-STR-004 | Topside Secondary Steel(W) |  |  | 5-4 | STR | N | L3 | LA |  | ZH | A | 2026-04-24 | 2026-05-23 | 2026-05-25 | 2026-06-08 | 2026-06-08 | 2026-06-12 | 2026-07-10 | 2026-07-14 |  | 2026-10-28: 2026-07-14; 2026-10-30: 2026-07-14; 2026-11-06: 2026-06-29
82 | MM-ZTK-1F-GEN-STR-MR-1002 | RFQ-STR-004 | Topside Secondary Steel(L,C) |  |  | 5-4 | STR | N | L3 | LA |  | ZH | P | 2026-04-28 | 2026-04-29 | 2026-05-08 | 2026-07-19 | 2026-07-19 | 2026-07-25 | 2026-08-02 | 2026-08-16 |  | 2026-08-16 | 2026-08-17 | 2026-08-28 | 2026-08-25 | 2026-09-22 | 2026-10-06 | 2026-10-11 | 2026-10-13 | 2026-11-12 02:24 | 2026-11-19 02:24 | 2026-11-24 02:24 | 2026-11-22 02:24 | 2026-12-24 02:24 | 14.3 | 100.1 | 2026-11-24 02:24 | 2026-12-02 | -10.1 | Chen Yang
| MM-ZTK-1F-GEN-STR-MR-1002 | RFQ-STR-004 | Topside Secondary Steel(L,C) |  |  | 5-4 | STR | N | L3 | LA |  | ZH | F | 2026-07-15 | [5 empty] | 2026-08-24 | 2026-09-03 |  | 2026-09-03 | 2026-09-04 | 2026-09-11 | 2026-09-28 | 2026-10-12 | 2026-10-06 | 2026-10-11 | 2026-10-13 | 2026-11-12 02:24 | 2026-11-19 02:24 | 2026-11-24 02:24 | 2026-11-22 02:24 | 2026-12-24 02:24 |  |  | 2026-12-12 02:24
| MM-ZTK-1F-GEN-STR-MR-1002 | RFQ-STR-004 | Topside Secondary Steel(L,C) |  |  | 5-4 | STR | N | L3 | LA |  | ZH | A |  | 2026-05-23 | 2026-05-25 | 2026-07-03 | 2026-07-03 | 2026-07-24
83 | MM-ZTK-1F-GEN-STR-MR-1022 | RFQ-STR-005 | Topside Tertiary Steel |  |  | 5-4 | STR | N | L4 | LA |  | ZH | P | 2026-05-26 | 2026-05-27 | 2026-06-05 | 2026-07-24 | 2026-07-24 | 2026-07-30 | 2026-08-22 | 2026-09-09 |  | 2026-09-17 | 2026-09-19 | 2026-09-26 | 2026-10-24 | 2026-11-07 |  | 1900-01-29 | 2026-11-09 | 2026-12-06 00:29 | 2026-12-11 00:29 | 2026-12-16 00:29 | 2026-12-19 00:29 | 2027-01-15 00:29 | 12.86 | 90.02 | 2026-12-16 00:29 | 2026-12-21 | 4.98 | Chen Yang
| MM-ZTK-1F-GEN-STR-MR-1022 | RFQ-STR-005 | Topside Tertiary Steel |  |  | 5-4 | STR | N | L4 | LA |  | ZH | F | 2026-07-20 | [5 empty] | 2026-08-24 | 2026-09-09 |  | 2026-09-17 | 2026-09-19 | 2026-09-26 | 2026-10-24 | 2026-11-07 |  | 1900-01-29 | 2026-11-09 | 2026-12-06 00:29 | 2026-12-11 00:29 | 2026-12-16 00:29 | 2026-12-19 00:29 | 2027-01-15 00:29 |  |  | 2026-12-16 00:29
| MM-ZTK-1F-GEN-STR-MR-1022 | RFQ-STR-005 | Topside Tertiary Steel |  |  | 5-4 | STR | N | L4 | LA |  | ZH | A |  | 2026-05-29 | 2026-06-01 | 2026-07-03 | 2026-07-03 | 2026-07-24
84 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-1 | ZWP21 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD | ZWP 21-Place order 4323T | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-06-27 | 2026-06-29 | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 2026-09-09 | 8.5 | 59.5 | 2026-08-10 | 2026-08-16 | 6 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-1 | ZWP21 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-04-29: 2026-09-09 |  |  | 2026-08-10
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-1 | ZWP21 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10
85 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-2 | ZWP21 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-07-18 | 2026-07-11 | 2026-08-10 | 2026-08-17 | 2026-08-22 | 2026-08-25 | 2026-09-21 | 8.5 | 59.5 | 2026-08-22 | 2026-08-28 | 6 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-2 | ZWP21 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-04-02: 2026-08-25; 2027-04-29: 2026-09-21 |  |  | 2026-08-22
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-2 | ZWP21 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-10 | 2026-08-10 | 2026-08-10
86 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-3 | ZWP21 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-08-08 | 2026-07-23 | 2026-08-22 | 2026-08-29 | 2026-09-03 | 2026-09-06 | 2026-10-03 | 8.5 | 59.5 | 2026-09-03 | 2026-09-09 | 6 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-3 | ZWP21 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-04-02: 2026-09-06; 2027-04-29: 2026-10-03 |  |  | 2026-09-03
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-3 | ZWP21 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-10 | 2026-08-10 | 2026-08-10
87 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-4 | ZWP21 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-08-29 | 2026-08-04 | 2026-09-03 | 2026-09-10 | 2026-09-15 | 2026-09-18 | 2026-10-15 | 8.5 | 59.5 | 2026-09-15 | 2026-09-21 | 6 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-4 | ZWP21 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-02-18: 2026-09-03; 2027-02-28: 2026-09-10; 2027-03-30: 2026-09-15; 2027-04-02: 2026-09-18; 2027-04-29: 2026-10-15 |  |  | 2026-09-15
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-4 | ZWP21 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26
88 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-5 | ZWP21 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-07-04 | 2026-08-16 | 2026-09-15 | 2026-09-22 | 2026-09-27 | 2026-09-30 | 2026-10-27 | 8.5 | 59.5 | 2026-09-27 | 2026-10-03 | 6 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-5 | ZWP21 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-02-18: 2026-09-15; 2027-02-28: 2026-09-22; 2027-03-30: 2026-09-27; 2027-04-02: 2026-09-30; 2027-04-29: 2026-10-27 |  |  | 2026-09-27
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-5 | ZWP21 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-07-03 | 2026-07-03 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-07-04 | 2026-07-04 | 2026-07-17
89 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-6 | ZWP21 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-10-10 | 2026-08-28 | 2026-09-27 | 2026-10-04 | 2026-10-09 | 2026-10-12 | 2026-11-08 | 8.5 | 59.5 | 2026-10-09 | 2026-10-15 | 6 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-6 | ZWP21 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-03-30: 2026-10-09; 2027-04-02: 2026-10-12; 2027-04-29: 2026-11-08 |  |  | 2026-10-09
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-6 | ZWP21 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-07 | 2026-08-07
90 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-0067 | ZWP21 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-10-31 | 2026-09-09 | 2026-10-09 | 2026-10-16 | 2026-10-21 | 2026-10-24 | 2026-11-20 | 8.5 | 59.5 | 2026-10-21 | 2026-10-27 | 6 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-7 | ZWP21 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-03-30: 2026-10-21; 2027-04-02: 2026-10-24; 2027-04-29: 2026-11-20 |  |  | 2026-10-21
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-7 | ZWP21 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-10 | 2026-08-10
91 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-1 | ZWP23 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD | ZWP 21-Total 4421.8T | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-08-22 | 2026-08-28 | 2026-08-30 | 2026-08-30 | 2026-09-29 | 8.5 | 59.5 | 2026-08-30 | 2026-08-31 | 21 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-1 | ZWP23 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-02-18: 2026-08-22; 2027-02-28: 2026-08-28; 2027-03-30: 2026-08-30; 2027-04-02: 2026-08-30; 2027-04-29: 2026-09-29 |  |  | 2026-08-10
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-1 | ZWP23 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-09 | 2026-07-09 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-07-24 | 2026-07-24 | 2026-07-24
92 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-2 | ZWP23 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-08-20 | 2026-08-20 | 2026-09-12 | 2026-09-18 | 2026-09-20 | 2026-09-20 | 2026-10-20 | 8.5 | 59.5 | 2026-09-20 | 2026-09-21 | 30 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-2 | ZWP23 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-01-13: 2026-08-20; 2027-01-15: 2026-08-20; 2027-02-18: 2026-09-12; 2027-02-28: 2026-09-18; 2027-03-30: 2026-09-20; 2027-04-02: 2026-09-20; 2027-04-29: 2026-10-20 |  |  | 2026-08-22
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-2 | ZWP23 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-10-28: 2026-07-30; 2026-10-30: 2026-07-30; 2026-11-06: 2026-04-20; 2026-11-27: 2026-06-20; 2026-12-14: 2026-06-20; 2027-01-13: 2026-07-30
93 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-3 | ZWP23 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-09-10 | 2026-09-10 | 2026-10-03 | 2026-10-09 | 2026-10-11 | 2026-10-11 | 2026-11-10 | 8.5 | 59.5 | 2026-10-11 | 2026-10-12 | 39 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-3 | ZWP23 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-02-18: 2026-10-03; 2027-02-28: 2026-10-09; 2027-03-30: 2026-10-11; 2027-04-02: 2026-10-11; 2027-04-29: 2026-11-10 |  |  | 2026-09-03
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-3 | ZWP23 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-09 | 2026-07-09 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-07-24 | 2026-07-24 | 2026-07-24
94 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-4 | ZWP23 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-10-01 | 2026-10-01 | 2026-10-24 | 2026-10-30 | 2026-11-01 | 2026-11-01 | 2026-12-01 | 8.5 | 59.5 | 2026-11-01 | 2026-11-02 | 48 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-4 | ZWP23 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-02-18: 2026-10-24; 2027-02-28: 2026-10-30; 2027-03-30: 2026-11-01; 2027-04-02: 2026-11-01; 2027-04-29: 2026-12-01 |  |  | 2026-09-15
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-4 | ZWP23 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-09 | 2026-07-09 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-07-24 | 2026-07-24 | 2026-07-24
95 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-5 | ZWP23 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-10-22 | 2026-10-22 | 2026-11-14 | 2026-11-20 | 2026-11-22 | 2026-11-22 | 2026-12-22 | 8.5 | 59.5 | 2026-11-22 | 2026-11-23 | 57 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-5 | ZWP23 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-02-18: 2026-11-14; 2027-02-28: 2026-11-20; 2027-03-30: 2026-11-22; 2027-04-02: 2026-11-22; 2027-04-29: 2026-12-22 |  |  | 2026-09-27
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-5 | ZWP23 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-09 | 2026-07-09 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-07-24 | 2026-07-24 | 2026-07-24
96 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-6 | ZWP23 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-11-12 | 2026-11-12 | 2026-12-05 | 2026-12-11 | 2026-12-13 | 2026-12-13 | 2027-01-12 | 8.5 | 59.5 | 2026-12-13 | 2026-12-14 | 66 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-6 | ZWP23 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-02-18: 2026-12-05; 2027-02-28: 2026-12-11; 2027-03-30: 2026-12-13; 2027-04-02: 2026-12-13; 2027-04-29: 2027-01-12 |  |  | 2026-10-09
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-6 | ZWP23 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-09 | 2026-07-09 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-07-24 | 2026-07-24 | 2026-07-24
97 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-0067 | ZWP23 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-12-03 | 2026-12-03 | 2026-12-03 | 2026-12-26 | 2027-01-01 | 2027-01-03 | 2027-01-03 | 2027-02-02 | 8.5 | 59.5 | 2027-01-03 | 2027-01-04 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-7 | ZWP23 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2027-02-18: 2026-12-26; 2027-02-28: 2027-01-01; 2027-03-30: 2027-01-03; 2027-04-02: 2027-01-03; 2027-04-29: 2027-02-02 |  |  | 2027-01-03
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-7 | ZWP23 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-14 | 2026-07-14 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-08-10 | 2026-08-10 | 2026-08-10
98 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-1 | ZWP22 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-09-03 | 2026-09-03 | 2026-09-03 | 2026-09-26 | 2026-10-02 | 2026-10-04 | 2026-10-04 | 2026-11-03 | 8.5 | 59.5 | 2026-10-04 | 2026-10-05 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-1 | ZWP22 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2026-08-14 | 2026-08-14 |  | 2026-08-18 | 2026-08-03 | 2026-09-03 | 2026-09-03 | 2026-09-03 | 2026-09-26 | 2026-10-02 | 2026-10-04 | 2026-10-04 | 2026-11-03 |  |  | 2026-10-04
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-1 | ZWP22 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  | 2026-11-06: 2026-04-20
99 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-2 | ZWP22 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-10-17 | 2026-10-23 | 2026-10-25 | 2026-10-25 | 2026-11-24 | 8.5 | 59.5 | 2026-10-25 | 2026-10-26 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-2 | ZWP22 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2026-08-14 | 2026-08-14 |  |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-10-17 | 2026-10-23 | 2026-10-25 | 2026-10-25 | 2026-11-24 |  |  | 2026-10-25
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-2 | ZWP22 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  |  |  | 2026-04-20 | 2026-08-04 | 2026-08-04
100 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-3 | ZWP22 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-11-15 | 2026-12-15 | 8.5 | 59.5 | 2026-11-15 | 2026-11-16 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-3 | ZWP22 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [14 empty] | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-11-15 | 2026-12-15 |  |  | 2026-11-15
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-3 | ZWP22 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  | 2026-08-03 | 2026-08-03 | 2026-04-20 | 2026-08-04 | 2026-08-04
101 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-4 | ZWP22 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-28 | 2026-12-04 | 2026-12-06 | 2026-12-06 | 2027-01-05 | 8.5 | 59.5 | 2026-12-06 | 2026-12-07 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-4 | ZWP22 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [14 empty] | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-28 | 2026-12-04 | 2026-12-06 | 2026-12-06 | 2027-01-05 |  |  | 2026-12-06
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-4 | ZWP22 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  | 2026-08-03 | 2026-08-03 | 2026-04-20 | 2026-08-04 | 2026-08-04
102 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-5 | ZWP22 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-12-19 | 2026-12-25 | 2026-12-27 | 2026-12-27 | 2027-01-26 | 8.5 | 59.5 | 2026-12-27 | 2026-12-28 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-5 | ZWP22 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F |  | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | [8 empty] | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-12-19 | 2026-12-25 | 2026-12-27 | 2026-12-27 | 2027-01-26 |  |  | 2026-12-27
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-5 | ZWP22 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  | 2026-08-03 | 2026-08-03 | 2026-04-20 | 2026-08-10 | 2026-08-10
103 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-6 | ZWP22 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2027-01-09 | 2027-01-15 | 2027-01-17 | 2027-01-17 | 2027-02-16 | 8.5 | 59.5 | 2027-01-17 | 2027-01-18 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-6 | ZWP22 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [12 empty] | 2026-08-18 | 2026-08-03 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2027-01-09 | 2027-01-15 | 2027-01-17 | 2027-01-17 | 2027-02-16 |  |  | 2027-01-17
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-6 | ZWP22 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  | 2026-08-03 | 2026-08-03 | 2026-04-20
104 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-0067 | ZWP22 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2027-01-09 | 2027-01-15 | 2027-01-17 | 2027-01-17 | 2027-02-16 | 8.5 | 59.5 | 2027-01-17 | 2027-02-08 | 22 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-7 | ZWP22 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2026-08-14 | 2026-08-14 |  | 2026-08-18 | 2026-08-03 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2027-01-09 | 2027-01-15 | 2027-01-17 | 2027-01-17 | 2027-02-16 |  |  | 2027-01-17
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-7 | ZWP22 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  |  |  | 2026-04-20
105 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-1 | ZWP20 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-10-11 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-11-18 | 8.5 | 59.5 | 2026-10-04 | 2026-10-20 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-1 | ZWP20 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2026-08-29 | 2026-08-29 |  | 2026-09-02 | 2026-08-18 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-10-11 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-11-18 |  |  | 2026-10-19
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-1 | ZWP20 Jacket Launch Cradle Plates+Ring Stiff Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  |  |  | 2026-04-20
106 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-2 | ZWP20 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 2026-11-01 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 2026-12-09 | 8.5 | 59.5 | 2026-11-09 | 2026-11-10 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-2 | ZWP20 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2026-08-29 | 2026-08-29 |  | 2026-09-02 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 2026-11-01 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 2026-12-09 |  |  | 2026-11-09
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-2 | ZWP20 Jacket Leg Partition/Closure Plates |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  |  |  | 2026-04-20
107 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-3 | ZWP20 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-11-22 | 2026-11-28 | 2026-11-30 | 2026-11-30 | 2026-12-30 | 8.5 | 59.5 | 2026-11-30 | 2026-12-01 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-3 | ZWP20 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [14 empty] | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-11-22 | 2026-11-28 | 2026-11-30 | 2026-11-30 | 2026-12-30 |  |  | 2026-11-30
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-3 | ZWP20 Jacket Primary Steel-Tubular TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  | 2026-07-30 | 2026-07-30 | 2026-04-20 | 2026-07-30 | 2026-07-31
108 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-4 | ZWP20 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2026-11-20 | 2026-11-20 | 2026-11-20 | 2026-12-13 | 2026-12-19 | 2026-12-21 | 2026-12-21 | 2027-01-20 | 8.5 | 59.5 | 2026-12-21 | 2026-12-22 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-4 | ZWP20 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [14 empty] | 2026-11-20 | 2026-11-20 | 2026-11-20 | 2026-12-13 | 2026-12-19 | 2026-12-21 | 2026-12-21 | 2027-01-20 |  |  | 2026-12-21
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-4 | ZWP20 Jacket Primary Steel-Tubular CONE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  | 2026-07-30 | 2026-07-30 | 2026-04-20 | 2026-07-30 | 2026-07-31
109 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-5 | ZWP20 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2026-12-11 | 2026-12-11 | 2026-12-11 | 2027-01-03 | 2027-01-09 | 2027-01-11 | 2027-01-11 | 2027-02-10 | 8.5 | 59.5 | 2027-01-11 | 2027-01-12 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-5 | ZWP20 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [14 empty] | 2026-12-11 | 2026-12-11 | 2026-12-11 | 2027-01-03 | 2027-01-09 | 2027-01-11 | 2027-01-11 | 2027-02-10 |  |  | 2027-01-11
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-5 | ZWP20 Jacket Primary Steel-Tubular JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  | 2026-07-30 | 2026-07-30 | 2026-04-20 | 2026-07-30 | 2026-07-31
110 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-6 | ZWP20 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2027-01-01 | 2027-01-01 | 2027-01-01 | 2027-01-24 | 2027-01-30 | 2027-02-01 | 2027-02-01 | 2027-03-03 | 8.5 | 59.5 | 2027-02-01 | 2027-02-02 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-6 | ZWP20 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2026-08-29 | 2026-08-29 |  | 2026-09-02 | 2026-08-18 | 2027-01-01 | 2027-01-01 | 2027-01-01 | 2027-01-24 | 2027-01-30 | 2027-02-01 | 2027-02-01 | 2027-03-03 |  |  | 2027-02-01
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-6 | ZWP20 Jacket Hydro static Ring Stiff Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  |  |  | 2026-04-20
111 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-0067 | ZWP20 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2027-01-22 | 2027-01-22 | 2027-01-22 | 2027-02-14 | 2027-02-20 | 2027-02-22 | 2027-02-22 | 2027-03-24 | 8.5 | 59.5 | 2027-02-22 | 2027-02-23 | 1 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1)
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-7 | ZWP20 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [9 empty] | 2026-08-14 | 2026-08-14 |  | 2026-09-02 | 2026-08-18 | 2027-01-22 | 2027-01-22 | 2027-01-22 | 2027-02-14 | 2027-02-20 | 2027-02-22 | 2027-02-22 | 2027-03-24 |  |  | 2027-02-22
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-7 | ZWP20 Jacket Piles Sleeve Plate |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  |  |  | 2026-04-20
112 |  | RFQ-STR-006-8 | Jacket Primary Steel-Piles-1st |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-09-21 | 2026-09-30 | 2026-10-12 | 2026-10-15 | 2026-10-15 | 2026-10-22 | 2026-10-27 | 2026-11-01 |  | 2026-11-07 | 2026-11-11 | 2026-11-18 | 2026-12-02 | 2026-12-17 | 2026-12-22 | 2026-12-25 | 2026-12-28 | 2027-01-26 | 2027-01-31 | 2027-02-05 | 2027-02-08 | 2027-03-07 | 8.5 | 59.5 | 2027-02-05 | 2027-02-17 | 12 | Huang liudong
|  | RFQ-STR-006-8 | Jacket Primary Steel-Piles-1st |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | 2026-09-21 | 2026-09-30 | 2026-10-12 | 2026-10-15 | 2026-10-15 | 2026-10-22 | 2026-10-27 | 2026-11-01 |  | 2026-11-07 | 2026-11-11 | 2026-11-18 | 2026-12-02 | 2026-12-17 | 2026-12-22 | 2026-12-25 | 2026-12-28 | 2027-01-26 | 2027-01-31 | 2027-02-05 | 2027-02-08 | 2027-03-07 |  |  | 2027-02-05
|  | RFQ-STR-006-8 | Jacket Primary Steel-Piles-1st |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A
113 |  | RFQ-STR-006-9 | Jacket Primary Steel-Piles-2nd |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-09-21 | 2026-10-29 | 2026-11-10 | 2026-11-13 | 2026-11-13 | 2026-11-20 | 2026-11-25 | 2026-11-30 |  | 2026-12-07 | 2026-12-11 | 2026-12-18 | 2027-01-01 | 2027-01-16 | 2027-01-21 | 2027-01-24 | 2027-01-27 | 2027-02-25 | 2027-03-02 | 2027-03-07 | 2027-03-10 | 2027-04-06 | 8.5 | 59.5 | 2027-03-07 | 2027-03-17 | 40.5 | Huang liudong
|  | RFQ-STR-006-9 | Jacket Primary Steel-Piles-2nd |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | 2026-09-21 | 2026-10-29 | 2026-11-10 | 2026-11-13 | 2026-11-13 | 2026-11-20 | 2026-11-25 | 2026-11-30 |  | 2026-12-07 | 2026-12-11 | 2026-12-18 | 2027-01-01 | 2027-01-16 | 2027-01-21 | 2027-01-24 | 2027-01-27 | 2027-02-25 | 2027-03-02 | 2027-03-07 | 2027-03-10 | 2027-04-06 |  |  | 2027-02-04 12:00
|  | RFQ-STR-006-9 | Jacket Primary Steel-Piles-2nd |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A
114 |  | RFQ-STR-006-10 | Jacket Primary Steel-Piles-3rd |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-09-21 | 2026-11-27 | 2026-12-09 | 2026-12-12 | 2026-12-12 | 2026-12-19 | 2026-12-24 | 2026-12-29 |  | 2027-01-06 | 2027-01-10 | 2027-01-17 | 2027-01-31 | 2027-02-15 | 2027-02-20 | 2027-02-23 | 2027-02-26 | 2027-03-27 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 8.5 | 59.5 | 2027-03-06 12:00 | 2027-04-17 | 41.5 | Huang liudong
|  | RFQ-STR-006-10 | Jacket Primary Steel-Piles-3rd |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | 2026-09-21 | 2026-11-27 | 2026-12-09 | 2026-12-12 | 2026-12-12 | 2026-12-19 | 2026-12-24 | 2026-12-29 |  | 2027-01-06 | 2027-01-10 | 2027-01-17 | 2027-01-31 | 2027-02-15 | 2027-02-20 | 2027-02-23 | 2027-02-26 | 2027-03-27 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-03-06 12:00
|  | RFQ-STR-006-10 | Jacket Primary Steel-Piles-3rd |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A
115 | MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-1 | Jacket Primary Steel-Tubular-JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-05-12 | 2026-06-15 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-06 | 2026-07-15 | 2026-07-31 |  | 2026-08-01 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-09-10 | 2026-08-20 | 2026-08-21 | 2026-08-25 | 2026-10-03 | 2026-10-10 | 2026-10-15 | 2026-10-18 | 2026-11-14 | 4 | 28 | 2026-10-15 | 2026-10-21 | 6 | Huang liudong | 2-Apr-26: Received ZWP20 /21/22/23 : IFR(2026/4/2) 10-Apr-26:Received MM-ZTK-1F-GEN-STR-MR-1001 (IFR) MM-ZTK-1F-GEN-STR-MR-1011 (IFR) Topside High StrengthTubular steel
| MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-1 | Jacket Primary Steel-Tubular-JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [11 empty] | 2026-08-09 | 2026-08-16 | 2026-09-10 | 2026-08-20 | 2026-08-21 | 2026-08-25 | 2026-10-03 | 2026-10-10 | 2026-10-15 | 2026-10-18 | 2026-11-14 |  |  | 2026-10-15
| MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-1 | Jacket Primary Steel-Tubular-JCOE |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-06-10 | 2026-05-04 | 2026-05-15 | 2026-06-10 | 2026-06-10 | 2026-06-12 | 2026-07-24 | 2026-08-06 |  | 2027-01-06: 2026-08-06; 2027-01-10: 2026-08-06
116 | MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-2 | Jacket Primary Steel-Tubular-TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | P | 2026-05-12 | 2026-06-15 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-06 | 2026-07-15 | 2026-07-31 |  | 2026-08-01 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-09-10 | 2026-08-20 | 2026-08-21 | 2026-08-25 | 2026-09-21 | 2026-09-28 | 2026-10-03 | 2026-10-06 | 2026-11-02 | 4 | 28 | 2026-10-03 | 2026-10-09 | 6 | Huang liudong | 2-Apr-26: Received ZWP20 /21/22/23 : IFR(2026/4/2) 10-Apr-26:Received MM-ZTK-1F-GEN-STR-MR-1001 (IFR) MM-ZTK-1F-GEN-STR-MR-1011 (IFR) Topside High StrengthTubular steel
| MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-2 | Jacket Primary Steel-Tubular-TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | F | [11 empty] | 2026-08-09 | 2026-08-16 | 2026-09-10 | 2026-08-20 | 2026-08-21 | 2026-08-25 | 2026-09-21 | 2026-09-28 | 2026-10-03 | 2026-10-06 | 2026-11-02 |  |  | 2026-10-03
| MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-2 | Jacket Primary Steel-Tubular-TRB |  |  | 5-4 | STR | Y | L2 | LD |  | ZH | A | 2026-06-10 | 2026-05-04 | 2026-05-15 | 2026-06-10 | 2026-06-10 | 2026-06-12 | 2026-07-24 | 2026-08-06 |  | 2027-01-06: 2026-08-06; 2027-01-10: 2026-08-06
117 |  | RFQ-STR-008 | Jacket Miscellaneous Steel (boatlandings, ACCESS ladder, Riser Clamps, Casing Guides etc) |  |  | 5-4 | STR | N | L4 | LD |  | ZH | P | 2026-07-10 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-18 | 2026-07-25 | 2026-08-05 | 2026-08-07 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-04 | 2026-11-02 00:29 | 2026-11-07 00:29 | 2026-11-12 00:29 | 2026-11-15 00:29 | 2026-12-02 00:29 | 12.8571 | 90 | 2026-11-12 00:29 | 2026-11-14 | -45 | Kuang Yuanna | MM-ZTK-1F-ZWPX-STR-DWG-2231 JACKET - BOATLANDING ARRANGEMENT A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2232 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2233 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2234 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2235 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2236 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2237 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2238 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWP22-STR-DWG-2241 ZWP22 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP23-STR-DWG-2241 ZWP23 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP21-STR-DWG-2241 ZWP21 JACKET - RISER PROTECTOR ZWP21 JACKET - CASING GUIDE DETAILS MM-ZTK-1F-ZWP21-STR-DWG-2301
|  | RFQ-STR-008 | Jacket Miscellaneous Steel (boatlandings, ACCESS ladder, Riser Clamps, Casing Guides etc) |  |  | 5-4 | STR | N | L4 | LD |  | ZH | F | 2026-08-20 |  | 2026-07-14 | 2026-08-21 | 2026-08-21 | 2026-08-28 | 2026-09-08 | 2026-09-22 |  | 2026-09-30 | 2026-10-09 | 2026-10-09 | 2026-10-23 | 2026-11-06 | 2026-12-06 | 2026-12-06 | 2026-12-06 | 2026-12-19 | 2026-12-24 | 2026-12-29 | 2027-01-05 | 2027-01-28 |  |  | 2026-12-29
|  | RFQ-STR-008 | Jacket Miscellaneous Steel (boatlandings, ACCESS ladder, Riser Clamps, Casing Guides etc) |  |  | 5-4 | STR | N | L4 | LD |  | ZH | A |  | 2026-07-10
118 | MM-ZTK-1F-GEN-STR-MR-0004 | RFQ-STR-009 | JKT Anode |  |  | 5-4 | STR | N | L4 | LA |  | ZH | P | 2026-05-26 | 2026-05-27 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-25 | 2026-07-20 | 2026-08-05 |  | 2026-08-18 | 2026-08-20 | 2026-08-27 | 2026-09-10 | 2026-09-24 | 2026-09-10 | 2026-09-13 | 2026-09-15 | 2026-10-09 12:00 | 2026-10-12 12:00 | 2026-10-16 12:00 | 2026-10-19 12:00 | 2026-11-05 12:00 | 8.5 | 59.5 | 2026-10-16 12:00 | 2026-10-27 | 8.5 | Zhang Jianwei | 2026.5.9 MR to yard
| MM-ZTK-1F-GEN-STR-MR-0004 | RFQ-STR-009 | JKT Anode |  |  | 5-4 | STR | N | L4 | LA |  | ZH | F | [9 empty] | 2026-08-20 | 2026-08-24 | 2026-08-31 | 2026-09-10 | 2026-09-24 | 2026-09-10 | 2026-09-13 | 2026-09-15 | 2026-10-09 12:00 | 2026-10-12 12:00 | 2026-10-16 12:00 | 2026-10-19 12:00 | 2026-11-05 12:00 |  |  | 2026-10-18 12:00
| MM-ZTK-1F-GEN-STR-MR-0004 | RFQ-STR-009 | JKT Anode |  |  | 5-4 | STR | N | L4 | LA |  | ZH | A | 2026-05-22 | 2026-05-04 | 2026-05-15 | 2026-06-08 | 2026-06-08 | 2026-06-23 | 2026-07-27 | 2026-07-31 | Waiting for TBE APPR
119 | MM-ZTK-1F-GEN-STR-MR-0001 MM-ZTK-1F-GEN-STR-MR-0002 | RFQ-STR-010 | Gripper, Packer and Diaphragm |  |  | 5-4 | STR | N | L4 | LA | OIL STATES | SH | P | 2026-05-11 | 2026-05-12 | 2026-05-19 | 2026-05-20 | 2026-05-27 | 2026-06-10 | 2026-07-08 | 2026-07-13 |  | 2026-07-27 | 2026-07-29 | 2026-08-05 | 2026-09-02 | 2026-09-16 | 2026-10-16 | 2026-10-16 | 2026-10-18 | 2027-01-29 | 2027-02-13 | 2027-03-15 | 2027-03-18 | 2027-04-04 | 33 | 231 | 2027-03-15 | 2027-03-23 | 8 | Liu Lei | [14 empty] | DDP 24 weeks after PO
| MM-ZTK-1F-GEN-STR-MR-0001 MM-ZTK-1F-GEN-STR-MR-0002 | RFQ-STR-010 | Gripper, Packer and Diaphragm |  |  | 5-4 | STR | N | L4 | LA | ZM169-WP1-PO-STR-001 | SH | F | [9 empty] | 2026-08-17 | 2026-08-19 |  |  | 2026-08-26 | 2026-09-25 | 2026-09-25 | 2026-09-27 | 2027-02-05 | 2027-02-20 | 2027-03-22 | 2027-03-18 | 2027-04-11 | 31 | 217 | 2027-03-22
| MM-ZTK-1F-GEN-STR-MR-0001 MM-ZTK-1F-GEN-STR-MR-0002 | RFQ-STR-010 | Gripper, Packer and Diaphragm |  |  | 5-4 | STR | N | L4 | LA |  | SH | A | 2026-05-22 | 2026-05-11 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-06-12 | 2026-07-17 | 2026-07-24 | 2026-08-04 | 2026-10-09: 2026-08-11; 2026-10-23: 2026-08-11 | 33 | 231 | 2027-03-23
|  | RFQ-STR-011 | Grouting System |  |  | 5-4 | STR | N | L3 | LA | ruputure disc and check valve combine with Gripper | ZH | P | 2026-05-11 | 2026-05-10 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-06-05 | 2026-06-30 | 2026-07-14 |  | 2026-07-27 | 2026-07-29 | 2026-08-05 | 2026-09-02 | 2026-09-16 | 2026-10-08 | 2026-10-08 | 2026-10-10 | 2027-02-28 | 2027-03-05 | 2027-03-15 | 2027-03-18 | 2027-04-04 | 33 | 231 | 2027-03-15 | 2027-03-25 | 10 | Zhang Xiaorui | 2026.6.4 MR to yard 2026.6.4 short vendor list to CPY approval 2026.6.9 Received comments from CPY. Not approved. 2026.6.11 Short bidder list is approved
|  | RFQ-STR-011 | Grouting System |  |  | 5-4 | STR | N | L3 | LA | grouting pipes combine with seamless pipes | ZH | F | [5 empty] | 2026-06-22 | 2026-07-15 | 2026-07-31 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2027-03-17 | 2027-03-22 | 2027-04-01 | 2027-03-18 | 2027-04-21 |  |  | 2027-04-01
|  | RFQ-STR-011 | Grouting System |  |  | 5-4 | STR | N | L3 | LA |  | ZH | A | 2026-06-11 | 2026-06-04 | 2026-06-11 | 2026-06-11 | 2026-06-11
120 |  | RFQ-STR-012 | Flooding and Venting system |  |  | 5-4 | STR | N | L3 | LA | COOEC | ZH | P | 2026-05-11 | 2026-05-10 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-06-05 | 2026-06-30 | 2026-07-14 |  | 2026-07-27 | 2026-07-29 | 2026-08-05 | 2026-09-02 | 2026-09-16 | 2026-10-08 | 2026-10-08 | 2026-10-10 | 2027-02-28 | 2027-03-05 | 2027-03-15 | 2027-03-18 | 2027-04-04 | 33 | 231 | 2027-03-15 | 2027-03-23 | -17 | Zhang Xiaorui | 2026.6.4 MR to yard 2026.6.4 short vendor list to CPY approval 2026.6.9 Received comments from CPY. Not approved. 2026.6.11 Short bidder list is approved | [11 empty] | Bidder1 | DDP: 38 weeks after PO
|  | RFQ-STR-012 | Flooding and Venting system |  |  | 5-4 | STR | N | L3 | LA |  | ZH | F | [8 empty] | 2026-08-18 | 2026-08-21 | 2026-08-25 | 2026-09-01 | 2026-09-30 | 2026-10-15 | 2026-11-06 | 2026-11-06 | 2026-11-08 | 2027-03-25 | 2027-03-30 | 2027-04-09 | 2027-03-18 | 2027-04-29 | 28 | 196 | 2027-04-09
|  | RFQ-STR-012 | Flooding and Venting system |  |  | 5-4 | STR | N | L3 | LA |  | ZH | A | 2026-06-11 | 2026-06-04 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-28 | 2026-07-15 | 2026-07-30 | Waiting for TBE APPR
121 | MM-ZTK-1F-GEN-STR-MR-0005 | RFQ-STR-013 | Timber for Launch cradle |  |  | 5-4 | STR | N | L3 | LA | Shanghai Hongyu | ZH | P | 2026-04-22 | 2026-04-23 | 2026-04-30 | 2026-05-04 | 2026-05-11 | 2026-05-25 | 2026-06-24 | 2026-06-29 |  | 2026-07-13 | 2026-07-15 | 2026-07-22 | 2026-08-19 | 2026-09-02 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2026-09-30 14:24 | 2026-10-05 14:24 | 2026-10-10 14:24 | 2026-10-13 14:24 | 2026-10-30 14:24 | 12.8 | 90 | 2026-10-10 | 2026-10-13 | 46218 | Liu Bin | 2026.5.11 MR to yard 2026.6.8 Short bidder list is approved by CPY | [11 empty] | on-shore | 55-60 days
| MM-ZTK-1F-GEN-STR-MR-0005 | RFQ-STR-013 | Timber for Launch cradle |  |  | 5-4 | STR | N | L3 | LA | ZH26PO0453 | ZH | F | [13 empty] | 2026-08-21 | 2026-08-26 | 2026-08-26 | 2026-08-28 | 1900-03-20 | 1900-03-25 | 1900-03-30 | 2026-10-13 | 1900-04-19 |  |  | 1900-03-30
| MM-ZTK-1F-GEN-STR-MR-0005 | RFQ-STR-013 | Timber for Launch cradle |  |  | 5-4 | STR | N | L3 | LA |  | ZH | A | 2026-06-08 | 2026-05-11 | 2026-05-15 | 2026-06-10 | 2026-06-10 | 2026-06-16 | 2026-06-30 | 2026-07-08 |  | 2026-09-30: 2026-07-09; 2026-10-09: 2026-07-10; 2026-10-09: No need; 2026-10-23: 2026-08-06
122 |  | RFQ-STR-014 | Teflon plate for Launch cradle(Grease) |  |  | 5-4 | STR | N | L3 | LA |  | ZH | P | 2026-04-22 | 2026-04-23 | 2026-04-30 | 2026-05-04 | 2026-05-11 | 2026-05-25 | 2026-06-24 | 2026-06-29 |  | 2026-07-13 | 2026-07-15 | 2026-07-22 | 2026-08-19 | 2026-09-02 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2026-09-30 14:24 | 2026-10-05 14:24 | 2026-10-10 14:24 | 2026-10-13 14:24 | 2026-10-30 14:24 | 12.8 | 89.6 | 2026-10-10 | 2026-10-13 | 3 | Ren Dongzhi | 2026.6.11 Short bidder list sent to CPY, CPY requested to provide performace list. | [11 empty] | on-shore | from 30-45days, till 90days
|  | RFQ-STR-014 | Teflon plate for Launch cradle(Grease) |  |  | 5-4 | STR | N | L3 | LA |  | ZH | F |  | N/A | N/A | [11 empty] | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2026-09-12 | 2026-09-17 | 2026-09-22 | 2026-10-13 | 2026-10-12 |  |  | 2026-09-22 | [15 empty] | off-shore | 90-100 days
|  | RFQ-STR-014 | Teflon plate for Launch cradle(Grease) |  |  | 5-4 | STR | N | L3 | LA |  | ZH | A | 2026-06-12 | N/A | N/A | 2026-06-12 | 2026-06-12 | 2026-07-03 | 2026-07-10 | 2026-07-16 |  | 2026-09-30: 2026-08-09; 2026-10-09: 2026-08-09; 2026-10-09: No need; 2026-10-23: no need; 2026-11-06: no need
123 | MM-ZTK-1F-GEN-STR-MR-0003 | RFQ-STR-015 | Jacket Barge Bumpers and Fender |  |  | 5-4 | STR | N | L3 | LA |  | ZH | P | 2026-08-13 | 2026-08-14 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-09-09 | 2026-10-02 | 2026-10-19 |  | 2026-10-30 | 2026-11-03 | 2026-11-10 | 2026-12-08 | 2026-12-22 | 2026-12-27 | 2026-12-27 | 2026-12-29 | 2027-02-16 16:48 | 2027-02-21 16:48 | 2027-02-26 16:48 | 2027-03-01 16:48 | 2027-03-18 16:48 | 17.1 | 119.7 | 2027-02-26 16:48 | 2027-04-23 | 55.3 | Liu Bin | 2026.5.9 MR to yard
| MM-ZTK-1F-GEN-STR-MR-0003 | RFQ-STR-015 | Jacket Barge Bumpers and Fender |  |  | 5-4 | STR | N | L3 | LA |  | ZH | F | 2026-08-13 | [5 empty] | 2026-09-03 | 2026-09-17 |  | 2026-10-08 | 2026-10-12 | 2026-10-19 | 2026-11-16 | 2026-11-30 | 2026-12-05 | 2026-12-05 | 2026-12-07 | 2027-02-16 16:48 | 2027-02-21 16:48 | 2027-02-26 16:48 | 2027-03-01 16:48 | 2027-03-18 16:48 |  |  | 2027-02-04 16:48
| MM-ZTK-1F-GEN-STR-MR-0003 | RFQ-STR-015 | Jacket Barge Bumpers and Fender |  |  | 5-4 | STR | N | L3 | LA |  | ZH | A |  | 2026-05-04 | 2026-05-15 | 2026-08-03 | 2026-08-03 | 2026-08-10
124 |  | RFQ-STR-016 | Neoprene |  |  | 5-4 | STR | N | L3 | LA |  | ZH | P | 2026-08-13 | 2026-08-04 | 2026-08-04 | 2026-08-26 | 2026-08-26 | 2026-09-09 | 2026-10-02 | 2026-10-19 |  | 2026-10-30 | 2026-11-03 | 2026-11-10 | 2026-12-08 | 2026-12-22 | 2026-12-27 | 2026-12-27 | 2026-12-29 | 2027-02-16 16:48 | 2027-02-21 16:48 | 2027-02-26 16:48 | 2027-03-01 16:48 | 2027-03-18 16:48 | 17.1 | 119.7 | 2027-02-26 16:48 | 2027-04-23 | 55.3 | Liu Bin | 2026.5.9 MR to yard
|  | RFQ-STR-016 | Neoprene |  |  | 5-4 | STR | N | L3 | LA |  | ZH | F | 2026-08-20 |  |  | 2026-08-20 | 2026-08-20 | 2026-09-09 | 2026-10-02 | 2026-10-19 |  | 2026-10-30 | 2026-11-03 | 2026-11-10 | 2026-11-24 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 |  |  | 2027-02-26 16:48
|  | RFQ-STR-016 | Neoprene |  |  | 5-4 | STR | N | L3 | LA |  | ZH | A |  | 2026-08-04 | no need
Formulas:
ENG = WORKDAY([Vendor, row below], AB6, IF(AB12="China",'China Holidays'!$A2:A84,'Thai Holidays'!$A2:A65))
ENG = WORKDAY([Vendor, row below],AB6, IF(AB12="China",'China Holidays'!$A2:A84,'Thai Holidays'!$A2:A65))
Vendor = [Vendor, row above]
Vendor = [THE Worksite]-14
THE Worksite = [TJE PRC]+7
THE Worksite = [TJE PRC]
TJE QA/QC = [TJE PRC, row above]+3
TJE QA/QC = [Vendor]+2
TJE PRC = [TJE PRC, row above]+30
TJE PRC = [TJE PRC, row above]
PTTEP = [TJE PRC]
PTTEP = WORKDAY([ENG], V6, IF(V12="China",'China Holidays'!$A2:A84,'Thai Holidays'!$A2:A65))
Note on M16: Administrator: 珠海建造
Note on M19: Administrator: 珠海建造
Note on M22: Administrator: 珠海建造
Note on M31: Administrator: 珠海建造
Note on V48: Zhang Juan: 6-Aug:AWC 14-Aug: C2 submit
Note on F79: Administrator: ZWP-20:6 ZWP-21:10 ZWP-22:7 ZWP-23:9
Note on F80: Administrator: ZWP-20:6 ZWP-21:10 ZWP-22:7 ZWP-23:9
Note on M106: Administrator: 如果只是型钢板材拼接类的支撑由珠海采购。
Note on V111: Zhang Juan: 12-Aug: AWC
Note on V114: Zhang Juan: 11-Aug: AWC
Note on V117: Zhang Juan: 12-Aug: AWC
Note on U120: Zhang Juan: 5-Aug:C2
Note on U129: Zhang Juan: 2026.8.9:Pending on hot drawn for 3" pipes
Note on V180: Zhang Juan: 2-Aug;AWC
Note on V201: Zhang Juan: 6-Aug: AWC
Note on V204: Zhang Juan: 2-Aug: AWC
Note on V393: Zhang Juan: 31-Jul:AWC

## Thai Holidays
Date | Holiday Name
2025-12-05 | Father's Day
2025-12-10 | Constitution Day
2025-12-29 | New Year's Day
2025-12-30 | New Year's Day
2025-12-31 | New Year's Day
2026-01-01 | New Year's Day
2026-01-02 | New Year's Day
2026-02-12 | The Buddha Day
2026-04-06 | Kutkuri Dynasty Memorial Day
2026-04-13 | Songkran Festival
2026-04-14 | Songkran Festival
2026-04-15 | Songkran Festival
2026-04-16 | Songkran Festival
2026-04-17 | Songkran Festival
2026-05-01 | International Workers' Day
2026-05-04 | The anniversary of the King's accession to the throne
2026-06-01
2026-06-03
2026-07-28
2026-07-29
2026-08-12 | Mother's Day
2026-10-13 | The anniversary of the death of the 9th King
2026-10-23 | The anniversary of the death of the 5th King Father's Day
2026-12-07 | Father's Day
2026-12-31 | New Year's Day
2027-01-01 | New Year's Day | 佛历节日，日期为预测
2027-01-02
2027-02-21 | The Buddha Day
2027-02-22
2027-04-06 | Kutkuri Dynasty Memorial Day
2027-04-13 | Songkran Festival
2027-04-14 | Songkran Festival
2027-04-15 | Songkran Festival | 佛历节日，日期为预测
2027-05-01 | International Workers' Day
2027-05-04 | The anniversary of the King's accession to the throne
2027-05-20 | Vesak Festival
2027-06-03 | The Birthday Anniversary of the Queen
2027-08-12 | Mother's Day | 佛历节日，日期为预测
2027-10-13 | The anniversary of the death of the 9th King
2027-10-23 | The anniversary of the death of the 5th King Father's Day |  | The anniversary of the death of the 5th King Father's Day
2027-10-25
2027-12-05 | Father's Day
2027-12-06
2027-12-10 | 宪法纪念日
2027-12-31 | New Year's Day
2028-01-01 | New Year's Day | 佛历节日，日期为预测
2028-02-08 | 万佛节
2028-04-06 | 却克里王朝纪念日
2028-04-13 | Songkran Festival
2028-04-14 | Songkran Festival
2028-04-15 | Songkran Festival
2028-05-01 | International Workers' Day
2028-05-05 | The anniversary of the King's accession to the throne | 佛历节日，日期为预测
2028-06-08 | 卫塞节
2028-06-03 | The Birthday Anniversary of the Queen | 佛历节日，日期为预测
2028-07-24 | 守夏节
2028-08-12 | Mother's Day
2028-10-13 | The anniversary of the death of the 9th King
2028-10-23 | The anniversary of the death of the 5th King Father's Day
2028-12-05 | Father's Day
2028-12-10 | 宪法纪念日
2028-12-31 | New Year's Day

## China Holidays
Date | Holiday Name
2026-01-01 | New Year's Day
2026-01-02 | New Year's Day
2026-01-03 | New Year's Day
2026-02-15 | Spring Festival
2026-02-16 | Spring Festival
2026-02-17 | Spring Festival
2026-02-18 | Spring Festival
2026-02-19 | Spring Festival
2026-02-20 | Spring Festival
2026-02-21 | Spring Festival
2026-04-04 | Qingming Festival
2026-04-05 | Qingming Festival
2026-04-06 | Qingming Festival
2026-05-01 | International Workers' Day
2026-05-02 | International Workers' Day
2026-05-03 | International Workers' Day
2026-06-19 | Dragon Boat Festival
2026-06-20 | Dragon Boat Festival
2026-06-21 | Dragon Boat Festival
2026-09-25 | Middle Moon Festival
2026-09-26 | Middle Moon Festival
2026-09-27 | Middle Moon Festival
2026-10-01 | National Day
2026-10-02 | National Day
2026-10-03 | National Day
2026-10-04 | National Day
2026-10-05 | National Day
2026-10-06 | National Day
2026-10-07 | National Day
2027-01-01 | New Year's Day
2027-01-02 | New Year's Day
2027-01-03 | New Year's Day
2027-02-06 | Spring Festival
2027-02-07 | Spring Festival
2027-02-08 | Spring Festival
2027-02-09 | Spring Festival
2027-02-10 | Spring Festival
2027-02-11 | Spring Festival
2027-02-12 | Spring Festival
2027-04-03 | Qingming Festival
2027-04-04 | Qingming Festival
2027-04-05 | Qingming Festival
2027-05-01 | International Workers' Day
2027-05-02 | International Workers' Day
2027-05-03 | International Workers' Day
2027-06-11 | Dragon Boat Festival
2027-06-12 | Dragon Boat Festival
2027-06-13 | Dragon Boat Festival
2027-06-14 | Dragon Boat Festival
2027-09-15 | Middle Moon Festival
2027-10-01 | National Day
2027-10-02 | National Day
2027-10-03 | National Day
2027-10-04 | National Day
2027-10-05 | National Day
2027-10-06 | National Day
2027-10-07 | National Day
2028-01-01 | New Year's Day
2028-01-02 | New Year's Day
2028-01-03 | New Year's Day
2028-01-25 | Spring Festival
2028-01-26 | Spring Festival
2028-01-27 | Spring Festival
2028-01-28 | Spring Festival
2028-01-29 | Spring Festival
2028-01-30 | Spring Festival
2028-01-31 | Spring Festival
2028-04-04 | Qingming Festival
2028-04-05 | Qingming Festival
2028-04-06 | Qingming Festival
2028-05-01 | International Workers' Day
2028-05-02 | International Workers' Day
2028-05-03 | International Workers' Day
2028-05-31 | Dragon Boat Festival
2028-06-01 | Dragon Boat Festival
2028-06-02 | Dragon Boat Festival
2028-10-01 | National Day
2028-10-02 | National Day
2028-10-03 | National Day
2028-10-04 | National Day
2028-10-05 | National Day
2028-10-06 | National Day
2028-10-07 | National Day

## STR MR
Document No. | Document Title |  |  | Rev. | Document Status Code | Distribution Date | Approver Actual Finish | Return Status Name
MM-ZTK-1F-GEN-STR-MR-1021 | MATERIAL REQUISITION FOR TOPSIDES HIGH STRENGTH STEEL PLATES | RFQ-STR-001 | Topside Primary Steel- Plate | A1 | IFR | 20-May-2026 18:20:49 | 22-May-2026 01:16:45 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-GEN-STR-MR-1011 | MATERIAL REǪUISITION FOR TOPSIDES HIGH STRENGTH HOT-ROLLED STEEL SECTIONS (SHAPE | RFQ-STR-002 | Topside Primary Steel-Beam | A1 | IFR | 08-May-2026 13:17:04 | 15-May-2026 23:34:18 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-GEN-STR-MR-1001 | MATERIAL REǪUISITION FOR TOPSIDES HIGH STRENGTH TUBULAR STEEL | RFQ-STR-003 RFQ-STR-016 | Topside Primary Steel- Tubular TUBULARS (SAW + SEAMLESS) | A1 | IFR | 04-May-2026 13:07:12 | 15-May-2026 23:30:40 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-GEN-STR-MR-1012 | MATERIAL REQUISITION FOR TOPSIDES SECONDARY AND TERTIARY HOT-ROLLED STEEL | RFQ-STR-004 RFQ-STR-005 | Topside Secondary and Tertiary Steel BEAMS | A1 | IFR | 23-May-2026 09:31:31 | 25-May-2026 20:37:08 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-GEN-STR-MR-1002 | MATERIAL REQUISITION FOR TOPSIDES SECONDARY AND TERTIARY TUBULAR STEEL | RFQ-STR-004 RFQ-STR-005 | Topside Secondary and Tertiary Steel TUBULARS (SEAMLESS) | A1 | IFR | 23-May-2026 08:52:07 | 25-May-2026 20:36:04 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-GEN-STR-MR-1022 | MATERIAL REQUISITION FOR TOPSIDE LOW STRENGTH STEEL PLATE | RFQ-STR-005 | Topside Tertiary Steel-Plate | A1 | IFR | 29-May-2026 19:06:31 | 01-Jun-2026 09:19:45 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-ZWP20-STR-MR-2002 | MATERIAL REǪUISITION FOR ZWP20 JACKET PRIMARY STEEL (PLATE) | RFQ-STR-006 | Jacket Primary Steel-Plate | A1 | IFR | 06-May-2026 10:31:53 | 15-May-2026 23:20:12 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-ZWP21-STR-MR-2002 | MATERIAL REǪUISITION FOR ZWP21 JACKET PRIMARY STEEL (PLATE) | RFQ-STR-006 | Jacket Primary Steel-Plate | A1 | IFR | 06-May-2026 10:32:08 | 15-May-2026 23:33:14 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-ZWP22-STR-MR-2002 | MATERIAL REǪUISITION FOR ZWP22 JACKET PRIMARY STEEL (PLATE) | RFQ-STR-006 | Jacket Primary Steel-Plate | A1 | IFR | 06-May-2026 10:32:27 | 15-May-2026 23:22:53 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-ZWP23-STR-MR-2002 | MATERIAL REǪUISITION FOR ZWP23 JACKET PRIMARY STEEL (PLATE) | RFQ-STR-006 | Jacket Primary Steel-Plate | A1 | IFR | 06-May-2026 10:32:43 | 15-May-2026 23:25:28 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-ZWP20-STR-MR-2001 | MATERIAL REǪUISITION FOR ZWP20 JACKET PRIMARY TUBULAR STEEL | RFQ-STR-007 | Jacket Primary Steel-Tubular TUBULARS - SAW PIPE | A1 | IFR | 04-May-2026 13:11:09 | 15-May-2026 22:45:39 | Approved with Comment
MM-ZTK-1F-ZWP21-STR-MR-2001 | MATERIAL REǪUISITION FOR ZWP21 JACKET PRIMARY TUBULAR STEEL | RFQ-STR-007 | Jacket Primary Steel-Tubular TUBULARS - SAW PIPE | A1 | IFR | 04-May-2026 13:11:25 | 15-May-2026 23:19:31 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-ZWP22-STR-MR-2001 | MATERIAL REǪUISITION FOR ZWP22 JACKET PRIMARY TUBULAR STEEL | RFQ-STR-007 | Jacket Primary Steel-Tubular TUBULARS - SAW PIPE | A1 | IFR | 04-May-2026 13:11:39 | 15-May-2026 23:31:52 | Approved with Comment (Proceed to Rev.C)
MM-ZTK-1F-ZWP23-STR-MR-2001 | MATERIAL REǪUISITION FOR ZWP23 JACKET PRIMARY TUBULAR STEEL | RFQ-STR-007 | Jacket Primary Steel-Tubular TUBULARS - SAW PIPE | A1 | IFR | 04-May-2026 13:11:55 | 15-May-2026 23:33:47 | Approved with Comment (Proceed to Rev.C)

## Primary steel-plate
Plateform | Drawing No. | REV | Drawing Name | Vendor | Weight (T) | Ordered(T) | Rest | Order No. | Order Date | IRC
ZWP21 | ZM169-SE-ST-ML-004 | REV. 4 | Steel Plate for ZWP21 Launch Cradle and Vertical Framing Internal Ring Stiffener | XISC | 420.97 | 225.296 | -2.1432 | ZH26FA001(02) | 2026-06-22 | 2026-08-08
ZWP21 | ZM169-SE-ST-ML-004 | REV. 5 | Steel Plate for ZWP22 Launch Cradle and Vertical Framing Internal Ring Stiffener | XISC |  | 197.8172 |  | ZH26FA001(19) | 2026-07-02
ZWP21 | ZM169-ZWP21-ST-ML-001 | REV. 4 | ZWP21 Jacket Primary, TRB Rolling Plate | XISC | 1877.39 | 1296.894 | 13.642 | ZH26FA001(03) | 2026-06-22 | 2026-08-08
ZWP21 | ZM169-ZWP21-ST-ML-001 | REV. 5 | ZWP21 Jacket Primary, TRB Rolling Plate | XISC |  | 566.854 |  | ZH26FA001(16) | 2026-07-01
ZWP21 | ZM169-ZWP21-ST-ML-002 | REV. 2 | ZWP21 Jacket Primary, JCOE Rolling Plate | XISC | 1581.53 | 1049.5919 | -14.1333 | ZH26FA001(04) | 2026-06-22 | 2026-08-08
ZWP21 | ZM169-ZWP21-ST-ML-002 | REV. 3 | ZWP21 Jacket Primary, JCOE Rolling Plate | XISC |  | 530.0265 |  | ZH26FA001(21) | 2026-07-02
ZWP21 | ZM169-ZWP21-ST-ML-002 | REV. 4 | ZWP21 Jacket Primary, JCOE Rolling Plate | XISC |  | 16.0449 |  | ZH26FA001(40) | 2026-07-27
ZWP21 | ZM169-ZWP21-ST-ML-007 | REV. 2 | ZWP21 Jacket Primary, Cone Plate | XISC | 65 | 55.5516 | -27.3416 | ZH26FA001(05) | 2026-06-22 | 2026-08-08
ZWP21 | ZM169-ZWP21-ST-ML-007 | REV.1 | ZWP21 Jacket Primary, Cone Plate | XISC
ZWP21 | ZM169-ZWP21-ST-ML-007 | REV. 3 | ZWP21 Jacket Primary, Cone Plate | XISC |  | 36.79 |  | ZH26FA001(14) | 2026-07-01
ZWP21 | ZM169-ZWP21-ST-ML-008 |  | ZWP21 Jacket Hydro static Ring Stiff Plates | XISC | 25.756 | 9.3977 | -20.2254 | ZH26FA001(10) | 2026-06-22
ZWP21 | ZM169-ZWP21-ST-ML-008 | REV.1 | ZWP21 Jacket Hydro static Ring Stiff Plates | XISC |  | 36.5837 |  | ZH26FA001(20) | 2026-07-02
ZWP21 | ZM169-ZWP21-ST-ML-009 | REV.0 | ZWP21 Jacket Leg Partition/Closure Plates | XISC | 17.117 | 47.3551 | -30.2381 | ZH26FA001(24) | 2026-07-06
ZWP21 | ZM169-ZWP21-ST-ML-010 | REV.0 | ZWP21 Jacket Piles Sleeve Plate | XISC | 437.539 | 271.8191 | 165.7199 | ZH26FA001(07) | 2026-06-22
[5 empty] | 4425.302 | 4340.0217 | 85.2803
ZWP23 | ZM169-ZWP23-ST-ML-001 | REV.0 | ZWP23 Jacket Primary, TRB Rolling Plate | XISC | 1761 | 1316.7808 | -67.3858 | ZH26FA001(13) | 2026-06-26
ZWP23 | ZM169-ZWP23-ST-ML-001 | REV.1 | ZWP23 Jacket Primary, TRB Rolling Plate | XISC |  | 511.605 |  | ZH26FA001(23) | 2026-07-03
ZWP23 | ZM169-ZWP23-ST-ML-002 | REV.0 | ZWP23 Jacket Primary, JCOE Rolling Plate | XISC | 1514 | 1555.7683 | -57.8132 | ZH26FA001(22) | 2026-07-03
ZWP23 | ZM169-ZWP23-ST-ML-002 | REV.1 | ZWP23 Jacket Primary, JCOE Rolling Plate | XISC |  | 16.0449 |  | ZH26FA001(41) | 2026-07-27
ZWP23 | ZM169-ZWP23-ST-ML-007 | REV.1 | ZWP23 Jacket Primary, Cone Plate | XISC | 65 | 22.7018 | -27.3416 | ZH26FA001(06) | 2026-06-10
ZWP23 | ZM169-ZWP23-ST-ML-007 | REV.2 | ZWP23 Jacket Primary, Cone Plate | XISC |  | 69.6397 |  | ZH26FA001(15) | 2026-07-01
ZWP23 | ZM169-ZWP23-ST-ML-008 | REV.0 | ZWP23 Jacket Hydro static Ring Stiff Plates | XISC |  | 49.7302 | -49.7302 | ZH26FA001(18) | 2026-07-02
ZWP23 | ZM169-ZWP23-ST-ML-009 | REV.0 | ZWP23 Jacket Leg Partition/Closure Plates | XISC | 17.117 | 47.4031 | -30.286 | ZH26FA001(42) | 2026-07-27
ZWP23 | ZM169-ZWP23-ST-ML-010 | REV.0 | ZWP23 Jacket Piles Sleeve Plate | XISC | 437.539 | 271.8572 | -116.6959 | ZH26FA001(28) | 2026-07-14
ZWP23 | ZM169-ZWP23-ST-ML-010 | REV.1 | ZWP23 Jacket Piles Sleeve Plate | XISC |  | 282.3776 |  | ZH26FA001(37) | 2026-07-20
ZWP23 | ZM169-ZWP23-ST-ML-011 | REV.0 | ZWP23 Jacket Launch Cradle Plates+Ring Stiff Plates | XISC | 427.221 | 274.628 | 24.5188 | ZH26FA001(12) | 2026-06-26
ZWP23 | ZM169-ZWP23-ST-ML-011 | REV.1 | ZWP23 Jacket Launch Cradle Plates+Ring Stiff Plates | XISC |  | 128.0742 |  | ZH26FA001(17) | 2026-07-02
[5 empty] | 4221.877 | 4546.6109 | -324.7339
ZWP20 | ZM169-ZWP20-ST-ML-001 | Rev.0 | ZWP20 Jacket Primary, TRB Rolling Plate | XISC | 1641 | 1359.5412 | 281.4588 | ZH26FA006 (34) | 2026-07-20
ZWP20 | ZM169-ZWP20-ST-ML-002 | Rev.0 | ZWP20 Jacket Primary, JCOE Rolling Plate | XISC | 1439 | 1031.1834 | 407.8166 | ZH26FA006 (33) | 2026-07-20
ZWP20 | ZM169-ZWP20-ST-ML-007 | Rev.0 | ZWP20 Jacket Primary, Cone Plate | XISC | 65 | 76.813 | -11.813 | ZH26FA006 (31) | 2026-07-16
ZWP20 | ZM169-ZWP20-ST-ML-008 |  | ZWP20 Jacket Hydro static Ring Stiff Plates | XISC | [5 empty] | No drawing to SE
ZWP20 | ZM169-ZWP20-ST-ML-009 |  | ZWP20 Jacket Leg Partition/Closure Plates | XISC | 17.117
ZWP20 | ZM169-ZWP20-ST-ML-010 |  | ZWP20 Jacket Piles Sleeve Plate | XISC | 465.604
ZWP20 | ZM169-ZWP20-ST-ML-011 |  | ZWP20 Jacket Launch Cradle Plates+Ring Stiff Plates | XISC | 393.737
ZWP20 | ZM169-ZWP20-ST-ML-012 | Rev.0 |  | XISC |  | 23.5661 |  | ZH26FA006 (36) | 2026-07-20
ZWP22 | ZM169-ZWP22-ST-ML-001 | Rev.0 | ZWP22 Jacket Primary, TRB Rolling Plate | XISC | 1696 | 1359.5412 | 336.4588 | ZH26FA006 (27) | 2026-07-13
ZWP22 | ZM169-ZWP22-ST-ML-002 | Rev.0 | ZWP22 Jacket Primary, JCOE Rolling Plate | XISC | 1425 | 1031.1834 | 393.8166 | ZH26FA006 (29) | 2026-07-13
ZWP22 | ZM169-ZWP22-ST-ML-007 | Rev.0 | ZWP22 Jacket Primary, Cone Plate | XISC | 65 | 76.813 | -11.813 | ZH26FA006 (26) | 2026-07-10
ZWP22 | ZM169-ZWP22-ST-ML-008 |  | ZWP22 Jacket Hydro static Ring Stiff Plates | XISC | [5 empty] | No drawing to SE
ZWP22 | ZM169-ZWP22-ST-ML-009 |  | ZWP22 Jacket Leg Partition/Closure Plates | XISC | 17.117
ZWP22 | ZM169-ZWP22-ST-ML-010 |  | ZWP22 Jacket Piles Sleeve Plate | XISC | 456.604
ZWP22 | ZM169-ZWP22-ST-ML-011 | Rev.1 | ZWP22 Jacket Launch Cradle Plates+Ring Stiff Plates | XISC | 410.177 | 349.4055 | 60.7715 | ZH26FA006 (39) | 2026-07-27
ZWP22 | ZM169-ZWP22-ST-ML-012 | Rev.0 |  | XISC |  | 23.822 |  | ZH26FA006 (35) | 2026-07-20
Plateform | Drawing No. |  | Drawing Name | Vendor | Weight (T) | Ordered(T) | Rest | Order No. | Order Date | Remark
Topside | ZM169-SE-ST-ML-014 | REV.0 | Topside Primary-Seamless (ZWP20, 21, 22, 23) | Lontrin |  | 59.9892 |  | ZH26FA004(02) | 2026-06-17
Plateform | Drawing No. |  | Drawing Name | Vendor | Weight (T) | Ordered(T) | Rest | Order No. | Order Date | Remark
Topside | ZM169-SE-ST-ML-013 | REV.0 | Topside Primary-Beam (ZWP20, 21, 22, 23) | Laigang | 418 | 371.6016 | 46.3984 | ZH26FA006 (02) | 2026-06-22
Plateform | Drawing No. |  | Drawing Name | Vendor | Weight (T) | Ordered(T) | Rest | Order No. | Order Date | Remark
Topside | ZM169-SE-ST-ML-021 | REV.0 | Topside Secondary Steel(W)-Beam | Laigang |  | 250 |  | ZH26FA006 (03) | 2026-07-13