## PSR
PROVISION OF ENGINEERING, PROCUREMENT, CONSTRUCTION AND COMMISSIONING FOR WELLHEAD PLATFORMS, ASSOCIATED PIPLINES AND BROWNFIELD MODIFICATIONS FOR ZAWTIKA DEVELOPMENT PROJECT PHASE 1F
Procurement Plan
[8 empty] | LA | Most complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 10 | 17 | 10 |  | 9 | 2 | 5 | 20 | 10 | [15 empty] | 3 |  | 10 | 2
[8 empty] | LB | High complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 10 | 17 | 10 |  | 9 | 2 | 5 | 20 | 10 | [15 empty] | 3 |  | 10 | 2
[8 empty] | LC | Normal complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 10 | 13 | 10 |  | 9 | 2 | 5 | 15 | 10 | [15 empty] | 3 |  | 10 | 2
Contract no: MMC25-5001 | [7 empty] | LD | Low complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 5 | 7 | 10 |  | 5 | 2 | 5 | 10 | 10 | [14 empty] | Update:18-Sep-2026 | 2 |  | 5 | 2
No. | MR No. | RFQ No. | Package Name | CODE | DIS | LLI (Y/N) | CR | Priority Level | PO description | Bidders | TC | TBE | Price bid | Price Negotiation | Owner | P/F/A | Bidder list Approval | MR Issued (IFR) | MR Approved | RFQ Issued | RFQ Approved | Bid Closing Date | TBE Issued | TBE Approved | LOA issued | PO Issued | Vendor Acknowledgement | KOM | VDB Submission | Approval of Key VP | Main Material Arrived | PIM | Start Production | FAT | Ready for Shipment | Receipt at WORKSITE | Punch List Clearance(all punch clearance before Tag Equipment Ready for Shipping ) | Approval of Final Documentation (To be confirmed later) | Delivery Duration (Weeks) | days | Delivery Date(1st Batch for ZWP21) | ROS Date | Float | Responder | Remarks | 2010-05-31 | 2010-06-30 | 2010-07-31 | 2010-08-31 | 2010-09-30 | 2010-10-31 | 2010-11-30 | 2010-12-31 | 2011-01-31 | 2011-02-28 | 2026-09-22 | Palteform | PO Delivery date | Puchase Qty
[16 empty] | Matrix | PTTEP | ENG | PTTEP | TJE PRC | PTTEP | TJE PRC | ENG | PTTEP | TJE PRC | TJE PRC | BIDDER | TJE PRC | Vendor | ENG | Vendor | TJE QA/QC | Vendor | TJE QA/QC | Vendor | THE Worksite | TJE QA/QC | TJE PRC |  |  | TJE PRC
[16 empty] | Holiday | China | Thai | Thai | China | Thai | China | Thai | Thai | China | China | China | China | China | Thai | [15 empty] | Thai |  | China | China
1 | MM-ZTK-1F-GEN-MEC-MR-0001 | RFQ-MA-001 | Offshore Pedestal Crane | 4-2 | MA | Y | L2 | LA | Favelle Favco | Oil State | Oil State | Oil State | Oil State | Oil State | SH | P | 2026-04-21 | 2026-04-21 | 2026-04-24 | 2026-04-27 | 2026-05-06 | 2026-05-17 | 2026-06-11 | 2026-06-25 |  | 2026-07-08 | 2026-07-10 | 2026-07-17 | 2026-08-14 | 2026-08-28 | 2026-11-26 | 2026-12-01 | 2026-12-04 | 2027-04-24 | 2027-05-24 | 2027-06-23 | 2027-06-26 | 2027-07-23 | 50 | 350 | 2027-06-23 |  |  | Chris | 2026.4.16: Issued RFQ 2026.4.28-5.1: Received Bid 2026.5.7: TC 2026.5.19: Vendor will reply TC 2026.2.26-27 Hold TC meeting (ZWP21)1st Unit of Pedestal Adaptor = 42 Weeks after LOA (3-May-2027) (ZWP21)1st Unit of 100RL = 46 Weeks after LOA (31-May-2027) (ZWP23)2nd Unit of Pedestal Adaptor = 45 Weeks after LOA (24-May-2027) (ZWP23)2nd Unit of 100RL = 49 Weeks after LOA (21-Jun-2027) (ZWP22)3rd Unit of Pedestal Adaptor = 48 Weeks after LOA (14-Jun-2027) (ZWP22)3rd Unit of 100RL = 52 Weeks after LOA (12-Jul-2027) (ZWP20)4th Unit of Pedestal Adaptor = 51 Weeks after LOA (5-Jul-2027) (ZWP20)4th Unit of 100RL = 55 Weeks after LOA (2-Aug-2027) 2026.8.9 Expedite drawings by e-mail 2026.9.10: GA drawing submitted to CPY to review | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0001 | RFQ-MA-001 | Offshore Pedestal Crane | 4-2 | MA | Y | L2 | LA | ZM169-WP1-PO-MEC-001 | TOS (PVL) | TOS | TOS | TOS | TOS | SH | F | [13 empty] | 2026-09-24 | 2026-10-06 | 2026-10-06 | 2026-12-04 | 2027-04-24 | 2027-05-31 | 2027-06-14 | 2027-06-26 | 2027-07-23 | 46 | 322 | 2027-06-07 | 2027-06-22 | 15 | CIF Zhuhai Port |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP21 | 2027-05-31
| MM-ZTK-1F-GEN-MEC-MR-0001 | RFQ-MA-001 | Offshore Pedestal Crane |  | MA | Y | L2 | LA |  | Favelle Favco | Favelle Favco | Favelle Favco | Favelle Favco | Favelle Favco | SH | F | [22 empty] | 49 | 343 | 2027-06-28 | 2027-07-01 | 3 | CIF Zhuhai Port | [12 empty] | ZWP23 | 2027-06-21
| MM-ZTK-1F-GEN-MEC-MR-0001 | RFQ-MA-001 | Offshore Pedestal Crane |  | MA | Y | L2 | LA |  | Huanan |  |  |  |  | SH | F | [22 empty] | 52 | 364 | 2027-07-19 | 2027-08-10 | 22 | CIF Zhuhai Port | [12 empty] | ZWP22 | 2027-07-12
| MM-ZTK-1F-GEN-MEC-MR-0001 | RFQ-MA-001 | Offshore Pedestal Crane |  | MA | Y | L2 | LA | [6 empty] | SH | F | [22 empty] | 55 | 385 | 2027-08-09 | 2027-08-26 | 17 | CIF Zhuhai Port | [12 empty] | ZWP20 | 2027-08-02
| MM-ZTK-1F-GEN-MEC-MR-0001 | RFQ-MA-001 | Offshore Pedestal Crane | 4-2 | MA | Y | L2 | LA | [6 empty] | SH | A | 2026-04-08 | 2026-04-13 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 2026-05-01 | 2026-06-19 | 2026-07-13 | 2026-07-13 | 2026-07-17 | 2026-07-24 | 2026-07-17 | 2026-08-14 | [11 empty] | CD+7 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2 | MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-1 | Closed Drain Sump Vessel | 4-10 | MA | Y | L3 | LA | Zhuhai Jutal | Zhuhai Jutal |  |  |  |  | SH | P | 2026-05-25 | 2026-05-26 | 2026-06-04 | 2026-06-05 | 2026-06-12 | 2026-06-24 | 2026-06-24 | 2026-07-08 |  | 2026-07-15 | 2026-07-17 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2027-01-21 | 2027-02-05 | 2027-02-15 | 2027-02-18 | 2027-03-17 | 26 | 182 | 2027-02-15 | 2027-03-02 | 15 | HuangWei | 2026.5.6 Issued RFQ to Zhuhai yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | Plate:45-60days
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-1 | Closed Drain Sump Vessel | 4-10 | MA | Y | L3 | LA | ZM169-WP1-PO-MEC-002 | [5 empty] | SH | F | [13 empty] | 2026-09-24 | 2026-11-23 | 2026-11-25 | 2026-11-27 | 2027-01-30 | 2027-02-14 | 2027-02-15 | 2027-02-18 | 2027-03-17 |  |  | 2027-02-15 |  |  | DDP Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 2027-02-15 |  | 3.2 certificate: 15days
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-1 | Closed Drain Sump Vessel | 4-10 | MA | Y | L3 | LA | [6 empty] | SH | A |  | 2026-04-17 | 2026-05-01 | 2026-05-06 | 2026-05-06 | 2026-06-10 | 2026-06-27 | 2026-07-08 | N/A | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-08-10 | [16 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3 | MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-2 | Test Separator | 4-8 | MA | Y | L2 | LA | Zhuhai Jutal | Zhuhai Jutal |  |  |  |  | SH | P | 2026-04-23 | 2026-04-24 | 2026-05-05 | 2026-05-06 | 2026-05-13 | 2026-06-24 | 2026-06-24 | 2026-07-08 |  | 2026-07-15 | 2026-07-17 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2027-02-11 | 2027-02-26 | 2027-03-03 | 2027-03-06 | 2027-04-02 | 33 | 231 | 2027-03-03 | 2027-04-12 | 14 | HuangWei | 2026.5.6 Issued RFQ to Zhuhai yard 2026.8.24 GA drawing and CAL report are submitted to D2 2026.9.8 GA drawing and CAL report are approved | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-2 | Test Separator | 4-8 | MA | Y | L2 | LA | ZM169-WP1-PO-MEC-002 | [5 empty] | SH | F | [13 empty] | 2026-09-24 | 2026-11-23 | 2026-11-25 | 2026-11-27 | 2027-03-14 | 2027-03-29 | 2027-03-29 | 2027-03-06 | 2027-04-02 |  |  | 2027-03-29 |  |  | DDP Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 2027-03-29
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-2 | Test Separator | 4-8 | MA | Y | L2 | LA | [6 empty] | SH | A |  | 2026-04-17 | 2026-05-01 | 2026-05-06 | 2026-05-06 | 2026-06-10 | 2026-06-27 | 2026-07-08 | N/A | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-08-06 | GA:8-Sep-26 CAL:8-Sep-26 | [15 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4 | MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-3 | Instrument Gas Filter Coalescer | 4-11 | MA | Y | L2 | LA | Zhuhai Jutal | Zhuhai Jutal |  |  |  |  | SH | P | 2026-06-04 | 2026-06-05 | 2026-06-12 | 2026-06-15 | 2026-06-22 | 2026-06-24 | 2026-06-24 | 2026-07-08 |  | 2026-07-15 | 2026-07-17 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2027-01-21 | 2027-02-05 | 2027-02-20 | 2027-02-23 | 2027-03-22 | 26 | 180 | 2027-02-20 | 2027-04-14 | 53 | HuangWei | 2026.5.6 Issued RFQ to Zhuhai yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-3 | Instrument Gas Filter Coalescer | 4-11 | MA | Y | L2 | LA | ZM169-WP1-PO-MEC-002 | [5 empty] | SH | F | [13 empty] | 2026-10-02 | 2026-12-01 | 2026-12-03 | 2026-12-05 | 2027-01-21 | 2027-02-05 | 2027-02-20 | 2027-02-23 | 2027-03-22 |  |  | 2027-02-20 |  |  | DDP Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 2027-02-20
| MM-ZTK-1F-GEN-MEC-MR-0002 | RFQ-MA-002-3 | Instrument Gas Filter Coalescer | 4-11 | MA | Y | L2 | LA | [6 empty] | SH | A |  | 2026-04-29 | 2026-05-01 | 2026-05-06 | 2026-05-06 | 2026-06-18 | 2026-06-27 | 2026-07-08 | N/A | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-09-04 | [16 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5 | MM-ZTK-1F-GEN-MEC-MR-0003 | RFQ-MA-003 | Closed Drain Sump Pump skids | 4-18 | MA | Y | L3 | LA | Multipahse | Multipahse | Multipahse |  | Multipahse | Multipahse | SH | P | 2026-04-28 | 2026-04-29 | 2026-05-08 | 2026-05-11 | 2026-05-18 | 2026-05-26 | 2026-06-22 | 2026-07-06 |  | 2026-07-17 | 2026-07-21 | 2026-07-28 | 2026-08-25 | 2026-09-08 | 2026-12-07 | 2026-12-07 | 2026-12-10 | 2027-01-14 | 2027-01-29 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 32 | 224 | 2027-02-26 | 2027-03-21 | -4 | Chris | 2026.5.6 Issued RFQ bid due day:22-May | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0003 | RFQ-MA-003 | Closed Drain Sump Pump skids | 4-18 | MA | Y | L3 | LA | ZM169-WP1-PO-MEC-003 | PKK | PKK |  | PKK | PKK | SH | F | [13 empty] | 2026-09-24 | 2026-12-23 | 2026-12-23 | 2026-12-26 | 2027-02-17 | 2027-03-04 | 2027-04-01 | 2027-03-01 | 2027-03-28 | 32 | 224 | 2027-03-25 |  |  | CIF Zhuhai Port |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2027-03-18
| MM-ZTK-1F-GEN-MEC-MR-0003 | RFQ-MA-003 | Closed Drain Sump Pump skids | 4-18 | MA | Y | L3 | LA |  | CSI | CSI |  | CSI |  | SH | A | 2026-04-21 | 2026-04-18 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 2026-05-22 | 2026-07-03 | 2026-07-17 | 2026-08-04 | 2026-08-11 | 2026-09-02 | 2026-08-07 | 2026-08-28 | [11 empty] | CD+7 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6 | MM-ZTK-1F-GEN-MEC-MR-0004 | RFQ-MA-004 | Chemical injection pump skids | 4-4 | MA | Y | L3 | LA | Multipahse | Multipahse | Multipahse |  | Multipahse | Multipahse | SH | P | 2026-04-28 | 2026-04-29 | 2026-05-08 | 2026-05-11 | 2026-05-18 | 2026-05-26 | 2026-06-22 | 2026-07-06 |  | 2026-07-17 | 2026-07-21 | 2026-07-28 | 2026-08-25 | 2026-09-08 | 2026-12-07 | 2026-12-07 | 2026-12-10 | 2027-02-06 | 2027-02-21 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 34 | 238 | 2027-03-12 | 2027-04-13 | 39 | Chris | 2026.5.6 Issued RFQ bid due day:22-May 2025.5.31-6.5 TC | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0004 | RFQ-MA-004 | Chemical injection pump skids | 4-4 | MA | Y | L3 | LA | ZM169-WP1-PO-MEC-003 | PKK | PKK |  | PKK | PKK | SH | F | [13 empty] | 2026-09-24 | 2026-12-23 | 2026-12-23 | 2026-12-26 | 2027-01-28 | 2027-02-12 | 2027-03-12 | 2027-03-15 | 2027-04-11 | 28 | 196 | 2027-03-05 |  |  | CIF Zhuhai Port |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2027-02-18
| MM-ZTK-1F-GEN-MEC-MR-0004 | RFQ-MA-004 | Chemical injection pump skids | 4-4 | MA | Y | L3 | LA |  | CSI | CSI |  | CSI | CSI | SH | A | 2026-04-21 | 2026-04-18 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 2026-05-22 | 2026-06-29 | 2026-08-07 | 2026-08-04 | 2026-08-11 | 2026-09-02 | 2026-08-07 | 2026-09-03 | [11 empty] | CD+Spring F+15 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7 | MM-ZTK-1F-GEN-MEC-MR-0005 | RFQ-MA-005 | Chemical storage tank | 4-39 | MA | Y | L3 | LA | Zhuhai Jutal | Zhuhai Jutal |  |  |  |  | SH | P | 2026-05-11 | 2026-05-12 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-06-30 | 2026-06-30 | 2026-07-14 |  | 2026-07-27 | 2026-07-29 | 2026-08-05 | 2026-09-02 | 2026-09-16 | 2026-10-16 | 2026-10-19 | 2026-10-22 | 2026-12-31 | 2027-01-10 | 2027-01-11 | 2027-01-14 | 2027-02-10 | 24 | 168 | 2027-01-11 | 2027-04-15 | 55 | HuangWei | 2026.5.6 Issued RFQ to Zhuhai yard 2026.9.4 GA drawing submitted to D2. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0005 | RFQ-MA-005 | Chemical storage tank | 4-39 | MA | Y | L3 | LA | ZM169-WP1-PO-MEC-005 | [5 empty] | SH | F | [13 empty] | 2026-09-24 | 2026-10-16 | 2026-10-19 | 2026-10-22 | 2027-02-09 | 2027-02-19 | 2027-02-19 | 2027-01-14 | 2027-02-10 |  |  | 2027-02-19 |  |  | DDP Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0005 | RFQ-MA-005 | Chemical storage tank | 4-39 | MA | Y | L3 | LA | [6 empty] | SH | A |  | 2026-04-21 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-06-08 | 2026-07-01 | 2026-07-08 | N/A | 2026-07-14 | 2026-07-15 | 2026-07-17 | 2026-08-07 | [16 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8 | MM-ZTK-1F-GEN-MEC-MR-0006 | RFQ-MA-006 | Material Handling Equipment | 4-7 | MA | N | L4 | LC | MGW(Yale) | Weihua, Megaway | Weihua |  |  |  | SH | P | 2026-06-09 | 2026-06-09 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-30 | 2026-07-09 | 2026-07-23 |  | 2026-08-25 | 2026-08-27 | 2026-08-27 | 2026-09-10 | 2026-09-30 | 2026-10-30 | 2026-11-02 | 2026-11-05 | 2027-01-04 | 2027-01-19 | 2027-02-16 | 2027-02-19 | 2027-03-18 | 25 | 175 | 2027-02-16 | 2027-05-14 | 73 | Chris |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-MEC-MR-0006 | RFQ-MA-006 | Material Handling Equipment | 4-7 | MA | N | L4 | LC | ZM169-WP1-PO-MEC-006 | Crosby | Crosby | Crosby(PVL) | Crosby(PVL) |  | SH | F | [11 empty] | 2026-09-22 | 2026-09-24 | 2026-09-30 | 2026-10-30 | 2026-11-02 | 2026-11-05 | 2027-01-04 | 2027-01-19 | 2027-02-16 | 2027-02-19 | 2027-03-18 | 25 | 175 | 2027-03-02 |  |  | CIF Zhuhai Port |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2027-02-23
| MM-ZTK-1F-GEN-MEC-MR-0006 | RFQ-MA-006 | Material Handling Equipment | 4-7 | MA | N | L4 | LC |  | TOS, Konecranes | Megaway(Yale) | Megaway(Yale) | Megaway(Yale) | Megaway(Yale) | SH | A | 2026-06-19 | 2026-05-12 | 2026-05-28 | 2026-06-23 | 2026-06-23 | 2026-06-30 | 2026-07-17 | C1:2026/8/12 C2:2026/9/11 | 2026-08-28 | 2026-09-11 | [14 empty] | CD+7 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9 | MM-ZTK-1F-GEN-SAF-MR-0001 | RFQ-SA-001 | Fire Fighting, Safety Equipment (Including Lifesaving) | 4-38 | SA | N | L3 | LD |  | AIG | AIG |  |  |  | SH | P | 2026-07-10 | 2026-06-28 | 2026-07-10 | 2026-09-18 | 2026-09-18 | 2026-09-25 | 2026-10-08 | 2026-10-23 |  | 2026-10-30 | 2026-11-03 | 2026-11-03 | 2026-11-17 | 2026-12-01 | 2027-01-30 | 2027-01-30 | 2027-02-02 | 2027-04-13 | 2027-04-28 | 2027-05-28 | 2027-05-31 | 2027-06-27 | 30 | 210 | 2027-05-28 | 2027-06-08 | 4 | Han Jingxin |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-SAF-MR-0001 | RFQ-SA-001 | Fire Fighting, Safety Equipment (Including Lifesaving) | 4-38 | SA | N | L3 | LD |  | WRLEADING | WRLEADING |  |  |  | SH | F | [6 empty] | 2026-10-08 | 2026-10-26 |  | 2026-11-06 | 2026-11-10 | 2026-11-17 | 2026-12-15 | 2026-12-29 | 2027-01-30 | 2027-01-30 | 2027-02-02 | 2027-04-13 | 2027-04-28 | 2027-05-28 | 2027-05-31 | 2027-06-27 |  |  | 2027-06-04 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-SAF-MR-0001 | RFQ-SA-001 | Fire Fighting, Safety Equipment (Including Lifesaving) | 4-38 | SA | N | L3 | LD |  | TPI | TPI |  |  |  | SH | A | 2026-07-27 | 2026-06-10 | 2026-06-24 | 2026-07-28 | 2026-07-28 | 2026-08-14 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
10 | MM-ZTK-1F-GEN-SAF-MR-0002 | RFQ-SA-002 | Safety Signs | 4-38 | SA | N | L3 | LD | [6 empty] | ZH | P | 2026-12-25 | 2026-12-25 | 2027-01-12 | 2027-01-12 | 2027-01-12 | 2027-01-19 | 2027-01-28 | 2027-02-11 |  | 2027-02-19 | 2027-02-23 | 2027-03-02 | 2027-03-16 | 2027-03-30 | 2027-04-14 | 2027-04-14 | 2027-04-16 | 2027-05-16 | 2027-05-18 | 2027-05-23 | 2027-05-26 | 2027-06-22 | 5 | 35 | 2027-05-23 | 2027-06-08 | 74 | Kuang Cuichang | 2026.6.10 Issued RFQ to Zhuhai yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-SAF-MR-0002 | RFQ-SA-002 | Safety Signs | 4-38 | SA | N | L3 | LD | [6 empty] | ZH | F | [6 empty] | 2027-01-28 | 2027-02-11 |  | 2027-02-19 | 2027-02-23 | 2027-03-02 | 2027-03-16 | 2027-03-30 | 2027-04-14 | 2027-04-14 | 2027-04-16 | 2027-05-16 | 2027-05-18 | 2027-05-23 | 2027-05-26 | 2027-06-22 |  |  | 2027-03-26 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-SAF-MR-0002 | RFQ-SA-002 | Safety Signs | 4-38 | SA | N | L3 | LD | [6 empty] | ZH | A | 2026-07-14 | 2026-06-01 | 2026-06-09 | 2026-07-27 | 2026-07-27 | 2026-08-06 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-001 | Ball Valve (Flange End) | 4-19 | PI | N | L3 | LC | BOTELI | DHV,Huaying,Boteli,VALVITALIA, | Neway | Neway | Neway | Boteli | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-05-14 | 148 | Lin Yazhen |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-001 | Ball Valve (Flange End) | 4-19 | PI | N | L3 | LC | ZM169-WP1-PO-PIP-001 | PIBIVIESSE,STARLINE-no reply | Boteli | Boteli | Boteli | Huaying | SH | F | [13 empty] | 2026-09-29 | 2026-11-08 | 2026-11-11 | 2026-11-14 | 2026-11-25 | 2026-12-10 | 2026-12-17 | 2027-03-01 | 2027-03-28 |  |  | 2026-12-17 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2026-12-17
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-001 | Ball Valve (Flange End) | 4-19 | PI | N | L3 | LC |  | CAMERON & KCON-declined | Huaying | Huaying | Huaying |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-01 | 2026-06-01 | 2026-06-18 | C1:2026/7/16 C2:2026/8/14 | 2026-08-18 | 2026-08-18 | 2027-02-19: 2026-08-24; 2027-02-23: 2026-08-31; 2027-03-02: 2026-08-25; 2027-03-16: 2026-09-09 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-021 | Ball Valve (Welded End) | 4-19 | PI | N | L3 | LC | DHV | Boteli,STARLINE | Neway | Neway | Neway | Boteli | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-04-10 | 96 | Lin Yazhen |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-021 | Ball Valve (Welded End) | 4-19 | PI | N | L3 | LC | ZM169-WP1-PO-PIP-002 | VALVITALIA,DHV | Boteli | Boteli | Boteli | DHV | SH | F | [13 empty] | 2026-09-29 | 2026-11-08 | 2026-11-11 | 2026-11-14 | 2026-12-13 | 2026-12-28 | 2027-01-04 | 2027-03-01 | 2027-03-28 | 22 | 154 | 2027-01-04 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2027-01-04
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-021 | Ball Valve (Welded End) | 4-19 | PI | N | L3 | LC | VALVITALIA,STARLINE | Neway | DHV | DHV | DHV |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-01 | 2026-06-01 | 2026-06-27 | C1:2026/7/16 C2:2026/8/14 | 2026/8/6 2026/8/18 | 2026-08-14 | 2027-02-19: 2026-08-21; 2027-02-23: 2026-08-26; 2027-03-02: 2026-08-26; 2027-03-16: 2026-08-21 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-002 | Globe Valve (without equal percentage) | 4-21 | PI | N | L3 | LC | DHV | KCON, CAMERON-declined | Neway |  |  |  | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-04-10 | 96 | Lin yazhen |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-002 | Globe Valve (without equal percentage) | 4-21 | PI | N | L3 | LC | ZM169-WP1-PO-PIP-002 | Neway,HDV, Boteli | Boteli | Boteli | Boteli | Boteli | SH | F | [13 empty] | 2026-09-29 | 2026-11-08 | 2026-11-11 | 2026-11-14 | 2026-12-13 | 2026-12-28 | 2027-01-04 | 2027-03-01 | 2027-03-28 |  |  | 2027-01-04 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2027-01-04
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-002 | Globe Valve (without equal percentage) | 4-21 | PI | N | L3 | LC |  | RAIMONDI (BY TYCO VALVE)-declined | DHV | DHV | DHV | DHV | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-05 | 2026-06-05 | 2026-06-25 | 2026-07-16 | 2026-08-11 | 2026-08-14 | 2027-02-19: 2026-08-21; 2027-02-23: 2026-08-26; 2027-03-02: 2026-08-26; 2027-03-16: 2026-08-21 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-028 | Globe Valve (with equal percentage) | 4-21 | PI | N | L3 | LC | THS(LVF) | Pentair | Pentair | Pentair | Pentair |  | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-04-10 | 24 | Lin Yazhen |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-028 | Globe Valve (withequal percentage) | 4-21 | PI | N | L3 | LC | ZM169-WP1-PO-PIP-003 | TFS(LVF) | TFS(LVF) | TFS(LVF) | TFS(LVF) |  | SH | F | [13 empty] | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-23 | 2027-03-10 | 2027-03-17 | 2027-03-01 | 2027-03-28 |  |  | 2027-03-17 |  |  | CIF Guangzhou and Shenzhen Airport |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2027-02-25
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-028 | Globe Valve (withequal percentage) | 4-21 | PI | N | L3 | LC |  | Crane(No product) |  |  |  |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-05 | 2026-06-05 | 2026-06-25 | 2026-07-16 | 2026-08-11 | 2026-08-19 | 2027-02-19: 2026-08-24; 2027-02-23: 2026-09-11; 2027-03-02: 2026-08-27; 2027-03-16: 2026-09-08 |  |  | CD+Spr F+20 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-003 | Check Valve (Swing) | 4-22 | PI | N | L3 | LC | Combined with Check Wafer | [5 empty] | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-003 | Check Valve (Swing) | 4-22 | PI | N | L3 | LC | [6 empty] | SH | F | [6 empty] | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 |  |  | 2027-02-26 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-003 | Check Valve (Swing) | 4-22 | PI | N | L3 | LC | [6 empty] | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-29 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-029 | Check Valve (Position) | 4-22 | PI | N | L3 | LC | Combined with Check Wafer | [5 empty] | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-029 | Check Valve (Position) | 4-22 | PI | N | L3 | LC | [6 empty] | SH | F | [6 empty] | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 |  |  | 2027-02-26 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-029 | Check Valve (Position) | 4-22 | PI | N | L3 | LC | [6 empty] | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-29 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
15 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-030 | Check Valve (Wafer) | 4-22 | PI | N | L3 | LC | BOTELI | Neway | Neway | Neway | Neway |  | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-12 | 2026-06-29 | 2026-07-16 | 2026-08-03 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-04-10 | 109 | Lin yazhen |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-030 | Check Valve (Wafer) | 4-22 | PI | N | L3 | LC | ZM169-WP1-PO-PIP-001 | Boteli | Boteli | Boteli | Boteli | Boteli | SH | F | [13 empty] | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2026-11-30 | 2026-12-15 | 2026-12-22 | 2027-03-01 | 2027-03-28 | 22 | 154 | 2026-12-22 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2026-12-22
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-030 | Check Valve (Wafer) | 4-22 | PI | N | L3 | LC |  | Huaying, keystone | Huaying | Huaying | Huaying | Huaying | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-29 | 2026-07-16 | 2026-08-11 | 2026-08-14 | 2026-08-14: 2026-08-24; 2026-08-18: 2026-08-31; 2026-08-25: 2026-08-25; 2026-09-15: 2026-09-10 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
16 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-004 | Check valve (Compact) | 4-41 | PI | N | L3 | LB | KCON | PIPER VALVE | PIPER VALVE | PIPER VALVE | PIPER VALVE | KCON | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-12 | 2026-06-12 | 2026-06-04 | 2026-06-18 | 2026-07-13 | 2026-07-27 |  | 2026-08-10 | 2026-08-12 | 2026-08-19 | 2026-09-16 | 2026-09-30 | 2026-10-30 | 2026-11-02 | 2026-11-05 | 2027-02-02 | 2027-02-17 | 2027-02-22 | 2027-02-25 | 2027-03-24 | 28 | 196 | 2027-02-22 | 2027-04-10 | 47 | Lin Yazhen |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-004 | Check valve (Compact) | 4-41 | PI | N | L3 | LB | ZM169-WP1-PO-PIP-004 | COMBET | COMBET | COMBET-declined |  |  | SH | F | [13 empty] | 2026-09-30 | 2026-10-30 | 2026-11-02 | 2026-11-05 | 2027-02-07 | 2027-02-17 | 2027-02-22 | 2027-02-25 | 2027-03-24 | 28 | 196 | 2027-02-22 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2027-02-22
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-004 | Check valve (Compact) | 4-41 | PI | N | L3 | LB |  | KCON, FMC | KCON |  | KCON |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-01 | 2026-06-01 | 2026-06-15 | 2026-07-10 | 2026-08-07 | 2026-08-07 | 2026-08-14: 2026-08-10; 2026-08-18: 2026-08-12; 2026-08-25: 2026-08-06; 2026-09-15: 2026-08-24 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
17 | MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-030 | ButterflyValve | 4-22 | PI | N | L3 | LC | BOTELI |  | Neway | Neway | Neway |  | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-24 | 2026-07-31 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-02-04 | 2027-02-19 | 2027-02-26 | 2027-03-01 | 2027-03-28 | 28 | 196 | 2027-02-26 | 2027-04-10 | 109 | Lin yazhen | 2026.6.8 Short bidder list to CPY for approval | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-030 | ButterflyValve | 4-22 | PI | N | L3 | LC | ZM169-WP1-PO-PIP-001 |  | Boteli | Boteli | Boteli | Boteli | SH | F | [13 empty] | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2026-12-05 | 2026-12-15 | 2026-12-22 | 2027-03-01 | 2027-03-28 | 22 | 154 | 2026-12-22 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2026-12-22
| MM-ZTK-1F-GEN-PIP-MR-0001 | RFQ-PIP-030 | ButterflyValve | 4-22 | PI | N | L3 | LC | Combined with check valve |  | Huaying | Huaying | Huaying | Huaying | SH | A | 2026-06-10 | 2026-05-06 | 2026-05-23 | 2026-06-09 | 2026-06-09 | 2026-06-29 | 2026-07-16 | 2026-08-11 | 2026-08-14 | 2026-08-14: 2026-08-24; 2026-08-18: 2026-08-31; 2026-08-25: 2026-08-25; 2026-09-15: 2026-09-10 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
18 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-006 | Special items-Chemical Injection Quill | 5-5 | PI | N | L3 | LA |  | Oliver Valves | Oliver Valves | Oliver Valves-22 weeks |  |  | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-24 | 2026-07-31 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-11-01 | 2026-11-04 | 2027-01-14 | 2027-01-24 | 2027-01-29 | 2027-02-01 | 2027-02-28 | 24 | 168 | 2027-01-29 | 2027-05-23 | 56 | Liu Lei |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | 20-22 weeks DDP Zhuhai after after drawing approval
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-006 | Special items-Chemical Injection Quill | 5-5 | PI | N | L3 | LA | [6 empty] | SH | F | [6 empty] | 2026-09-24 | 2026-09-29 | 2026-10-09 | 2026-10-11 | 2026-10-13 | 2026-10-20 | 2026-11-17 | 2026-12-01 | 2026-12-24 | 2026-12-24 | 2026-12-27 | 2027-03-13 | 2027-03-23 | 2027-03-28 | 2027-02-01 | 2027-02-28 |  |  | 2027-03-28 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-006 | Special items-Chemical Injection Quill | 5-5 | PI | N | L3 | LA |  | RIBO(McMurray) | RIBO(McMurray) |  |  |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-24 | 2026-06-09 | 2026-06-12 | 2026-07-21 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
19 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-023 | Special items-Hoses and Connections | 5-5 | PI | N | L4 | LA |  | Eaton-reply |  |  |  |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2027-02-03 | 2027-02-23 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 24 | 168 | 2027-03-25 | 2027-05-23 | 68 | Lin Yazhen | 2026.6.10 Short bidder list to CPY for approval | [11 empty] | Bidder1
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-023 | Special items-Hoses and Connections | 5-5 | PI | N | L4 | LA |  | MANN TEK（RIBO） | RIBO(MANN TEK ) | RIBO(Dexion ) | RIBO(Dexion ) |  | SH | F | [7 empty] | 2026-09-29 |  | 2026-09-29 | 2026-10-08 | 2026-10-15 | 2026-11-12 | 2026-11-26 | 2026-12-26 | 2026-12-26 | 2026-12-26 | 2027-01-25 | 2027-02-14 | 2027-03-16 | 2027-03-28 | 2027-04-24 |  |  | 2027-03-16 | [15 empty] | Bidder2 | 12 weeks DDP Zhuhai after after drawing approval
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-023 | Special items-Hoses and Connections | 5-5 | PI | N | L4 | LA |  | DIXON, TPI | DIXON |  |  |  | SH | A | 2026-06-11 | 2026-05-06 | 2026-05-24 | 2026-06-12 | 2026-06-12 | 2026-06-26 | 2026-09-15 | [33 empty] | Bidder3 | 12 weeks DDP Zhuhai after after drawing approval
20 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-022 | Special items-Liquid trap | 5-5 | PI | N | L3 | LA |  | ARMSTRONG | ARMSTRONG |  |  |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2027-02-03 | 2027-02-23 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 24 | 168 | 2027-03-25 | 2027-05-23 | 68 | Lin Yazhen | [12 empty] | Bidder1 | after drawing approved 16 weeks
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-022 | Special items-Liquid trap | 5-5 | PI | N | L3 | LA |  | Gestra | Gestra | Gestra (Shanghai) | Gestra (Shanghai) |  | SH | F | [7 empty] | 2026-09-29 |  | 2026-09-29 | 2026-10-08 | 2026-10-15 | 2026-11-12 | 2026-11-26 | 2026-12-26 | 2026-12-26 | 2026-12-26 | 2027-01-25 | 2027-02-14 | 2027-03-16 | 2027-03-28 | 2027-04-24 | 20 | 140 | 2027-03-16
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-022 | Special items-Liquid trap | 5-5 | PI | N | L3 | LA |  | Gestra（RIBO), TPI | Gestra (RIBO） |  |  |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-24 | 2026-06-10 | 2026-06-10 | 2026-06-26 | 2026-09-15
21 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-032 | Special items-Clamp Type Connector and Target Tee with Clamp Type Connector | 5-5 | PI | N | L3 | LA |  | Destec(RIBO) | RIBO(Destec) | RIBO(Destec)-bundle4# pending |  |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2027-02-03 | 2027-02-23 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 24 | 168 | 2027-03-25 | 2027-05-23 | 72 | Liu Lei | 2026.6.10 Short bidder list to CPY for approval | [11 empty] | Bidder1 | 36 weeks DDP Zhuhai after after drawing approval
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-032 | Special items-Clamp Type Connector and Target Tee with Clamp Type Connector | 5-5 | PI | N | L3 | LA |  | Multiphase(GRAYLOC) | Multiphase(GRAYLOC) | GRAYLOC(7.10, 9.10)-合规性审查 |  |  | SH | F | [6 empty] | 2026-09-18 | 2026-09-25 | 2026-09-25 | 2026-09-25 | 2026-09-29 | 2026-10-13 | 2026-11-10 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2027-01-21 | 2027-02-10 | 2027-03-12 | 2027-03-28 | 2027-04-24 |  |  | 2027-03-12 | [15 empty] | Bidder2 | 20 weeks DDP Zhuhai after after drawing approval
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-032 | Special items-Clamp Type Connector and Target Tee with Clamp Type Connector | 5-5 | PI | N | L3 | LA |  | VIAR, TPI |  | Meritus-sourcing |  |  | SH | A | 2026-06-11 | 2026-05-06 | 2026-05-24 | 2026-06-12 | 2026-06-12 | 2026-07-21
22 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-031 | Special items-Corrosion Probe & Coupon | 5-5 | PI | N | L3 | LA |  | MCMURRAY HUGHES | RIBO (RCSL) | RIBO (RCSL)-制裁 |  |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2027-02-03 | 2027-02-23 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 24 | 168 | 2027-03-25 | 2027-05-23 | 58 | Liu Lei
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-031 | Special items-Corrosion Probe & Coupon | 5-5 | PI | N | L3 | LA |  | Cosasco | Cosasco | Cosasco-TC-用香港代理签 |  |  | SH | F | [6 empty] | 2026-09-25 | 2026-10-09 |  | 2026-10-09 | 2026-10-13 | 2026-10-20 | 2026-11-17 | 2026-12-01 | 2026-12-31 | 2026-12-31 | 2027-01-02 | 2027-02-04 | 2027-02-24 | 2027-03-26 | 2027-03-28 | 2027-04-24 |  |  | 2027-03-26
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-031 | Special items-Corrosion Probe & Coupon | 5-5 | PI | N | L3 | LA |  | Clampon |  | Clampon |  |  | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-24 | 2026-06-12 | 2026-06-12 | 2026-07-22
23 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-024 | Special items-Portable Valve Actuator | 5-5 | PI | N | L4 | LA |  | Modec-France | Modec-France |  |  |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-09-21 | 2026-09-28 |  | 2026-10-12 | 2026-10-16 | 2026-10-23 | 2026-11-20 | 2026-12-04 | 2027-01-03 | 2027-01-03 | 2027-01-05 | 2027-04-04 | 2027-04-24 | 2027-05-24 | 2027-05-27 | 2027-06-23 | 24 | 168 | 2027-03-25 | 2027-06-23 | 86 | Liu Lei
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-024 | Special items-Portable Valve Actuator | 5-5 | PI | N | L4 | LA |  | Sofis-Netherlands | Sofis-Netherlands |  |  |  | SH | F | [6 empty] | 2026-09-25 | 2026-09-28 |  | 2026-10-12 | 2026-10-16 | 2026-10-23 | 2026-11-20 | 2026-12-04 | 2027-01-03 | 2027-01-03 | 2027-01-05 | 2027-04-04 | 2027-04-24 | 2027-05-24 | 2027-05-27 | 2027-06-23 |  |  | 2027-03-29
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-024 | Special items-Portable Valve Actuator | 5-5 | PI | N | L4 | LA |  | Valtorx-declined |  |  |  |  | SH | A | 2026-08-17 | 2026-05-06 | 2026-05-24 | 2026-08-17 | 2026-08-17 | 2026-08-28
24 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-019 | Special items-Strainers | 5-5 | PI | N | L3 | LA | MULTIPHASE(Barton Firtop) | Trelleborg-trade sanction | Trelleborg |  |  |  | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-04 | 2026-11-04 | 2026-11-06 | 2027-02-03 | 2027-02-23 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 32 | 224 | 2027-03-25 | 2027-04-08 | 28 | Liu Lei
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-019 | Special items-Strainers | 5-5 | PI | N | L3 | LA | ZM169-WP1-PO-PIP-005 | Eaton-no reply |  |  |  |  | SH | F | [7 empty] | 2026-09-25 | 2026-09-16 | 2026-09-24 | 2026-09-29 | 2026-10-13 | 2026-11-10 | 2026-11-24 | 2026-12-24 | 2026-12-24 | 2026-12-26 | 2027-01-20 | 2027-02-09 | 2027-03-11 | 2027-03-28 | 2027-04-24 | 24 | 168 | 2027-03-11 |  |  | CIF Zhuhai Port | [12 empty] | ZWP20-23 | 22 weeks
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-019 | Special items-Strainers | 5-5 | PI | N | L3 | LA |  | MULTIPHASE | MULTIPHASE | MULTIPHASE(Barton) | MULTIPHASE(Barton) | MULTIPHASE(Barto) | SH | A | 2026-06-01 | 2026-05-06 | 2026-05-24 | 2026-06-10 | 2026-06-10 | 2026-07-22 | C1:2026/8/28 C2:2026/9/18 | C1:11-Sep | Reject by vendor | 2026-10-12: Pending |  |  | CD+7
25 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barred Tees | 5-5 | PI | N | L3 | LA |  | BASSI LUIGI | BASSI LUIGI | BASSI LUIGI |  |  | SH | P | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-05 | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 28 | 196 | 2027-04-27 | 2027-05-23 | 31 | Lin Yazhen | 2026.6.8 Short bidder list to CPY for approval | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | 24 weeks FCA from approval of manufacturing drawing and procedures (Summer / Christmas shutdown excluded)
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barred Tees | 5-5 | PI | N | L3 | LA |  | COPROSIDER S.R.L. | COPROSIDER-holiday | TECTUBI |  |  | SH | F | [7 empty] | 2026-09-23 | 2026-09-24 | 2026-10-08 | 2026-10-12 | 2026-10-19 | 2026-11-16 | 2026-11-30 | 2026-12-30 | 2026-12-30 | 2027-01-01 | 2027-03-08 | 2027-03-23 | 2027-04-22 | 2027-04-30 | 2027-05-27 |  |  | 2027-04-22 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2 | 12/14 WORKING WEEKS FROM PIM DATE.(Working weeks means by excluding 2 weeks of August and 2 weeks of Christmas shut-down)
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barred Tees | 5-5 | PI | N | L3 | LA |  | VIAR MECCANICA SRL, TECTUBI RACCORDI | VIAR MECCANICA SRL,TECTUBI RACCORDI |  |  |  | SH | A | 2026-06-11 | 2026-05-06 | 2026-05-24 | 2026-06-11 | 2026-06-11 | 2026-06-22 | 2026-09-11 | [22 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder3 | EXW Italy 24-32 weeks after PO
26 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barrel Reducer (For PIG L&R) | 5-5 | PI | N | L3 | LA | Combine with Barred tee | BASSI LUIGI | BASSI LUIGI | BASSI LUIGI |  |  | SH | P | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-05 | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 28 | 196 | 2027-04-27 | 2027-05-23 | 31 | Lin Yazhen |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | 24 weeks FCA from approval of manufacturing drawing and procedures (Summer / Christmas shutdown excluded)
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barrel Reducer (For PIG L&R) | 5-5 | PI | N | L3 | LA |  | COPROSIDER S.R.L. | COPROSIDER S.R.L. | TECTUBI |  |  | SH | F | [7 empty] | 2026-09-23 | 2026-09-24 | 2026-10-08 | 2026-10-12 | 2026-10-19 | 2026-11-16 | 2026-11-30 | 2026-12-30 | 2026-12-30 | 2027-01-01 | 2027-03-08 | 2027-03-23 | 2027-04-22 | 2027-04-30 | 2027-05-27 |  |  | 2027-04-22 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2 | 12/14 WORKING WEEKS FROM PIM DATE.(Working weeks means by excluding 2 weeks of August and 2 weeks of Christmas shut-down)
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-025 | Special items-Barrel Reducer (For PIG L&R) | 5-5 | PI | N | L3 | LA |  | VIAR MECCANICA SRL,TECTUBI RACCORDI | VIAR MECCANICA SRL,TECTUBI RACCORDI |  |  |  | SH | A | 2026-06-11 | 2026-05-06 | 2026-05-24 | 2026-06-11 | 2026-06-11 | 2026-06-22 | 2026-09-11 | [22 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder3 | EXW Italy 24-32 weeks after PO
27 | MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-026 | PIPELINE BULK (B31.8)-3D Bend | 5-5 | PI | N | L2 | LA |  | BASSI LUIGI | BASSI LUIGI,MERITUS | Hebei Shengtian-TC(7 weeks) |  |  | SH | P | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-05 | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 28 | 196 | 2027-04-27 | 2027-03-05 | 5 | Liu Lei |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder1 | Delivery time FCA Italy : 24-30 weeks, from approval of manufacturing drawing and procedures |  | (Summer / Christmas shutdown excluded)
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-026 | PIPELINE BULK (B31.8)-3D Bend | 5-5 | PI | N | L2 | LA |  | COPROSIDER S.R.L. | COPROSIDER S.R.L. | Roc-Master |  |  | SH | F | [8 empty] | 2026-09-22 | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 |  |  | 2027-02-28 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder2
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-026 | PIPELINE BULK (B31.8)-3D Bend | 5-5 | PI | N | L2 | LA |  | VIAR MECCANICA SRL,TECTUBI RACCORDI | VIAR MECCANICA SRL,TECTUBI RACCORDI | Julong |  |  | SH | A | 2026-07-28 | 2026-07-14 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-08-25 | No need | No Need | [21 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Bidder3 | FCA SIMAS workshop, 42-44 working weeks after PO receipt and documents approval
28 | MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Flanges | 5-5 | PI | N | L3 | LA | Galperti | [5 empty] | ZH | P | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-05 | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 28 | 196 | 2027-04-27 | 2027-04-23 | 26 | Kuang Yuanna
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Flanges | 5-5 | PI | N | L3 | LA | [6 empty] | ZH | F | [8 empty] | 2026-09-24 | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 |  |  | 2027-04-27
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Flanges | 5-5 | PI | N | L3 | LA | [6 empty] | ZH | A | 2026-08-16 | 2026-07-14 | 2026-07-28 | 2026-08-16 | 2026-08-16 | 2026-09-01 | No need | No Need
29 | MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Pipes (include material B31.8 for PIG L&R) | 5-5 | PI | N | L3 | LA | Julong | [5 empty] | ZH | P | 2026-07-17 | 2026-07-20 | 2026-07-27 | 2026-07-28 | 2026-08-05 | 2026-08-19 | 2026-09-16 | 2026-09-21 |  | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 28 | 196 | 2027-04-27 | 2027-04-23 | 23 | Wei Kefang | [12 empty] | LSAW | 2026-10-30 | 50m
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Pipes (include material B31.8 for PIG L&R) | 5-5 | PI | N | L3 | LA | [6 empty] | ZH | F | [9 empty] | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-11-19 | 2026-12-03 | 2027-01-02 | 2027-01-02 | 2027-01-04 | 2027-03-08 | 2027-03-28 | 2027-03-31 | 2027-04-05 | 2027-05-05 |  |  | 2026-10-30 | [15 empty] | Seamless | 2027-03-31 | 24m
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Pipes (include material B31.8 for PIG L&R) | 5-5 | PI | N | L3 | LA | [6 empty] | ZH | F | [8 empty] | 2026-09-24 | [15 empty] | 2027-03-31
| MM-ZTK-1F-GEN-PIP-MR-0004 | RFQ-PIP-033 | PIPELINE BULK (B31.8)-Pipes (include material B31.8 for PIG L&R) | 5-5 | PI | N | L3 | LA | [6 empty] | ZH | A | 2026-08-16 | 2026-07-14 | 2026-07-28 | 2026-08-16 | 2026-08-16 | 2026-09-11 | No need | No Need
|  | RFQ-PIP-007 | SPECIAL PIPE SUPPORT | 5-5 | PI | N | L4 | LC | As dicussed with ENG, it mabe has no special support. So it will confirm later | [5 empty] | SH | P | 2026-06-01 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-07-24 | 2026-07-31 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-15 | 2026-09-29 | 2026-10-29 | 2026-10-29 | 2026-11-01 | 2027-01-12 | 2027-01-22 | 2027-01-29 | 2027-02-01 | 2027-02-28 | 24 | 168 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | RFQ-PIP-007 | SPECIAL PIPE SUPPORT | 5-5 | PI | N | L4 | LC | [6 empty] | SH | F | 2026-06-20 | 2026-06-10 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-07-01 | 2026-07-10 | 2026-07-24 |  | 2026-07-31 | 2026-08-04 | 2026-08-11 | 2026-08-26 | 2026-09-09 | 2026-10-09 | 2026-10-09 | 2026-10-12 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | RFQ-PIP-007 | SPECIAL PIPE SUPPORT | 5-5 | PI | N | L4 | LC | [6 empty] | SH | A | [29 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
30 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-008 | CS Fitting | 5-5 | PI | N | L3 | LD | Roc-master (FA) | [5 empty] | ZH | P | 2026-06-16 | 2026-06-19 | 2026-06-26 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 2026-07-20 | 2026-07-22 |  | 2026-07-29 | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-09-04 | 2026-09-11 | 2026-09-11 | 2026-09-13 | 2026-10-17 | 2026-10-22 | 2026-10-27 | 2026-10-30 | 2026-11-26 | 12.8571 | 90 | 2026-10-27 | 2026-11-24 | 8 | Kuang Yuanna |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZH26FA020 (01) | 2026-11-16
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-008 | CS Fitting | 5-5 | PI | N | L3 | LD | [6 empty] | ZH | F | [12 empty] | 2026-09-24 | 2026-10-08 | 2026-10-15 | 2026-10-15 | 2026-10-17 | 2026-11-06 | 2026-11-11 | 2026-11-16 | 2026-11-19 | 2026-11-26 |  |  | 2026-11-16 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-008 | CS Fitting | 5-5 | PI | N | L3 | LD | [6 empty] | ZH | A | 2026-06-11 | 2026-05-06 | 2026-05-23 | 2026-06-11 | 2026-06-11 | 2026-07-10 | 2026-07-27 | 2026/8/12 2026/8/20 |  | 2026-10-13: FA:2026/8/21 PO:1-Sep-26; 2026-10-15: 2026-09-01; 2026-10-22: No need | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
31 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-009 | SS & DSS Fitting | 5-5 | PI | N | L3 | LC | Roc-master (FA) | [5 empty] | ZH | P | 2026-05-26 | 2026-05-29 | 2026-06-09 | 2026-06-10 | 2026-06-17 | 2026-07-02 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-14 | 2026-09-28 | 2026-10-28 | 2026-10-28 | 2026-10-30 | 2026-12-24 | 2026-12-29 | 2027-01-28 | 2027-01-31 | 2027-02-27 | 24 | 168 | 2027-01-28 | 2026-12-23 | 37 | Kuang Yuanna | 2026.5.31 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZH26FA020 (01) | 2026-11-16
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-009 | SS & DSS Fitting | 5-5 | PI | N | L3 | LC | [6 empty] | ZH | F | [12 empty] | 2026-09-24 | 2026-10-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2026-11-06 | 2026-11-11 | 2026-11-16 | 2026-11-19 | 2027-02-27 |  |  | 2026-11-16 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-009 | SS & DSS Fitting | 5-5 | PI | N | L3 | LC | [6 empty] | ZH | A | 2026-06-11 | 2026-05-06 | 2026-05-23 | 2026-06-11 | 2026-06-11 | 2026-07-11 | 2026-07-27 | 2026/8/11 2026/8/20 |  | 2026-10-13: FA:2026/8/21 PO:1-Sep-26; 2026-10-15: 2026-09-01; 2026-10-22: No need | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
32 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-010 | CS Flange | 5-5 | PI | N | L3 | LD | Jiangyin Zhongnan (FA) | [5 empty] | ZH | P | 2026-08-20 | 2026-08-25 | 2026-09-01 | 2026-09-02 | 2026-09-07 | 2026-09-14 | 2026-09-23 | 2026-09-25 |  | 2026-10-09 | 2026-10-13 | 2026-10-20 | 2026-11-03 | 2026-11-17 | 2026-11-27 | 2026-11-27 | 2026-11-29 | 2026-12-29 | 2027-01-03 | 2027-01-07 | 2027-01-10 | 2027-02-06 | 12.8571 | 90 | 2027-01-07 | 2026-12-08 | 32 | Kuang Yuanna |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZH26FA021 (01) | 2026-11-06
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-010 | CS Flange | 5-5 | PI | N | L3 | LD | [6 empty] | ZH | F | [12 empty] | 2026-11-03 | 2026-11-17 | 2026-11-27 | 2026-11-27 | 2026-11-29 | 2026-10-28 | 2026-11-02 | 2026-11-06 | 2026-11-11 | 2026-12-11 |  |  | 2026-11-06 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-010 | CS Flange | 5-5 | PI | N | L3 | LD | [6 empty] | ZH | A | 2026-06-11 | 2026-05-06 | 2026-05-23 | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-27 | 2026/8/12 2026/8/20 |  | 2026-10-13: FA:2026/8/21 PO:1-Sep-26; 2026-10-15: 2026-09-01; 2026-10-22: No need | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
33 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-011 | SS & DSS Flange | 5-5 | PI | N | L3 | LC | Roc-master (FA) |  | MELESI | MELESI | MELESI |  | ZH | P | 2026-06-18 | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-09 | 2026-07-23 | 2026-08-18 | 2026-08-21 |  | 2026-09-04 | 2026-09-08 | 2026-09-15 | 2026-10-14 | 2026-10-29 | 2026-11-28 | 2026-11-28 | 2026-11-30 | 2026-11-29 09:36 | 2026-12-04 09:36 | 2027-01-03 09:36 | 2027-01-06 09:36 | 2027-02-02 09:36 | 17.2 | 120.4 | 2027-01-03 09:36 | 2027-01-23 | 83 | Kuang Yuanna | 2026.5.31 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZH26FA020 (01) | 2026-11-01
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-011 | SS & DSS Flange | 5-5 | PI | N | L3 | LC |  |  | GALPERTI | GALPERTI | GALPERTI |  | ZH | F | [13 empty] | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-11-01 | 2026-11-06 | 2026-12-06 |  |  | 2026-11-01 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-011 | SS & DSS Flange | 5-5 | PI | N | L3 | LC |  |  | Roc-Master | Roc-Master(AVL with condition) | Roc-Master(AVL with condition) |  | ZH | A | 2026-06-11 | 2026-05-06 | 2026-05-23 | 2026-06-11 | 2026-06-11 | 2026-06-26 | 2026-07-17 | 2026-08-12 |  | 2026-10-13: FA:2026/8/21 PO:1-Sep-26; 2026-10-15: 2026-09-01; 2026-10-22: No need; 2026-11-19: 2026-09-09 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-012 | SAW Welded Pipe | 5-5 | PI | N | L3 | LD | Merge with CS pipes | [5 empty] | ZH | P | 2026-06-26 | 2026-07-01 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-21 | 2026-08-03 | 2026-08-05 |  | 2026-08-12 | 2026-08-14 | 2026-08-21 | 2026-09-04 | 2026-09-18 | 2026-09-28 | 2026-09-28 | 2026-09-30 | 2026-10-29 | 2026-11-03 | 2026-11-10 | 2026-11-13 | 2026-12-10 | 12.8571 | 90 | 2026-11-10 |  |  |  | To apply for changing to seamless pipes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-012 | SAW Welded Pipe | 5-5 | PI | N | L3 | LD | [6 empty] | ZH | F | [5 empty] | 2026-08-20 | 2026-08-03 | 2026-08-18 |  | 2026-08-18 | 2026-08-20 | 2026-08-27 | 2026-09-10 | 2026-09-24 | 2026-10-04 | 2026-10-04 | 2026-10-06 | 2026-11-04 | 2026-11-09 | 2026-11-16 | 2026-11-13 | 2026-12-10 |  |  | 2026-11-16 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-012 | SAW Welded Pipe | 5-5 | PI | N | L3 | LD | [6 empty] | ZH | A | 2026-06-12 | 2026-05-06 | 2026-05-23 | 2026-06-24 | 2026-06-24 | [24 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
34 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-013 | CS Pipe | 5-5 | PI | N | L3 | LD | Yangzhou Chengde | [5 empty] | ZH | P | 2026-06-16 | 2026-06-19 | 2026-06-26 | 2026-06-29 | 2026-07-02 | 2026-07-09 | 2026-07-20 | 2026-07-22 |  | 2026-07-29 | 2026-07-31 | 2026-08-07 | 2026-08-21 | 2026-09-04 | 2026-09-14 | 2026-09-14 | 2026-09-16 | 2026-10-18 | 2026-10-23 | 2026-10-27 | 2026-10-30 | 2026-11-26 | 12.8571 | 90 | 2026-10-27 | 2026-11-22 | 23 | Wei Kefang |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZH/26/FA022(01) | 2026-10-30
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-013 | CS Pipe | 5-5 | PI | N | L3 | LD | [6 empty] | ZH | F | [12 empty] | 2026-09-24 | 2026-10-08 | 2026-10-18 | 2026-10-18 | 2026-10-20 | 2026-10-21 | 2026-10-26 | 2026-10-30 | 2026-11-02 | 2026-12-02 |  |  | 2026-10-30 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-013 | CS Pipe | 5-5 | PI | N | L3 | LD | include SAW Welded Pipe and seamless pipe | [5 empty] | ZH | A | 2026-06-12 | 2026-05-06 | 2026-05-23 | 2026-06-24 | 2026-06-24 | 2026-07-09 | C1:2026/7/27 C2:2026/8/17 C3:2026/8/19 | 2026-08-29 |  | 2026-10-13: 2026-09-01; 2026-10-15: 2026-09-03; 2026-10-22: No need | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
35 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-014 | DSS Pipes and Seamless SS pipes | 5-5 | PI | N | L3 | LC | JJ Advance |  |  | JJ Advance | JJ Advance |  | ZH | P | 2026-05-26 | 2026-05-29 | 2026-06-09 | 2026-06-10 | 2026-06-17 | 2026-07-02 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-14 | 2026-09-28 | 2026-10-28 | 2026-10-28 | 2026-10-30 | 2026-12-24 | 2026-12-29 | 2027-01-28 | 2027-01-31 | 2027-02-27 | 24 | 168 | 2027-01-28 | 2026-12-23 | 20 | Wei Kefang | 2026.5.31 MR issued yard 2026.8.9 Domestic sullier cannot meet hot drawn requirement.Sourcing other vendors. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZH26PO0724 | 4-6 weeks
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-014 | DSS Pipes and Seamless SS pipes | 5-5 | PI | N | L3 | LC |  |  |  | Tubacex | Tubacex |  | ZH | F | [12 empty] | 2026-09-28 | 2026-10-12 | 2026-10-15 | 2026-10-15 | 2026-10-17 | 2026-10-29 | 2026-11-03 | 2026-12-03 | 2026-12-06 | 2027-01-05 | 7 | 49 | 2026-10-22 |  |  | CIF Guangzhou port |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZH26PO0724 | 10-12 weeks
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-014 | DSS Pipes and Seamless SS pipes |  | PI | N | L3 | LC | [6 empty] | ZH | F | [22 empty] | 13 | 91 | 2026-12-03
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-014 | DSS Pipes and Seamless SS pipes | 5-5 | PI | N | L3 | LC | [6 empty] | ZH | A | 2026-06-11 | 2026-05-06 | 2026-05-23 | 2026-06-12 | 2026-06-12 | 2026-07-06 | 2026-08-28 | 2026-08-29 |  | 2026-10-13: 2026-09-03; 2026-10-15: 2026-09-18; 2026-10-22: No need |  |  | CD+7 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-015 | Seamless SS pipes | 5-5 | PI | N | L3 | LD | merged with DSS pipes | [5 empty] | ZH | P | 2026-06-26 | 2026-07-01 | 2026-07-08 | 2026-07-09 | 2026-07-14 | 2026-07-21 | 2026-08-03 | 2026-08-05 |  | 2026-08-12 | 2026-08-14 | 2026-08-21 | 2026-09-04 | 2026-09-18 | 2026-10-08 | 2026-10-08 | 2026-10-10 | 2026-10-31 | 2026-11-05 | 2026-11-10 | 2026-11-13 | 2026-12-10 | 12.8571 | 90 | 2026-11-10 |  |  |  | 2026.5.31 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-015 | Seamless SS pipes | 5-5 | PI | N | L3 | LD | [6 empty] | ZH | F | [6 empty] | 2026-08-03 | 2026-08-18 |  | 2026-08-18 | 2026-08-20 | 2026-08-27 | 2026-09-10 | 2026-09-24 | 2026-10-14 | 2026-10-14 | 2026-10-16 | 2026-11-06 | 2026-11-11 | 2026-11-16 | 2026-11-13 | 2026-12-10 |  |  | 2026-11-16 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-015 | Seamless SS pipes | 5-5 | PI | N | L3 | LD | [6 empty] | ZH | A | 2026-06-12 | 2026-05-06 | 2026-05-23 | 2026-06-18 | 2026-06-18 | 2026-06-26 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
36 | MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-034 | UPVC Pipes, Fitting and Flanges | 5-5 | PI | N | L3 | LC | [6 empty] | ZH | P | 2026-07-28 | 2026-05-29 | 2026-06-09 | 2026-07-30 | 2026-07-29 | 2026-08-04 | 2026-08-24 | 2026-09-07 |  | 2026-09-18 | 2026-09-22 | 2026-09-30 | 2026-10-28 | 2026-11-11 | 2026-12-11 | 2026-12-11 | 2026-12-13 | 2026-11-12 | 2026-11-17 | 2026-12-17 | 2027-01-31 | 2027-02-27 | 12.8571 | 90 | 2027-01-28 | 2027-02-08 | 32 | Wei Kefang | 2026.7.17 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-034 | UPVC Pipes, Fitting and Flanges | 5-5 | PI | N | L3 | LC | [6 empty] | ZH | F | [7 empty] | 2026-09-30 |  | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-11-03 | 2026-11-17 | 2026-12-17 | 2026-12-17 | 2026-12-19 | 2026-12-03 | 2026-12-08 | 2027-01-07 | 2027-01-31 | 2027-02-27 |  |  | 2027-01-07 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0002 | RFQ-PIP-034 | UPVC Pipes, Fitting and Flanges | 5-5 | PI | N | L3 | LC | [6 empty] | ZH | A | 2026-06-12 | 2026-05-06 | 2026-05-23 | 2026-07-19 | 2026-07-19 | 2026-08-10 | 2026-09-16 | [22 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-SPE-0002 | RFQ-PIP-018-1 | Pig launcher and receiver | 4-6 | PI | N | L2 | LA | no separate procurement item for the Pig Launcher and Receiver. The Pig Launcher/Receiver will be procured as individual components, including loose piping (RFQ-PIP-013), pipeline (Saw Welded Pipe, RFQ-PIP-012), Quick Opening Closure (RFQ-PIP-018), and barrel reducers. | [5 empty] | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-09 | 2026-11-12 | 2026-11-15 | 2027-02-23 | 2027-03-10 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 32 | 224 | 2027-03-25 | 2027-04-23 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-SPE-0002 | RFQ-PIP-018-1 | Pig launcher and receiver | 4-6 | PI | N | L2 | LA | [6 empty] | SH | F | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-09 | 2026-11-12 | 2026-11-15 | 2027-02-28 | 2027-03-15 | 2027-03-30 | 2027-03-28 | 2027-04-24 |  |  | 2027-03-30 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-SPE-0002 | RFQ-PIP-018-1 | Pig launcher and receiver | 4-6 | PI | N | L2 | LA | [6 empty] | SH | A | [29 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
37 | MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-018-2 | Special irems-Quick Opening Closure (For PIG L&R) | 4-6 | PI | N | L3 | LA | TDW |  | G.D.ENGINEERING | G.D.ENGINEERING | G.D.ENGINEERING | G.D.ENGINEERING | ZH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-11-09 | 2026-11-12 | 2026-11-15 | 2027-02-23 | 2027-03-10 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 32 | 224 | 2027-03-25 | 2027-04-20 | 26 | Zahng Xiaorui | 2026.6.9 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | after drawing approved | 20-22 weeks
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-018-2 | Special items-Quick Opening Closure (For PIG L&R) | 4-6 | PI | N | L3 | LA |  |  | TDW | TDW | TDW | TDW | ZH | F | [12 empty] | 2026-09-25 | 2026-10-09 | 2026-11-08 | 2026-11-11 | 2026-11-14 | 2027-02-23 | 2027-03-10 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 28 | 196 | 2027-03-25 |  |  | DDP Zhuhai Yard |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-PIP-MR-0003 | RFQ-PIP-018-2 | Special irems-Quick Opening Closure (For PIG L&R) | 4-6 | PI | N | L3 | LA | [6 empty] | ZH | A | 2026-06-01 | 2026-05-06 | 2026-05-23 | 2026-06-10 | 2026-06-10 | 2026-06-25 | C1:2026/7/25 C2:2026/8/17 | 2026/8/11 2026/8/18 | 2026-09-03 | 2026-10-13: 2026-09-10; 2026-10-15: 2026-09-16; 2026-10-22: 2026-09-10 | [7 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
38 |  | RFQ-PIP-027 | Coating | 5-4 | PI | N | L4 | LD | JOTUN | [5 empty] | ZH | P | 2026-07-21 | 2026-07-13 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-13 | 2026-08-27 |  | 2026-09-04 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-15 |  |  |  |  | 2026-10-25 | 2026-10-30 | 2026-11-02 | 2026-11-29 | 8 | 56 | 2026-10-30 | 2026-12-15 | 46 | Zheng Hanliang | [13 empty] | 20 days
|  | RFQ-PIP-027 | Coating | 5-4 | PI | N | L4 | LD | [6 empty] | ZH | F | [9 empty] | 2026-10-22: 2026-09-24; 2026-11-19: 2026-10-16; 2026-12-03: 2026-11-02; 2027-03-28: 2026-10-25; 2027-03-31: 2026-10-30; 2027-04-05: 2026-11-02; 2027-05-05: 2026-11-29 |  |  | 2026-10-30
|  | RFQ-PIP-027 | Coating | 5-4 | PI | N | L4 | LD | [6 empty] | ZH | A | 2026-07-14 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-24 | No need | No Need |  | 2026-10-13: 2026-09-18; 2026-10-15: 2026-09-18
39 | MM-ZTK-1F-GEN-ELE-MR-0001 | RFQ-EL-001 | Solar Power System | 4-26 | EL | N | L3 | LA | Swift | Swift | Swift | Swift | Swift | Swift | SH | P | 2026-04-24 | 2026-04-27 | 2026-05-06 | 2026-05-07 | 2026-05-14 | 2026-05-28 | 2026-06-29 | 2026-07-02 |  | 2026-07-16 | 2026-07-20 | 2026-07-27 | 2026-08-24 | 2026-09-07 | 2026-09-27 | 2026-09-27 | 2026-09-30 | 2027-02-28 | 2027-03-15 | 2027-03-25 | 2027-03-28 | 2027-04-24 | 36 | 252 | 2027-03-25 | 2027-07-03 | 113 | Liu Lei | 2026.4.30 Issued RFQ bid due day:22-May | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-ELE-MR-0001 | RFQ-EL-001 | Solar Power System | 4-26 | EL | N | L3 | LA | ZM169-WP1-PO-ELE-001 | Semitech | Semitech | Semitech(AVL condition) | Semitech | Semitech | SH | F | [13 empty] | 2026-09-28 | 2026-10-18 | 2026-10-18 | 2026-10-21 | 2027-02-10 | 2027-03-02 | 2027-03-12 | 2027-03-28 | 2027-04-24 | 32 | 224 | 2027-03-12 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2027-03-05
| MM-ZTK-1F-GEN-ELE-MR-0001 | RFQ-EL-001 | Solar Power System | 4-26 | EL | N | L3 | LA |  | MDS(ORGA) | MDS(ORGA) |  | MDS(ORGA) |  | SH | A | 2026-04-21 | 2026-04-24 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-22 | 2026-07-02 | 2026-07-04 | 2026-07-24 | 2026-10-13: 2026-08-07; 2026-10-15: 2026-08-28; 2026-10-22: 2026-07-30; 2026-11-19: 2026-08-19 |  |  | CD+7 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
40 | MM-ZTK-1F-GEN-ELE-MR-0002 | RFQ-EL-002 | DC Distribution Boards |  | EL | Y | L3 | LB | Swift | Swift | Swift | Swift | Swift | Swift | SH | P | 2026-04-24 | 2026-04-27 | 2026-05-06 | 2026-05-07 | 2026-05-14 | 2026-05-28 | 2026-06-29 | 2026-07-02 |  | 2026-07-16 | 2026-07-20 | 2026-07-27 | 2026-08-24 | 2026-09-07 | 2026-09-27 | 2026-09-27 | 2026-09-30 | 2027-03-23 | 2027-04-12 | 2027-04-22 | 2027-04-25 | 2027-05-22 | 40 | 280 | 2027-04-16 | 2027-04-21 | 40 | Liu Lei | 2026.4.30 Issued RFQ bid due day:22-May | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-ELE-MR-0002 | RFQ-EL-002 | DC Distribution Boards |  | EL | Y | L3 | LB | ZM169-WP1-PO-ELE-001 | Semitech | Semitech |  | Semitech |  | SH | F | [13 empty] | 2026-09-28 | 2026-10-18 | 2026-10-18 | 2026-10-21 | 2027-02-10 | 2027-03-02 | 2027-03-12 | 2027-04-19 | 2027-05-16 | 32 | 224 | 2027-03-12 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2027-03-05
| MM-ZTK-1F-GEN-ELE-MR-0002 | RFQ-EL-002 | DC Distribution Boards |  | EL | Y | L3 | LB |  | MDS(ORGA) | MDS(ORGA) | MDS(ORGA) | MDS(ORGA) | MDS(ORGA) | SH | A | 2026-04-21 | 2026-04-28 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-22 | 2026-07-07 | 2026-07-08 | 2026-07-24 | 2026-10-13: 2026-08-07; 2026-10-15: 2026-08-28; 2026-10-22: 2026-07-30; 2026-11-19: 2026-08-19 |  |  | CD+7 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
41 | MM-ZTK-1F-GEN-ELE-MR-0003 | RFQ-EL-003 | AC Distribution Boards | 4-24 | EL | Y | L3 | LB | Swift | Swift | Swift | Swift(AVL condition) | Swift | Swift | SH | P | 2026-04-24 | 2026-04-27 | 2026-05-06 | 2026-05-07 | 2026-05-14 | 2026-05-28 | 2026-06-29 | 2026-07-02 |  | 2026-07-16 | 2026-07-20 | 2026-07-27 | 2026-08-24 | 2026-09-07 | 2026-09-27 | 2026-09-27 | 2026-09-30 | 2027-03-23 | 2027-04-12 | 2027-04-22 | 2027-04-25 | 2027-05-22 | 40 | 280 | 2027-04-16 | 2027-04-21 | 40 | Liu Lei | 2026.4.30 Issued RFQ bid due day:22-May | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-ELE-MR-0003 | RFQ-EL-003 | AC Distribution Boards | 4-24 | EL | Y | L3 | LB | ZM169-WP1-PO-ELE-001 | Semitech | Semitech |  | Semitech |  | SH | F | [13 empty] | 2026-09-28 | 2026-10-18 | 2026-10-18 | 2026-10-21 | 2027-02-10 | 2027-03-02 | 2027-03-12 | 2027-04-19 | 2027-05-16 | 32 | 224 | 2027-03-12 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2027-03-05
| MM-ZTK-1F-GEN-ELE-MR-0003 | RFQ-EL-003 | AC Distribution Boards | 4-24 | EL | Y | L3 | LB |  | MDS(ORGA) | MDS(ORGA) | MDS(ORGA) | MDS(ORGA) | MDS(ORGA) | SH | A | 2026-04-21 | 2026-04-28 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-22 | 2026-07-07 | 2026-07-12 | 2026-07-24 | 2026-10-13: 2026-08-07; 2026-10-15: 2026-08-28; 2026-10-22: 2026-07-30; 2026-11-19: 2026-08-19 |  |  | CD+7 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
42 | MM-ZTK-1F-GEN-ELE-MR-0004 | RFQ-EL-004 | Navigation Aid, Red Lantern, Flashing Beacon, Warning Siren and Fog Horn | 4-25 | EL | Y | L4 | LB | Swift | MDS(ORGA,TIDELAND) | MDS(ORGA,TIDELAND) | MDS(ORGA,TIDELAND) | MDS(ORGA,TIDELAND) | MDS(ORGA,TIDELAND) | SH | P | 2026-05-07 | 2026-05-08 | 2026-05-15 | 2026-05-18 | 2026-05-25 | 2026-06-08 | 2026-07-06 | 2026-07-09 |  | 2026-07-23 | 2026-07-27 | 2026-08-03 | 2026-08-31 | 2026-09-14 | 2026-10-14 | 2026-10-14 | 2026-10-17 | 2027-03-24 | 2027-04-13 | 2027-05-13 | 2027-05-16 | 2027-06-12 | 42 | 294 | 2027-05-13 | 2027-04-29 | 48 | Liu Lei | 2026.4.30 Issued RFQ bid due day:22-May Bidder 1: Received bid on 17 May | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-ELE-MR-0004 | RFQ-EL-004 | Navigation Aid, Red Lantern, Flashing Beacon, Warning Siren and Fog Horn | 4-25 | EL | Y | L4 | LB | ZM169-WP1-PO-ELE-001 | Swift | Swift | Swift | Swift | Swift | SH | F | [13 empty] | 2026-09-28 | 2026-10-28 | 2026-10-28 | 2026-10-31 | 2027-01-21 | 2027-02-10 | 2027-03-12 | 2027-05-16 | 2027-06-12 | 32 | 224 | 2027-03-12 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ZWP20-23 | 2027-03-05
| MM-ZTK-1F-GEN-ELE-MR-0004 | RFQ-EL-004 | Navigation Aid, Red Lantern, Flashing Beacon, Warning Siren and Fog Horn | 4-25 | EL | Y | L4 | LB |  | PHAROS MARINE | PHAROS MARINE |  | PHAROS MARINE |  | SH | A | 2026-04-21 | 2026-04-30 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-21 | 2026-07-10 | 2026-08-02 | 2026-08-02 | 2026-10-13: 2026-08-07; 2026-10-15: 2026-08-28; 2026-10-22: 2026-07-30; 2026-11-19: 2026-08-19 |  |  | CD+7 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
43 | MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-005 | EL Cable | 5-7 | EL | N | L3 | LD |  | Baosheng |  |  |  |  | ZH | P | 2026-08-28 | 2026-08-24 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-23 | 2026-10-07 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16 | 2027-05-17 | 121 | Kuang Yuena | 2026.6.4 MR issued yard | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-005 | EL Cable | 5-7 | EL | N | L3 | LD |  | Nexan |  |  |  |  | ZH | F | [6 empty] | 2026-09-23 | 2026-10-07 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-16 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-005 | EL Cable | 5-7 | EL | N | L3 | LD | [6 empty] | ZH | A | 2026-06-16 | 2026-05-18 | 2026-06-15 | 2026-06-17 | 2026-06-17 | 2026-07-09 | [23 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-006 | E&I Cable Gland | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | P | 2026-08-28 | 2026-08-24 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-23 | 2026-10-07 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16 | 2027-06-18 | 153
| MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-006 | E&I Cable Gland | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | F | 2026-09-08 | 2026-08-24 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-17 | 2026-09-28 | 2026-10-12 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-16
| MM-ZTK-1F-GEN-ELE-MR-0005 | RFQ-EL-006 | E&I Cable Gland | 5-7 | EL | N | L4 | LD | combined with RFQ-EL-010 | [5 empty] | ZH | A
44 | MM-ZTK-1F-GEN-ELE-MR-0006 | RFQ-EL-007 | Electrical Lighting Fixtures | 5-7 | EL | N | L4 | LD | Cooper China |  | Chalmit | Chalmit | Chalmit |  | ZH | P | 2026-06-03 | 2026-05-26 | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2026-06-16 | 2026-07-23 | 2026-08-06 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-07 | 2026-09-22 | 2026-10-02 | 2026-10-02 | 2026-10-04 | 2027-02-10 | 2027-02-20 | 2027-02-25 | 2027-02-28 | 2027-03-27 | 28 | 196 | 2027-01-28 | 2027-07-03 | 246 | Kuang Yuena | 2026.5.15 MR issued yard | [11 empty] | ZH26PO0691 | 2026-10-30
| MM-ZTK-1F-GEN-ELE-MR-0006 | RFQ-EL-007 | Electrical Lighting Fixtures | 5-7 | EL | N | L4 | LD |  |  | Cooper Crouse-Hinds | Cooper Crouse-Hinds | Cooper Crouse-Hinds |  | ZH | F | [12 empty] | 2026-09-25 | 2026-10-09 | 2026-10-19 | 2026-10-19 | 2026-10-21 | 2026-10-15 | 2026-10-25 | 2026-10-30 | 2027-01-31 | 2027-02-27 |  |  | 2026-10-30
| MM-ZTK-1F-GEN-ELE-MR-0006 | RFQ-EL-007 | Electrical Lighting Fixtures | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | A | 2026-06-16 | 2026-04-30 | 2026-05-18 | 2026-06-17 | 2026-06-17 | 2026-06-29 | 2026-08-05 | 2026-08-07 | 2026-08-28 | 2026-10-14: 2026-09-01; 2026-10-16: 2026-09-03; 2026-10-23: No need
45 | MM-ZTK-1F-GEN-ELE-MR-0007 | RFQ-EL-008 | E&I Cable Tray | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | P | 2026-08-28 | 2026-08-24 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-23 | 2026-10-07 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16 | 2027-04-09 | 83 |  | 2026.9.7 ENG team released MR to Procurement
| MM-ZTK-1F-GEN-ELE-MR-0007 | RFQ-EL-008 | E&I Cable Tray | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | F | 2026-09-22 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-30 | 2026-10-09 | 2026-10-27 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-16
| MM-ZTK-1F-GEN-ELE-MR-0007 | RFQ-EL-008 | E&I Cable Tray | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | A |  | 2026-06-21 | 2026-07-07
46 | MM-ZTK-1F-GEN-ELE-MR-0008 | RFQ-EL-009 | E&I Multi-Cable Transits (MCT) | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | P | 2026-08-13 | 2026-08-04 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-26 | 2026-09-04 | 2026-09-18 |  | 2026-09-28 | 2026-09-30 | 2026-10-14 | 2026-10-28 | 2026-11-11 | 2026-11-26 | 2026-11-26 | 2026-11-28 | 2027-01-04 | 2027-01-13 | 2027-01-18 | 2027-01-21 | 2027-02-17 | 16 | 112 | 2027-01-18 | 2027-06-08 | 44 |  | 2026.9.4 ENG team released MR to Procurement
| MM-ZTK-1F-GEN-ELE-MR-0008 | RFQ-EL-009 | E&I Multi-Cable Transits (MCT) | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | F | 2026-09-22 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-30 | 2026-10-09 | 2026-10-27 |  | 2026-10-27 | 2026-10-29 | 2026-11-05 | 2026-11-19 | 2026-12-03 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-02-02 | 2027-02-11 | 2027-02-16 | 2027-01-21 | 2027-02-17 |  |  | 2027-02-16
| MM-ZTK-1F-GEN-ELE-MR-0008 | RFQ-EL-009 | E&I Multi-Cable Transits (MCT) | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | A |  | 2026-06-12 | 2026-06-28
47 | MM-ZTK-1F-GEN-ELE-MR-0009 | RFQ-EL-010 | POWER SOCKET/PLUG, JUNCTION BOXES, EARH BAR AND CABLE GLAND | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | P | 2026-08-13 | 2026-08-04 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-26 | 2026-09-04 | 2026-09-18 |  | 2026-09-28 | 2026-09-30 | 2026-10-14 | 2026-10-28 | 2026-11-11 | 2026-11-26 | 2026-11-26 | 2026-11-28 | 2027-01-03 | 2027-01-13 | 2027-01-18 | 2027-01-21 | 2027-02-17 | 16 | 112 | 2027-01-18 | 2027-05-08 | 81 |  | 2026.9.7 ENG team released MR to Procurement
| MM-ZTK-1F-GEN-ELE-MR-0009 | RFQ-EL-010 | POWER SOCKET/PLUG, JUNCTION BOXES, EARH BAR AND CABLE GLAND | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | F | 2026-09-22 |  |  | 2026-09-22 | 2026-09-22 | 2026-09-30 | 2026-10-09 | 2026-10-27 |  | 2026-10-27 | 2026-10-29 | 2026-11-05 | 2026-11-19 | 2026-12-03 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-02-01 | 2027-02-11 | 2027-02-16 | 2027-01-21 | 2027-02-17 |  |  | 2027-02-16
| MM-ZTK-1F-GEN-ELE-MR-0009 | RFQ-EL-010 | POWER SOCKET/PLUG, JUNCTION BOXES, EARH BAR AND CABLE GLAND | 5-7 | EL | N | L4 | LD | [6 empty] | ZH | A |  | 2026-06-18 | 2026-07-04
48 | MM-ZTK-1F-GEN-INS-MR-0001 | RFQ-IN-001 | Actuated Choke Valve | 4-20 | IN | Y | L2 | LA | MASTER FLO | FZ | FZ |  |  |  | SH | P | 2026-04-17 | 2026-04-18 | 2026-04-27 | 2026-04-28 | 2026-05-05 | 2026-05-12 | 2026-05-21 | 2026-05-25 |  | 2026-06-01 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-09 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2027-02-14 | 2027-03-06 | 2027-04-05 | 2027-04-08 | 2027-05-05 | 44 | 308 | 2027-04-05 | 2027-04-15 | 31 | Lin Yazhen | 2026.5.9 Issued RFQ(no MR) bid due day:20-May 2026.6.12:TECHNICAL BID EVALUATION FOR ACTUATED CHOKE VALVES(C1) 2026.8.9 Expedite drawings by e-mail
| MM-ZTK-1F-GEN-INS-MR-0001 | RFQ-IN-001 | Actuated Choke Valve | 4-20 | IN | Y | L2 | LA | ZM169-WP1-PO-IN-001 | MASTER FLO | MASTER FLO | MASTER FLO | MASTER FLO | MASTER FLO | SH | F | [13 empty] | 2026-09-28 | 2026-10-28 | 2026-10-30 | 2026-11-01 | 2026-01-19 | 2026-02-08 | 2027-03-15 | 2027-04-08 | 2027-05-05 | 36 | 252 | 2027-03-15 |  |  | CIF Zhuhai port | [12 empty] | ZWP20-23 | 2027-03-08
| MM-ZTK-1F-GEN-INS-MR-0001 | RFQ-IN-001 | Actuated Choke Valve | 4-20 | IN | Y | L2 | LA |  | Cameron | Cameron | Cameron |  |  | SH | A | 2026-04-21 | 2026-04-10 | 2026-04-28 | 2026-05-09 | 2026-05-09 | 2026-05-22 | 2026-06-12 | 2026-06-18 | 2026-06-30 | 2026-10-14: 2026-07-03; 2026-10-16: 2026-07-17; 2026-10-23: 2026-07-10; 2026-11-06: 2026-08-14 |  |  | CD+7
49 | MM-ZTK-1F-GEN-INS-MR-0002 | RFQ-IN-002 | Actuated ball valve | 4-19 | IN | N | L2 | LB | KCON | KCON, Neway | KCON | KCON(AVL condition) | KCON(AVL condition) | KCON(AVL condition) | SH | P | 2026-04-29 | 2026-04-30 | 2026-05-11 | 2026-05-12 | 2026-05-19 | 2026-06-02 | 2026-07-01 | 2026-07-06 |  | 2026-07-20 | 2026-07-22 | 2026-07-29 | 2026-08-26 | 2026-09-09 | 2026-11-08 | 2026-11-08 | 2026-11-10 | 2027-02-02 | 2027-02-27 | 2027-03-29 | 2027-04-01 | 2027-04-28 | 36 | 252 | 2027-03-29 | 2027-04-15 | 52 | Lin Yazhen | 2026.5.25 Issued RFQ bid due day:2-Jun
| MM-ZTK-1F-GEN-INS-MR-0002 | RFQ-IN-002 | Actuated ball valve | 4-19 | IN | N | L2 | LB | ZM169-WP1-PO-IN-002 | VALVITALIA,AMPO-declined | VALVITALIA | VALVITALIA(AVL condition) | VALVITALIA(AVL condition) |  | SH | F | [13 empty] | 2026-10-06 | 2026-12-05 | 2026-12-05 | 2026-12-07 | 2026-12-29 | 2027-01-23 | 2027-02-22 | 2027-04-01 | 2027-04-28 |  |  | 2027-02-22 |  |  | DDP Zhuhai yard | [12 empty] | ZWP20-23 | 2027-02-22
| MM-ZTK-1F-GEN-INS-MR-0002 | RFQ-IN-002 | Actuated ball valve | 4-19 | IN | N | L2 | LB |  | CAMERON-declined | Neway | Neway |  |  | SH | A | 2026-05-22 | 2026-04-21 | 2026-05-11 | 2026-05-25 | 2026-05-25 | 2026-06-06 | C1:2026/7/27 C2:2026/8/24 | 2026/8/2 C2:2026/9/2 | 2026-09-02 | 2026-09-04 | 2026-09-04 | 2026-09-04 | 2026-09-04
50 | MM-ZTK-1F-GEN-INS-MR-0003 | RFQ-IN-003 | Actuated Compact Ball Valve | 4-40 | IN | Y | L2 | LA | OIL STATE | Neway,KCON | KCON | KCON-TNA |  |  | SH | P | 2026-04-28 | 2026-04-29 | 2026-05-08 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-30 | 2026-07-03 |  | 2026-07-17 | 2026-07-21 | 2026-07-28 | 2026-08-25 | 2026-09-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2027-03-04 | 2027-03-24 | 2027-04-23 | 2027-04-26 | 2027-05-23 | 40 | 280 | 2027-04-08 | 2027-04-15 | 47 | Lin Yazhen | 2026.5.9 Issued RFQ 2026.5.15 MR issued to bidders bid due day:20-May
| MM-ZTK-1F-GEN-INS-MR-0003 | RFQ-IN-003 | Actuated Compact Ball Valve | 4-40 | IN | Y | L2 | LA | ZM169-WP1-PO-IN-003 | PIPER valve | PIPER | PIPER | PIPER | PIPER | SH | F | [13 empty] | 2026-10-02 | 2026-12-01 | 2026-12-01 | 2026-12-03 | 2027-01-08 | 2027-01-28 | 2027-02-27 | 2027-04-11 | 2027-05-08 |  |  | 2027-02-27 |  |  | CIF Zhuhai Airport | [12 empty] | ZWP20-23 | 2027-02-20
| MM-ZTK-1F-GEN-INS-MR-0003 | RFQ-IN-003 | Actuated Compact Ball Valve | 4-40 | IN | Y | L2 | LA |  | FMC,Combet | Combet | Combet-declined |  |  | SH | A | 2026-04-21 | 2026-04-21 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-06-05 | 2026-07-14 | 2026-07-27 | 2026-07-21 | 2026-07-31 | 2026-09-03 | 2026-07-31 | 2026-09-02 | 2026-10-02: pending on Bettis |  |  | CD+7
51 | MM-ZTK-1F-GEN-INS-MR-0004 | RFQ-IN-004 | Safety Relief Valves | 4-30 | IN | N | L2 | LB | Eastern(Crosby) | Leser | Leser |  |  |  | SH | P | 2026-06-03 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-08-04 | 2026-08-07 |  | 2026-08-21 | 2026-08-25 | 2026-09-01 | 2026-09-30 | 2026-10-15 | 2026-12-14 | 2026-12-14 | 2026-12-16 | 2027-02-16 | 2027-03-03 | 2027-04-02 | 2027-04-05 | 2027-05-02 | 32 | 224 | 2027-04-02 | 2027-04-15 | 107 | Lin Yazhen | 2026.5.25 Issued RFQ bid due day:2-Jun
| MM-ZTK-1F-GEN-INS-MR-0004 | RFQ-IN-004 | Safety Relief Valves | 4-30 | IN | N | L2 | LB | ZM169-WP1-PO-IN-004 | Farris | Farris | Farris | Farris-8.5 |  | SH | F | [12 empty] | 2026-09-24 | 2026-10-08 | 2026-12-07 | 2026-12-07 | 2026-12-09 | 2027-02-16 | 2027-03-03 | 2027-04-02 | 2027-04-05 | 2027-05-02 |  |  | 2026-12-29 |  |  | DDP Zhuhai yard | [12 empty] | ZWP20-23 | 2026-12-29
| MM-ZTK-1F-GEN-INS-MR-0004 | RFQ-IN-004 | Safety Relief Valves | 4-30 | IN | N | L2 | LB |  | Cobrsby | Cobrsby | Cobrsby | Cobrsby-8.5 |  | SH | A | 2026-05-22 | 2026-04-13 | 2026-05-05 | 2026-05-28 | 2026-05-28 | 2026-06-10 | 2026-07-24 | 2026-08-02 | 2026-08-25 | 2026-09-01 | 2026-09-04 | 2026-09-04
52 | MM-ZTK-1F-GEN-INS-MR-0005 | RFQ-IN-005 | Coriolis Flow Meters | 4-32 | IN | N | L3 | LC |  | Emerson | Emerson-TC |  |  |  | SH | P | 2026-08-06 | 2026-08-09 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-09-07 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-24 | 2026-12-24 | 2026-12-26 | 2027-02-22 23:17 | 2027-03-04 23:17 | 2027-03-14 23:17 | 2027-03-17 23:17 | 2027-04-13 23:17 | 20.71 | 144.97 | 2027-03-14 23:17 | 2027-04-15 | 31.03 | Lin Yazhen
| MM-ZTK-1F-GEN-INS-MR-0005 | RFQ-IN-005 | Coriolis Flow Meters | 4-32 | IN | N | L3 | LC |  | Yokogawa | Yokogawa-TC |  |  |  | SH | F | [6 empty] | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-24 | 2026-12-24 | 2026-12-26 | 2027-02-22 23:17 | 2027-03-04 23:17 | 2027-03-14 23:17 | 2027-03-17 23:17 | 2027-04-13 23:17 |  |  | 2027-03-14 23:17
| MM-ZTK-1F-GEN-INS-MR-0005 | RFQ-IN-005 | Coriolis Flow Meters | 4-32 | IN | N | L3 | LC |  | Endress+Hauser | Krohne-TC |  |  |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30 | 2026-08-14 | 2026-08-14 | 2026-08-31
53 | MM-ZTK-1F-GEN-INS-MR-0006 | RFQ-IN-006 | Wellhead Control Panel | 4-28 | IN | Y | L2 | LA | Wilmax | Matorly, FST | Matorly | Matorly(AVL condition) | Matorly | Matorly | SH | P | 2026-04-23 | 2026-04-24 | 2026-05-05 | 2026-05-06 | 2026-05-13 | 2026-05-27 | 2026-06-26 | 2026-07-01 |  | 2026-07-15 | 2026-07-17 | 2026-07-24 | 2026-08-21 | 2026-09-04 | 2026-10-14 | 2026-10-14 | 2026-10-16 | 2027-02-22 | 2027-03-14 | 2027-03-24 | 2027-03-27 | 2027-04-23 | 32 | 252 | 2027-03-23 | 2027-03-23 | 1 | Lin Yazhen | 2026.5.9 Issued RFQ(No MR) bid due day:20-May
| MM-ZTK-1F-GEN-INS-MR-0006 | RFQ-IN-006 | Wellhead Control Panel | 4-28 | IN | Y | L2 | LA | ZM169-WP1-PO-IN-006 | Neway | Wilmax | Wilmax | Wilmax | Wilmax | SH | F | [13 empty] | 2026-09-18 | 2026-10-28 | 2026-10-28 | 2026-10-30 | 2027-02-21 | 2027-03-13 | 2027-03-23 | 2027-03-26 | 2027-04-22 |  |  | 2027-03-22 |  |  | CIF Zhuhai port | [12 empty] | ZWP20-23 | 2027-03-15
| MM-ZTK-1F-GEN-INS-MR-0006 | RFQ-IN-006 | Wellhead Control Panel | 4-28 | IN | Y | L2 | LA | Delivery time is related with drawing approved within 30 days | Wilmax |  |  |  |  | SH | A | 2026-04-21 | 2026-04-21 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-27 | 2026-07-14 | 2026-07-14 | 2026-07-23 | 2026-07-31 | 2026-08-13 | 2026-07-31 | 2026-08-07 | [11 empty] | CD+7
54 | MM-ZTK-1F-GEN-INS-MR-0008 | RFQ-IN-007 | PLC system | 4-27 | IN | N | L2 | LB | Rockwell(Thailand) | Rockwell | Rockwell | Rockwell | Rockwell-8.7 | Rockwell-8.7 | SH | P | 2026-05-26 | 2026-05-27 | 2026-06-05 | 2026-06-08 | 2026-06-15 | 2026-06-30 | 2026-07-30 | 2026-08-04 |  | 2026-08-18 | 2026-08-20 | 2026-08-27 | 2026-09-24 | 2026-10-08 | 2026-11-07 | 2026-11-07 | 2026-11-09 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 36 | 252 | 2027-04-27 | 2027-05-25 | 21 | Liu Lei
| MM-ZTK-1F-GEN-INS-MR-0008 | RFQ-IN-007 | PLC system | 4-27 | IN | N | L2 | LB | ZM169-WP1-PO-IN-007 | CIM-declined |  |  |  |  | SH | F | [8 empty] | 2026-09-23 |  | 2026-09-28 |  | 2026-10-08 | 2026-10-26 | 2026-11-25 | 2026-11-25 | 2026-11-27 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 |  |  | 2027-05-04 |  |  | CIF Zhuhai port | [12 empty] | ZWP20-23 | 2027-04-27
| MM-ZTK-1F-GEN-INS-MR-0008 | RFQ-IN-007 | PLC system | 4-27 | IN | N | L2 | LB | [6 empty] | SH | A | 2026-04-21 | 2026-04-22 | 2026-05-13 | 2026-06-04 | 2026-06-04 | 2026-06-15 | 2026-07-31 | 2026-08-03 | 2026-08-24 | 2026-08-27 |  | 2026-09-02 | [12 empty] | CD+7 | [16 empty] | The estimated delivery schedule for the proposed system is 30 to 34 weeks after acknowledgement of order and receipt of full and final design information.
55 | MM-ZTK-1F-ZPQ-INS-MR-0001 | RFQ-IN-009 | SCADA | 4-27 | IN | N | L2 | LB |  | Rockwell |  |  |  |  | SH | P | 2026-05-26 | 2026-05-27 | 2026-06-05 | 2026-06-08 | 2026-06-15 | 2026-06-30 | 2026-09-03 | 2026-09-13 |  | 2026-09-18 | 2026-09-20 | 2026-09-19 | 2026-10-26 | 2026-11-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2027-03-08 | 2027-03-28 | 2027-04-27 | 2027-04-30 | 2027-05-27 | 33 | 231 | 2027-04-27 | 2027-05-25 | -4 | Liu Lei
| MM-ZTK-1F-ZPQ-INS-MR-0001 | RFQ-IN-009 | SCADA | 4-27 | IN | N | L2 | LB |  | CIM |  |  |  |  | SH | F | [7 empty] | 2026-09-25 | 2026-10-10 | 2026-10-10 | 2026-10-13 | 2026-10-16 | 2026-11-06 | 2026-11-20 | 2026-12-20 | 2026-12-20 | 2026-12-20 | 2027-04-09 | 2027-04-29 | 2027-05-29 | 2027-06-03 | 2027-07-03 |  |  | 2027-05-29
| MM-ZTK-1F-ZPQ-INS-MR-0001 | RFQ-IN-009 | SCADA | 4-27 | IN | N | L2 | LB | [6 empty] | SH | A | 2026-04-21 | 2026-07-31 | 2026-08-05 | 2026-08-05 | 2026-08-05 | 2026-08-19 | 2026-09-17
56 | MM-ZTK-1F-GEN-INS-MR-0009 | RFQ-IN-008-1 | Control valve | 4-5 | IN | N | L2 | LB | Concord (Fisher) | Fisher | Fisher | Fisher | Fisher-8.7 | Fisher | SH | P | 2026-05-22 | 2026-05-25 | 2026-06-02 | 2026-06-03 | 2026-06-10 | 2026-06-25 | 2026-07-23 | 2026-07-30 |  | 2026-08-13 | 2026-08-17 | 2026-08-24 | 2026-09-21 | 2026-10-05 | 2026-12-04 | 2026-12-04 | 2026-12-06 | 2027-03-07 | 2027-03-22 | 2027-04-01 | 2027-04-04 | 2027-05-01 | 33 | 231 | 2027-04-01 | 2027-04-15 | 28 | Lin Yazhen | 2026.5.25 Issued RFQ bid due day:2-Jun 2026.9.18 Spare parts
| MM-ZTK-1F-GEN-INS-MR-0009 | RFQ-IN-008-1 | Control valve | 4-5 | IN | N | L2 | LB | ZM169-WP1-PO-IN-008 | Masonilan | Masonilan |  |  |  | SH | F | [12 empty] | 2026-09-21 | 2026-10-05 | 2026-12-04 | 2026-12-04 | 2026-12-06 | 2027-03-07 | 2027-03-22 | 2027-04-01 | 2027-04-04 | 2027-05-01 | 25.5 | 178.5 | 2027-03-18 |  |  | DDP Zhuhai yard | [12 empty] | ZWP20-23 | 2027-03-18
| MM-ZTK-1F-GEN-INS-MR-0009 | RFQ-IN-008-1 | Control valve | 4-5 | IN | N | L2 | LB |  | Flowserve | Flowserve | Flowserve | Flowserve-8.7 | Flowserve | SH | A | 2026-04-21 | 2026-04-22 | 2026-05-13 | 2026-05-25 | 2026-05-25 | 2026-06-15 | 2026-07-31 | 2026-09-25: 2026-08-06; 2026-10-10: 2026-08-28; 2026-10-10: 2026-09-04; 2026-10-13: 2026-09-20; 2026-10-16: 2026-09-08
57 | MM-ZTK-1F-GEN-INS-MR-0010 | RFQ-IN-008-2 | Self-Actuated Pressure Control Valves | 4-5 | IN | N | L2 | LB | Concord (Fisher) | Fisher | Fisher | Fisher | Fisher-8.5 | Fisher | SH | P | 2026-06-03 | 2026-06-04 | 2026-06-11 | 2026-06-12 | 2026-06-19 | 2026-07-03 | 2026-08-04 | 2026-08-07 |  | 2026-08-21 | 2026-08-25 | 2026-09-01 | 2026-09-30 | 2026-10-15 | 2026-12-14 | 2026-12-14 | 2026-12-16 | 2027-03-08 | 2027-03-23 | 2027-04-02 | 2027-04-05 | 2027-04-30 | 32 | 224 | 2027-04-02 | 2027-04-15 | 28 | Lin Yazhen | 2026.5.25 Issued RFQ bid due day:2-Jun 2026.9.18 Spare parts
| MM-ZTK-1F-GEN-INS-MR-0010 | RFQ-IN-008-2 | Self-Actuated Pressure Control Valves | 4-5 | IN | N | L2 | LB | ZM169-WP1-PO-IN-008 | Masonilan | Masonilan |  |  |  | SH | F | [12 empty] | 2026-09-21 | 2026-10-05 | 2026-12-04 | 2026-12-04 | 2026-12-06 | 2027-03-08 | 2027-03-23 | 2027-04-02 | 2027-04-05 | 2027-04-30 | 25.5 | 178.5 | 2027-03-18 |  |  | DDP Zhuhai yard | [12 empty] | ZWP20-23 | 2027-03-18
| MM-ZTK-1F-GEN-INS-MR-0010 | RFQ-IN-008-2 | Self-Actuated Pressure Control Valves | 4-5 | IN | N | L2 | LB | Combined with control valve (fisher) | Flowserve | Flowserve | Flowserve |  |  | SH | A | No need | 2026-04-21 | 2026-05-11 | 2026-05-25 | 2026-05-25 | 2026-06-15 | 2026-07-24 | 2026-09-25: 2026/8/2 2026/8/17; 2026-10-10: 2026-08-28; 2026-10-10: 2026-09-04; 2026-10-13: 2026-09-20; 2026-10-16: 2026-09-08
58 | MM-ZTK-1F-GEN-INS-MR-0011 | RFQ-IN-010 | Fire & Gas Detectors | 4-8 | IN | N | L3 | LC |  | GM | GM |  |  |  | SH | P | 2026-08-14 | 2026-08-19 | 2026-08-26 | 2026-08-27 | 2026-09-03 | 2026-09-17 | 2026-10-08 | 2026-10-14 |  | 2026-10-28 | 2026-10-30 | 2026-11-06 | 2026-11-27 | 2026-12-14 | 2027-01-03 | 2027-01-03 | 2027-01-05 | 2027-02-13 | 2027-02-28 | 2027-03-10 | 2027-03-13 | 2027-04-09 | 19 | 133 | 2027-03-10 | 2027-04-15 | 36 | Han Jingxin
| MM-ZTK-1F-GEN-INS-MR-0011 | RFQ-IN-010 | Fire & Gas Detectors | 4-8 | IN | N | L3 | LC |  | Det-Tronics | Det-Tronics |  |  |  | SH | F | [6 empty] | 2026-09-25 | 2026-10-09 |  | 2026-10-28 | 2026-10-30 | 2026-11-06 | 2026-11-27 | 2026-12-14 | 2027-01-03 | 2027-01-03 | 2027-01-05 | 2027-02-13 | 2027-02-28 | 2027-03-10 | 2027-03-13 | 2027-04-09 |  |  | 2027-03-10
| MM-ZTK-1F-GEN-INS-MR-0011 | RFQ-IN-010 | Fire & Gas Detectors | 4-8 | IN | N | L3 | LC |  | Emerson | Emerson |  |  |  | SH | A | 2026-08-07 | 2026-05-09 | 2026-05-24 | 2026-08-10 | 2026-08-10 | 2026-08-20
59 | MM-ZTK-1F-GEN-INS-MR-0012 | RFQ-IN-011 | IN Junction Box | 5-8 | IN | N | L3 | LD | [6 empty] | ZH | P | 2026-10-27 | 2026-10-18 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-09 | 2026-11-18 | 2026-12-02 |  | 2026-12-09 | 2026-12-11 | 2026-12-18 | 2027-01-04 | 2027-01-18 | 2027-02-02 | 2027-02-02 | 2027-02-04 | 2027-03-06 | 2027-03-21 | 2027-03-31 | 2027-04-03 | 2027-04-30 | 16 | 112 | 2027-03-31 | 2027-04-15 | 15 | Zhang Jianwei
| MM-ZTK-1F-GEN-INS-MR-0012 | RFQ-IN-011 | IN Junction Box | 5-8 | IN | N | L3 | LD | [6 empty] | ZH | F | [6 empty] | 2026-09-25 | 2026-10-09 |  | 2026-12-09 | 2026-12-11 | 2026-12-18 | 2027-01-04 | 2027-01-18 | 2027-02-02 | 2027-02-02 | 2027-02-04 | 2027-03-06 | 2027-03-21 | 2027-03-31 | 2027-04-03 | 2027-04-30 |  |  | 2027-03-31
| MM-ZTK-1F-GEN-INS-MR-0012 | RFQ-IN-011 | IN Junction Box | 5-8 | IN | N | L3 | LD | [6 empty] | ZH | A | 2026-08-27 | 2026-04-28 | 2026-05-08 | 2026-08-28 | 2026-08-28 | 2026-09-16
60 | MM-ZTK-1F-GEN-INS-MR-0013 | RFQ-IN-012 | Position Limit Switch | 4-36 | IN | N | L3 | LC |  | SATT Inter Supply | SATT Inter Supply |  |  |  | SH | P | 2026-08-13 | 2026-08-18 | 2026-08-25 | 2026-08-26 | 2026-09-02 | 2026-09-16 | 2026-10-07 | 2026-10-12 |  | 2026-10-26 | 2026-10-28 | 2026-11-04 | 2026-11-25 | 2026-12-10 | 2026-12-25 | 2026-12-25 | 2026-12-27 | 2027-02-04 | 2027-02-19 | 2027-03-01 | 2027-03-04 | 2027-03-31 | 18 | 126 | 2027-03-01 | 2027-04-15 | 45 | Liu Lei
| MM-ZTK-1F-GEN-INS-MR-0013 | RFQ-IN-012 | Position Limit Switch | 4-36 | IN | N | L3 | LC | [6 empty] | SH | F | [6 empty] | 2026-09-25 | 2026-10-09 |  | 2026-10-26 | 2026-10-28 | 2026-11-04 | 2026-11-25 | 2026-12-10 | 2026-12-25 | 2026-12-25 | 2026-12-27 | 2027-02-04 | 2027-02-19 | 2027-03-01 | 2027-03-04 | 2027-03-31 |  |  | 2027-03-01
| MM-ZTK-1F-GEN-INS-MR-0013 | RFQ-IN-012 | Position Limit Switch | 4-36 | IN | N | L3 | LC | [6 empty] | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-24 | 2026-08-20 | 2026-08-20 | 2026-08-28
61 | MM-ZTK-1F-GEN-INS-MR-0014 | RFQ-IN-013 | Pressure Gauges | 4-35 | IN | N | L4 | LC |  | Ashcroft | Ashcroft-TC |  |  |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-15 | 9 | Han Jingxin
| MM-ZTK-1F-GEN-INS-MR-0014 | RFQ-IN-013 | Pressure Gauges | 4-35 | IN | N | L4 | LC |  | Wika | Wika-TC |  |  |  | SH | F | [6 empty] | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0014 | RFQ-IN-013 | Pressure Gauges | 4-35 | IN | N | L4 | LC |  | Bourdon Haenni-declined |  |  |  |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-24 | 2026-08-12 | 2026-08-12 | 2026-08-24
62 | MM-ZTK-1F-GEN-INS-MR-0015 | RFQ-IN-014 | Pressure Gauges (Wireless Type) | 4-35 | IN | N | L4 | LC |  | Emerson | Emerson-TC |  |  |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-15 | 9 | Han Jingxin | [13 empty] | 12-14 weeks
| MM-ZTK-1F-GEN-INS-MR-0015 | RFQ-IN-014 | Pressure Gauges (Wireless Type) | 4-35 | IN | N | L4 | LC | [6 empty] | SH | F | [6 empty] | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0015 | RFQ-IN-014 | Pressure Gauges (Wireless Type) | 4-35 | IN | N | L4 | LC | [6 empty] | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30 | 2026-08-28 | 2026-08-28 | 2026-09-15
63 | MM-ZTK-1F-GEN-INS-MR-0016 | RFQ-IN-015 | Temperature Gauges and Thermowells | 4-35 | IN | N | L3 | LC |  | Ashcroft | Ashcroft-ENG |  |  |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-15 | 9 | Han Jingxin
| MM-ZTK-1F-GEN-INS-MR-0016 | RFQ-IN-015 | Temperature Gauges and Thermowells | 4-35 | IN | N | L3 | LC |  | Wika | Wika-ENG |  |  |  | SH | F | [6 empty] | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0016 | RFQ-IN-015 | Temperature Gauges and Thermowells | 4-35 | IN | N | L3 | LC |  | Bourdon Haenni-declined |  |  |  |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30 | 2026-08-13 | 2026-08-13 | 2026-08-28
64 | MM-ZTK-1F-GEN-INS-MR-0017 | RFQ-IN-016 | Temperature Transmitters and Thermowells | 4-35 | IN | N | L3 | LC |  | Emerson | Emerson-TC |  |  |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-15 | 9 | Han Jingxin
| MM-ZTK-1F-GEN-INS-MR-0017 | RFQ-IN-016 | Temperature Transmitters and Thermowells | 4-35 | IN | N | L3 | LC |  | Yokogawa-declined |  |  |  |  | SH | F | [6 empty] | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0017 | RFQ-IN-016 | Temperature Transmitters and Thermowells | 4-35 | IN | N | L3 | LC |  | Endress+Hauser-delcined |  |  |  |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30 | 2026-08-13 | 2026-08-13 | 2026-08-31
65 | MM-ZTK-1F-GEN-INS-MR-0018 | RFQ-IN-017 | Temperature Transmitters (Pipe Clamp) Wireless Type | 4-35 | IN | N | L3 | LC |  | Emerson | Emerson-TC |  |  |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-15 | 9
| MM-ZTK-1F-GEN-INS-MR-0018 | RFQ-IN-017 | Temperature Transmitters (Pipe Clamp) Wireless Type | 4-35 | IN | N | L3 | LC | [6 empty] | SH | F | [6 empty] | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0018 | RFQ-IN-017 | Temperature Transmitters (Pipe Clamp) Wireless Type | 4-35 | IN | N | L3 | LC | [6 empty] | SH | A | 2026-08-12 | 2026-05-12 | 2026-06-09 | 2026-08-28 | 2026-08-28 | 2026-09-11
66 | MM-ZTK-1F-GEN-INS-MR-0019 | RFQ-IN-018 | Pressure Transmitters | 4-35 | IN | N | L3 | LC |  | Emerson | Emerson-TC |  |  |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-15 | 9 | Han Jingxin
| MM-ZTK-1F-GEN-INS-MR-0019 | RFQ-IN-018 | Pressure Transmitters | 4-35 | IN | N | L3 | LC |  | Yokogawa | Yokogawa_TC |  |  |  | SH | F | [6 empty] | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0019 | RFQ-IN-018 | Pressure Transmitters | 4-35 | IN | N | L3 | LC |  | Endress+Hauser-declined |  |  |  |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30 | 2026-08-10 | 2026-08-10 | 2026-08-27
67 | MM-ZTK-1F-GEN-INS-MR-0020 | RFQ-IN-019 | Pressure Transmitters (Wireless Type) | 4-35 | IN | N | L3 | LC |  | Emerson | Emerson-ENG |  |  |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-15 | 9 | Han Jingxin
| MM-ZTK-1F-GEN-INS-MR-0020 | RFQ-IN-019 | Pressure Transmitters (Wireless Type) | 4-35 | IN | N | L3 | LC | [6 empty] | SH | F | [6 empty] | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0020 | RFQ-IN-019 | Pressure Transmitters (Wireless Type) | 4-35 | IN | N | L3 | LC | [6 empty] | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-30 | 2026-08-28 | 2026-08-28 | 2026-09-11
68 | MM-ZTK-1F-GEN-INS-MR-0021 | RFQ-IN-020 | Magnetic Level Gauges and Transmitters | 4-35 | IN | N | L3 | LC |  | MAGNETROL | MAGNETROL-TC |  |  |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-15 | 9 | Han Jingxin
| MM-ZTK-1F-GEN-INS-MR-0021 | RFQ-IN-020 | Magnetic Level Gauges and Transmitters | 4-35 | IN | N | L3 | LC |  | K-TEK (ABB) | K-TEK (ABB)-close |  |  |  | SH | F | [6 empty] | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0021 | RFQ-IN-020 | Magnetic Level Gauges and Transmitters | 4-35 | IN | N | L3 | LC |  | WIKA | WIKA- no reply |  |  |  | SH | A | 2026-07-27 | 2026-04-21 | 2026-05-11 | 2026-07-29 | 2026-07-29 | 2026-08-14
69 | MM-ZTK-1F-GEN-INS-MR-0023 | RFQ-IN-022 | DP Level Transmitters | 4-35 | IN | N | L3 | LC |  | Yokogawa | Yokogawa-TC |  |  |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-15 | 9 | Han Jingxin
| MM-ZTK-1F-GEN-INS-MR-0023 | RFQ-IN-022 | DP Level Transmitters | 4-35 | IN | N | L3 | LC |  | Emerson | Emerson-ENG |  |  |  | SH | F | [6 empty] | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0023 | RFQ-IN-022 | DP Level Transmitters | 4-35 | IN | N | L3 | LC |  | Endress+Hauser |  |  |  |  | SH | A | 2026-08-06 | 2026-05-09 | 2026-05-30 | 2026-08-10 | 2026-08-10 | 2026-08-31
70 | MM-ZTK-1F-GEN-INS-MR-0024 | RFQ-IN-023 | Restriction Orifices | 4-42 | IN | N | L4 | LC |  | Yokogawa-declined |  |  |  |  | SH | P | 2026-08-06 | 2026-08-08 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-09-07 | 2026-09-24 | 2026-10-08 |  | 2026-10-21 | 2026-10-23 | 2026-10-30 | 2026-11-20 | 2026-12-04 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-03-09 | 2027-03-19 | 2027-03-24 | 2027-03-27 | 2027-04-23 | 22 | 154 | 2027-03-24 | 2027-04-15 | 21 | Lin Yazhen
| MM-ZTK-1F-GEN-INS-MR-0024 | RFQ-IN-023 | Restriction Orifices | 4-42 | IN | N | L4 | LC |  | ROSEMOUNT | Emerson-9.16 TC reply |  |  |  | SH | F | [6 empty] | 2026-09-25 | 2026-10-09 |  | 2026-10-22 | 2026-10-26 | 2026-11-02 | 2026-11-23 | 2026-12-08 | 2026-12-23 | 2026-12-23 | 2026-12-25 | 2027-03-09 | 2027-03-19 | 2027-03-24 | 2027-03-27 | 2027-04-23 |  |  | 2027-03-25
| MM-ZTK-1F-GEN-INS-MR-0024 | RFQ-IN-023 | Restriction Orifices | 4-42 | IN | N | L4 | LC |  | WIKA | WIKA--9.16 TC reply |  |  |  | SH | A | 2026-08-12 | 2026-05-09 | 2026-05-18 | 2026-08-14 | 2026-08-14 | 2026-08-31
71 | MM-ZTK-1F-GEN-INS-MR-0025 | RFQ-IN-024 | Vortex Flow Meters | 4-32 | IN | N | L3 | LC |  | YOKOGAWA | YOKOGAWA-ENG |  |  |  | SH | P | 2026-09-11 | 2026-09-09 | 2026-09-23 | 2026-09-23 | 2026-09-23 | 2026-10-15 | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 18 | 126 | 2027-04-06 | 2027-04-15 | 9 | Lin Yazhen
| MM-ZTK-1F-GEN-INS-MR-0025 | RFQ-IN-024 | Vortex Flow Meters | 4-32 | IN | N | L3 | LC |  | ROSEMOUNT | ROSEMOUNT-ENG |  |  |  | SH | F | [6 empty] | 2026-11-04 | 2026-11-18 |  | 2026-12-01 | 2026-12-03 | 2026-12-10 | 2026-12-31 | 2027-01-15 | 2027-01-30 | 2027-01-30 | 2027-02-01 | 2027-03-22 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-04-06
| MM-ZTK-1F-GEN-INS-MR-0025 | RFQ-IN-024 | Vortex Flow Meters | 4-32 | IN | N | L3 | LC |  | Endress+Hauser-declined | KROHNE-ENG |  |  |  | SH | A | 2026-08-12 | 2026-05-11 | 2026-05-31 | 2026-08-14 | 2026-08-14 | 2026-08-28
72 | MM-ZTK-1F-GEN-INS-MR-0026 | RFQ-IN-025 | Non-Intrusive Sand Monitoring System (Acoustic Type) | 4-34 | IN | N | L3 | LC |  | Clampon | Qtech(Clampon)-TBE,TC |  |  |  | SH | P | 2026-06-22 | 2026-06-22 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-20 | 2026-08-10 | 2026-08-25 |  | 2026-09-07 | 2026-09-09 | 2026-09-16 | 2026-10-15 | 2026-10-30 | 2026-11-29 | 2026-11-29 | 2026-12-01 | 2027-02-14 | 2027-03-06 | 2027-04-05 | 2027-04-08 | 2027-05-05 | 30 | 210 | 2027-04-05 | 2027-06-25 | 38 | Lin Yazhen
| MM-ZTK-1F-GEN-INS-MR-0026 | RFQ-IN-025 | Non-Intrusive Sand Monitoring System (Acoustic Type) | 4-34 | IN | N | L3 | LC |  |  | SYSTAON(Clampon)-ENG |  |  |  | SH | F | [6 empty] | 2026-10-02 | 2026-10-15 |  | 2026-10-20 | 2026-10-22 | 2026-10-22 | 2026-11-12 | 2026-11-26 | 2026-12-06 | 2026-12-06 | 2026-12-08 | 2027-02-14 | 2027-03-06 | 2027-04-05 | 2027-04-08 | 2027-05-05 |  |  | 2027-05-18
| MM-ZTK-1F-GEN-INS-MR-0026 | RFQ-IN-025 | Non-Intrusive Sand Monitoring System (Acoustic Type) | 4-34 | IN | N | L3 | LC | [6 empty] | SH | A | 2026-08-17 | 2026-05-08 | 2026-05-31 | 2026-08-17 | 2026-08-17 | 2026-09-09
| MM-ZTK-1F-GEN-INS-MR-0033 | RFQ-IN-026 | on-Intrusive Wireless Sand Monitoring System (Ultrasonic Type) | 4-34 | IN | N | L3 | LC | Remove from Scope of supply | [5 empty] | SH | P | 2026-06-22 | 2026-06-22 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-20 | 2026-08-10 | 2026-08-25 |  | 2026-09-07 | 2026-09-09 | 2026-09-16 | 2026-10-15 | 2026-10-30 | 2026-11-29 | 2026-11-29 | 2026-12-01 | 2027-02-14 | 2027-03-06 | 2027-04-05 | 2027-04-08 | 2027-05-05 | 30 | 210 | 2027-04-05
| MM-ZTK-1F-GEN-INS-MR-0033 | RFQ-IN-026 | on-Intrusive Wireless Sand Monitoring System (Ultrasonic Type) | 4-34 | IN | N | L3 | LC | [6 empty] | SH | F | 2026-07-13 |  |  | 2026-07-13 | 2026-07-13 | 2026-07-27 | 2026-08-10 | 2026-08-25 |  | 2026-09-07 | 2026-09-09 | 2026-09-16 | 2026-10-15 | 2026-10-30 | 2026-11-29 | 2026-11-29 | 2026-12-01 | 2027-02-14 | 2027-03-06 | 2027-04-05 | 2027-04-08 | 2027-05-05 |  |  | 2027-04-05
| MM-ZTK-1F-GEN-INS-MR-0033 | RFQ-IN-026 | on-Intrusive Wireless Sand Monitoring System (Ultrasonic Type) | 4-34 | IN | N | L3 | LC | [6 empty] | SH | A |  | 2026-05-08 | 2026-05-31
73 | MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-027 | IN Cable | 5-8 | IN | N | L4 | LD | [6 empty] | ZH | P | 2026-08-28 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-16 | 2026-09-30 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16 | 2027-05-17 | 106 |  | 2026.9.17 received MR from ENG. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-027 | IN Cable | 5-8 | IN | N | L4 | LD | [6 empty] | ZH | F | 2026-09-18 | 2026-08-17 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-28 | 2026-10-07 | 2026-10-22 |  | 2026-10-29 | 2026-11-02 | 2026-11-09 | 2026-11-23 | 2026-12-08 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-31 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-027 | IN Cable | 5-8 | IN | N | L4 | LD | [6 empty] | ZH | A |  |  |  | 2026-09-18 | 2026-09-18 | [24 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-028 | IN Cable Tray | 5-8 | IN | N | L4 | LD | Combine with EL Cable Tray | [5 empty] | ZH | P | 2026-08-28 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-16 | 2026-09-30 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-028 | IN Cable Tray | 5-8 | IN | N | L4 | LD | [6 empty] | ZH | F | 2026-08-28 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-16 | 2026-09-30 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-16
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-028 | IN Cable Tray | 5-8 | IN | N | L4 | LD | [6 empty] | ZH | A
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-029 | IN Cable Gland | 5-8 | IN | N | L4 | LD | Combine with EL Cable Gland | [5 empty] | ZH | P | 2026-08-28 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-16 | 2026-09-30 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 | 13.4286 | 94 | 2027-01-16
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-029 | IN Cable Gland | 5-8 | IN | N | L4 | LD | [6 empty] | ZH | F | 2026-08-28 | 2026-08-17 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-16 | 2026-09-30 |  | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-11-06 | 2026-11-20 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2027-01-04 | 2027-01-11 | 2027-01-16 | 2027-01-19 | 2027-02-15 |  |  | 2027-01-16
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-029 | IN Cable Gland | 5-8 | IN | N | L4 | LD | [6 empty] | ZH | A
74 | MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-030 | IN Bulk Material including of Fitting, Tubing, isolated valve(small), fusible plug, STAUFF clamps | 5-8 | IN | N | L3 | LD | [6 empty] | ZH | P | 2026-09-07 | 2026-09-05 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-28 | 2026-10-07 | 2026-10-22 |  | 2026-10-29 | 2026-11-02 | 2026-11-09 | 2026-11-23 | 2026-12-08 | 2026-12-18 | 2026-12-18 | 2026-12-20 | 2027-03-06 | 2027-03-13 | 2027-03-18 | 2027-03-21 | 2027-04-17 | 20 | 140 | 2027-03-18 | 2027-06-04 | 64 |  | 2026.9.7 ENG team released MR to Procurement
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-030 | IN Bulk Material including of Fitting, Tubing, isolated valve(small), fusible plug, STAUFF clamps | 5-8 | IN | N | L3 | LD | [6 empty] | ZH | F | 2026-09-24 |  |  | 2026-09-24 | 2026-09-24 | 2026-10-09 | 2026-10-21 | 2026-11-05 |  | 2026-11-12 | 2026-11-16 | 2026-11-23 | 2026-12-07 | 2026-12-21 | 2026-12-31 | 2026-12-31 | 2027-01-02 | 2027-03-06 | 2027-03-13 | 2027-03-18 | 2027-03-21 | 2027-04-17 |  |  | 2027-04-01
| MM-ZTK-1F-GEN-INS-MR-0034 | RFQ-IN-030 | IN Bulk Material including of Fitting, Tubing, isolated valve(small), fusible plug, STAUFF clamps | 5-8 | IN | N | L3 | LD | [6 empty] | ZH | A |  | 2026-09-05 | 2026-09-07
75 | MM-ZTK-1F-GEN-TEL-MR-0001~0005 | RFQ-TEL-001 | Telecom materials(SCADA radio, Trunk Radio, Explosion Proof Telephone,Marine Racon,VHF FM Marine Radio System) | 4-37 | TEL | N | L3 | LC |  | Fusion | Fusion-ENG |  |  |  | SH | P | 2026-07-15 | 2026-07-14 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-08-13 | 2026-09-01 | 2026-09-15 |  | 2026-09-29 | 2026-10-08 | 2026-10-15 | 2026-11-05 | 2026-11-19 | 2026-12-19 | 2026-12-19 | 2026-12-21 | 2027-02-18 | 2027-02-28 | 2027-03-30 | 2027-04-02 | 2027-04-29 | 26 | 182 | 2027-03-30 | 2027-06-23 | 75 | Han Jingxin
| MM-ZTK-1F-GEN-TEL-MR-0001~0005 | RFQ-TEL-001 | Telecom materials(SCADA radio, Trunk Radio, Explosion Proof Telephone,Marine Racon,VHF FM Marine Radio System) | 4-37 | TEL | N | L3 | LC |  | Samart Thailand | Samart Thailand-ENG |  |  |  | SH | F | [6 empty] | 2026-09-25 | 2026-10-09 |  | 2026-10-09 | 2026-10-13 | 2026-10-20 | 2026-11-10 | 2026-11-24 | 2026-12-24 | 2026-12-24 | 2026-12-26 | 2027-02-18 | 2027-02-28 | 2027-03-30 | 2027-04-02 | 2027-04-29 |  |  | 2027-04-09
| MM-ZTK-1F-GEN-TEL-MR-0001~0005 | RFQ-TEL--001 | Telecom materials(SCADA radio, Trunk Radio, Explosion Proof Telephone,Marine Racon,VHF FM Marine Radio System) | 4-37 | TEL | N | L3 | LC | [6 empty] | SH | A | 2026-07-08 | 2026-05-18 | 2026-06-13 | 2026-08-28 | 2026-08-28 | 2026-09-08
76 | MM-ZTK-1F-GEN-STR-MR-1021 | RFQ-STR-001 | Topside Primary Steel- Plate | 5-1 | STR | Y | L2 | LA | Total: 1068T | [5 empty] | ZH | P | 2026-05-04 | 2026-06-05 | 2026-06-20 | 2026-06-23 | 2026-06-26 | 2026-06-29 | 2026-07-02 | 2026-07-05 |  | 2026-07-13 | 2026-07-15 | 2026-04-20 | 2026-04-23 | 2026-05-11 | 2026-07-28 | 2026-08-12 | 2026-08-14 | 2026-08-27 12:00 | 2026-09-03 12:00 | 2026-09-08 | 2026-09-11 | 2026-10-10 12:00 | 8.5 | 59.5 | 2026-09-08 | 2026-09-09 | 15 | Huang liudong | [12 empty] | ZH26FA001(08) | 2026.8.9-25
| MM-ZTK-1F-GEN-STR-MR-1021 | RFQ-STR-001 | Topside Primary Steel- Plate | 5-1 | STR | Y | L2 | LA | 121 pic in stock(wait for SRN) | [5 empty] | ZH | F | [9 empty] | 2027-02-18: 2026-08-21; 2027-02-28: 2026-08-23; 2027-03-30: 2026-08-25; 2027-04-02: 2026-09-11; 2027-04-29: 2026-10-10 12:00 |  |  | 2026-08-25
| MM-ZTK-1F-GEN-STR-MR-1021 | RFQ-STR-001 | Topside Primary Steel- Plate | 5-1 | STR | Y | L2 | LA | [6 empty] | ZH | A | 2026-04-08 | 2026-05-20 | 2026-05-22 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-07-03 | 2026-07-07 |  | 2026-07-07 | 2026-07-07 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-07-30 | 2026-07-30 | 2026-08-02
77 | MM-ZTK-1F-GEN-STR-MR-1011 | RFQ-STR-002 | Topside Primary Steel-Beam | 5-1 | STR | Y | L2 | LA | Laigang | [5 empty] | ZH | P | 2026-04-22 | 2026-05-29 | 2026-06-20 | 2026-06-23 | 2026-06-26 | 2026-06-29 | 2026-07-02 | 2026-07-05 |  | 2026-07-13 | 2026-07-15 | 2026-07-24 | 2026-08-21 | 2026-09-04 |  | 2026-09-09 | 2026-09-11 | 2026-10-09 02:24 | 2026-10-16 02:24 | 2026-10-21 02:24 | 2026-10-24 | 2026-11-10 02:24 | 14.3 | 100.1 | 2026-10-21 | 2026-10-26 | 5 | Wei kefang | MATERIAL REQUISITION FOR TOPSIDES HIGH STRENGTHHOT-ROLLED STEEL SECTIONS (SHAPE STR) MATERIAL REQUISITION FOR TOPSIDES SECONDARY ANDTERTIARY HOT-ROLLED STEEL | [11 empty] | ZH26FA006(02)
| MM-ZTK-1F-GEN-STR-MR-1011 | RFQ-STR-002 | Topside Primary Steel-Beam | 5-1 | STR | Y | L2 | LA | ZH26FA006 | [5 empty] | ZH | F | [9 empty] | 2027-02-18: 2026-10-09; 2027-02-28: 2026-10-16; 2027-03-30: 2026-10-21; 2027-04-02: 2026-10-24; 2027-04-29: 2026-11-10 |  |  | 2026-10-21
| MM-ZTK-1F-GEN-STR-MR-1011 | RFQ-STR-002 | Topside Primary Steel-Beam | 5-1 | STR | Y | L2 | LA | [6 empty] | ZH | A | 2026-04-24 | 2026-05-23 | 2026-05-25 | 2026-06-22 | 2026-06-22 | 2026-06-24 | 2026-07-10 | 2026-07-13 |  | 2026-07-14 | 2026-07-15 | 2026-06-29 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09
78 | MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-003 | Topside Primary Steel- Seamless | 5-1 | STR | Y | L2 | LA | Lontrin | [5 empty] | ZH | P | 2026-04-22 | 2026-05-29 | 2026-06-20 | 2026-06-23 | 2026-06-26 | 2026-06-29 | 2026-07-02 | 2026-07-05 |  | 2026-07-13 | 2026-07-15 | 2026-07-24 | 2026-08-21 | 2026-09-04 |  | 2026-09-09 | 2026-09-11 | 2026-10-09 02:24 | 2026-10-16 02:24 | 2026-10-21 02:24 | 2026-10-24 | 2026-11-10 02:24 | 14.3 | 100.1 | 2026-10-21 | 2026-11-12 | 33 | Wei kefang | MATERIAL REOUISITION FOR TOPSIDES HIGH STRENGTHSTRTUBULAR STEEL MATERIAL REQUISITION FOR TOPSIDES SECONDARY ANDTERTIARY TUBULAR STEEL | [11 empty] | ZH26FA004(02) | 2026.8.17-9.17
| MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-003 | Topside Primary Steel- Seamless | 5-1 | STR | Y | L2 | LA | [6 empty] | ZH | F | [12 empty] | 2026-09-14 | 2026-09-17 |  | 2026-09-17 | 2026-09-17 | 2026-10-09 02:24 | 2026-10-16 02:24 | 2026-10-21 02:24 | 2026-10-24 | 2026-11-10 02:24 |  |  | 2026-10-10
| MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-003 | Topside Primary Steel- Seamless |  | STR | Y | L2 | LA | [6 empty] | ZH | F | [24 empty] | 2026-10-20
| MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-003 | Topside Primary Steel- Seamless |  | STR | Y | L2 | LA | [6 empty] | ZH | F | [24 empty] | 2026-11-20
| MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-003 | Topside Primary Steel- Seamless | 5-1 | STR | Y | L2 | LA | [6 empty] | ZH | A | 2026-04-24 | 2026-05-04 | 2026-05-15 | 2026-06-22 | 2026-06-22 | 2026-06-24 | 2026-07-03 | 2026-07-10 |  | 2026-10-09: 2026-07-10; 2026-10-13: 2026-07-10; 2026-10-20: 2026-07-16 |  |  | 2026-12-03
79 | MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-016 | Topside Primary Steel- Tubular | 5-1 | STR | Y | L2 | LA | [6 empty] | ZH | P | 2026-04-22 | 2026-07-15 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-08-05 | 2026-08-14 | 2026-08-30 |  | 2026-09-08 | 2026-09-10 | 2026-09-14 | 2026-09-17 | 2026-10-10 | 2026-09-19 | 2026-09-20 | 2026-09-24 | 2026-10-21 | 2026-10-28 | 2026-11-02 | 2026-11-05 | 2026-12-02 | 7.8571 | 55 | 2026-11-02 | 2026-10-17 | 46257 | Tang Jiahe
| MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-016 | Topside Primary Steel- Tubular | 5-1 | STR | Y | L2 | LA | [6 empty] | ZH | F | [14 empty] | 2026-09-19 | 2026-09-20 | 2026-09-24 | 2026-10-21 | 2026-10-28 | 2026-11-02 | 2026-11-05 | 2026-12-02 |  |  | 1900-02-23
| MM-ZTK-1F-GEN-STR-MR-1001 | RFQ-STR-016 | Topside Primary Steel- Tubular | 5-1 | STR | Y | L2 | LA | [6 empty] | ZH | A | 2026-04-24 | 2026-05-04 | 2026-05-15 | 2026-06-10 | 2026-06-10 | 2026-06-12 | 2026-07-24 | 2026-09-18 |  | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-18
80 | MM-ZTK-1F-GEN-STR-MR-1012 | RFQ-STR-004 | Topside Secondary Steel(W) | 5-4 | STR | N | L3 | LA | Laigang | [5 empty] | ZH | P | 2026-04-28 | 2026-04-29 | 2026-05-08 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-07-28 | 2026-08-11 |  | 2026-08-07 | 2026-08-11 | 2026-08-18 | 2026-09-15 | 2026-09-29 |  | 2026-10-04 | 2026-10-06 | 2026-11-03 02:24 | 2026-11-10 02:24 | 2026-11-15 02:24 | 2026-11-18 02:24 | 2026-12-15 02:24 | 14.3 | 100.1 | 2026-11-15 02:24 | 2026-11-27 | 28 | Chen Yang | [12 empty] | ZH26FA006(03) | 2026-10-30 | 250 | pcs
| MM-ZTK-1F-GEN-STR-MR-1012 | RFQ-STR-004 | Topside Secondary Steel(W) | 5-4 | STR | N | L3 | LA | ZH26FA006 | [5 empty] | ZH | F | [17 empty] | 2026-11-03 02:24 | 2026-11-10 02:24 | 2026-11-15 02:24 | 2026-11-18 02:24 | 2026-12-15 02:24 |  |  | 2026-10-30
| MM-ZTK-1F-GEN-STR-MR-1012 | RFQ-STR-004 | Topside Secondary Steel(W) | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | A | 2026-04-24 | 2026-05-23 | 2026-05-25 | 2026-06-08 | 2026-06-08 | 2026-06-12 | 2026-07-10 | 2026-07-14 |  | 2026-07-14 | 2026-07-14 | 2026-06-29 | 2026-09-09 |  | 2026-09-20: 2026-09-09; 2026-09-24: 2026-09-09
81 | MM-ZTK-1F-GEN-STR-MR-1002 | RFQ-STR-004 | Topside Secondary Steel(L,C) | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | P | 2026-04-28 | 2026-04-29 | 2026-05-08 | 2026-07-19 | 2026-07-19 | 2026-07-25 | 2026-08-02 | 2026-08-16 |  | 2026-08-16 | 2026-08-17 | 2026-08-28 | 2026-08-25 | 2026-09-22 | 2026-10-06 | 2026-10-11 | 2026-10-13 | 2026-11-12 02:24 | 2026-11-19 02:24 | 2026-11-24 02:24 | 2026-11-22 02:24 | 2026-12-24 02:24 | 14.3 | 100.1 | 2026-11-24 02:24 | 2026-12-12 | -27.1 | Chen Yang
| MM-ZTK-1F-GEN-STR-MR-1002 | RFQ-STR-004 | Topside Secondary Steel(L,C) | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | F | 2026-07-15 | [5 empty] | 2026-09-25 | 2026-09-30 |  | 2026-09-30 | 2026-10-01 | 2026-10-14 | 2026-10-28 | 2026-11-11 | 2026-10-06 | 2026-10-11 | 2026-10-13 | 2026-11-12 02:24 | 2026-11-19 02:24 | 2026-11-24 02:24 | 2026-11-22 02:24 | 2026-12-24 02:24 |  |  | 2027-01-08 02:24
| MM-ZTK-1F-GEN-STR-MR-1002 | RFQ-STR-004 | Topside Secondary Steel(L,C) | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | A |  | 2026-05-23 | 2026-05-25 | 2026-07-03 | 2026-07-03 | 2026-07-24
82 | MM-ZTK-1F-GEN-STR-MR-1022 | RFQ-STR-005 | Topside Tertiary Steel | 5-4 | STR | N | L4 | LA | [6 empty] | ZH | P | 2026-05-26 | 2026-05-27 | 2026-06-05 | 2026-07-24 | 2026-07-24 | 2026-07-30 | 2026-08-22 | 2026-09-09 |  | 2026-09-17 | 2026-09-19 | 2026-09-26 | 2026-10-24 | 2026-11-07 |  | 1900-01-29 | 2026-11-09 | 2026-12-06 00:29 | 2026-12-11 00:29 | 2026-12-16 00:29 | 2026-12-19 00:29 | 2027-01-15 00:29 | 12.86 | 90.02 | 2026-12-16 00:29 | 2026-12-12 |  | Chen Yang
| MM-ZTK-1F-GEN-STR-MR-1022 | RFQ-STR-005 | Topside Tertiary Steel | 5-4 | STR | N | L4 | LA | [6 empty] | ZH | F | 2026-07-20 | [5 empty] | 2026-09-25 | 2026-09-30 |  | 2026-09-30 | 2026-09-19 | 2026-09-26 | 2026-10-24 | 2026-11-07 |  | 1900-01-29 | 2026-11-09 | 2026-12-06 00:29 | 2026-12-11 00:29 | 2026-12-16 00:29 | 2026-12-19 00:29 | 2027-01-15 00:29 |  |  | 2026-12-29 00:29
| MM-ZTK-1F-GEN-STR-MR-1022 | RFQ-STR-005 | Topside Tertiary Steel | 5-4 | STR | N | L4 | LA | [6 empty] | ZH | A |  | 2026-05-29 | 2026-06-01 | 2026-07-03 | 2026-07-03 | 2026-07-24
83 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-1 | ZWP21 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-06-27 | 2026-06-29 | 2026-07-29 | 2026-08-05 | 2026-08-10 | 2026-08-13 | 2026-09-09 | 8.5 | 59.5 | 2026-08-10 | 2026-08-15 | 5 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-1 | ZWP21 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [14 empty] | 2026-12-02: 2026-09-09 |  |  | 2026-08-10
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-1 | ZWP21 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-07 | 2026-08-07 | 2026-08-10 | 2026-08-10
84 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-2 | ZWP21 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-07-18 | 2026-07-11 | 2026-08-10 | 2026-08-17 | 2026-08-22 | 2026-08-25 | 2026-09-21 | 8.5 | 59.5 | 2026-08-22 | 2026-09-15 | 24 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-2 | ZWP21 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [14 empty] | 2026-11-05: 2026-08-25; 2026-12-02: 2026-09-21 |  |  | 2026-08-22
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-2 | ZWP21 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-10 | 2026-08-10 | 2026-08-10
85 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-3 | ZWP21 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-08-08 | 2026-07-23 | 2026-08-22 | 2026-08-29 | 2026-09-03 | 2026-09-06 | 2026-10-03 | 8.5 | 59.5 | 2026-09-03 | 2026-09-27 | 24 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-3 | ZWP21 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [14 empty] | 2026-11-05: 2026-09-06; 2026-12-02: 2026-10-03 |  |  | 2026-09-03
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-3 | ZWP21 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-10 | 2026-08-10 | 2026-08-10
86 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-4 | ZWP21 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-08-29 | 2026-08-04 | 2026-09-03 | 2026-09-10 | 2026-09-15 | 2026-09-18 | 2026-10-15 | 8.5 | 59.5 | 2026-09-15 | 2026-09-07 | -8 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-4 | ZWP21 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [17 empty] | 2026-09-03 | 2026-09-10 | 2026-09-15 | 2026-09-18 | 2026-10-15 |  |  | 2026-09-15
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-4 | ZWP21 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-09-19: 2026-06-26; 2026-09-20: 2026-06-26; 2026-09-24: 2026-06-26
87 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-5 | ZWP21 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-07-04 | 2026-08-16 | 2026-09-15 | 2026-09-22 | 2026-09-27 | 2026-09-30 | 2026-10-27 | 8.5 | 59.5 | 2026-09-27 | 2026-10-05 | 8 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001(40) | 2026-09-28 | 160.45 | T
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-5 | ZWP21 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [17 empty] | 2026-09-15 | 2026-09-22 | 2026-09-27 | 2026-09-30 | 2026-10-27 |  |  | 2026-09-27
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-5 | ZWP21 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-07-03 | 2026-07-03 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-09-19: 2026-07-04; 2026-09-20: 2026-07-04; 2026-09-24: 2026-07-17
88 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-6 | ZWP21 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-10-10 | 2026-08-28 | 2026-09-27 | 2026-10-04 | 2026-10-09 | 2026-10-12 | 2026-11-08 | 8.5 | 59.5 | 2026-10-09 | 2026-09-13 | -26 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-6 | ZWP21 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [14 empty] | 2026-11-02: 2026-10-09; 2026-11-05: 2026-10-12; 2026-12-02: 2026-11-08 |  |  | 2026-10-09
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-6 | ZWP21 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-07 | 2026-08-07
89 | MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-0067 | ZWP21 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-08 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-02 | 2026-06-07 |  | 2026-06-10 | 2026-06-12 | 2026-04-20 | 2026-04-23 | 2026-05-20 | 2026-06-25 | 2026-10-31 | 2026-09-09 | 2026-10-09 | 2026-10-16 | 2026-10-21 | 2026-10-24 | 2026-11-20 | 8.5 | 59.5 | 2026-10-21 | 2026-10-26 | 5 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-7 | ZWP21 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [14 empty] | 2026-11-02: 2026-10-21; 2026-11-05: 2026-10-24; 2026-12-02: 2026-11-20 |  |  | 2026-10-21
| MM-ZTK-1F-ZWP21-STR-MR-2002 | RFQ-STR-006-7 | ZWP21 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-06-12 | 2026-06-19 |  | 2026-06-22 | 2026-06-22 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-08-10 | 2026-08-10
90 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-1 | ZWP23 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-07-30 | 2026-07-30 | 2026-08-22 | 2026-08-28 | 2026-08-30 | 2026-08-30 | 2026-09-29 | 8.5 | 59.5 | 2026-08-30 | 2026-09-02 | 23 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-1 | ZWP23 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [17 empty] | 2026-08-22 | 2026-08-28 | 2026-08-30 | 2026-08-30 | 2026-09-29 |  |  | 2026-08-10
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-1 | ZWP23 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-09 | 2026-07-09 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-09-19: 2026-07-24; 2026-09-20: 2026-07-24; 2026-09-24: 2026-07-24
91 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-2 | ZWP23 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-08-20 | 2026-08-20 | 2026-09-12 | 2026-09-18 | 2026-09-20 | 2026-09-20 | 2026-10-20 | 8.5 | 59.5 | 2026-09-20 | 2026-09-25 | 34 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-2 | ZWP23 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [15 empty] | 2026-08-20 | 2026-08-20 | 2026-09-12 | 2026-09-18 | 2026-09-20 | 2026-09-20 | 2026-10-20 |  |  | 2026-08-22
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-2 | ZWP23 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-30 | 2026-07-30 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-09-19: 2026-07-30
92 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-3 | ZWP23 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-09-10 | 2026-09-10 | 2026-10-03 | 2026-10-09 | 2026-10-11 | 2026-10-11 | 2026-11-10 | 8.5 | 59.5 | 2026-10-11 | 2026-10-06 | 33 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-3 | ZWP23 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [17 empty] | 2026-10-03 | 2026-10-09 | 2026-10-11 | 2026-10-11 | 2026-11-10 |  |  | 2026-09-03
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-3 | ZWP23 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-09 | 2026-07-09 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-09-19: 2026-07-24; 2026-09-20: 2026-07-24; 2026-09-24: 2026-07-24
93 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-4 | ZWP23 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-10-01 | 2026-10-01 | 2026-10-24 | 2026-10-30 | 2026-11-01 | 2026-11-01 | 2026-12-01 | 8.5 | 59.5 | 2026-11-01 | 2026-10-06 | 21 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-4 | ZWP23 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [17 empty] | 2026-10-24 | 2026-10-30 | 2026-11-01 | 2026-11-01 | 2026-12-01 |  |  | 2026-09-15
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-4 | ZWP23 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-09 | 2026-07-09 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-09-19: 2026-07-24; 2026-09-20: 2026-07-24; 2026-09-24: 2026-07-24
94 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-5 | ZWP23 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-10-22 | 2026-10-22 | 2026-11-14 | 2026-11-20 | 2026-11-22 | 2026-11-22 | 2026-12-22 | 8.5 | 59.5 | 2026-11-22 | 2026-10-23 | 26 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-5 | ZWP23 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [17 empty] | 2026-11-14 | 2026-11-20 | 2026-11-22 | 2026-11-22 | 2026-12-22 |  |  | 2026-09-27
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-5 | ZWP23 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-09 | 2026-07-09 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-09-19: 2026-07-24; 2026-09-20: 2026-07-24; 2026-09-24: 2026-07-24
95 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-6 | ZWP23 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-07-30 | 2026-11-12 | 2026-11-12 | 2026-12-05 | 2026-12-11 | 2026-12-13 | 2026-12-13 | 2027-01-12 | 8.5 | 59.5 | 2026-12-13 | 2026-09-19 | -20 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-6 | ZWP23 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [17 empty] | 2026-12-05 | 2026-12-11 | 2026-12-13 | 2026-12-13 | 2027-01-12 |  |  | 2026-10-09
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-6 | ZWP23 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-09 | 2026-07-09 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-09-19: 2026-07-24; 2026-09-20: 2026-07-24; 2026-09-24: 2026-07-24
96 | MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-0067 | ZWP23 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-05-28 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-19 | 2026-06-30 | 2026-07-10 |  | 2026-07-10 | 2026-07-10 | 2026-04-20 | 2026-07-14 | 2026-06-19 | 2026-12-03 | 2026-12-03 | 2026-12-03 | 2026-12-26 | 2027-01-01 | 2027-01-03 | 2027-01-03 | 2027-02-02 | 8.5 | 59.5 | 2027-01-03 | 2026-10-20 | -75 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001(28) | 2026-09-15 | 271.8572 | T
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-7 | ZWP23 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [17 empty] | 2026-12-26 | 2027-01-01 | 2027-01-03 | 2027-01-03 | 2027-02-02 |  |  | 2027-01-03 | [15 empty] | ZH26FA001(37) | 2026-09-21 | 282.3776 | T
| MM-ZTK-1F-ZWP23-STR-MR-2002 | RFQ-STR-006-7 | ZWP23 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-02 | 2026-07-07 |  | 2026-07-14 | 2026-07-14 | 2026-04-20 | 2026-06-20 | 2026-06-20 | 2026-09-19: 2026-08-10; 2026-09-20: 2026-08-10; 2026-09-24: 2026-08-10
97 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-1 | ZWP22 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-09-03 | 2026-09-03 | 2026-09-03 | 2026-09-26 | 2026-10-02 | 2026-10-04 | 2026-10-04 | 2026-11-03 | 8.5 | 59.5 | 2026-10-04 | 2026-10-11 | 7 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-1 | ZWP22 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [9 empty] | 2026-08-14 | 2026-08-14 |  | 2026-08-18 | 2026-08-03 | 2026-09-03 | 2026-09-03 | 2026-09-03 | 2026-09-26 | 2026-10-02 | 2026-10-04 | 2026-10-04 | 2026-11-03 |  |  | 2026-10-04
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-1 | ZWP22 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  |  |  | 2026-04-20
98 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-2 | ZWP22 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-10-17 | 2026-10-23 | 2026-10-25 | 2026-10-25 | 2026-11-24 | 8.5 | 59.5 | 2026-10-25 | 2026-11-11 | 17 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-2 | ZWP22 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [9 empty] | 2026-08-14 | 2026-08-14 |  |  |  | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-10-17 | 2026-10-23 | 2026-10-25 | 2026-10-25 | 2026-11-24 |  |  | 2026-10-25
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-2 | ZWP22 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  |  |  | 2026-04-20 | 2026-08-04 | 2026-08-04
99 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-3 | ZWP22 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-11-15 | 2026-12-15 | 8.5 | 59.5 | 2026-11-15 | 2026-11-06 | -9 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-3 | ZWP22 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [14 empty] | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-11-15 | 2026-12-15 |  |  | 2026-11-15
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-3 | ZWP22 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  | 2026-08-03 | 2026-08-03 | 2026-04-20 | 2026-08-04 | 2026-08-04
100 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-4 | ZWP22 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-28 | 2026-12-04 | 2026-12-06 | 2026-12-06 | 2027-01-05 | 8.5 | 59.5 | 2026-12-06 | 2026-11-21 | -15 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-4 | ZWP22 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [14 empty] | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-28 | 2026-12-04 | 2026-12-06 | 2026-12-06 | 2027-01-05 |  |  | 2026-12-06
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-4 | ZWP22 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  | 2026-08-03 | 2026-08-03 | 2026-04-20 | 2026-08-04 | 2026-08-04
101 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-5 | ZWP22 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-12-19 | 2026-12-25 | 2026-12-27 | 2026-12-27 | 2027-01-26 | 8.5 | 59.5 | 2026-12-27 | 2027-01-12 | 16 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-5 | ZWP22 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F |  | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | [8 empty] | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-12-19 | 2026-12-25 | 2026-12-27 | 2026-12-27 | 2027-01-26 |  |  | 2026-12-27
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-5 | ZWP22 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  | 2026-08-03 | 2026-08-03 | 2026-04-20 | 2026-08-10 | 2026-08-10
102 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-6 | ZWP22 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2027-01-09 | 2027-01-15 | 2027-01-17 | 2027-01-17 | 2027-02-16 | 8.5 | 59.5 | 2027-01-17 | 2026-11-03 | -75 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-6 | ZWP22 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [12 empty] | 2026-08-18 | 2026-08-03 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2027-01-09 | 2027-01-15 | 2027-01-17 | 2027-01-17 | 2027-02-16 |  |  | 2027-01-17
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-6 | ZWP22 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  | 2026-08-03 | 2026-08-03 | 2026-04-20
103 | MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-0067 | ZWP22 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-08-18 | 2026-08-03 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2027-01-09 | 2027-01-15 | 2027-01-17 | 2027-01-17 | 2027-02-16 | 8.5 | 59.5 | 2027-01-17 | 2026-11-18 | -60 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-7 | ZWP22 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [9 empty] | 2026-08-14 | 2026-08-14 |  | 2026-08-18 | 2026-08-03 | 2026-12-17 | 2026-12-17 | 2026-12-17 | 2027-01-09 | 2027-01-15 | 2027-01-17 | 2027-01-17 | 2027-02-16 |  |  | 2027-01-17
| MM-ZTK-1F-ZWP22-STR-MR-2002 | RFQ-STR-006-7 | ZWP22 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-08-03 |  |  |  | 2026-04-20
104 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-1 | ZWP20 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-10-11 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-11-18 | 8.5 | 59.5 | 2026-10-04 | 2026-10-25 | 6 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-1 | ZWP20 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [9 empty] | 2026-08-29 | 2026-08-29 |  | 2026-09-02 | 2026-08-18 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-10-11 | 2026-10-17 | 2026-10-19 | 2026-10-19 | 2026-11-18 |  |  | 2026-10-19
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-1 | ZWP20 Jacket Launch Cradle Plates+Ring Stiff Plates | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  |  |  | 2026-04-20
105 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-2 | ZWP20 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 2026-11-01 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 2026-12-09 | 8.5 | 59.5 | 2026-11-09 | 2026-11-25 | 16 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-2 | ZWP20 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [9 empty] | 2026-08-29 | 2026-08-29 |  | 2026-09-02 | 2026-08-18 | 2026-10-09 | 2026-10-09 | 2026-10-09 | 2026-11-01 | 2026-11-07 | 2026-11-09 | 2026-11-09 | 2026-12-09 |  |  | 2026-11-09
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-2 | ZWP20 Jacket Leg Partition/Closure Plates | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  |  |  | 2026-04-20
106 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-3 | ZWP20 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-11-22 | 2026-11-28 | 2026-11-30 | 2026-11-30 | 2026-12-30 | 8.5 | 59.5 | 2026-11-30 | 2026-12-07 | 7 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-3 | ZWP20 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [14 empty] | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-11-22 | 2026-11-28 | 2026-11-30 | 2026-11-30 | 2026-12-30 |  |  | 2026-11-30
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-3 | ZWP20 Jacket Primary Steel-Tubular TRB | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  | 2026-07-30 | 2026-07-30 | 2026-04-20 | 2026-07-30 | 2026-07-31
107 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-4 | ZWP20 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2026-11-20 | 2026-11-20 | 2026-11-20 | 2026-12-13 | 2026-12-19 | 2026-12-21 | 2026-12-21 | 2027-01-20 | 8.5 | 59.5 | 2026-12-21 | 2026-12-19 | -2 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-4 | ZWP20 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [14 empty] | 2026-11-20 | 2026-11-20 | 2026-11-20 | 2026-12-13 | 2026-12-19 | 2026-12-21 | 2026-12-21 | 2027-01-20 |  |  | 2026-12-21
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-4 | ZWP20 Jacket Primary Steel-Tubular CONE | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  | 2026-07-30 | 2026-07-30 | 2026-04-20 | 2026-07-30 | 2026-07-31
108 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-5 | ZWP20 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2026-12-11 | 2026-12-11 | 2026-12-11 | 2027-01-03 | 2027-01-09 | 2027-01-11 | 2027-01-11 | 2027-02-10 | 8.5 | 59.5 | 2027-01-11 | 2027-01-27 | 16 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-5 | ZWP20 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [14 empty] | 2026-12-11 | 2026-12-11 | 2026-12-11 | 2027-01-03 | 2027-01-09 | 2027-01-11 | 2027-01-11 | 2027-02-10 |  |  | 2027-01-11
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-5 | ZWP20 Jacket Primary Steel-Tubular JCOE | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  | 2026-07-30 | 2026-07-30 | 2026-04-20 | 2026-07-30 | 2026-07-31
109 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-6 | ZWP20 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-17 | 2026-08-01 | 2026-08-03 | 2026-08-03 | 2026-08-08 | 2026-08-19 | 2026-08-29 |  | 2026-08-29 | 2026-08-29 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2027-01-01 | 2027-01-01 | 2027-01-01 | 2027-01-24 | 2027-01-30 | 2027-02-01 | 2027-02-01 | 2027-03-03 | 8.5 | 59.5 | 2027-02-01 | 2026-11-20 | -73 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-6 | ZWP20 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [9 empty] | 2026-08-29 | 2026-08-29 |  | 2026-09-02 | 2026-08-18 | 2027-01-01 | 2027-01-01 | 2027-01-01 | 2027-01-24 | 2027-01-30 | 2027-02-01 | 2027-02-01 | 2027-03-03 |  |  | 2027-02-01
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-6 | ZWP20 Jacket Hydro static Ring Stiff Plate | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  |  |  | 2026-04-20
110 | MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-0067 | ZWP20 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-04-23 | 2026-07-02 | 2026-07-17 | 2026-07-19 | 2026-07-19 | 2026-07-24 | 2026-08-04 | 2026-08-14 |  | 2026-08-14 | 2026-08-14 | 2026-04-20 | 2026-09-02 | 2026-08-18 | 2027-01-22 | 2027-01-22 | 2027-01-22 | 2027-02-14 | 2027-02-20 | 2027-02-22 | 2027-02-22 | 2027-03-24 | 8.5 | 59.5 | 2027-02-22 | 2026-12-25 | -59 | Huang liudong | 31-Mar-26: Received ZWP20 /21/22/23 : IFC(2025/4/11) 2026.6.12: TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE(C1) | [11 empty] | ZH26FA001
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-7 | ZWP20 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [9 empty] | 2026-08-14 | 2026-08-14 |  | 2026-09-02 | 2026-08-18 | 2027-01-22 | 2027-01-22 | 2027-01-22 | 2027-02-14 | 2027-02-20 | 2027-02-22 | 2027-02-22 | 2027-03-24 |  |  | 2027-02-22
| MM-ZTK-1F-ZWP20-STR-MR-2002 | RFQ-STR-006-7 | ZWP20 Jacket Piles Sleeve Plate | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-04-08 | 2026-05-06 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-05-30 | 2026-07-27 | 2026-07-30 |  |  |  | 2026-04-20
111 |  | RFQ-STR-006-8 | Jacket Primary Steel-Piles-1st | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-09-21 | 2026-09-30 | 2026-10-12 | 2026-10-15 | 2026-10-15 | 2026-10-22 | 2026-10-27 | 2026-11-01 |  | 2026-11-07 | 2026-11-11 | 2026-11-18 | 2026-12-02 | 2026-12-17 | 2026-12-22 | 2026-12-25 | 2026-12-28 | 2027-01-26 | 2027-01-31 | 2027-02-05 | 2027-02-08 | 2027-03-07 | 8.5 | 59.5 | 2027-02-05 | 2027-02-14 | 9 | Huang liudong
|  | RFQ-STR-006-8 | Jacket Primary Steel-Piles-1st | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | 2026-09-21 | 2026-09-30 | 2026-10-12 | 2026-10-15 | 2026-10-15 | 2026-10-22 | 2026-10-27 | 2026-11-01 |  | 2026-11-07 | 2026-11-11 | 2026-11-18 | 2026-12-02 | 2026-12-17 | 2026-12-22 | 2026-12-25 | 2026-12-28 | 2027-01-26 | 2027-01-31 | 2027-02-05 | 2027-02-08 | 2027-03-07 |  |  | 2027-02-05
|  | RFQ-STR-006-8 | Jacket Primary Steel-Piles-1st | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A
112 |  | RFQ-STR-006-9 | Jacket Primary Steel-Piles-2nd | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-09-21 | 2026-10-29 | 2026-11-10 | 2026-11-13 | 2026-11-13 | 2026-11-20 | 2026-11-25 | 2026-11-30 |  | 2026-12-07 | 2026-12-11 | 2026-12-18 | 2027-01-01 | 2027-01-16 | 2027-01-21 | 2027-01-24 | 2027-01-27 | 2027-02-25 | 2027-03-02 | 2027-03-07 | 2027-03-10 | 2027-04-06 | 8.5 | 59.5 | 2027-03-07 | 2027-03-16 | 39.5 | Huang liudong
|  | RFQ-STR-006-9 | Jacket Primary Steel-Piles-2nd | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | 2026-09-21 | 2026-10-29 | 2026-11-10 | 2026-11-13 | 2026-11-13 | 2026-11-20 | 2026-11-25 | 2026-11-30 |  | 2026-12-07 | 2026-12-11 | 2026-12-18 | 2027-01-01 | 2027-01-16 | 2027-01-21 | 2027-01-24 | 2027-01-27 | 2027-02-25 | 2027-03-02 | 2027-03-07 | 2027-03-10 | 2027-04-06 |  |  | 2027-02-04 12:00
|  | RFQ-STR-006-9 | Jacket Primary Steel-Piles-2nd | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A
113 |  | RFQ-STR-006-10 | Jacket Primary Steel-Piles-3rd | 5-4 | STR | Y | L2 | LD | XISC | [5 empty] | ZH | P | 2026-09-21 | 2026-11-27 | 2026-12-09 | 2026-12-12 | 2026-12-12 | 2026-12-19 | 2026-12-24 | 2026-12-29 |  | 2027-01-06 | 2027-01-10 | 2027-01-17 | 2027-01-31 | 2027-02-15 | 2027-02-20 | 2027-02-23 | 2027-02-26 | 2027-03-27 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 | 8.5 | 59.5 | 2027-03-06 12:00 | 2027-04-15 | 39.5 | Huang liudong
|  | RFQ-STR-006-10 | Jacket Primary Steel-Piles-3rd | 5-4 | STR | Y | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | 2026-09-21 | 2026-11-27 | 2026-12-09 | 2026-12-12 | 2026-12-12 | 2026-12-19 | 2026-12-24 | 2026-12-29 |  | 2027-01-06 | 2027-01-10 | 2027-01-17 | 2027-01-31 | 2027-02-15 | 2027-02-20 | 2027-02-23 | 2027-02-26 | 2027-03-27 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-06 |  |  | 2027-03-06 12:00
|  | RFQ-STR-006-10 | Jacket Primary Steel-Piles-3rd | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A
114 | MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-1 | Jacket Primary Steel-Tubular-JCOE | 5-4 | STR | Y | L2 | LD | PCK | [5 empty] | ZH | P | 2026-05-12 | 2026-06-15 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-06 | 2026-07-15 | 2026-07-31 |  | 2026-08-01 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-09-10 | 2026-08-20 | 2026-08-21 | 2026-08-25 | 2026-10-03 | 2026-10-10 | 2026-10-15 | 2026-10-18 | 2026-11-14 | 4 | 28 | 2026-10-15 | 2026-10-06 | -9 | Huang liudong | 2-Apr-26: Received ZWP20 /21/22/23 : IFR(2026/4/2) 10-Apr-26:Received MM-ZTK-1F-GEN-STR-MR-1001 (IFR) MM-ZTK-1F-GEN-STR-MR-1011 (IFR) Topside High StrengthTubular steel | [11 empty] | ZHJT-SC-2026-99
| MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-1 | Jacket Primary Steel-Tubular-JCOE | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | F | [12 empty] | 2026-08-16 | 2026-09-10 | 2026-08-20 | 2026-08-21 | 2026-08-25 | 2026-10-03 | 2026-10-10 | 2026-10-15 | 2026-10-18 | 2026-11-14 |  |  | 2026-10-15
| MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-1 | Jacket Primary Steel-Tubular-JCOE | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-06-10 | 2026-05-04 | 2026-05-15 | 2026-06-10 | 2026-06-10 | 2026-06-12 | 2026-07-24 | 2026-08-06 |  | 2027-01-06: 2026-08-06; 2027-01-10: 2026-08-06; 2027-01-17: 2026-08-28
115 | MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-2 | Jacket Primary Steel-Tubular-TRB | 5-4 | STR | Y | L2 | LD | Ziking | [5 empty] | ZH | P | 2026-05-12 | 2026-06-15 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-06 | 2026-07-15 | 2026-07-31 |  | 2026-08-01 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-09-10 | 2026-08-20 | 2026-08-21 | 2026-08-25 | 2026-09-21 | 2026-09-28 | 2026-10-03 | 2026-10-06 | 2026-11-02 | 4 | 28 | 2026-10-03 | 2026-09-28 | -5 | Huang liudong | 2-Apr-26: Received ZWP20 /21/22/23 : IFR(2026/4/2) 10-Apr-26:Received MM-ZTK-1F-GEN-STR-MR-1001 (IFR) MM-ZTK-1F-GEN-STR-MR-1011 (IFR) Topside High StrengthTubular steel | [11 empty] | ZHJT-SC-2026-100
| MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-2 | Jacket Primary Steel-Tubular-TRB | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | F | [12 empty] | 2026-08-16 | 2026-09-10 | 2026-08-20 | 2026-08-21 | 2026-08-25 | 2026-09-21 | 2026-09-28 | 2026-10-03 | 2026-10-06 | 2026-11-02 |  |  | 2026-10-03
| MM-ZTK-1F-ZWP20-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 MM-ZTK-1F-ZWP22-STR-MR-2001 MM-ZTK-1F-ZWP23-STR-MR-2001 | RFQ-STR-007-2 | Jacket Primary Steel-Tubular-TRB | 5-4 | STR | Y | L2 | LD | [6 empty] | ZH | A | 2026-06-10 | 2026-05-04 | 2026-05-15 | 2026-06-10 | 2026-06-10 | 2026-06-12 | 2026-07-24 | 2026-08-06 |  | 2027-01-06: 2026-08-06; 2027-01-10: 2026-08-06; 2027-01-17: 2026-09-10
|  | RFQ-STR-008 | Jacket Miscellaneous Steel (boatlandings, ACCESS ladder, Riser Clamps, Casing Guides etc) | 5-4 | STR | N | L4 | LD | [6 empty] | ZH | P | 2026-07-10 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-18 | 2026-07-25 | 2026-08-05 | 2026-08-07 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-04 | 2026-11-02 00:29 | 2026-11-07 00:29 | 2026-11-12 00:29 | 2026-11-15 00:29 | 2026-12-02 00:29 | 12.8571 | 90 | 2026-11-12 00:29 |  |  |  | MM-ZTK-1F-ZWPX-STR-DWG-2231 JACKET - BOATLANDING ARRANGEMENT A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2232 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2233 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2234 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2235 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2236 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2237 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2238 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWP22-STR-DWG-2241 ZWP22 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP23-STR-DWG-2241 ZWP23 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP21-STR-DWG-2241 ZWP21 JACKET - RISER PROTECTOR ZWP21 JACKET - CASING GUIDE DETAILS MM-ZTK-1F-ZWP21-STR-DWG-2301
|  | RFQ-STR-008 | Jacket Miscellaneous Steel (boatlandings, ACCESS ladder, Riser Clamps, Casing Guides etc) | 5-4 | STR | N | L4 | LD | [6 empty] | ZH | F | 2026-08-26 |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-09-02 | 2026-09-11 | 2026-09-25 |  | 2026-10-09 | 2026-10-13 | 2026-10-13 | 2026-10-27 | 2026-11-10 | 2026-12-10 | 2026-12-10 | 2026-12-10 | 2026-12-28 | 2027-01-02 | 2027-01-07 | 2027-01-14 | 2027-02-06 |  |  | 2027-01-07
|  | RFQ-STR-008 | Jacket Miscellaneous Steel (boatlandings, ACCESS ladder, Riser Clamps, Casing Guides etc) | 5-4 | STR | N | L4 | LD | [6 empty] | ZH | A |  | 2026-07-10
116 |  | RFQ-STR-008-1 | Anode Doubler Plate and Stiffener | 5-4 | STR | N | L2 | LD | XISC | [5 empty] | ZH | P | 2026-07-10 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-18 | 2026-07-25 | 2026-08-05 | 2026-08-07 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-04 | 2026-11-02 00:29 | 2026-11-07 00:29 | 2026-11-12 00:29 | 2026-11-15 00:29 | 2026-12-02 00:29 | 12.8571 | 90 | 2026-11-12 00:29 | 2026-10-11 | -52 | Kuang Yuanna | MM-ZTK-1F-ZWPX-STR-DWG-2231 JACKET - BOATLANDING ARRANGEMENT A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2232 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2233 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2234 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2235 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2236 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2237 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2238 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWP22-STR-DWG-2241 ZWP22 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP23-STR-DWG-2241 ZWP23 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP21-STR-DWG-2241 ZWP21 JACKET - RISER PROTECTOR ZWP21 JACKET - CASING GUIDE DETAILS MM-ZTK-1F-ZWP21-STR-DWG-2301 | [11 empty] | ZH26FA001
|  | RFQ-STR-008-1 | Anode Doubler Plate and Stiffener | 5-4 | STR | N | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [9 empty] | 2026-09-03 | 2026-09-07 | 2026-09-14 | 2026-10-13 | 2026-10-28 | 2026-11-27 | 2026-11-27 | 2026-11-27 | 2026-11-22 | 2026-11-27 | 2026-12-02 | 2026-12-09 | 2027-01-01 |  |  | 2026-12-02
|  | RFQ-STR-008-1 | Anode Doubler Plate and Stiffener | 5-4 | STR | N | L2 | LD | [6 empty] | ZH | A | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22
117 |  | RFQ-STR-008-2 | Riser Protector | 5-4 | STR | N | L2 | LD | XISC | [5 empty] | ZH | P | 2026-07-10 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-18 | 2026-07-25 | 2026-08-05 | 2026-08-07 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-04 | 2026-11-02 00:29 | 2026-11-07 00:29 | 2026-11-12 00:29 | 2026-11-15 00:29 | 2026-12-02 00:29 | 12.8571 | 90 | 2026-11-12 00:29 | 2027-04-11 | 138 | Kuang Yuanna | MM-ZTK-1F-ZWPX-STR-DWG-2231 JACKET - BOATLANDING ARRANGEMENT A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2232 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2233 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2234 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2235 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2236 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2237 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2238 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWP22-STR-DWG-2241 ZWP22 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP23-STR-DWG-2241 ZWP23 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP21-STR-DWG-2241 ZWP21 JACKET - RISER PROTECTOR ZWP21 JACKET - CASING GUIDE DETAILS MM-ZTK-1F-ZWP21-STR-DWG-2301
|  | RFQ-STR-008-2 | Riser Protector | 5-4 | STR | N | L2 | LD | ZH26FA001 | [5 empty] | ZH | F |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-09-25 | 2026-09-25 | 2026-09-25 | 2026-11-14 | 2026-11-19 | 2026-11-24 | 2026-12-01 | 2026-12-24 |  |  | 2026-11-24
|  | RFQ-STR-008-2 | Riser Protector | 5-4 | STR | N | L2 | LD | [6 empty] | ZH | A | 2026-08-22 | 2026-07-10
118 |  | RFQ-STR-008-3 | Casing Guide | 5-4 | STR | N | L2 | LD | XISC | [5 empty] | ZH | P | 2026-07-10 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-18 | 2026-07-25 | 2026-08-05 | 2026-08-07 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-04 | 2026-11-02 00:29 | 2026-11-07 00:29 | 2026-11-12 00:29 | 2026-11-15 00:29 | 2026-12-02 00:29 | 12.8571 | 90 | 2026-11-12 00:29 | 2026-10-12 | -56 | Kuang Yuanna | MM-ZTK-1F-ZWPX-STR-DWG-2231 JACKET - BOATLANDING ARRANGEMENT A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2232 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2233 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2234 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2235 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2236 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2237 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2238 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWP22-STR-DWG-2241 ZWP22 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP23-STR-DWG-2241 ZWP23 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP21-STR-DWG-2241 ZWP21 JACKET - RISER PROTECTOR ZWP21 JACKET - CASING GUIDE DETAILS MM-ZTK-1F-ZWP21-STR-DWG-2301
|  | RFQ-STR-008-3 | Casing Guide | 5-4 | STR | N | L2 | LD | ZH26FA001 | [5 empty] | ZH | F |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 |  | 2026-09-08 | 2203-12-29 | 2203-12-29 | 2381-04-07 | 2381-04-07 | 2381-05-07 | 2381-05-07 | 2381-05-07 | 2026-11-27 | 2026-12-02 | 2026-12-07 | 2026-12-14 | 2027-01-06 |  |  | 2026-12-07
|  | RFQ-STR-008-3 | Casing Guide | 5-4 | STR | N | L2 | LD | [6 empty] | ZH | A | 2026-08-22 | 2026-07-10
119 |  | RFQ-STR-008-4 | Upending | 5-4 | STR | N | L2 | LD | XISC | [5 empty] | ZH | P | 2026-07-10 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-18 | 2026-07-25 | 2026-08-05 | 2026-08-07 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-04 | 2026-11-02 00:29 | 2026-11-07 00:29 | 2026-11-12 00:29 | 2026-11-15 00:29 | 2026-12-02 00:29 | 12.8571 | 90 | 2026-11-12 00:29 | 2026-12-15 | 13 | Kuang Yuanna | MM-ZTK-1F-ZWPX-STR-DWG-2231 JACKET - BOATLANDING ARRANGEMENT A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2232 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2233 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2234 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2235 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2236 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2237 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2238 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWP22-STR-DWG-2241 ZWP22 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP23-STR-DWG-2241 ZWP23 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP21-STR-DWG-2241 ZWP21 JACKET - RISER PROTECTOR ZWP21 JACKET - CASING GUIDE DETAILS MM-ZTK-1F-ZWP21-STR-DWG-2301 | [11 empty] | ZH26FA001
|  | RFQ-STR-008-4 | Upending | 5-4 | STR | N | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [9 empty] | 2026-09-03 | 2203-12-13 | 2203-12-13 | 2381-03-16 | 2381-03-16 | 2381-04-15 | 2381-04-15 | 2381-04-15 | 2026-11-22 | 2026-11-27 | 2026-12-02 | 2026-12-09 | 2027-01-01 |  |  | 2026-12-02
|  | RFQ-STR-008-4 | Upending | 5-4 | STR | N | L2 | LD | [6 empty] | ZH | A | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22
120 |  | RFQ-STR-008-5 | Access | 5-4 | STR | N | L2 | LD | XISC | [5 empty] | ZH | P | 2026-07-10 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-18 | 2026-07-25 | 2026-08-05 | 2026-08-07 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-04 | 2026-11-02 00:29 | 2026-11-07 00:29 | 2026-11-12 00:29 | 2026-11-15 00:29 | 2026-12-02 00:29 | 12.8571 | 90 | 2026-11-12 00:29 | 2027-03-28 | 110 | Kuang Yuanna | MM-ZTK-1F-ZWPX-STR-DWG-2231 JACKET - BOATLANDING ARRANGEMENT A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2232 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2233 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2234 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2235 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2236 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2237 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2238 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWP22-STR-DWG-2241 ZWP22 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP23-STR-DWG-2241 ZWP23 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP21-STR-DWG-2241 ZWP21 JACKET - RISER PROTECTOR ZWP21 JACKET - CASING GUIDE DETAILS MM-ZTK-1F-ZWP21-STR-DWG-2301 | [11 empty] | ZH26FA001
|  | RFQ-STR-008-5 | Access | 5-4 | STR | N | L2 | LD | ZH26FA001 | [5 empty] | ZH | F | [14 empty] | 2026-10-09 | 2026-10-09 | 2026-10-09 | 2026-11-28 | 2026-12-03 | 2026-12-08 | 2026-12-15 | 2027-01-07 |  |  | 2026-12-08
|  | RFQ-STR-008-5 | Access | 5-4 | STR | N | L2 | LD | [6 empty] | ZH | A | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-09-09 | 2026-09-09 | No need | No need | No need
121 |  | RFQ-STR-008-6 | Walkway Stair and Landing | 5-4 | STR | N | L2 | LD | XISC | [5 empty] | ZH | P | 2026-07-10 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-18 | 2026-07-25 | 2026-08-05 | 2026-08-07 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-04 | 2026-11-02 00:29 | 2026-11-07 00:29 | 2026-11-12 00:29 | 2026-11-15 00:29 | 2026-12-02 00:29 | 12.8571 | 90 | 2026-11-12 00:29 | 2027-03-30 | 113 | Kuang Yuanna | MM-ZTK-1F-ZWPX-STR-DWG-2231 JACKET - BOATLANDING ARRANGEMENT A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2232 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2233 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2234 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2235 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2236 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2237 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2238 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWP22-STR-DWG-2241 ZWP22 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP23-STR-DWG-2241 ZWP23 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP21-STR-DWG-2241 ZWP21 JACKET - RISER PROTECTOR ZWP21 JACKET - CASING GUIDE DETAILS MM-ZTK-1F-ZWP21-STR-DWG-2301 | [11 empty] | ZH26FA001
|  | RFQ-STR-008-6 | Walkway Stair and Landing | 5-4 | STR | N | L2 | LD | ZH26FA001 | [5 empty] | ZH | F |  | 2026-08-22 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 |  | 2026-09-08 | 2203-12-16 | 2203-12-16 | 2381-04-23 | 2381-04-23 | 2381-05-23 | 2381-05-23 | 2381-05-23 | 2026-11-27 | 2026-12-02 | 2026-12-07 | 2026-12-14 | 2027-01-06 |  |  | 2026-12-07
|  | RFQ-STR-008-6 | Walkway Stair and Landing | 5-4 | STR | N | L2 | LD | [6 empty] | ZH | A | [8 empty] | 2026-08-22
122 |  | RFQ-STR-008-7 | Boatlanding | 5-4 | STR | N | L2 | LD | XISC | [5 empty] | ZH | P | 2026-07-10 | 2026-07-07 | 2026-07-14 | 2026-07-15 | 2026-07-18 | 2026-07-25 | 2026-08-05 | 2026-08-07 |  | 2026-08-14 | 2026-08-18 | 2026-08-25 | 2026-09-08 | 2026-09-23 | 2026-09-28 | 2026-10-01 | 2026-10-04 | 2026-11-02 00:29 | 2026-11-07 00:29 | 2026-11-12 00:29 | 2026-11-15 00:29 | 2026-12-02 00:29 | 12.8571 | 90 | 2026-11-12 00:29 | 2026-12-14 | 7 | Kuang Yuanna | MM-ZTK-1F-ZWPX-STR-DWG-2231 JACKET - BOATLANDING ARRANGEMENT A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2232 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2233 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2234 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2235 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2236 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2237 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWPX-STR-DWG-2238 JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 A1 21-May-26 FOR MATERIAL PURCHASE MM-ZTK-1F-ZWP22-STR-DWG-2241 ZWP22 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP23-STR-DWG-2241 ZWP23 JACKET - RISER PROTECTOR MM-ZTK-1F-ZWP21-STR-DWG-2241 ZWP21 JACKET - RISER PROTECTOR ZWP21 JACKET - CASING GUIDE DETAILS MM-ZTK-1F-ZWP21-STR-DWG-2301
|  | RFQ-STR-008-7 | Boatlanding | 5-4 | STR | N | L2 | LD | ZH26FA001 | [5 empty] | ZH | F |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 |  | 2026-09-08 | 2204-02-23 | 2204-02-23 | 2381-06-22 | 2381-06-22 | 2381-07-22 | 2381-07-22 | 2381-07-22 | 2026-11-27 | 2026-12-02 | 2026-12-07 | 2026-12-14 | 2027-01-06 |  |  | 2026-12-07
|  | RFQ-STR-008-7 | Boatlanding | 5-4 | STR | N | L2 | LD | [6 empty] | ZH | A | 2026-08-22 | 2026-07-10
123 | MM-ZTK-1F-GEN-STR-MR-0004 | RFQ-STR-009 | JKT Anode | 5-4 | STR | N | L4 | LA | Sunrui | [5 empty] | ZH | P | 2026-05-26 | 2026-05-27 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-25 | 2026-07-20 | 2026-08-05 |  | 2026-08-18 | 2026-08-20 | 2026-08-27 | 2026-09-10 | 2026-09-24 | 2026-09-10 | 2026-09-13 | 2026-09-15 | 2026-10-09 12:00 | 2026-10-12 12:00 | 2026-10-16 12:00 | 2026-10-19 12:00 | 2026-11-05 12:00 | 8.5 | 59.5 | 2026-10-16 12:00 | 2026-10-11 | 0 | Zhang Jianwei | 2026.5.9 MR to yard 2026.9.11 ITP upload D2 for approval | [11 empty] | ZH26FA013 | 2026-10-20
| MM-ZTK-1F-GEN-STR-MR-0004 | RFQ-STR-009 | JKT Anode | 5-4 | STR | N | L4 | LA | ZH26FA013 | [5 empty] | ZH | F | [13 empty] | 2026-09-24 | 2026-09-24 |  | 2026-09-24 | 2026-10-04 | 2026-10-07 | 2026-10-11 | 2026-10-19 12:00 | 2026-10-31 |  |  | 2026-10-11
| MM-ZTK-1F-GEN-STR-MR-0004 | RFQ-STR-009 | JKT Anode | 5-4 | STR | N | L4 | LA | [6 empty] | ZH | A | 2026-05-22 | 2026-05-04 | 2026-05-15 | 2026-06-08 | 2026-06-08 | 2026-06-23 | 2026-07-27 | 2026/7/31 2026/8/26 |  | FA:2026/8/26 2026/9/1 | 2026-09-01 | No need | 2026-09-11 |  | 2026-10-09: No need
124 | MM-ZTK-1F-GEN-STR-MR-0001 MM-ZTK-1F-GEN-STR-MR-0002 | RFQ-STR-010 | Gripper, Packer and Diaphragm | 5-4 | STR | N | L3 | LA | OIL STATES | [5 empty] | SH | P | 2026-05-11 | 2026-05-12 | 2026-05-19 | 2026-05-20 | 2026-05-27 | 2026-06-10 | 2026-07-08 | 2026-07-13 |  | 2026-07-27 | 2026-07-29 | 2026-08-05 | 2026-09-02 | 2026-09-16 | 2026-10-16 | 2026-10-16 | 2026-10-18 | 2027-01-29 | 2027-02-13 | 2027-03-15 | 2027-03-18 | 2027-04-04 | 33 | 231 | 2027-03-15 |  |  | Liu Lei | [9 empty] | DDP 24 weeks after PO
| MM-ZTK-1F-GEN-STR-MR-0001 MM-ZTK-1F-GEN-STR-MR-0002 | RFQ-STR-010 | Gripper, Packer and Diaphragm | 5-4 | STR | N | L3 | LA | ZM169-WP1-PO-STR-001 | [5 empty] | SH | F | [13 empty] | 2026-09-28 | 2026-10-28 | 2026-10-28 | 2026-10-30 | 2027-02-09 | 2027-02-24 | 2027-03-26 | 2027-03-18 | 2027-04-15 | 28 | 196 | 2027-03-26 | 2027-02-08 | -46 | CIF Zhuhai Port | [12 empty] | ZWP21 | 2027-03-19
| MM-ZTK-1F-GEN-STR-MR-0001 MM-ZTK-1F-GEN-STR-MR-0002 | RFQ-STR-010 | Gripper, Packer and Diaphragm |  | STR | N | L3 | LA | Delivery time is related with drawing approved within 22 days | [5 empty] | SH | F | [22 empty] | 30 | 210 | 2027-04-06 | 2027-03-04 | -33 | [13 empty] | ZWP23 | 2027-03-30
| MM-ZTK-1F-GEN-STR-MR-0001 MM-ZTK-1F-GEN-STR-MR-0002 | RFQ-STR-010 | Gripper, Packer and Diaphragm |  | STR | N | L3 | LA | [6 empty] | SH | F | [22 empty] | 32 | 224 | 2027-04-20 | 2027-03-26 | -25 | [13 empty] | ZWP22 | 2027-04-13
| MM-ZTK-1F-GEN-STR-MR-0001 MM-ZTK-1F-GEN-STR-MR-0002 | RFQ-STR-010 | Gripper, Packer and Diaphragm |  | STR | N | L3 | LA | [6 empty] | SH | F | [22 empty] | 34 | 238 | 2027-05-04 | 2027-04-27 | -7 | [13 empty] | ZWP20 | 2027-04-27
| MM-ZTK-1F-GEN-STR-MR-0001 MM-ZTK-1F-GEN-STR-MR-0002 | RFQ-STR-010 | Gripper, Packer and Diaphragm | 5-4 | STR | N | L3 | LA | [6 empty] | SH | A | 2026-05-22 | 2026-05-11 | 2026-05-15 | 2026-05-25 | 2026-05-25 | 2026-06-12 | 2026-07-17 | 2026/7/24 2026/8/17 | 2026-08-04 | 2026-08-17 | 2026-09-06 | 2026-08-11 | 2026-08-11 | [11 empty] | CD+7
|  | RFQ-STR-011 | Grouting System | 5-4 | STR | N | L3 | LA | ruputure disc and check valve combine with Gripper | [5 empty] | ZH | P | 2026-05-11 | 2026-05-10 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-06-05 | 2026-06-30 | 2026-07-14 |  | 2026-07-27 | 2026-07-29 | 2026-08-05 | 2026-09-02 | 2026-09-16 | 2026-10-08 | 2026-10-08 | 2026-10-10 | 2027-02-28 | 2027-03-05 | 2027-03-15 | 2027-03-18 | 2027-04-04 | 33 | 231 | 2027-03-15 | 2027-03-25 | 10 | Zhang Xiaorui | 2026.6.4 MR to yard 2026.6.4 short vendor list to CPY approval 2026.6.9 Received comments from CPY. Not approved. 2026.6.11 Short bidder list is approved
|  | RFQ-STR-011 | Grouting System | 5-4 | STR | N | L3 | LA | grouting pipes combine with seamless pipes | [5 empty] | ZH | F
|  | RFQ-STR-011 | Grouting System | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | A | 2026-06-11 | 2026-06-04 | 2026-06-11 | 2026-06-11 | 2026-06-11
125 |  | RFQ-STR-012 | Flooding and Venting system | 5-4 | STR | N | L3 | LA | COOEC | [5 empty] | ZH | P | 2026-05-11 | 2026-05-10 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-06-05 | 2026-06-30 | 2026-07-14 |  | 2026-07-27 | 2026-07-29 | 2026-08-05 | 2026-09-02 | 2026-09-16 | 2026-10-08 | 2026-10-08 | 2026-10-10 | 2027-02-28 | 2027-03-05 | 2027-03-15 | 2027-03-18 | 2027-04-04 | 33 | 231 | 2027-03-15 | 2027-04-21 | -9 | Zhang Xiaorui | 2026.6.4 MR to yard 2026.6.4 short vendor list to CPY approval 2026.6.9 Received comments from CPY. Not approved. 2026.6.11 Short bidder list is approved | [6 empty] | Bidder1 | DDP: 38 weeks after PO
|  | RFQ-STR-012 | Flooding and Venting system | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | F | [10 empty] | 2026-09-21 |  |  | 2026-10-14 | 2026-11-13 | 2026-11-13 | 2026-11-15 | 2027-04-15 | 2027-04-20 | 2027-04-30 | 2027-03-18 | 2027-05-20 | 33 | 231 | 2027-04-30 | [16 empty] | 28 weeks after drawing approved
|  | RFQ-STR-012 | Flooding and Venting system | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | A | 2026-06-11 | 2026-06-04 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-28 | 2026-07-15 | 2026/7/30 2026/8/20 | 2026-08-31 | 2026-09-11 |  | 2026-08-24 | 2026-09-14
126 | MM-ZTK-1F-GEN-STR-MR-0005 | RFQ-STR-013 | Timber for Launch cradle | 5-4 | STR | N | L3 | LA | Shanghai Hongyu | [5 empty] | ZH | P | 2026-04-22 | 2026-04-23 | 2026-04-30 | 2026-05-04 | 2026-05-11 | 2026-05-25 | 2026-06-24 | 2026-06-29 |  | 2026-07-13 | 2026-07-15 | 2026-07-22 | 2026-08-19 | 2026-09-02 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2026-09-30 14:24 | 2026-10-05 14:24 | 2026-10-10 14:24 | 2026-10-13 14:24 | 2026-10-30 14:24 | 12.8 | 90 | 2026-10-10 | 2026-09-30 | 15 | Liu Bin | 2026.5.11 MR to yard 2026.6.8 Short bidder list is approved by CPY | [11 empty] | ZH26PO0453 | 2026-09-15
| MM-ZTK-1F-GEN-STR-MR-0005 | RFQ-STR-013 | Timber for Launch cradle | 5-4 | STR | N | L3 | LA | ZH26PO0453 | [5 empty] | ZH | F | [15 empty] | 2026-09-07 | 2026-09-09 | 2026-09-05 | 2026-09-10 | 2026-09-15 | 2026-10-13 | 2026-10-05 |  |  | 2026-09-15
| MM-ZTK-1F-GEN-STR-MR-0005 | RFQ-STR-013 | Timber for Launch cradle | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | A | 2026-06-08 | 2026-05-11 | 2026-05-15 | 2026-06-10 | 2026-06-10 | 2026-06-16 | 2026-06-30 | 2026-07-08 |  | 2026-07-09 | 2026-07-10 | No need | 2026-08-06 | 2026-08-10 | 2026-10-09: 2026-08-11
126 |  | RFQ-STR-014 | Teflon plate for Launch cradle(Grease) | 5-4 | STR | N | L3 | LA | Lugang | [5 empty] | ZH | P | 2026-04-22 | 2026-04-23 | 2026-04-30 | 2026-05-04 | 2026-05-11 | 2026-05-25 | 2026-06-24 | 2026-06-29 |  | 2026-07-13 | 2026-07-15 | 2026-07-22 | 2026-08-19 | 2026-09-02 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2026-09-30 14:24 | 2026-10-05 14:24 | 2026-10-10 14:24 | 2026-10-13 14:24 | 2026-10-30 14:24 | 12.8 | 90 | 2026-10-10 | 2026-09-30 | 8 | Huang liudong | 2026.5.11 MR to yard 2026.6.8 Short bidder list is approved by CPY | [11 empty] | ZH26PO013 | 2026-09-22 | 179 Drums
|  | RFQ-STR-014 | Teflon plate for Launch cradle(Grease) | 5-4 | STR | N | L3 | LA | ZH26PO013 | [5 empty] | ZH | F | [14 empty] | 2027-01-07: 2026-10-18 |  |  | 2026-09-22
|  | RFQ-STR-014 | Teflon plate for Launch cradle(Grease) | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | A | 2026-06-08 | 2026-05-11 | 2026-05-15 | 2026-06-10 | 2026-06-10 | 2026-06-16 | 2026-06-30 | 2026-07-08 |  | 2026-07-09 | 2026-07-10 | No need | 2026-08-06 | no need | no need | no need | 2026-09-11 | No need | 2026-09-17 | 2026-09-18 | 2026-09-18
127 | MM-ZTK-1F-GEN-STR-MR-0003 | RFQ-STR-015 | Jacket Barge Bumpers and Fender | 5-4 | STR | N | L3 | LA | Trelleborg | [5 empty] | ZH | P | 2026-08-13 | 2026-08-14 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-09-09 | 2026-10-02 | 2026-10-19 |  | 2026-10-30 | 2026-11-03 | 2026-11-10 | 2026-12-08 | 2026-12-22 | 2026-12-27 | 2026-12-27 | 2026-12-29 | 2027-02-16 16:48 | 2027-02-21 16:48 | 2027-02-26 16:48 | 2027-03-01 16:48 | 2027-03-18 16:48 | 17.1 | 119.7 | 2027-02-26 16:48 | 2027-02-17 | -9.7 | Liu Bin | 2026.5.9 MR to yard
| MM-ZTK-1F-GEN-STR-MR-0003 | RFQ-STR-015 | Jacket Barge Bumpers and Fender | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | F | 2026-08-13 | [8 empty] | 2026-09-24 | 2026-09-29 | 2026-10-13 | 2026-11-10 | 2026-11-24 | 2026-11-29 | 2026-11-29 | 2026-12-01 | 2027-02-16 16:48 | 2027-02-21 16:48 | 2027-02-26 16:48 | 2027-03-01 16:48 | 2027-03-18 16:48 |  |  | 2027-01-21 16:48
| MM-ZTK-1F-GEN-STR-MR-0003 | RFQ-STR-015 | Jacket Barge Bumpers and Fender | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | A |  | 2026-05-04 | 2026-05-15 | 2026-08-03 | 2026-08-03 | 2026-08-10 | 2026-08-28 | C1:11-Sep-26
128 |  | RFQ-STR-016 | Neoprene | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | P | 2026-08-13 | 2026-08-04 | 2026-08-04 | 2026-08-26 | 2026-08-26 | 2026-09-09 | 2026-10-02 | 2026-10-19 |  | 2026-10-30 | 2026-11-03 | 2026-11-10 | 2026-12-08 | 2026-12-22 | 2026-12-27 | 2026-12-27 | 2026-12-29 | 2027-02-16 16:48 | 2027-02-21 16:48 | 2027-02-26 16:48 | 2027-03-01 16:48 | 2027-03-18 16:48 | 17.1 | 119.7 | 2027-02-26 16:48 | 2027-01-25 | -32.7 | Liu Bin | 2026.5.9 MR to yard
|  | RFQ-STR-016 | Neoprene | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | F | [5 empty] | 2026-09-25 | 2026-10-02 | 2026-10-19 |  | 2026-10-30 | 2026-11-03 | 2026-11-10 | 2026-11-24 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 | 2026-12-09 |  |  | 2027-02-26 16:48
|  | RFQ-STR-016 | Neoprene | 5-4 | STR | N | L3 | LA | [6 empty] | ZH | A |  | 2026-08-04 | no need | 2026-08-26 | 2026-08-26
Formulas:
Vendor = [THE Worksite]-14
Vendor = [ENG]+60
THE Worksite = [TJE PRC]+7
THE Worksite = [TJE PRC]
TJE QA/QC = [TJE PRC, row above]+3
TJE QA/QC = [Vendor]+2
TJE PRC = [TJE PRC, row above]+30
TJE PRC = [TJE PRC, row above]
PTTEP = [TJE PRC]
PTTEP = WORKDAY([ENG], Y6, IF(Y12="China",'China Holidays'!$A2:A84,'Thai Holidays'!$A2:A65))
ENG = WORKDAY([Vendor, row below], 20, IF(AE12="China",'China Holidays'!$A2:A84,'Thai Holidays'!$A2:A65))
ENG = [ENG, row above]
BIDDER = [TJE PRC]+2
BIDDER = WORKDAY([TJE PRC], AB27, IF(AB30="China",'China Holidays'!$A2:A84,'Thai Holidays'!$A2:A65))
Note on P19: Administrator: 珠海建造
Note on P22: Administrator: 珠海建造
Note on P25: Administrator: 珠海建造
Note on P34: Administrator: 珠海建造
Note on Y51: Zhang Juan: 6-Aug:AWC 14-Aug: C2 submit
Note on P110: Administrator: 如果只是型钢板材拼接类的支撑由珠海采购。
Note on Y115: Zhang Juan: 12-Aug: AWC 20-Aug:APPR
Note on Y118: Zhang Juan: 11-Aug: AWC 20-Aug:APPR
Note on Y121: Zhang Juan: 12-Aug: AWC 20-Aug: APPR
Note on X124: Zhang Juan: 5-Aug:C2
Note on Y130: Zhang Juan: 11-Aug:TBE C` not approved 19-Aug: TBE C2 not approved
Note on X134: Zhang Juan: 2026.8.9:Pending on hot drawn for 3" pipes
Note on Y146: Zhang Juan: 18-Aug: TBE C2 APPR
Note on Y185: Zhang Juan: 2-Aug;AWC
Note on Y206: Zhang Juan: 6-Aug: AWC
Note on Y209: Zhang Juan: 2-Aug: AWC
Note on Y421: Zhang Juan: 31-Jul:AWC
Note on Y427: Zhang Juan: 17-Aug:TBE APPR
Note on Y433: Zhang Juan: 20-Aug:TBE APPR

## Brownfield
PROVISION OF ENGINEERING, PROCUREMENT, CONSTRUCTION AND COMMISSIONING FOR WELLHEAD PLATFORMS, ASSOCIATED PIPLINES AND BROWNFIELD MODIFICATIONS FOR ZAWTIKA DEVELOPMENT PROJECT PHASE 1F
Procurement Plan
[8 empty] | LA | Most complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 10 | 17 | 10 |  | 9 | 2 | 5 | 20 | 10 | [15 empty] | 3 |  | 10 | 2
[8 empty] | LB | High complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 10 | 17 | 10 |  | 9 | 2 | 5 | 20 | 10 | [15 empty] | 3 |  | 10 | 2
[8 empty] | LC | Normal complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 10 | 13 | 10 |  | 9 | 2 | 5 | 15 | 10 | [15 empty] | 3 |  | 10 | 2
Contract no: MMC25-5001 | [7 empty] | LD | Low complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 5 | 7 | 10 |  | 5 | 2 | 5 | 10 | 10 | [14 empty] | Update:11-Sep-2026 | 2 |  | 5 | 2
No. | MR No. | RFQ No. | Package Name | CODE | DIS | LLI (Y/N) | CR | Priority Level | PO description | Bidders | TC | TBE | Price bid | Price Negotiation | Owner | P/F/A | Bidder list Approval | MR Issued (IFR) | MR Approved | RFQ Issued | RFQ Approved | Bid Closing Date | TBE Issued | TBE Approved | LOA issued | PO Issued | Vendor Acknowledgement | KOM | VDB Submission | Approval of Key VP | Main Material Arrived | PIM | Start Production | FAT | Ready for Shipment | Receipt at WORKSITE | Punch List Clearance(all punch clearance before Tag Equipment Ready for Shipping ) | Approval of Final Documentation (To be confirmed later) | Delivery Duration (Weeks) | days | Delivery Date(1st Batch for ZWP21) | ROS Date | Float | Responder | Remarks | 2010-05-31 | 2010-06-30 | 2010-07-31 | 2010-08-31 | 2010-09-30 | 2010-10-31 | 2010-11-30 | 2010-12-31 | 2011-01-31 | 2011-02-28 | 2026-09-22 | Palteform | PO Delivery date | Puchase Qty
[16 empty] | Matrix | PTTEP | ENG | PTTEP | TJE PRC | PTTEP | TJE PRC | ENG | PTTEP | TJE PRC | TJE PRC | BIDDER | TJE PRC | Vendor | ENG | Vendor | TJE QA/QC | Vendor | TJE QA/QC | Vendor | THE Worksite | TJE QA/QC | TJE PRC |  |  | TJE PRC
[16 empty] | Holiday | China | Thai | Thai | China | Thai | China | Thai | Thai | China | China | China | China | China | Thai | [15 empty] | Thai |  | China | China
1 | MM-ZTK-1F-ZWP8-INS-MR-0001 | RFQ-IN-B01 | ESDV MODIFICATION |  | IN | N |  | LD | [6 empty] | SH | P | [28 empty] | 2026.9.20 ENG team released MR to Procurement
| MM-ZTK-1F-ZWP8-INS-MR-0001 | RFQ-IN-B01 | ESDV MODIFICATION |  | IN | N |  | LD | [6 empty] | SH | F
| MM-ZTK-1F-ZWP8-INS-MR-0001 | RFQ-IN-B01 | ESDV MODIFICATION |  | IN | N |  | LD | [6 empty] | SH | A

## Future Well
PROVISION OF ENGINEERING, PROCUREMENT, CONSTRUCTION AND COMMISSIONING FOR WELLHEAD PLATFORMS, ASSOCIATED PIPLINES AND BROWNFIELD MODIFICATIONS FOR ZAWTIKA DEVELOPMENT PROJECT PHASE 1F
Procurement Plan
[8 empty] | LA | Most complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 10 | 17 | 10 |  | 9 | 2 | 5 | 20 | 10 | [15 empty] | 3 |  | 10 | 2
[8 empty] | LB | High complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 10 | 17 | 10 |  | 9 | 2 | 5 | 20 | 10 | [15 empty] | 3 |  | 10 | 2
[8 empty] | LC | Normal complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 10 | 13 | 10 |  | 9 | 2 | 5 | 15 | 10 | [15 empty] | 3 |  | 10 | 2
Contract no: MMC25-5001 | [7 empty] | LD | Low complexity RFQ | [8 empty] | 1 | 10 | 0 | 0 | 5 | 7 | 10 |  | 5 | 2 | 5 | 10 | 10 | [14 empty] | Update:11-Sep-2026 | 2 |  | 5 | 2
No. | MR No. | RFQ No. | Package Name | CODE | DIS | LLI (Y/N) | CR | Priority Level | PO description | Bidders | TC | TBE | Price bid | Price Negotiation | Owner | P/F/A | Bidder list Approval | MR Issued (IFR) | MR Approved | RFQ Issued | RFQ Approved | Bid Closing Date | TBE Issued | TBE Approved | LOA issued | PO Issued | Vendor Acknowledgement | KOM | VDB Submission | Approval of Key VP | Main Material Arrived | PIM | Start Production | FAT | Ready for Shipment | Receipt at WORKSITE | Punch List Clearance(all punch clearance before Tag Equipment Ready for Shipping ) | Approval of Final Documentation (To be confirmed later) | Delivery Duration (Weeks) | days | Delivery Date(1st Batch for ZWP21) | ROS Date | Float | Responder | Remarks | 2010-05-31 | 2010-06-30 | 2010-07-31 | 2010-08-31 | 2010-09-30 | 2010-10-31 | 2010-11-30 | 2010-12-31 | 2011-01-31 | 2011-02-28 | 2026-09-22 | Palteform | PO Delivery date | Puchase Qty
[16 empty] | Matrix | PTTEP | ENG | PTTEP | TJE PRC | PTTEP | TJE PRC | ENG | PTTEP | TJE PRC | TJE PRC | BIDDER | TJE PRC | Vendor | ENG | Vendor | TJE QA/QC | Vendor | TJE QA/QC | Vendor | THE Worksite | TJE QA/QC | TJE PRC |  |  | TJE PRC
[16 empty] | Holiday | China | Thai | Thai | China | Thai | China | Thai | Thai | China | China | China | China | China | Thai | [15 empty] | Thai |  | China | China
1 |  | RFQ-IN-F01 | Actuated Choke Valve | 4-20 | IN | Y | L2 | LA | MASTER FLO | FZ | FZ |  |  |  | SH | P | [22 empty] | 44 | 308 | 2027-04-05 | 2027-05-08 | 54 | Lin Yazhen
|  | RFQ-IN-F01 | Actuated Choke Valve | 4-20 | IN | Y | L2 | LA |  | MASTER FLO | MASTER FLO | MASTER FLO | MASTER FLO | MASTER FLO | SH | F | [22 empty] | 36 | 252 | 2027-03-15 |  |  | CIF Zhuhai port | [12 empty] | ZWP20-23 | 2027-03-08
|  | RFQ-IN-F01 | Actuated Choke Valve | 4-20 | IN | Y | L2 | LA |  | Cameron | Cameron | Cameron |  |  | SH | A | [24 empty] | CD+7
2 |  | RFQ-IN-F02 | Actuated Compact Ball Valve | 4-40 | IN | Y | L2 | LA | OIL STATE | Neway,KCON | KCON | KCON-TNA |  |  | SH | P | [22 empty] | 40 | 280 | 2027-04-23 | 2027-04-30 | 46507 | Lin Yazhen
|  | RFQ-IN-F02 | Actuated Compact Ball Valve | 4-40 | IN | Y | L2 | LA |  | PIPER valve | PIPER | PIPER | PIPER | PIPER | SH | F | [27 empty] | CIF Zhuhai Airport
|  | RFQ-IN-F02 | Actuated Compact Ball Valve | 4-40 | IN | Y | L2 | LA |  | FMC,Combet | Combet | Combet-declined |  |  | SH | A | [24 empty] | CD+7

## Thai Holidays
Date | Holiday Name
2025-12-05 | Father's Day
2025-12-10 | Constitution Day
2025-12-29 | New Year's Day
2025-12-30 | New Year's Day
2025-12-31 | New Year's Day
2026-01-01 | New Year's Day
2026-01-02 | New Year's Day
2026-02-12 | The Buddha Day
2026-04-06 | Kutkuri Dynasty Memorial Day
2026-04-13 | Songkran Festival
2026-04-14 | Songkran Festival
2026-04-15 | Songkran Festival
2026-04-16 | Songkran Festival
2026-04-17 | Songkran Festival
2026-05-01 | International Workers' Day
2026-05-04 | The anniversary of the King's accession to the throne
2026-06-01
2026-06-03
2026-07-28
2026-07-29
2026-08-12 | Mother's Day
2026-10-13 | The anniversary of the death of the 9th King
2026-10-23 | The anniversary of the death of the 5th King Father's Day
2026-12-07 | Father's Day
2026-12-31 | New Year's Day
2027-01-01 | New Year's Day | 佛历节日，日期为预测
2027-01-02
2027-02-21 | The Buddha Day
2027-02-22
2027-04-06 | Kutkuri Dynasty Memorial Day
2027-04-13 | Songkran Festival
2027-04-14 | Songkran Festival
2027-04-15 | Songkran Festival | 佛历节日，日期为预测
2027-05-01 | International Workers' Day
2027-05-04 | The anniversary of the King's accession to the throne
2027-05-20 | Vesak Festival
2027-06-03 | The Birthday Anniversary of the Queen
2027-08-12 | Mother's Day | 佛历节日，日期为预测
2027-10-13 | The anniversary of the death of the 9th King
2027-10-23 | The anniversary of the death of the 5th King Father's Day |  | The anniversary of the death of the 5th King Father's Day
2027-10-25
2027-12-05 | Father's Day
2027-12-06
2027-12-10 | 宪法纪念日
2027-12-31 | New Year's Day
2028-01-01 | New Year's Day | 佛历节日，日期为预测
2028-02-08 | 万佛节
2028-04-06 | 却克里王朝纪念日
2028-04-13 | Songkran Festival
2028-04-14 | Songkran Festival
2028-04-15 | Songkran Festival
2028-05-01 | International Workers' Day
2028-05-05 | The anniversary of the King's accession to the throne | 佛历节日，日期为预测
2028-06-08 | 卫塞节
2028-06-03 | The Birthday Anniversary of the Queen | 佛历节日，日期为预测
2028-07-24 | 守夏节
2028-08-12 | Mother's Day
2028-10-13 | The anniversary of the death of the 9th King
2028-10-23 | The anniversary of the death of the 5th King Father's Day
2028-12-05 | Father's Day
2028-12-10 | 宪法纪念日
2028-12-31 | New Year's Day

## China Holidays
Date | Holiday Name
2026-01-01 | New Year's Day
2026-01-02 | New Year's Day
2026-01-03 | New Year's Day
2026-02-15 | Spring Festival
2026-02-16 | Spring Festival
2026-02-17 | Spring Festival
2026-02-18 | Spring Festival
2026-02-19 | Spring Festival
2026-02-20 | Spring Festival
2026-02-21 | Spring Festival
2026-04-04 | Qingming Festival
2026-04-05 | Qingming Festival
2026-04-06 | Qingming Festival
2026-05-01 | International Workers' Day
2026-05-02 | International Workers' Day
2026-05-03 | International Workers' Day
2026-06-19 | Dragon Boat Festival
2026-06-20 | Dragon Boat Festival
2026-06-21 | Dragon Boat Festival
2026-09-25 | Middle Moon Festival
2026-09-26 | Middle Moon Festival
2026-09-27 | Middle Moon Festival
2026-10-01 | National Day
2026-10-02 | National Day
2026-10-03 | National Day
2026-10-04 | National Day
2026-10-05 | National Day
2026-10-06 | National Day
2026-10-07 | National Day
2027-01-01 | New Year's Day
2027-01-02 | New Year's Day
2027-01-03 | New Year's Day
2027-02-06 | Spring Festival
2027-02-07 | Spring Festival
2027-02-08 | Spring Festival
2027-02-09 | Spring Festival
2027-02-10 | Spring Festival
2027-02-11 | Spring Festival
2027-02-12 | Spring Festival
2027-04-03 | Qingming Festival
2027-04-04 | Qingming Festival
2027-04-05 | Qingming Festival
2027-05-01 | International Workers' Day
2027-05-02 | International Workers' Day
2027-05-03 | International Workers' Day
2027-06-11 | Dragon Boat Festival
2027-06-12 | Dragon Boat Festival
2027-06-13 | Dragon Boat Festival
2027-06-14 | Dragon Boat Festival
2027-09-15 | Middle Moon Festival
2027-10-01 | National Day
2027-10-02 | National Day
2027-10-03 | National Day
2027-10-04 | National Day
2027-10-05 | National Day
2027-10-06 | National Day
2027-10-07 | National Day
2028-01-01 | New Year's Day
2028-01-02 | New Year's Day
2028-01-03 | New Year's Day
2028-01-25 | Spring Festival
2028-01-26 | Spring Festival
2028-01-27 | Spring Festival
2028-01-28 | Spring Festival
2028-01-29 | Spring Festival
2028-01-30 | Spring Festival
2028-01-31 | Spring Festival
2028-04-04 | Qingming Festival
2028-04-05 | Qingming Festival
2028-04-06 | Qingming Festival
2028-05-01 | International Workers' Day
2028-05-02 | International Workers' Day
2028-05-03 | International Workers' Day
2028-05-31 | Dragon Boat Festival
2028-06-01 | Dragon Boat Festival
2028-06-02 | Dragon Boat Festival
2028-10-01 | National Day
2028-10-02 | National Day
2028-10-03 | National Day
2028-10-04 | National Day
2028-10-05 | National Day
2028-10-06 | National Day
2028-10-07 | National Day